## Sheet1
LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | GIS_Shapefile
City of Kissimmee | N/A | KS-01 | Education and Outreach | PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 441 | 18 | Upper Kissimmee | N/A | 65000 | 45000 | City of Kissimmee | $110,000 | N/A
City of Kissimmee | N/A | KS-02 | Street Sweeping | Complete 6,573 miles of street sweeping and collect approximately 3,100 cubic yards of debris. | Street Sweeping | Completed | N/A | 612 | 221 | Upper Kissimmee | N/A | 50000 | 50000 | City of Kissimmee | $100,000 | N/A
City of Kissimmee | TBD | KS-03 | Lake Tivoli | Treatment for older existing development as well as future online development; treatment provides 2.5 times the proposed percent impervious area. | On-line Retention BMPs | Underway | TBD | TBD | TBD | Upper Kissimmee | 132.8 | 300000 | TBD | TBD | TBD | N/A
City of Kissimmee | N/A | KS-04 | Lakefront Park Redevelopment - Swales/ Rain Gardens | Swale/rain garden system with 2.07 acres of dry detention. | Grass Swales Without Swale Blocks or Raised Culverts | Completed | 2015 | 13 | 0 | Upper Kissimmee | 14.2 | 500000 | Not provided | City of Kissimmee | $500,000 | N/A
City of Kissimmee | N/A | KS-05 | Lakefront Park Redevelopment Baffle Boxes | Three nutrient separating baffle boxes and 3 filter boxes within the lakefront park area. wILL install up to additional two baffle boxes in the next 5 years. | Baffle Boxes- Second Generation | Completed | 2015 | 22 | 0 | Upper Kissimmee | 14.2 | 394267 | Not provided | City of Kissimmee | $394,267 | N/A
City of Kissimmee | N/A | KS-06 | Martin Luther King Boulevard Phase III from Thacker Avenue to Dyer Boulevard | Construction of dry detention with SPECIFIC standards (side slopes, littoral zones) per the Federal Aviation Administration for reduction of bird strikes. | Grass Swales Without Swale Blocks or Raised Culverts | Completed | 2015 | 3 | 0 | Upper Kissimmee | 5.5 | 1500000 | 1500 | City of Kissimmee | $1,501,500 | N/A
City of Kissimmee | DEP | KS-07 | Emory Avenue Stormwater Management Pond | An off-line stormwater pond to provide extra storage to alleviate flooding. The pond shall also catch the first flush during rain events to help provide water quality treatment to the West City Ditch. | Wet Detention Pond | Completed | 2017 | TBD | TBD | Upper Kissimmee | TBD | 500000 | 1000 | DEP | $500,000 | S0725
City of Kissimmee | NRCS | KS-08 | Mill Slough Restoration | Mill Slough restored erroded banks and removed excess silt that was washed from the bank along with removal of down trees. | Shoreline Stabilization | Underway | 2019 | TBD | TBD | Upper Kissimmee | TBD | 1857026 | TBD | NRCS/ City of Kissimmee | $1,434,974 | N/A
City of Kissimmee | DEP | KS-09 | Woodside drainage improvement | The project would reduce flooding and improve the water quality that goes into Shingle Creek basin. | Wet Detention Pond | Planned | 2021 | TBD | TBD | Upper Kissimmee | TBD | TBD | TBD | DEP/ City of Kissimmee | TBD | TBD