## Sheet1
LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | GIS_Shapefile
Glades County | N/A | GC-01 | Education and Outreach | FYN; landscaping, irrigation, and fertilizer ordinances; PSAs, pamphlets, website, and illicit discharge program. | Education Efforts | Completed | N/A | 174 | 30 | Fisheating Creek | N/A | Not provided | 5500 | Glades County | Not provided | N/A
Glades County | N/A | GC-02 | Education and Outreach | FYN; landscaping, irrigation, and fertilizer ordinances; PSAs, pamphlets, website, and illicit discharge program. | Education Efforts | Completed | N/A | 915 | 65 | Indian Prairie | N/A | Not provided | 5500 | Glades County | Not provided | N/A
Glades County | N/A | GC-03 | Glades County Caloosahatchee River & Estuary Area Wastewater Grant | Elimination of aging and/or failing existing septic systems in the City of Moore Haven. The Project also provides for additional conveyance capacity for additional homes and businesses. | OSTDS Phase Out | Planned | 2021 | TBD | TBD | West Lake Okeechobee | 86.5 | 891848 | 12240 | GAA | $891,848.00 | LP22023
Glades County | N/A | GC-04 | Glades County Business Park Wetlands | Wetland Maintenance and Planting Agreement | Wetland treatment | In process | 2021 |  |  |  | 8.84 | 42395 |  | Glades County | Not provided
WWTF Disposal Site | Structural | Reuse of reclaimed water or the disposal of effluent on, above, or into the surface of the ground through spray irrigation, other irrigation techniques, rapid-rate systems, absorption fields, overland flow systems, or other methods.