## Project Collection Sheet
Lead Entity | Partners | Project Name | Project Description | Project Type | Project Status | Estimated Completion Date | TN Reduction (lbs/yr) | TP Reduction (lbs/yr) | Location | Acres Treated | Cost Estimate | Cost Annual O&M | Funding Source | Funding Amount | DEP Contract Agreement Number | GIS_Shapefile
Orange County | NA | Shingle Creek Design | Design the top BMPs recommended in the 2019 feasability study. |  | Planned | 2020-09-30 | NA | NA | Upper Kissimmee | TBD | 70000 | NA | Orange County
Orange County | NA | Hickorynut Lake Feasibility Study | Determine the constructability of the top BMPs recommended in the 2019 assessment. |  | Planned | 2020-09-30 | NA | NA | Upper Kissimmee | TBD | 95000 | NA | Orange County
Orange County |  | Skylake Canal Segment K | Slope stabilization along B-01 Canal (Boggy Creek Drainage Basin). Installation of approximately 500 lineal feet of sheet pile and erosion control mat. | Stormwater System Rehabilitation | Underway | 2019 | TBD | TBD | Upper Kissimmee | TBD | 374575 | N/A | Orange County | 374575 | N/A
Orange County |  | Skylake Canal Segment L | Slope stabilization along B-01 Canal (Boggy Creek Drainage Basin). Installation of approximately 700 lineal feet of sheet pile and erosion control mat. | Stormwater System Rehabilitation | Planned | 2020 | TBD | TBD | Upper Kissimmee | TBD | 500000 | N/A | Orange County | 500000 | N/A
Orange County | N/A | Lake Gem Mary Alum Treatment. | In-lake alum surface water treatment. | In-lake surface water alum application. | Proposed | TBD | TBD | TBD | Upper Kissimmee | ±14 Ac | TBD | 0 | OC BCC | TBD | N/A
Orange County | N/A | Shingle Creek Feasibility Study | Determine constructability of BMPs intended to improve water quality and / or impound water. | Various | Underway | TBD | TBD | TBD | Upper Kissimmee | TBD | 197354.17 | 0 | OC BCC | 197354.17 | N/A

## Project Types
Project Type | Structural/Non Structural | Description
100% On-site Retention | Structural | "Retention" means a system designed to prevent the discharge of stormwater runoff into surface waters in the state by complete on-site storage. Examples are systems such as excavated or natural depression storage areas, borrow pits, or above ground storage areas.
Agricultural BMPs | Use Past Designation | Agricultural BMPs are practical, cost-effective actions that agricultural producers can implement to conserve water and reduce the amount of pesticides, fertilizers, animal waste and other pollutants entering our water resources. BMPs are designed to benefit water quality and water conservation while maintaining or even enhancing agricultural production.
Alum Injection Systems | Structural | Alum injection systems are chemical treatment systems that inject aluminum sulfate into stormwater pipes to cause coagulation of pollutants.
Aquatic Vegetation Harvesting | Non-structural | For purposes of project credit, aquatic vegetation is defined as freshwater plants that live in water or on the surface of water. Aquatic vegetation generally includes plant material that is typically herbaceous and predominately angiosperms (flowering plants) and algae. Mechanical removal or harvest of aquatic vegetation is treatment without herbicides or other control mechanisms
Baffle Boxes- First Generation (hydrodynamic separator) | Structural | Concrete or fiberglass structures containing a series of sediment settling chambers separated by baffles.
Baffle Boxes- Second Generation | Structural | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients.
Baffle Boxes- Second Generation with Media | Structural | A second-generation baffle box with the addition of a proprietary blend of sorption media.
Biological/ Bacteria Treatment | Structural | Bacteria used to stimulate the breakdown of the floating organic matter in the pond water column to speed up the decomposition of nutrient-rich organic debris in the muck layer.
Biosorption Activated Media (BAM) | Structural | Engineered media for use in stormwater BMPs to increase the removal of pollutants, especially nutrients.
Bioswales | Structural | A bioswale or vegetated swale is a form of bioretention used to partially treat water quality, attenuate flooding potential, and convey stormwater away from critical infrastructure. These systems are linear, with length to width dimensions much greater than the more typical 2:1 applied to bioretention cells.
BMP Cleanout | Non-structural | Removal of material collected from basins, tanks, vaults, wet ponds, dry ponds, and hydrodynamic separators (such as second-generation baffle boxes).
BMP Treatment Train | Structural | A stormwater management system could be considered a BMP treatment train, in which the individual BMPs are the cars where the water flows from one BMP to another through engineered connections. Generally, the more BMPs that are incorporated into the system, the better the performance of the treatment train.
Catch Basin Inserts/Inlet Filter Cleanout | Non-structural | Devices installed in storm drain inlets that provide water quality treatment through filtration, settling, or adsorption. Catch basin inserts are commercially available products and are generally configured to remove one or more of the following contaminants: coarse sediment, oil and grease, and litter and debris. They may include oil absorbent bags that require regular changing.
Closed Basin | Non-structural | An area that does not discharge to a surface waterbody or an adjacent basin, and is therefore "closed" to exchanging flow with nearby surface waters.
Control Structure | Structural | Weirs, channel control structures, and other control structures are structural components of a stormwater system that detain stormwater and allow its controlled release. Weirs and other control structures are common components of most of the traditional structural controls. They also are found within conveyance systems, such as ditches or secondary/tertiary canals.
Creating/ Enhancing Living Shoreline | Structural | Living shorelines provide shoreline stabilization using a combination of coastal native vegetation for sediment stabilization and, if needed, breakwaters constructed of oyster shells, limestone rock, or other structures conducive to the natural environment.
Creating/ Enhancing Oyster Reefs | Structural | Oyster reefs are built primarily by the eastern oyster, Crassostrea virginica. Oyster reefs are built via the successive reproduction and settlement of larvae onto hard structures such as existing oyster reefs, pilings, rocks, downed trees and recycled oyster shell. Thus, with continued settlement and subsequent generational growth, oysters may form massive reef structures in estuarine systems.
Credit Trade | Trade | Credit Trading
Dairy Remediation | Structural | Waste lagoon remediation including soil excavation for crop fertilization, routing of stormwater to remediated pond to minimize discharge, and reuse of stormwater to reduce groundwater withdrawal.
Decommission/ Abandonment | Non-structural | Closing an industrial/domestic WWTF or Powerplant, etc.
Deep Injection Well | Structural | Class I wells are used to inject hazardous waste (new hazardous waste wells were banned in 1983), nonhazardous waste, or municipal waste below the lowermost underground sources of drinking water. There are more than 180 active Class I wells in Florida. The majority of the Class I injection facilities in Florida dispose of non-hazardous, secondary-treated effluent from domestic wastewater treatment plants.
Denitrification Walls | Structural | Denitrification walls are constructed by mixing a carbon source-such as sawdust-into soils through which groundwater passes. These systems can reduce nitrate inputs to receiving waters by enhancing denitrification.
Dispersed Water Management (DWM) | Structural | DWM programs encourage private property owners to retain water on their land rather than drain it, accept and detain regional runoff for storage, or do both. Landowners typically become involved in the program through cost-share cooperative projects, easements, or payment for environmental services.
Dry Detention Pond | Structural | Dry detention systems are typically utilized in high groundwater table areas where the normal groundwater level makes the use of a retention type facility less feasible. Dry detention systems are intended to be dry basins which are designed to hold a specific quantity of stormwater runoff (treatment volume). Recovery of the design treatment volume occurs as a result of water migration of the stormwater runoff through the pond bottom, discharge through an outfall orifice structure, or into an underdrain system or side bank filter constructed around the perimeter or bottom of the pond.
Education Efforts | Non-structural | Public education efforts include the Florida Yards & Neighborhoods Program, landscaping local code/ordinance, irrigation local code/ordinance, fertilizer local code/ordinance, public service announcements, informational pamphlets, websites, and an inspection program with call-in number for illicit discharges.
Enhanced Public Education | Non-structural | Public education efforts above and beyond the defined public education efforts.
Exfiltration Trench | Structural | An exfiltration trench is a subsurface retention system consisting of a conduit such as perforated pipe surrounded by natural or artificial aggregate which temporarily stores and infiltrates stormwater runoff.
Exotic Vegetation Removal | Non-structural | Removal of a plant species introduced to Florida, purposefully or accidentally, from a natural range outside of Florida, including naturalized exotic species and invasive exotic species.
Fertilizer Cessation | Non-structural | Elimination of fertilizer application.
Fertilizer Reduction | Non-structural | Reduction of fertilizer application.
Filter Marsh | Structural | An artificial ecosystem consisting of a shallow basin established with hydrophytic vegetation that is constructed to intersect and treat the flow of a waste stream or contaminated runoff.
Fish Harvesting | Non-structural | The harvest of fish (often gizzard shad) to improve water quality. These fish feed on algae on the bottom of the waterway, stirring up sediments and clouding the water and excrete nutrients back into the water.
Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Structural | MAPS are aquatic plant-based BMPs that remove nutrients through a variety of processes related to nutrient uptake, transformation, and microbial activities.
Floodplain Restoration | Structural | Converting back to a historic condition those wetlands, surface waters, or uplands that currently exist as one form that differs from the historic condition.
Golf Course or Sports Field BMPs | Non-structural | Practices to reduce fertilizer use on golf courses and/or sports fields
Grass swales with swale blocks or raised culverts | Structural | Swales are designed to infiltrate a defined quantity of runoff (the treatment volume) through the permeable soils of the swale floor and side slopes into the shallow ground water aquifer immediately following a storm event. A swale with swale blocks or raised driveway culverts essentially is a linear retention system in which the treatment volume is retained within the swale by designing periodic linear flow barriers (blocks and culverts) and the water is retained to promote percolation.
Grass swales without swale blocks or raised culverts | Structural | Swales are designed to infiltrate a defined quantity of runoff (the treatment volume) through the permeable soils of the swale floor and side slopes into the shallow ground water aquifer immediately following a storm event. Conveyance swales are designed and constructed to properly convey and infiltrate stormwater runoff as it travels through the swale.
Hybrid wetland treatment technology (HWTT) | Structural | The patented HWTT represents a combination of chemical and wetland treatment approaches, with the system comprised of vegetated zones (primarily with floating and/or submerged macrophytes), non-vegetated zones, internal floc recycling mechanisms, and the drying of floc material with subsequent re-introduction into the treatment train.
Hydrodynamic Separators | Structural | Hydrodynamic separators are small, flow-through devices that remove sediment, trap debris, and separate floating oils from runoff. While their proprietary designs vary, they all primarily rely on swirl action and particle settling to remove pollutants. They appear to be most effective when used for pretreatment in areas where runoff is expected to contain sediment particles greater than 100 microns in diameter. Types of hydrodynamic separators include specific products such as Stormceptor, Storm Treat, VortSentry, CDS, and Aqua-Swirl.
Hydrologic Restoration | Structural | Converting back to a historic condition those wetlands, surface waters, or uplands that currently exist as one form that differs from the historic condition.
Impoundment | Structural | "Retention" means a system designed to prevent the discharge of stormwater runoff into surface waters in the state by complete on-site storage. Examples are systems such as excavated or natural depression storage areas, borrow pits, or above ground storage areas.
Industrial Facility Upgrades | Structural | Upgrades to industrial facilities as outlined in the US EPA 11 regulated categories which reduce point source or nonpoint source pollution which DEP has included in their loading estimates. Examples of EPA Industrial facilities include heavy manufacturing, mining operations, hazardous waste facilities, power plants, and others.
Land Acquisition | Non-structural | Purchasing environmentally significant lands to protect those lands from imminent development or alteration, thereby ensuring present and future generations’ access to important waterways, open spaces, and recreation and conservation lands
Land Preservation | Non-structural | Environmental preservation is the strict setting aside of natural resources to prevent the use or contact by humans or by human intervention. In terms of policy making this often means setting aside areas as nature reserves (otherwise known as wildlife reserves), parks, or other conservation areas.
Land Use Change | Non-structural | “Land use” is the term used to describe the human use of land; land use represents the economic and cultural activities (e.g., agricultural, residential, industrial, mining, and recreational uses) that are practiced at a place. "Land use change" is when the use transitions from one type to another.
LID- Green Roofs | Structural | A roof area built to specifications that includes vegetation, media, and a waterproof membrane. To receive water quality credit, it is specifically built with a cistern or water holding system from which irrigation is provided.
LID- Other | Structural | LID. A stormwater management approach that uses a suite of BMPs (structural and non-structural) distributed throughout the site and integrated as a BMP treatment train (i.e., in series) to replicate the natural hydrologic functioning of the landscape and to reduce the average annual stormwater pollutant loading discharged off-site.
LID- Rain Gardens | Structural | Rain gardens are small retention basins that are integrated into a site's landscaping. They also are called bioretention systems. A rain garden is a shallow, constructed depression that is planted with deep-rooted Florida-Friendly or native plants.
LID- Tree Boxes/Tree Wells | Structural | Tree box filters typically are pre-cast concrete boxes filled with biofiltration media installed below grade at the curb line. They can be installed in open- or closed-bottomed chambers where infiltration is undesirable or not possible.
Macroalgal Harvesting | Non-structural | Mechanical removal of algae from the water surface.
Monitoring/Data Collection | Non-structural | To measure the condition of the chemical, physical, biological, and radiological characteristics of water relative to the requirements of one or more biotic species and/or to any human need or purpose.
Muck Removal/Restoration Dredging | Non-structural | "Dredging" means excavation by any means in surface waters or wetlands, as delineated in Section 373.421(1), F.S. Dredging also means the excavation, or creation, of a water body which is, or is to be, connected to surface waters or wetlands, as delineated in Section 373.421(1), F .S., directly or via an excavated water body or series of water bodies [Section 373 .403(13), F.S.]
Natural Wetlands as Filters | Non-structural | Wetlands are filters for water coming off the land, reducing sediment and chemicals in run off before it gets into open water. These chemicals and sediment could kill fish and amphibian eggs, smother bottom feeding wildlife and plants, and clog waterways. In wetlands, water flow slows so suspended sediment drops out and settles to the wetland floor. Nutrients from manure, sewage systems, and other sources are absorbed for leaf and stem growth of plants. Others are trapped in the soil and used by microorganisms there.
Non-contributing Basin | Non-structural | An area that does not discharge to a surface waterbody or an adjacent basin, and is therefore "closed" to exchanging flow with nearby surface waters.
Off-line Retention BMPs | Structural | Offline BMPs divert the first flush of polluted stormwater (often called "treatment volume") and isolate it from the remaining stormwater, which is managed for flood control. A "retention basin"' is a recessed area within the landscape that is designed to store and retain a defined quantity of runoff, allowing it to percolate through permeable soils into the shallow ground water aquifer.
On-line Retention BMPs | Structural | Online BMPs temporarily store runoff before they discharge to surface waters. A "retention basin"' is a recessed area within the landscape that is designed to store and retain a defined quantity of runoff, allowing it to percolate through permeable soils into the shallow ground water aquifer.
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Structural | Enhancements to conventional septic systems, with nitrogen removal efficiencies expected to be above the 10 % - 50 % estimated for operational level 1 systems, while ensuring that the systems continue to function and provide their expected level of public health protection. This may include drainfield enhancements or the addition of advanced technologies to the tank such as those certified under NSF45 and NSF245.
OSTDS Phase Out | Structural | Phased approach of connecting properties to sanitary sewer in septic tank failure areas.
Pervious Pavement | Structural | Pervious pavement systems include the subsoil, the sub-base, and the pervious pavement. They can include several types of materials or designed systems such as pervious concrete, pervious aggregate/binder products, pervious paver systems, and modular paver systems. Pervious pavement systems are retention systems. They should be used as part of a treatment train to reduce stormwater volume and pollutant load from parking lots, or similar types of areas.
Pervious Pavers | Structural | Pervious pavement systems include the subsoil, the sub-base, and the pervious pavement. They can include several types of materials or designed systems such as pervious concrete, pervious aggregate/binder products, pervious paver systems, and modular paver systems. Pervious pavement systems are retention systems. They should be used as part of a treatment train to reduce stormwater volume and pollutant load from parking lots, or similar types of areas.
Plugging Artesian Wells | Structural | An artesian well (also known as a "free-flowing well") is a well that has been drilled into an aquifer in a location where the underground pressure is great enough for the water to rise inside the well. In some cases, the water is under enough pressure to rise from the aquifer to the land's surface without using a pump. The process of permanently plugging an abandoned well involves installation of a temporary plug where possible, and permanent well abandonment by a licensed well driller.
Reclaimed Water | Structural | "Reclaimed water," except as specifically provided in Chapter 62-610, Florida Administrative Code (F.A.C.), means water that has received at least secondary treatment and basic disinfection, and is reused after flowing out of a domestic wastewater treatment facility.
Regional Stormwater Treatment | Structural | A designed system constructed, operated, and maintained to collect convey, store, absorb, inhibit, treat, use or reuse stormwater to prevent or reduce flooding, overdrainage, environmental degradation and water pollution or otherwise affect the quantity and quality of discharges from multiple parcels and projects within the drainage area served by the regional system, where the term 'drainage area" refers to the land or development that is served by or contributes stormwater to the regional system.
Regulations, Ordinances, and Guidelines | Non-structural | A rule or order issued by an executive authority or regulatory agency of a government and having the force of law.
Retention/Detention BMP Retrofit with Nutrient Reducing Media | Structural | Retrofit of an existing retention or detention BMP with the addition of BAM. BAM is engineered media for use in stormwater BMPs to increase the removal of pollutants, especially nutrients.
Retention/Detention BMP with Nutrient Reducing Media | Structural | Construction of a retention or detention BMP with the addition of BAM. BAM is engineered media for use in stormwater BMPs to increase the removal of pollutants, especially nutrients.
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Structural | Ongoing maintenance associated with WWTFs and sanitary sewers.
Sanitary Sewer Inspections | Non-structural | Inspections of the sanitary sewer system.
SAV Planting | Structural | Planting of seagrasses (grass-like flowering plants that live completely submerged in marine and estuarine waters).
Shoreline Stabilization | Structural | Shoreline stabilization is usually constructed to protect upland property or a shoreline from erosion. Types include natural vegetation stabilization (salt marshes, mangroves, seagrasses, and other native plants) and hardened stabilizers (sea walls, riprap, groins and bulkheads).
Stormwater Aeration System | Structural | Fountain or subsurface aeration system that introduces air into stormwater pond to facilitate biological decomposition of pond muck, de-stratify thermal layers in the water and improve the ecological health of the system. In general, air promotes biological activity, which reduces the amount of available nutrients for algae.
Stormwater Reuse | Structural | "Reuse" means the deliberate application of reclaimed water, in compliance with DEP and District rules, for a beneficial purpose.
Stormwater System Rehabilitation | Structural | "Maintenance" or "Repair'' means remedial work of a nature as may affect the safety of any dam, impoundment, reservoir, or appurtenant work or works, but excludes routine custodial maintenance. [Section 373.403(8), F.S.]
Stormwater Treatment Areas (STAs) | Structural | Constructed wetlands to treat runoff. This is a term commonly used by SFWMD.
Street Sweeping | Non-structural | Pavement cleaning by sweeping, vacuum, or washing.
Study | Non-structural | A detailed investigation and analysis of a subject or situation.
Turbidity Reducing Polymers (e.g., Floc logs ®) | Non-structural | Polymer product that is used to treat turbid or nutrient-laden stormwater.
Vegetated Buffers | Non-structural | Buffers and filter strips are areas of permanent vegetation located within and between agricultural fields, or other nonpoint sources, and the water courses to which they drain. These buffers are intended to intercept and slow runoff thereby providing water quality benefits. In addition, in many settings they are intended to intercept shallow groundwater moving through the root zone below the buffer.
Wastewater Service Area Expansion | Structural | Expansion of the collection/transmission systems including sewers, pipelines, conduits, manholes, pumping stations, force mains, and all other facilities used for collection and transmission of wastewater from individual service connection laterals to WWTFs intended for the purpose of providing treatment prior to release to the environment.
Wet Detention Pond | Structural | "Wet detention" means the collection and temporary storage of stormwater in a permanently wet impoundment in such a manner as to provide for treatment through physical, chemical, and biological processes with subsequent gradual release of the stormwater.
Wetland Restoration | Structural | The return of a wetland and its functions to a close approximation of its original condition as it existed prior to disturbance on a former or degraded wetland site.
Wetland Treatment | Structural | Constructed treatment wetlands are defined as engineered or constructed wetlands that utilize natural processes involving wetland vegetation, soils, and their associated microbial assemblages to assist, at least partially, in treating an effluent or other water source.
WWTF Disposal Site | Structural | Reuse of reclaimed water or the disposal of effluent on, above, or into the surface of the ground through spray irrigation, other irrigation techniques, rapid-rate systems, absorption fields, overland flow systems, or other methods.
WWTF Diversion to Reuse | Structural | Diversion of treated effluent for stormwater reuse. "Reuse" means the deliberate application of reclaimed water, in compliance with Department and District rules, for a beneficial purpose.
WWTF Nutrient Reduction | Structural | WWTF upgrades that are specifically designed to achieve higher levels of nutrient removal.
WWTF Upgrade | Structural | Upgrades to WWTFs as well as the collection/transmission systems including sewers, pipelines, conduits, manholes, pumping stations, force mains, and all other facilities used for collection and transmission of wastewater from individual service connection laterals to WWTFs.
PLEASE CHOOSE A PROJECT TYPE

## Sheet3 (hidden)
Planned | East Lake Okeechobee
Underway | Fisheating Creek
Completed | Indian Prarie
Canceled | Lake Istokpoga
Lower Kissimmee
South Lake Okeechobee
Taylor Creek/Nubbin Slough
Upper Kissimmee
West Lake Okeechobee
Multiple