## Sheet1
LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | GIS_Shapefile
Osceola County | N/A | OSC-01 | Narcoossee Road IB Ponds 2 and 3 | Roadway widening. | Wet Detention Pond | Completed | 2011 | 13 | 0 | Upper Kissimmee | 29.3 | Not provided | 4195 | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-02 | Narcoossee Road III Ponds C3A & C3B | Roadway widening. | Wet Detention Pond | Completed | 2012 | 8 | 0 | Upper Kissimmee | 20.5 | Not provided | 4195 | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-03 | Narcoossee Road III Pond D3 | Roadway widening. | Wet Detention Pond | Completed | 2012 | 8 | 0 | Upper Kissimmee | 24.3 | Not provided | 4195 | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-04 | Narcoossee Road III Pond E1 | Roadway widening. | Wet Detention Pond | Completed | 2012 | 5 | 0 | Upper Kissimmee | 22.4 | Not provided | 4195 | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-05 | Neptune Road I - Ponds 100, 200, and 300 | Road improvement. | Wet Detention Pond | Completed | 2010 | 483 | 18 | Upper Kissimmee | 226.8 | Not provided | 4195 | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-06 | Old Wilson Road Pond D002-P | Road improvement. | On-line Retention BMPs | Completed | 2012 | 42 | 1 | Upper Kissimmee | 55.8 | Not provided | Not provided | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-07 | Old Wilson Road Pond D004-P | Road improvement. | On-line Retention BMPs | Completed | 2012 | 44 | 1 | Upper Kissimmee | 18.7 | Not provided | Not provided | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-08 | Old Wilson Road Pond E002-P | Road improvement. | On-line Retention BMPs | Completed | 2012 | 47 | 2 | Upper Kissimmee | 12.5 | Not provided | Not provided | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-09 | Stewart Street Regional Pond Retrofit | Regional pond retrofit. | Wet Detention Pond | Completed | 2009 | 3851 | 155 | Upper Kissimmee | 2249.2 | Not provided | Not provided | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-10 | Education and Outreach | FYN; landscaping, irrigation, fertilizer, and pet waste management ordinances; PSAs; pamphlets; website; and illicit discharge program. | Education Efforts | Completed | N/A | 23396 | 709 | Upper Kissimmee | N/A | Not provided | 60000 | Osceola County | $60,000 | N/A
Osceola County | N/A | OSC-11 | Education and Outreach | FYN; landscaping, irrigation, fertilizer, and pet waste management ordinances; PSAs; pamphlets; website; and illicit discharge program. | Education Efforts | Completed | N/A | 54 | 6 | Lower Kissimmee | N/A | Not provided | 5000 | Osceola County | $5,000 | N/A
Osceola County | HOA | OSC-12 | East Lake Reserve Stormwater Reuse | Stormwater reuse for landscape irrigation from pond A1 (9.1A). | Stormwater Reuse | Completed | Not provided | 806 | 12 | Upper Kissimmee | 130.8 | Not provided | Not provided | HOA | Not provided | N/A
Osceola County | N/A | OSC-13 | Neptune Rd. Stormwater Reuse | Stormwater reuse for landscape irrigation from Ponds 100/101 and 300. | Stormwater Reuse | Completed | Not provided | 55 | 2 | Upper Kissimmee | 35.7 | 640690 | 26000 | Osceola County | Not provided | N/A
Osceola County | HOA | OSC-14 | Bellalago and Isles of Bellalago Stormwater Reuse | Stormwater reuse for landscape irrigation (197A). | Stormwater Reuse | Completed | Not provided | 6772 | 141 | Upper Kissimmee | 1386.8 | Not provided | Not provided | HOA | Not provided | N/A
Osceola County | Private | OSC-15 | Poinciana Commerce Center Reuse | Stormwater reuse for landscape irrigation from Pond 1. | Stormwater Reuse | Completed | Not provided | 30 | 1 | Upper Kissimmee | 10.2 | Not provided | Not provided | Private | Not provided | N/A
Osceola County | Private | OSC-16 | Kissimmee Bay Reuse | Stormwater reuse; 20-year duration for 84.5 acres of golf course and five-year duration for 45.5 acres of landscape irrigation. | Stormwater Reuse | Completed | Not provided | 2006 | 43 | Upper Kissimmee | 271 | Not provided | Not provided | Private | Not provided | N/A
Osceola County | Private | OSC-17 | Remington Reuse | Stormwater reuse for golf course irrigation from Ponds 12, 13, 14A, and 14B. | Stormwater Reuse | Completed | Not provided | 1154 | 27 | Upper Kissimmee | 149.4 | Not provided | Not provided | Private | Not provided | N/A
Osceola County | Private | OSC-18 | Eagle Lake Reuse | Stormwater reuse for turf irrigation. | Stormwater Reuse | Completed | Not provided | 1927 | 42 | Upper Kissimmee | 435.1 | Not provided | Not provided | Private | Not provided | N/A
Osceola County | Private | OSC-19 | La Quinta Inn Reuse | Stormwater reuse for turf irrigation. | Stormwater Reuse | Completed | Not provided | 31 | 4 | Upper Kissimmee | 12.5 | Not provided | Not provided | Private | Not provided | N/A
Osceola County | DEP/ SFWMD | OSC-20 | Lake Toho Regional Water Storage Facility (Judge Farms) | Construction of a regional stormwater pond and an alternative water supply reservoir | Stormwater Treatment Areas and reuse system | Underway | 2020 | 25500 | 2700 | Upper Kissimmee | 5883 | TBD | TBD | County/ DEP/ SFWMD/Toho Water Authority | County - $32,850,000/ DEP - $1,750,000 SFWMD - $400,000 | LP49021 and S0806
Osceola County | N/A | OSC-21 | Street Sweeping | Monthly street sweeping. | Street Sweeping | Completed | N/A | 102 | 35 | Upper Kissimmee | N/A | Not provided | 60000 | Osceola County | $60,000 | N/A
Osceola County | N/A | OSC-22 | Buenaventura Lakes Golf Course Ponds | Two new lakes at golf course. | Wet Detention Pond | Completed | Not provided | 13 | 4 | Upper Kissimmee | 517.7 | Not provided | Not provided | Osceola County | Not provided | N/A
Osceola County | N/A | OSC-23 | Slaman | Conservation areas. | Land Preservation | Completed | 2008 | 1 | 0 | Upper Kissimmee | 32.2 | Not provided | 1500 | Osceola County | $1,500 | N/A
Osceola County | N/A | OSC-24 | Jim Yates | Conservation areas. | Land Preservation | Completed | 2009 | 7 | 1 | Upper Kissimmee | 5.3 | Not provided | 3750 | Osceola County | $3,750 | N/A
Osceola County | N/A | OSC-25 | Udstad | Conservation areas. | Land Preservation | Completed | 2008 | 17 | 1 | Upper Kissimmee | 5.9 | Not provided | 3500 | Osceola County | $3,500 | N/A
Osceola County | N/A | OSC-26 | Proctor | Conservation areas. | Land Preservation | Completed | 2009 | 1 | 0 | Upper Kissimmee | 0.7 | Not provided | 1750 | Osceola County | $1,750 | N/A
Osceola County | N/A | OSC-27 | Twin Oaks | Conservation areas. | Land Preservation | Completed | 2009 | 584 | 104 | Upper Kissimmee | 399.6 | Not provided | 16500 | Osceola County | $16,500 | N/A
Osceola County | N/A | OSC-28 | Cherokee Point | Conservation areas. | Land Preservation | Completed | 2005 | 15 | 3 | Upper Kissimmee | 178.6 | Not provided | 21800 | Osceola County | $21,800 | N/A
Osceola County | HOA | OSC-29 | Encatada Resort | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 73 | 7 | Upper Kissimmee | 57.6 | Not provided | Not provided | HOA | Not provided | N/A
Osceola County | HOA | OSC-30 | Cypress Palms Condos | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 23 | 2 | Upper Kissimmee | 12.4 | Not provided | Not provided | HOA | Not provided | N/A
Osceola County | HOA | OSC-31 | Lake Pointe | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 711 | 13 | Upper Kissimmee | 150.2 | Not provided | Not provided | HOA | Not provided | N/A
Osceola County | HOA | OSC-32 | Traditions at Westside | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 43 | 5 | Upper Kissimmee | 21.7 | Not provided | Not provided | HOA | Not provided | N/A
Osceola County | N/A | OSC-33 | Hoagland Blvd Phase III | Road Widening | Hydrodynamic Separators | Underway | 2020 | N/A | 0 | Upper Kissimmee | 14.6 | 16000 | 2400 | Osceola County | $16,000.00 | N/A