## Sheet1
LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | GIS_Shapefile
Polk County | Extension Office/ County Utilities/ Lakes Education Action Drive/ Municipal Agencies | PC-01 | Education and Outreach | FYN, fertilizer ordinance, PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 2396 | 86 | Lake Istokpoga | N/A | N/A | 2000 | Polk County | $2,000 | N/A
Polk County | Extension Office/ County Utilities/ Lakes Education Action Drive/ Municipal Agencies | PC-02 | Education and Outreach | FYN, fertilizer ordinance, PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 901 | 50 | Lower Kissimmee | N/A | N/A | 3000 | Polk County | $3,000 | N/A
Polk County | Extension Office/ County Utilities/ Lakes Education Action Drive/ Municipal Agencies | PC-03 | Education and Outreach | FYN, fertilizer ordinance, PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 9784 | 262 | Upper Kissimmee | N/A | N/A | 2000 | Polk County | $2,000 | N/A
Polk County | SFWMD | PC-04 | Sumica Preserve Water Storage/Hydrologic Restoration | Construction of a gravel berm to store water onsite for wetland restoration. | Wetland Restoration | Completed | 2010 | 21 | 17 | Upper Kissimmee | 4077.4 | 42850 | 13000 | Polk County/ SFWMD | County - $21,425/ SFWMD - $21,245 | N/A
Polk County | SWFWMD / NRCS / FDOT |  | Crooked Lake Surface Water Restoration | Block old agricultural ditches thrugh wetland for re-hydration | Wetland Restoration | On county CIP, design and permitting at 60% | 2022 | TBD | TBD | Upper Kissimmee | 4660 | 804150 | 4000 | Polk County/ SFWMD | County - $402, 075/ SFWMD - $402,075 | N/A
Polk County | SWFWMD |  | Sunset Trail Water Quality Improvements (Crooked Lake basin) | Divert roadway runoff to treatment area | Pollutant load reduction | On county CIP | 2023 | TBD | TBD | Upper Kissimmee | 75 | TBD | TBD | TBD | TBD | N/A
Polk County | DEP |  | Lake Rosalie Canal Restoration (Lake Kissimmee State Park) | Restore historical flow patterns to adjacent wetlands | Wetland Restoration | Unfunded county CIP project | TBD | TBD | TBD | Upper Kissimmee | 600 | TBD | TBD | TBD | TBD | N/A
Polk County | City Davenport |  | Restoration of Lake Play and nearby Wetlands | Water quality treatment, habitat enhancement | Wetland Restoration, Water Quality Treatment | Unfunded county CIP project | TBD | TBD | TBD | Upper Kissimmee |  | TBD | TBD | TBD | TBD | N/A