LSJR Main Stem BMAP Implementation Schedule
for the 2010 Annual Report


PROJECT MILESTONES FOR NOVEMBER 1, 2009 THROUGH DECEMBER 31, 2010
	DATE
	ENTITY
	PROJECT NUMBER
	DESCRIPTION

	11/01/09
	Orange Park
	OP-2
	Final plans and specifications complete for Phase Two improvements at WWTF

	12/31/09
	Seminole Electric
	SE-1
	SCR upgrade complete

	01/01/10
	St. Johns County
	SJC-5, SJC-13, SJC-23
	Start development of slow release fertilizer ordinance

	01/30/10
	Orange Park
	OP-1
	Complete construction of Phase One improvements at WWTF

	2/28/10
	Orange Park
	OP-1
	Begin operation of Phase One improvements at WWTF

	04/01/10
	Atlantic Beach
	AB-2
	Begin construction on reuse water line to Selva Marine Golf Course (pending agreement with county club)

	04/15/10
	Orange Park
	OP-1
	Operational level attained for Phase One improvements at WWTF

	05/30/10
	Palatka
	PAL-5
	Complete construction on zero discharge at WWTF

	08/31/10
	Putnam County
	PUT-2
	Complete construction and trade with Hiawatha WWTF

	09/01/10
	Neptune Beach
	NB-1
	Complete final plans and specifications for the WWTF upgrade

	09/30/10
	Green Cove Springs
	GCS-1, GCS-2
	Preliminary plans complete for WWTFs upgrades

	10/01/10
	Atlantic Beach
	AB-3
	Complete plans and specifications for WWTF upgrade to AWT

	10/01/10
	CCUA
	CCUA-2
	Complete construction on reuse water upgrades

	10/01/10
	Putnam County
	PUT-4
	Take over O&M at Edgefield RST

	10/01/10
	St. Johns County
	SJC-6
	Take over O&M at Deep Creek RST

	10/31/10
	Putnam County
	PUT-6
	Complete project assessment for Algal Initiative

	10/31/10
	St. Johns County
	SJC-17, SJC-26
	Complete project assessment for Algal Initiative

	11/01/10
	Orange Park
	OP-3
	Preliminary plans complete for Phase Three improvements at WWTF

	11/30/10
	Atlantic Beach
	AB-2
	Complete construction on reuse water line to Selva Marine Golf Course (pending agreement with county club)

	12/01/10
	CCUA
	CCUA-2
	Achieve operational level on reuse water upgrades

	12/15/10
	Atlantic Beach
	AB-2
	Begin operation on reuse water line to Selva Marine Golf Course (pending agreement with county club)

	12/31/10
	Camp Blanding
	CB-1
	Complete regrade/maintenance of next set of swales

	12/31/10
	FDOT
	COJ-94
	Complete construction of Beach Blvd improvements from west of FCCJ to east of San Pablo

	12/31/10
	Jacksonville Beach
	JB-2
	Complete FDOT Beach Blvd widening (Pond 2)

	12/31/10
	JEA
	JEA-10
	Complete phase out of Beacon Hills

	12/31/10
	JEA
	JEA-13
	Complete construction of Arlington East

	12/31/10
	Palatka
	PAL-5
	Operational level attained for zero discharge at WWTF

	12/31/10
	St. Johns County
	SJC-7
	Purchase TP credits from Hastings WWTF




ONGOING PROJECT EFFORTS
	ENTITY
	PROJECT NUMBER
	DESCRIPTION

	City of Jacksonville
	COJ-51
	Education

	Clay County
	CC-1, CC-3, CC-12, CC-17
	Education

	FDOT
	COJ-117, COJ-118
	Education

	St. Johns County
	SJC-3, SJC-11, SJC-21
	Education

	St. Johns County 
	SJC-4, SJC-12, SJC-22
	LID

	St. Johns County
	SJC-2, SJC-10, SJC-20
	Street sweeping
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