



Tributaries of the Lower St. Johns
Fecal Coliform BMAP-Phase I Process and Schedule
August 11, 2008
	Action*
	Agency/Committee
	Date

	Project collection sheets due (for first seven WBIDs in Set A)
	All responsible parties (COJ, JEA, FDOT, DCHD)
	August 29, 2008

	Basin Working Group meeting – background information and overview
	Basin Working Group
	Early/mid-September, 2008

	Start review of sufficiency of effort and monitoring plan discussions at the September meeting
	Technical Working Group
	September 18, 2008

	Project collection sheets due (for last three WBIDs in Set A and first WBID in Set B)
	All responsible parties (COJ, JEA, FDOT, DCHD)
	September 30, 2008

	Partial draft BMAP with one complete WBID analysis for TWG review; continue sufficiency of effort review at the October meeting
	FDEP (draft BMAP), TWG (review BMAP)
	October 16, 2008

	Comments on partial draft BMAP due 
	Technical Working Group
	October 30, 2008

	BWG starts review of sufficiency of effort and project collection sheets 
	Basin Working Group
	November 6, 2008

	Complete review of sufficiency of effort and monitoring plan discussions at November meeting for eleven WBIDs
	Technical Working Group
	November 13, 2008

	BWG completes review of sufficiency of effort and project collection sheets 
	Basin Working Group
	December 11, 2008

	Draft BMAP available for TWG review
	FDEP (draft BMAP), TWG (review BMAP)
	January 16, 2009

	Comments on BMAP from TWG due
	Technical Working Group
	February 13, 2009

	Final Draft BMAP for BWG review
	FDEP
	February 27, 2009

	FDEP staff file notice for public meeting
	FDEP
	March 13, 2009

	BWG review and endorsement of BMAP
	Basin Working Group
	March 26, 2009

	Public meeting on BMAP
	Public/FDEP
	April 9, 2009

	Public comment period closes
	FDEP
	April 24, 2009

	Review of public comments by staff complete
	FDEP
	May 1, 2009

	Proposed BMAP
	FDEP
	May 8, 2009

	Notify interested parties and place FAW notice
	FDEP
	May 11, 2009

	End of challenge period (21-days after notice)
	FDEP
	June 1, 2009

	BMAP adopted and enforceable (if there are no challenges) (eleven WBIDs)
	FDEP
	June 1, 2009


*While the first set of WBIDs is incorporated into the BMAP, the next set of technical reports and project collection efforts will be underway.  This schedule only shows the process for the Phase I BMAP.

