Lakes Harney and Monroe Basin Management Action Plan (BMAP)
Draft Process and Schedule
December 15, 2011


Stakeholder and FDEP Staff Actions for BMAP Adoption
	ACTION
	RESPONSIBLE PARTY
	DATE

	Draft BMAP to stakeholders for review
	FDEP (draft BMAP), Technical Stakeholders (review BMAP)
	January 13, 2012

	Comments on Draft BMAP due to FDEP
	Technical Stakeholders
	February 3, 2012

	Revised Draft BMAP to stakeholders for review
	FDEP
	February 9, 2012

	Technical meeting to discuss Revised Draft BMAP
	FDEP and Technical Stakeholders
	February 16, 2012

	Comments on Revised Draft BMAP due to FDEP
	Technical Stakeholders
	February 23, 2012

	Final Draft BMAP for stakeholder review
	FDEP
	March 1, 2012

	Policy briefing on Final Draft BMAP
	FDEP, Policy Makers, and Technical Stakeholders
	March 15, 2012

	Public meeting on BMAP
	Public/FDEP
	Early-April 2012

	Public comment period closes (30 days)
	FDEP
	Early-May 2012

	Review of public comments by staff complete
	FDEP
	Mid-May 2012

	Letters of commitment due for inclusion in BMAP package to FDEP Secretary
	BWG and Technical Stakeholders
	End-May 2012




FDEP Secretarial Adoption Process
	ACTION
	DATE

	Brief FDEP DEAR  management on BMAP
	Early-June 2012

	Brief FDEP Deputy Secretary on BMAP
	Mid-June 2012

	Brief FDEP Secretary on BMAP and obtain Secretarial approval
	End-June 2012

	Notify interested parties and place FAW notice
	End-June 2012

	End of challenge period (21-days after notice)
	End-July 2012

	BMAP adopted and enforceable (if there are no challenges)
	End-July 2012
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