## Sheet1
Step | Instruction | Stage Description | Explanation
1 | Engage district leadership | Project management
2 | Establish district training date | Project management
3 | Get account-holder names from district contact | Project management
4 | Format account request for OTIS | OTIS coordination
5 | Correct district structure data | Data prep
6 | Create point layer from polygons | Data prep
7 | Fix up attributes | Data prep | Join insurance on building number & calculate most current data; find underlying date of construction & calculate historic based on spatial location where historic; calculate ADA base on spatial location where ADA; replacement cost; round sq ft
8 | Create demo copy of data | Demo/Training | In order to not mess up real data; create a copy of the data to host on AGO that contains only the park that we're training at
9 | Host to AGO | Demo/Training | upload as a new service entirely separate from OTIS-hosted data
10 | Create demo map | Demo/Training | copy real map & replace service
11 | Create local copy of hosted data | Production data | add district's real data to production layer
12 | Add in district facility points | Production data | add district's real data to production layer
13 | Add in district facility polygons | Production data | add district's real data to production layer
14 | Sync changes to service | Production data | add district's real data to production layer
15 | Ask OTIS for accounts | OTIS coordination
16 | Receive accounts | OTIS coordination
17 | Intro email to district account-holders | Project management | download collector; download test park or not; we'll see you there; reach out with any questions
18 | Train at district meeting | Project management