## Communication plan
Item | Owner | Audience | Contents | Frequency | Channel
Cadence Meetings | EarthSoft Implementation Team | Client Implementation Team | Meetings to discuss project goals, planning, schedules, deliverables, and administration. Planned as separate meetings with EarthSoft and Client teams. | Weekly | Online-Meeting
KPI indicators | EarthSoft Project Manager | Client Project Manager | Updates with Key Performance Indicators as Budget at Completion, Actual Cost, Actual Percent Completed, Planned Percent Completed, Earned Value (EV), Planned Value (PV), Cost Variance (CV), Cost Performance Index (CPI), Schedule Variance (SV), Schedule Performance Index (SPI), Estimate at Completion (EAC), Estimate to Completion (ETC), Variance at Completion (VAC) and To-Complete Performance Index (TCPI). | Monthly | Sharepoint and Email
Financial status report | EarthSoft Project Manager | Client Project Manager | Monthly Billing report | Monthly | Email
Ad-hoc technical meetings | EarthSoft Technical Lead | Client Implementation Team and SMEs | Meetings to discuss technical solutions for certain tasks. | As needed | Online-Meeting
Working Session and Q&A Meetings | EarthSoft Technical Lead | Client Implementation Team and SMEs | Purpose is to transfer EQuIS knowledge and skills to the Client and allow for Q&A between the Client and technical staff on EQuIS features and specific deliverables in an informal learning setting. | As needed | Online-Meeting
Demonstration of Deliverable | EarthSoft Technical Lead | Client Implementation Team and SMEs | The purpose of these meetings is to present a deliverable and show the Client how it works/where it is, etc. It will punctuate EarthSoft´s delivery of a feature, customization or milestone and receive feedback from the Client. | As needed | Online-Meeting
Issue Log | EarthSoft Project Manager | Client Implementation Team | Log of issues encountered during project implementation. | As needed | Sharepoint
Project Schedule | EarthSoft Project Manager | Client Implementation Team | Regular updates to the Project schedule, based on project progress, task status and deliverables. | Monthly | Sharepoint
Change Order | EarthSoft Project Manager | Client Project Manager | If budget increases or addition of task not included in the SoW are necessary EarthSoft will create a Change Order and send it to the Client for approval. | As needed | Email

## Communication methods
Form | Method | Code | Column1
Informal Written | Email, Memorandums
Formal Written | Contracts, Project Documents, Change Orders
Informal Verbal | Phone calls, unscheduled discussions
Formal Verbal | Presentations
Push | Email; Parcel Post for confidential information
Pull | Download (Sharepoint)
Interactive | Meetings; Minutes provided by EarthSoft; Recording if required

## Stakeholder List
Organization | Name | Role | Group | Email
EarthSoft | Jürgen Schütz | Project Manager | EarthSoft Implementation Team | jurgen.schutz@earthsoft.com
EarthSoft | Ridmi Rathnasooriya | Supporting PM | EarthSoft Implementation Team | ridmi.rathnasooriya@earthsoft.com
EarthSoft | Andrew Tomlins | Technical Lead | EarthSoft Implementation Team | andrew.tomlins@earthsoft.com
EarthSoft | Donald Grospe | Supporting TL | EarthSoft Implementation Team | donald.grospe@earthsoft.com
EarthSoft | Karina Smith | Supporting TL | EarthSoft Implementation Team | karina.smith@earthsoft.com
EarthSoft | Jo Tidmarsh | Key Technical Resource Data Migration | EarthSoft Data Migration Team | jo.tidmarsh@earthsoft.com
EarthSoft | Jenna Hunsinger | Key Technical Resource Training | EarthSoft Data Training Team | jenna.hunsinger@earthsoft.com
EarthSoft | Kathy Garvin | Implementation Solutions Director | EarthSoft Management | kathy.garvin@earthsoft.com
EarthSoft | Tara Wojtowicz | Technical Solutions Director | EarthSoft Management | tara.wojtowicz@earthsoft.com
|  | TCLW, Project Manager | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Data Manager | Client Implementation Team
|  | Corporate Environment | Client Implementation Team
|  | Delivery Lead | Client Implementation Team
|  | PMO, Manager | Client Implementation Team
|  | Technology Adoption | Client Implementation Team
|  | Business Analyst | Client Implementation Team
|  | Mining SME | Client Implementation Team
|  | Site Project Sponsor | Client Implementation Team
|  | Environment | Client Implementation Team
|  | TRMP | Client Implementation Team
|  | MIS | Client Implementation Team
|  | TRMP | Client Implementation Team
|  | TRMP | Client Implementation Team
|  | MIS | Client Implementation Team
|  | MIS | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Environment | Client Implementation Team
|  | Environment | Client Implementation Team

## RACI Matrix ES
Task / Stakeholders | Project Manager (PM) | Technical Lead (TL) | Key Technical Resource | Primary Task Contributor | Supporting PM | Developer | RACI
Track 1 Task 1- EQuIS Configuration | R | A |  |  | C |  | R - Responsible The people who take action to get the task done. They are responsible for the work or making the decision. You can have more than one person responsible for a task, but to make the decision-making process effective, try having one person responsible for a single task. | A - Accountable The person who owns the task or devlierable. They might not get the work done themselves, but they are responsible for making sure it is finalized. To avoid confusion and the the diffusion of responsibility, it's better to have one accountable person per project task.
Track 1 Task 2- EQuIS Online Training | C | C | R | A | I
Track 1 Task 3- Data Management Plan | R | C | I | A | C
Track 1 Task 4- EQuIS Workflow Documentation | R | A |  | A | C |  | C - Consulted The person, role, or group who will help complete the task. They will have two-way communication with the people responsible for the task by providing input and feeback over the task completion. | I - Informed The people, roles, or groups that need to be up to date on the task's progress. They will not have two-way communication, but it's essential to keep them informed since they will be affected by the final outcome of the task/project.
Track 2- Data Migration | C | I | R | A | I
Track 3- Project Managemt, Cadence Meetgs & Comm Plans | A | C |  |  | C
Track 4- Systems Integration | C | R |  | A | I | A
Change Orders | R | A | C | C | I

## RACI Matrix Client
Task / Stakeholders | Project Sponsor | Project Manager (PM) | Supporting PM | Technical Lead (TL) | ITAS lead | Data Management Support | Subject Matter experts | End users | Line Management | Procurement | Finance | RACI
Track 1 Task 1- EQuIS Configuration | A | R | C | C | C | C | C |  |  |  |  | R - Responsible The people who take action to get the task done. They are responsible for the work or making the decision. You can have more than one person responsible for a task, but to make the decision-making process effective, try having one person responsible for a single task. | A - Accountable The person who owns the task or devlierable. They might not get the work done themselves, but they are responsible for making sure it is finalized. To avoid confusion and the the diffusion of responsibility, it's better to have one accountable person per project task.
Track 1 Task 2- EQuIS Online Training |  | A | R | R | R | R | R | R | R |  | I
Track 1 Task 3- Data Management Plan | A | R | R | C | C | C | C
Track 1 Task 4- EQuIS Workflow Documentation | A | R | R | C | C | C | C | C | C |  |  | C - Consulted The person, role, or group who will help complete the task. They will have two-way communication with the people responsible for the task by providing input and feeback over the task completion. | I - Informed The people, roles, or groups that need to be up to date on the task's progress. They will not have two-way communication, but it's essential to keep them informed since they will be affected by the final outcome of the task/project.
Track 2- Data Migration |  | A | R | C | R | C | R | C | C | I
Track 3- Project Managemt, Cadence Meetgs & Comm Plans |  | A | A | R | R | R | C |  | I |  | I
Track 4- Systems Integration |  | A | R | C | R | C | C
Change orders | A | [9 empty] | C | bar: A to R; I

## Requirements
The Communications Management Plan will organize and document the process, types, and expectations of communications. It provides the following:
The stakeholder communications requirements in order to communicate the appropriate information as demanded by the stakeholders.
Information on what is to be communicated. This plan includes the expected format, content, and detail—e.g. project reports versus quick e-mail updates.
Details on how needed information flows through the project to the correct individuals. The communication structure documents where the information will originate, to whom the information will be sent, and in what modality the information is acceptable.
Appropriate methods for communicating include e-mails, memos, reports.
Schedules of when the various types of communication should occur. Some communications, such as cadence meetings, should happen on a regular schedule, while other communications may be prompted by conditions within the project.
Escalation processes and timeframes for moving issues upwards in the organizations when they can't be solved at lower levels.
Methods to retrieve information as needed.
Communications Management Plan
 Who should receive project communications
 What communications they should receive
 Who should send the communication
 How the communication will be sent
 How often it will be updated
 Definitions so that everyone has a common understanding of terms.