## Sheet1
| Program Area SW or HW | Report Title | Issue | Report Criteria Entered | Tester | Date | Resolved by | Resolved Date | Retest by | Retest Date
1 | HWs | new notifiers | There are no records based on the selected criteria. | all districts for LQG for 6 months date range. | Jack G | 2008-10-02
2 | HWs | CM&E Activities | There are no records based on the selected criteria. | all 01/01/07 to today - PDF or HTML | Jack G | 2008-10-02
3 | HWs | Unlinked Enforcement Activities | There are no records based on the selected criteria. | all 01/01/07 to today - PDF or HTML | Jack G | 2008-10-02
4 | HWs | RCRA Related Case Report | header incorrect/for CRMS/COMP Drill downs not working | no criteria selectable - PDF | Jack G | 2008-10-02
5 | HWs | RCRA Related Case Report | There are no records based on the selected criteria. | no criteria selectable - HTML | Jack G | 2008-10-02
6 | SW | Number of Facility Inspections | There are no records based on the selected criteria. | all 01/01/07 to today - PDF or HTML | Jack G | 2008-10-02
7 | SW | Solid Waste Inspections by | There are no records based on the selected criteria. | all 01/01/07 to today - PDF or HTML | Jack G | 2008-10-02
8 | SW | Solid Waste Projects by | There are no records based on the selected criteria. | all 01/01/07 to today - PDF or HTML | Jack G | 2008-10-02
9 | SW | Solid Waste Activities Coded as | There are no records based on the selected criteria. | all 01/01/07 to today - PDF or HTML | Jack G | 2008-10-02
10 | SW | Solid waste facility inventory Report | drill downs - some work / some don’t | Jackson County | Jack G | 2008-10-02
11 | SW/HWs | Handler Search | drill downs - some work / most don’t | safet | Jack G | 2008-10-02
12 | SW/HWs | Enforcement activity tracking report | lots of not available yet | SW or HWs no criteria selectable - PDF | Jack G | 2008-10-02
13 | SW/HWs | Enforcement activity tracking report | no display | SW orHWs no criteria selectable - HTML | Jack G | 2008-10-02
14 | SW/HWs | PMDC | no live data - all test. Otherwise - OK except for some missing inspection types | all inspections - PDF | Jack G | 2008-10-02
15 | SW/HWs | PMDC | no output | all inspections - HTML | Jack G | 2008-10-02
16 | HWs | RCRA Related Case Report | Incorrect Header for COMP - Days until Complaint Field |  | Kowit J | 2008-10-02
17 | HWs | RCRA Related Case Report | Detail page of OGC case history is not working |  | Kowit J | 2008-10-02
18 | HWs | RCRA Related Case Report | No total facility count |  | Kowit J | 2008-10-02
19 | HWs | RCRA Related Case Report | Other Active Litigation Cases for RCRA Report Purposes is not working |  | Kowit J | 2008-10-02
20 | HWs | RCRA Related Case Report | CRMS - Days until Authorization to Sue memo was sent to Secretary Office should be CRMS - Days since Authorization to Sue memo was sent to Secretary Office |  | Jack G | 2008-10-03
21 | HWs | RCRA Related Case Report | CRMS - Days until Complaint should be Filed CRMS - Days since Complaint Filed |  | Jack G | 2008-10-03
22 | HWs | RCRA Related Case Report | ETA Key going to be click-through to get to the case? Will it be explained? Is it important, useful or valuable information? |  | Jack G | 2008-10-03
23 | HWs | RCRA Related Case Report | Details click-through is not working |  | Jack G | 2008-10-03
24 | HWs | Unlinked Enforcement Activities | Sort by fuction is not working | all from 01/01/2008 and 10/02/2008, Active Principal :all, Sort By : all four choices - PDF | Kowit J | 2008-10-02
25 | HWs | Unlinked Enforcement Activities | Principal List contains inactive inspector name. |  | Kowit J | 2008-10-02
26 | HWs | CM&E –Haz Waste report | Name sort was selected and the output was not sorted by name – same for EPA ID sort – sort option appears to not be working. |  | Jack G | 2008-10-03
27 | HWs | CM&E –Haz Waste report | Are ETA Key and Activity Key going to be click-through? Will they be explained? Are they important, useful or valuable information? |  | Jack G | 2008-10-03
28 | HWs | CM&E –Haz Waste report | Legacy data activity code description is pretty sketchy, is this all we have? |  | Jack G | 2008-10-03
29 | HWs | CM&E –Haz Waste report | Can we get an EPA ID Number as a Criteria/Parameter? This could be useful on a site by site basis as well. |  | Jack G | 2008-10-03
30 | HWs | Unlinked Enforcement Activities For Hazardous Waste | Name sort was selected and the output was not sorted by name – same for EPA ID sort – sort option appears to not be working. |  | Jack G | 2008-10-03
31 | HWs | Unlinked Enforcement Activities For Hazardous Waste | is ETA Key going to be click-through to get to the unlinked activity? Will it be explained? Is it important, useful or valuable information? |  | Jack G | 2008-10-03
32 | HWs | Unlinked Enforcement Activities For Hazardous Waste | the Activity Code Description could be more descriptive – “Enforcement Tracking” is a little generic. |  | Jack G | 2008-10-03
33 | HWs | New Notifications of Hazardous Waste Generators -- and Status Changes - There are no records based on the selected criteria. (within 6 months – all) |  |  | Jack G | 2008-10-03
34 | HWs | Enforcement Tracking Report | many Not Available Yet columns |  | Jack G | 2008-10-03
35 | HWs | Enforcement Tracking Report | is Activity Key going to be click-through to get to an activity? Will it be explained? Is it important, useful or valuable information? |  | Jack G | 2008-10-03
36 | HWs | Enforcement Tracking Report | legacy data for significance through final order columns (10-15) do not appear to have legacy data yet. |  | Jack G | 2008-10-03
37 | HWs | Handler Search | Status sort was selected and the output was not sorted by status– sort option appears to not be working. |  | Jack G | 2008-10-03
38 | HWs | Handler Search | Details click-throughs not working |  | Jack G | 2008-10-03
39 | HWs | PMDC results | columns 12-15 could be removed from the Haz Waste display – They will always be empty. |  | Jack G | 2008-10-03
40 | SWs | PMDC results | columns 12-17 do not line up under the headings –HTML - All Site Inspections in the fourth quarter FY 2007/2008 and first quarter FY 2008/2009 |  | Jack G | 2008-10-03