## Sheet1
Item # | Type Code | Team Code | Mediumission IMediumpact | Barrier Description (from flip chart) | Dispo Code | Term | Action to be taken | Contact
TEAM BLUE
1 | 1 | o | Medium | incomplete info in the databases for the files | A | S | 39. Provide guidance to staff when multiple site numbers are identified with the same property to link each site number for future searches in PA or ERP ce (correct inaccurate information). (same for barriers 5, 21) | Linda Hodges, Jen | b
2 | 2 | o | High | title determination turn around time is too long | M, A | S | 9. District enforcement staff communicates time constraints to Title Section so that Title Section understands priorities. Add deadline field to Title Determination request form. | Aaron | Alissa, Tonya, Mike, Greg, Eric
3 | 2 | o | Medium | survey mapping responses that are faxed are not readable | A | S | 37. District need to get rights to access stitle determinations contained in OCULUS. Title will email when determination is complete. | Kate G.
4 | 2 | o | Medium | searching BTLDS is difficult to navigate | A | S | 36. DSL meets in OSLER staff for tutorial who will relay information to District which OSLER will demonstrate specific problems to DSL (example - Mount Royal) | donna |  | TEAM PINK
5 | 2 | o | Medium | searching for PA past permits is difficult because you don't have an ID number | A | S | 39. Provide guidance to staff when multiple site numbers are identified with the same property to link each site number for future searches in PA or ERP ce (correct inaccurate information). (same for barriers 1, 21) | Linda Hodges, Jen | p
6 | 1 | p | Medium | Water Management authorizations are unclear, prevents enforcement | A | S | 33. Bring up specific cases on WMD at upcoming Anti-drift meetings | Tim | Jen, Tim, JJ, Terri, Jim
7 | 2 | o | Medium | the SDE layer for State Lands is inaccurate (Map Direct) | A | S | 35. Contact Gary Kekelis in OTIS to see if accuracy issues can be addressed. Also someone in SL to address GIS layer. | Kate G.
8 |  |  |  | Map Direct is inaccurate and search engine is difficult to navigate |  |  |  |  | TEAM ORANGE
9 | 1 | o | High | Staff (SLIs) don't know all the info and issues to compile | A | S | 23. Obtain clear understanding of site history via use of: checklist/ SLERC form. (same for barriers 25, 36) | Savage | o
10 | 2 | o | Medium | have to pull data from multiple databases to compile site investigation history | A | S | 41. create list in OPM manual the available databases/ websites so every one has knowledge of all available databases/ websites (Internal and external sources) (same for barrier 53) | Jim | Russell, Aaron, Kelli, Donna
11 | 1,2 | p | Low | aerials between 1970 and 1990 are not available | A | S
12 | 1 | o | Low | local clerk sites are not DEP friendly regarding access and printability | A | S
13 | 2 | o | Low | specific title determination between state lands and private lands is difficult to obtain. Specific title determination does not provide a survey | P | S
14 |  |  |  | large areas of title determination is difficult to get a determination (answer)
15 | 1 | b | Medium | determining lessee/responsible party can be difficult | P | S | 29. Use "accurint" or law enforcement or contact Laurie Roughton. | ?
16 | 1 |  |  | contacting responsible parties can be difficult
17 | 1 | p | High | determining what is a violation is inconsistent | M, A | L | 18. Develop a penalty matrix when chapter 18-14 revisions are approved. Include categorization of common violations good faith adjustments (as guidance not rule). Include instructions on how to use Matrix. (same for barriers 26, 29, 30, 31, 32, 33, 44, 61) | Donna, Scott W, Ryan, Terri
18 | 1,2 | o | Medium | current inspection report is not applicable to easements | A | S | 38. Develop easement inspection report with assistance from Susan Riggs utilizing existing lease inspection report | Aaron, Russell
19 | 1 | o | Medium | have to hand write the inspection report and then type it in the computer into the form | A | S | 42. Incorporate SL inspection form into existing PDAs (same for barrier h12) | ?
20 | 1 | o | Low | language is inspection report is inconsistent in the comment section | A | S
21 | 1 | o | Medium | previous ERPce data entry is incomplete | A | S | 39. Provide guidance to staff when multiple site numbers are identified with the same property to link each site number for future searches in PA or ERP ce (correct inaccurate information). (same for barriers 1, 5) | Linda Hodges, Jen
23 | 1 | o | Low | language used in ERPce data entry is inconsistent | A | S
24 | 1 | p | Medium | management is not always available to discuss the case with SLI | P | S | 28. Have weekly meeting to have management supervisor to go over issues important issues to SLI. Management must have Agenda placed on common drive so any SLI can add to the agenda SLI must have penalty calculations, site inspections report and case. Use as preparation for respondent meeting (same for barriers 65, 67, 68, 70, 103, h39) | Eric
25 | 1 | o | High | SLI needs to be ready to meet with management regularly case discussion (needs to know history of case) | A | S | 23. Obtain clear understanding of site history via use of: checklist/ SLERC form. (same for barriers 9, 36) | Savage
26 | 1 | p | High | determine penalties is inconsistent between districts | M, A | L | 18. Develop a penalty matrix when chapter 18-14 revisions are approved. Include categorization of common violations good faith adjustments (as guidance not rule). Include instructions on how to use Matrix. (same for barriers 17, 29, 30, 31, 32, 33, 44, 61) | Donna, Scott W, Ryan, Terri
27 | 3 |  |  | political pressure dictates penalties assessed | D
28 | 1 | p | Low | penalty calculations over a certain size ($25k) need to be routed through OGC & through chain, slows process | Dropped
29 | 1 | p | High | inconsistent assessment of 18-14 doesn't give a specific criteria | M, A | L | 18. Develop a penalty matrix when chapter 18-14 revisions are approved. Include categorization of common violations good faith adjustments (as guidance not rule). Include instructions on how to use Matrix. (same for barriers 17, 26, 44, 61) | Donna, Scott W, Ryan, Terri
30 |  |  |  | determination of how to use the penalty matrix is confusing
31 |  |  |  | inconsistent application of good faith/bad faith adjustments
32 |  |  |  | inconsistent assess of LFIA
33 |  |  |  | there is no penalty matrix for SSL violation
34 | 3 | b |  | respondent does not like penalty calculations | solved as similar barriers
35 | 1 | p | Medium | determination of Department cost associated with investigation and tracking is inconsistent due to lack of guidance | A | L | 30. revise and update enforcement manual guidance including more case specific examples | Alissa
36 | 1 | o | High | NED SLERP form has not been shared with other districts | A | S | 23. Obtain clear understanding of site history via use of: checklist/ SLERC form. (same for barriers 25, 9) | Savage
37 | 1 | p | High | not sure who to contact in OGC regarding tricky history | A | S | 5. Develop a contact list for OSLER and OGC to address specific questions (stating their specialization) (same for barrier 42) | Ryan, Jen
38 |  |  |  | not sure who to contact in OSLER TLH regarding tricky history
39 | 1 | p | High | lengthy timeframe to get answer from OGC or OSLER regarding tricky history | M, A | S | 4. POC in districts for each policy change discussed in ERPAs to share changes with staff and OGC and OSLER will send policy changes and summaries to POCs. Group OG topics on ERPRA teleconference or with OSLER conversations. Create repository. (same for barriers 45, 41, h22, h23, h30, h31) | Aaron
40 | 1 | p | Medium | tricky history questions are not assigned to specific attorneys so attorneys assigned later don't know history | A, M | S | 32. For tricky history questions OGC will include a box in the LCT form for assistance. SLI must include summary of history with LCT form so correct attorney can be assigned. When document is sent up for review, SLI will put attorney's name who had been working on the case before on the LCT form. | Alissa
41 | 1 | p | High | staff/respondent contacting OGC talks to different attorney to get answer they want regarding tricky issues (violations) and attorney does not share with other attorneys | M, A | S | 4. POC in districts for each policy change discussed in ERPAs to share changes with staff and OGC and OSLER will send policy changes and summaries to POCs. Group OG topics on ERPRA teleconference or with OSLER conversations. Create repository. (same for barriers 39, 45, h22, h23, h30, h31) | Aaron
42 | 1 | p | High | staff does not know what determines 'tricky history' | A | S | 5. Develop a contact list for OSLER and OGC to address specific questions (stating their specialization) (same for barrier 37, 38) | Ryan, Jen
43 | 3 |  |  | politically charged projects are treated differently than other projects | Dropped
44 | 1 | p | High | OGC + OSLER PA are not always available to assist with determining to pursue penalties | M, A | L | 18. Develop a penalty matrix when chapter 18-14 revisions are approved. Include categorization of common violations good faith adjustments (as guidance not rule). Include instructions on how to use Matrix. (same for barriers 17, 26, 29, 30, 31, 32, 33, 61) | Donna, Scott W, Ryan, Terri
45 | 1 | p | High | guidance given by OGC + OSLER is not always applied by District/ staff | M, A | S | 4. POC in districts for each policy change discussed in ERPAs to share changes with staff and OGC and OSLER will send policy changes and summaries to POCs. Group OG topics on ERPRA teleconference or with OSLER conversations. Create repository. (same for barriers 39, 41, h22, h23, h30, h31) | Aaron
46 | 1 | o | High | template for 18-14 letter does not exist, not everybody drafts same 18-14 letter | A | L | 19. Once a new rule is adopted, two letters will be drafted one mixed, one proprietary (warning letters) | OGC
47 | 1 | o | High | 18-14 revisions have not been adopted. We do not have a combo letter that allows us to access proprietary fines
48 | 1,2 | o | Low | staff has to manually track when the certified letter green card comes in | P, A | S
49 | 1 | o | Low | staff has to go to US Post Office website to see if certified green card has been received | P | S
50 | 1 | o | Low | staff (SLI) does not get returned mail and do not know if green card has been received | P | S
51 | 1 | b | Low | getting DEP law enforcement to assist SLI is difficult because they do not feel it is important which slows down the process | A | S
52 | 1 | o | Low | Having to send out 18-14 letter again slows down process | P | S
53 | 1 | o | Medium | finding address for responsible party is difficult (for 18-14 party letter) | A | S | 41. create list in OPM manual the available databases/ websites so every one has knowledge of all available databases/ websites (Internal and external sources) (same for barrier 10) | Jim
54 | 1 | o | Low | Staff (SLI) has to take time to pull activities report from ERP ce | P | S
55 |  |  |  | two different places in ERP ce to get activities due and over due report
56 | 1 | b | High | incomplete information received from respondent confirming that non-compliance issue has been resolved | A | S | 8. Create task deadline checklist to send to respondent that includes summary of each action and due dates. Do site inspection to confirm that what respondent tells you is accurate. (same for barrier 58) | tonya
57 | 3 | b | High | respondent non responsive regarding compliance verification | M | S | 13. A. with an attorney or consultant require all comments and tracked changes to consent order 5 business days prior to meeting for efficiency. Cancel meeting if they do not comply and go to NOV or CR. B. If unsophisticated respondent give 90 days from day of proposed CO to reach agreement (signed CO). C. If unresponsive respondent wait 30 days from date of 18-14 letter (call after 20) and initiate NOV or CR. (same for barriers 87, 98, 101, h26, h37, h43) | donna
58 | 3 | b | High | respondent skews information to appear compliant causing DEP action | A | S | 8. Create task deadline checklist to send to respondent that includes summary of each action and due dates. Do site inspection to confirm that what respondent tells you is accurate. (same for barrier 56) | tonya
59 | 1 | b |  | takes time to review file and do inspection
60 | 1 | o | High | access to site for determining if respondent has complied with 18-14 letter can be difficult | M | S | 21. Refer to enforcement manual on how to get access. Try waterside access (look to CAM and Parks for cooperation). Access via neighboring property. | Donna
61 | 1 | p | High | there is inconsistency whether to assess fines for specific violations | M, A | L | 18. Develop a penalty matrix when chapter 18-14 revisions are approved. Include categorization of common violations good faith adjustments (as guidance not rule). Include instructions on how to use Matrix. (same for barriers 17, 26, 29, 30, 31, 32, 33, 44) | Donna, Scott W, Ryan, Terri
62 | 1 | b | High | model NOV insufficient for a variety of issues that District encounters | A, P | L | 1. OGC will update enforcement manual with more examples of NOVs that have been approved. But make it clear that all NOVSs must be reviewed by OGC. (same for barrier h25) | Alissa
63 | 1 | b | Low | there is no clear guidance on how to transport NOV to supervisor/ EM | P | S
64 | 1 | b | High | waiting for OGC to respond to an NOV can take a long time -also for signature | M, A | S | 10. The SLI needs to organize file + CR, prioritize file before sending to OGC. Include Case summary (story) with CR. OGC will re-review current CR model (same for barriers 77, 78, 79, 83) | Alissa, Tonya
65 | 1 | b | Medium | takes time for supervisor to review NOV | P | S | 28. Have weekly meeting to have management supervisor to go over issues important issues to SLI. Management must have Agenda placed on common drive so any SLI can add to the agenda SLI must have penalty calculations, site inspections report and case. Use as preparation for respondent meeting (same for barriers 24, 67, 68, 70, 103, h39) | Eric
66 | 1 | b | High | NOV contains errors and insufficient information when sent out for review | A | S, L | 16. OGC shall outline expectations for writing style and substance depth. Let the manager or supervisor know if OGC is constantly is having issues with draft documents. As an interim measure OGC shall provide a library of NOV examples. OGC will finish updating the enforcement document forms in the enforcement manual. (same for barriers 80, H19, h34, h38, h42) | Alissa
67 | 1 | b | Medium | takes time for manager to review enforcement document | P | S | 28. Have weekly meeting to have management supervisor to go over issues important issues to SLI. Management must have Agenda placed on common drive so any SLI can add to the agenda SLI must have penalty calculations, site inspections report and case. Use as preparation for respondent meeting (same for barriers 24, 65, 70, 103, h39) | Eric
68 |  |  |  | takes time for supervisors to review 18-14 letter, CR, CO, NOV, DFO, cover letter
69 | 1 | b | Medium | takes time to get DD signature on CR | A | S | 73. Request change of DOA from Mimi and Directors, see event notes for recommended changes (same for barrier h11) | Tim
70 | 1 | b | Medium | availability of EA, EM, supervisor or DD for review of documents for edits + signature can be problematic | P | S | 28. Have weekly meeting to have management supervisor to go over issues important issues to SLI. Management must have Agenda placed on common drive so any SLI can add to the agenda SLI must have penalty calculations, site inspections report and case. Use as preparation for respondent meeting (same for barriers 24, 65, 67, 68, 103, h39) | Eric
71 | 1 | o | Low | clerical does not know when to send CO, CR, NOV certified | A, P | S
72 | 1 | o | Low | on receipt to the office, difficult to determine which SLI should receive green card | P | S
73 | 1 | b | Low | wrong email/physical address given to clerical staff to transmit enforcement documents | P | S
74 | 1 | b | Low | inaccurate completion of LCT form from SLI | P | S
75 |  |  |  | LCT form sent to wrong person by SLI
76 | 1 | o | Low | there is a delay in assigning cases to Public Lands Attorneys | A | S
77 | 1 | b | High | File review + workload delay preparation ATS | M, A | S | 10. The SLI needs to organize file + CR, prioritize file before sending to OGC. Include Case summary (story) with CR. OGC will re-review current CR model (same for barriers 64, 83) | Alissa, Tonya
78 |  |  |  | ATS may not get prepared immediately because there is still discussion between District + OGC as to what direction to take
79 |  |  |  | time it takes for DGC Enforcement to review ATS + provide comments
80 | 1 | b | High | initial draft received by OGC is insufficient due to quality (enforcement documents) | A | S, L | 16. OGC shall outline expectations for writing style and substance depth. Let the manager or supervisor know if OGC is constantly is having issues with draft documents. As an interim measure OGC shall provide a library of NOV examples. OGC will finish updating the enforcement document forms in the enforcement manual. (same for barriers 66, H19, h34, h38, h42) | Alissa
81 | 1 | b | High | workload delays review of CO, CR, NOV (etc.) | M, A | S | 3. District prioritize cases on monthly basis with PA. PA will communicate with OGC on District's priorities on monthly basis. Add to LTC form a required L, M, H priority box with comments. Initial that document is proof read and property address and responsible party was identified. SLI will include copy of deed in sunbiz info if applicable. OGC will look at substance instead of style and will include standardized language in email communicating that document has been approved. (same for barriers h15, h29, h40) | Alissa, Jen
82 |  |  |  | unclear priorities from district level to OGC results in spending time on lesser priorities
83 | 1 | b |  | delay in receiving approved enforcement documents from OGC to SLI | M, A | S | 10. The SLI needs to organize file + CR, prioritize file before sending to OGC. Include Case summary (story) with CR. OGC will re-review current CR model (same for barriers 77, 78, 79, 64) | Alissa, Tonya
84 | 1 | b | Medium | district finds it difficult to determine what OGC is trying to communicate in the enforcement documents returned post review | M, A | S | 26. In email returning reviewed documents from OGC, OGC will offer short meeting (15 min) to discuss comments, changes in the documents. SLI will schedule meeting if desired. | Alissa
85 | 1 | b | Low | SLI feels it is hard to determine whether the enforcement document is approved | P | S
86 | 1 | b | High | wrong respondent signs the CO | M, A | S | 14. Include name of party in signature line on CO and resend entire CO if wrong party signs it. | donna
87 | 1 | b | High | time it takes to receive the CO (signed) from the respondent | M | S | 13. A. with an attorney or consultant require all comments and tracked changes to consent order 5 business days prior to meeting for efficiency. Cancel meeting if they do not comply and go to NOV or CR. B. If unsophisticated respondent give 90 days from day of proposed CO to reach agreement (signed CO). C. If unresponsive respondent wait 30 days from date of 18-14 letter (call after 20) and initiate NOV or CR. (same for barriers 57, 98, 101, h26, h37, h43) | donna
89 | 1 | b | High | respondent alters ED prior to signing it | P | S | 15. SLI reviews document (CO) prior to execution any non model changes made by respondent must be reviewed by OGC | donna
88 | 1 | b | High | staff turnover makes it difficult to track compliance with judgments/ orders | F | done | see solutions for first event - new employee checklist, etc. same for h16
90 | 1 | b | High | poorly written inspection reports make it difficult to determine if compliance with FO, CO is complete | M | S | 2. review task deadline checklist prior to site inspection. Review judgment/ order prior to and post inspection to confirm everything is done. Writ e inspection report within in 1 week of inspection. Have a standardized statewide C&E inspection report. Supervisor reviews report to confirm all actions were completed and must sign of on closure. Need to include caveats regarding checklist as aid. Transmit inspection report as soon as completed. | Eric
91 | 1 | o | Low | remembering to close case by SLI once facility returns in to compliance | A | L
92 | 1 | b | Medium | once a case has been finalized difficult to identify who in OGC is responsible | P | S | 27. SLI will look in LCT | ?
93 | 1 | o | Low | it is difficult to determine by SLI if previously approved ED constitutes a model | A, P | S
94 | 1 | o | High | SLI unsure of how much info to include in the CR |  |  | 22. OGC will look at providing more specific guidance in enformcent manual such as using an actual CR as an example explaining why various elements are needed on helpful. House in re-write of SLER 1710 and discuss in ERPA teleconferences | Donna, Alissa
95 |  |  |  | OGC not receiving enough/ correct information in CR to make next decision
96 | 1,2 | o | High | there is no model default DFO for 18-14 | A | L | Have OGC experiment by using default, then develop based on results. B. Use Fury Management as experimental case. C. Draft Model DFO based on experience.
97 | 1 | o | Low | determination how formal the extension for time 18-14 letter needs to be is difficult | A, M | L
98 | 1 | b | High | when is enough enough for settlement negotiations? | M | S | 13. A. with an attorney or consultant require all comments and tracked changes to consent order 5 business days prior to meeting for efficiency. Cancel meeting if they do not comply and go to NOV or CR. B. If unsophisticated respondent give 90 days from day of proposed CO to reach agreement (signed CO). C. If unresponsive respondent wait 30 days from date of 18-14 letter (call after 20) and initiate NOV or CR. (same for barriers 57, 87, 101, h26, h37, h43) | donna
99 | 1 | b | Low | respondent is unclear of what the letter they received means | A | S
100 |  |  |  | respondent not aware that they have a lease or know what it is
101 | 1 | b | High | respondent slows process when they involve attorney/ consultant | M | S | 13. A. with an attorney or consultant require all comments and tracked changes to consent order 5 business days prior to meeting for efficiency. Cancel meeting if they do not comply and go to NOV or CR. B. If unsophisticated respondent give 90 days from day of proposed CO to reach agreement (signed CO). C. If unresponsive respondent wait 30 days from date of 18-14 letter (call after 20) and initiate NOV or CR. (same for barriers 57, 87, 98, h26, h37, h43) | donna
102 | 1 | b | Medium | respondents come unprepared to an enforcement meeting | P, M, A | S | 24. Clearly communicate expectations of meeting with respondent. Provide respondent checklist of items to bring to meeting and be prepared to discuss. | Greg
103 | 1 | o | Medium | DEP not prepared for respondents meeting | P | S | 28. Have weekly meeting to have management supervisor to go over issues important issues to SLI. Management must have Agenda placed on common drive so any SLI can add to the agenda SLI must have penalty calculations, site inspections report and case. Use as preparation for respondent meeting (same for barriers 24, 65, 67, 68, 70, h39) | Eric
104 | 1 | b | Low | matching schedules from FDEP + respondent is challenging for enforcement meeting | P | S
105 | 1 | b | High | financial resources of respondent to comply not sufficient | A | S | 12. Will not consider reductions for state land violations for regulatory if willing to findings of violation. SLI can consider financial ability. Consider restoration as a priority; see video teleconference with John Alden + Larry Morgan for more information on ability to pay determination. Provide web link with training list to staff. | Ann Lazar
106 | 1 | b | Low | respondent sends petition to wrong place | A | S
107 | 1 | b | Medium | District is not aware that respondent petitions | M | S | 25. Attorneys must inform SLI of petition and if SLI is repeatedly not made aware of status, SLI will inform either deputy or lead attorney. (same for barrier 115) | Alissa
108 | 1 | b | Low | respondent may not understand rights | A | S
109 |  |  |  | respondent has to write down request for extension
110 | 1 | b | Low | inconsistent clerking of docs by district office staff | P | S
111 | 1 | p | Low | when extension of time are given verbally by SLI to Respondant without authority to give an extension is a problem | P | S
112 | 2 | o | High | SLI does not always receive information Why a lease is not executed | M, A | S | 7. within 20 days of identifying DOA package deficiency, DSL contacts district processor via email about the deficiency stating what is needed. District staff develop tickler system to get reminder to checkup on status of DOA. DSL will copy District on correspondence with applicant lessee | Aaron
113 |  |  |  | SLI does not always receive information that a lease has been executed
114 | 1 | o | Low | not all case closure memos result incases being closed in LCT. Reason: not always communicated back to SLI | A, P | S
115 | 1 | b | Medium | lack of communication regarding CR status- Inspector doesnot know is going on | M | S | 25. Attorneys must inform SLI of petition and if SLI is repeatedly not made aware of status, SLI will inform either deputy or lead attorney. (same for barrier 107) | Alissa
116 | 1 | o | Low | unclear looking at the DSL C&E report what cases are in OGC | A | S
117 |  |  |  | OGC does not receive the C&E report from DSL
From High level Issues table
h1 |  |  |  | Similar databases doing similar work that do not communicate with one another. Duplication of effort. | dropped
h2 |  |  |  | Takes a long time to get answers like state lands title determinations. Cannot make comprehensive decisions. | solved as similar barriers
h3 |  |  |  | Politics plays a big role in enforcement decisions. | solved as similar barriers
h4 |  |  |  | Inconsistencies between district office work products such as penalties, lease fees in arrears, enforcement discretion. | solved as similar barriers
h5 |  |  |  | Reassigned staff, temporarily, are not sufficiently completing project processing. | dropped |  | resolved in project #1
h6 |  |  |  | Duplicative and excessive District management review process. | solved as similar barriers
h7 |  |  |  | Excessive review in OGC due to non-model projects. | solved as similar barriers
h8 |  |  |  | All templates are not robust enough to be able to preclude OGC review for most of their projects. | solved as similar barriers
h9 |  |  |  | The desired outcome of getting a lease is complicated by going through a TUA process unnecessarily. | solved as similar barriers
h10 |  |  |  | Too much wait time in between transporting documents via mail. | solved as similar barriers
h11 | 2 | b | Medium | Delegation of authority directive inconsistency adds confusion and slows down the process. | A | S | 73. Request change of DOA from Mimi and Directors, see event notes for recommended changes (same for barrier 69) | Tim
h12 | 1 | o | Medium | The process is in series of database entry and writing an inspection report and slows down the process. | A | S | 42. Incorporate SL inspection form into existing PDAs (same for barrier 19) | ?
h13 |  |  |  | OGC review delays process of | solved as similar barriers
h14 | 1 | p | Medium | Staff unsure of when OGC needs to get involved. | A | S | 31. Include OGC link to flowchart in SLI new employee checklist and inform current SLI of that link | Tonya
h15 | 1 | b | High | Staff unsure of OGC priorities at the OGC level. | M, A | S | 3. District prioritize cases on monthly basis with PA. PA will communicate with OGC on District's priorities on monthly basis. Add to LTC form a required L, M, H priority box with comments. Initial that document is proof read and property address and responsible party was identified. SLI will include copy of deed in sunbiz info if applicable. OGC will look at substance instead of style and will include standardized language in email communicating that document has been approved. (same for barriers 81, 82, h29, h40) | Alissa, Jen
h16 | done | b | High | Duplication of work due to staff turnover leads to cases being indefinitely unresolved. | F | done | see solutions for first event - new employee checklist, etc. same for 88
h17 | 2 | o | High | Unclear division of duties between DSL and districts like getting leases signed and delivering invoices and reassignments. | A | S | 6. District will generate a list of division of responsibilities and send to DSL for concurrence concerning assignments. Post on OPM. . Float draft to other Districts. (District duties versus DSL duties, to aid in clear understanding of division of duties (invoice delivery/ collection, reassignments, Notice to Correct letter)). | Watkin, Scott W, Russell
h18 |  |  |  | Excessive edit loops cause more delays. These edits are caused by 0 training at all enforcement process. | solved as similar barriers
h19 | 1 | b | High | First draft to OGC is missing basic and or common elements. | A | S, L | 16. OGC shall outline expectations for writing style and substance depth. Let the manager or supervisor know if OGC is constantly is having issues with draft documents. As an interim measure OGC shall provide a library of NOV examples. OGC will finish updating the enforcement document forms in the enforcement manual. (same for barriers 66, 80, h34, h38, h42) | Alissa
h20 |  |  |  | Duplicate work being done by two sections in OGC which slows down the process as a whole (4 attorneys looking at the same thing). | solved as similar barriers
h21 |  |  |  | Back and forth hands-off are excessive, time is lost between. | solved as similar barriers
h22 | 1 | p | High | Requiring input from others slows down the process when having a main go-to place could free up "people" resources. | M, A | S | 4. POC in districts for each policy change discussed in ERPAs to share changes with staff and OGC and OSLER will send policy changes and summaries to POCs. Group OG topics on ERPRA teleconference or with OSLER conversations. Create repository. (same for barriers 45, 41, 39, h30, h31) | Aaron
h23 |  |  |  | Frequent changes to policy lead to variations/inconsistent decision making. .
h24 | 1 | b | Low | District level, two sets of clerical staff do duplicative work - can be streamlined. | A, P | S
h25 | 1 | b | High | All NOVs require review. Lack of pre-approved model requires further review from OGC resources. | A, P | L | 1. OGC will update enforcement manual with more examples of NOVs that have been approved. But make it clear that all NOVSs must be reviewed by OGC. (same for barrier h25) | Alissa
h26 | 1 | b | High | Respondent non-response loop keeps the process going without any value-added. | M | S | 13. A. with an attorney or consultant require all comments and tracked changes to consent order 5 business days prior to meeting for efficiency. Cancel meeting if they do not comply and go to NOV or CR. B. If unsophisticated respondent give 90 days from day of proposed CO to reach agreement (signed CO). C. If unresponsive respondent wait 30 days from date of 18-14 letter (call after 20) and initiate NOV or CR. (same for barriers 57, 87, 98, 101, h37, h43) | donna
h27 | 1 | p | Medium | After going down one work-process trail, a completely different path is taken. Work time is lost on original process decision. | A | L | 34. Put guidance in Enforcement Manual as to when to do a CR versus NOV. Call OGC with questions. | Alissa
h28 |  |  |  | Unclear when to do NOV verses a case report.
h29 | 1 | b | High | Too much time spent on lower level issues (minor infractions). | M, A | S | 3. District prioritize cases on monthly basis with PA. PA will communicate with OGC on District's priorities on monthly basis. Add to LTC form a required L, M, H priority box with comments. Initial that document is proof read and property address and responsible party was identified. SLI will include copy of deed in sunbiz info if applicable. OGC will look at substance instead of style and will include standardized language in email communicating that document has been approved. (same for barriers h15, 81, 82, h40) | Alissa, Jen
h30 | 1 | p | High | Improper levels of guidance available. Lack of program wide communication between Districts and administration. Example NTC | M, A | S | 4. POC in districts for each policy change discussed in ERPAs to share changes with staff and OGC and OSLER will send policy changes and summaries to POCs. Group OG topics on ERPRA teleconference or with OSLER conversations. Create repository. (same for barriers 41, h23,, h22,, 39, 45) | Aaron
h31 |  |  |  | Final outcome resolutions communicated with individual districts is not broadcast with all other districts. Repetitive conversations become necessary without information sharing.
h32 | 1 | b | Low | unclear OGC case entry for both proprietary and regulatory projects of downstream rework (reassignment) currently multiple OGC staff must review for proper assignment | P | S
h33 |  |  |  | Work performed is unnecessary like case closed letter being sent to respondent and routing memo. | solved as similar barriers
h34 | 1 | b | High | Review process time is increased because work product expectations vary from OGC. | A | S, L | 16. OGC shall outline expectations for writing style and substance depth. Let the manager or supervisor know if OGC is constantly is having issues with draft documents. As an interim measure OGC shall provide a library of NOV examples. OGC will finish updating the enforcement document forms in the enforcement manual. (same for barriers 66, 80, h19, h38, h42) | Alissa
h35 | 2 | p | High | Conflicting/confusing direction from state lands causes duplicative efforts within the TUA process (6 months timeframe vs. 1 year) | A | S | 17. Revise OPM guidance and TUA template to allow for flexibility regarding six month to 12 month term considering cooperation AP/ public interest and timeframes for corrective actions. Revise the TUA template to include approved optional language. TUA fees will be locked into rate at the time of execution. | JJ, Jim, Ryan and Susan
h36 | done |  |  | Inspection report process is inefficient due to hand entry on site and duplicating entry into separate report in-office upon return from site visit. | solved as similar barriers
h37 | 1 | b | High | Too many meetings take up resource time (too many letters, loops). | M | S | 13. A. with an attorney or consultant require all comments and tracked changes to consent order 5 business days prior to meeting for efficiency. Cancel meeting if they do not comply and go to NOV or CR. B. If unsophisticated respondent give 90 days from day of proposed CO to reach agreement (signed CO). C. If unresponsive respondent wait 30 days from date of 18-14 letter (call after 20) and initiate NOV or CR. (same for barriers 57, 87, 98, 101, h26, h43) | donna
h38 | 1 | b | High | Work products are sub-par when sent for review, causing edit time by valuable resource time. | A | S, L | 16. OGC shall outline expectations for writing style and substance depth. Let the manager or supervisor know if OGC is constantly is having issues with draft documents. As an interim measure OGC shall provide a library of NOV examples. OGC will finish updating the enforcement document forms in the enforcement manual. (same for barriers 66, 80, h19, h34, h42) | Alissa
h39 | 1 | b | Medium | Meetings are not structured to come to specific outcome. | P | S | 28. Have weekly meeting to have management supervisor to go over issues important issues to SLI. Management must have Agenda placed on common drive so any SLI can add to the agenda SLI must have penalty calculations, site inspections report and case. Use as preparation for respondent meeting (same for barriers 24, 65, 67, 68, 70, 103) | Eric
h40 | 1 | b | High | Communications between Districts and OGC, regarding priority levels, are unclear OGC unsure of what to do first. | M, A | S | 3. District prioritize cases on monthly basis with PA. PA will communicate with OGC on District's priorities on monthly basis. Add to LTC form a required L, M, H priority box with comments. Initial that document is proof read and property address and responsible party was identified. SLI will include copy of deed in sunbiz info if applicable. OGC will look at substance instead of style and will include standardized language in email communicating that document has been approved. (same for barriers h15, h29, 81, 82) | Alissa, Jen
h41 | 1 | o | High | We don't have a process for eviction and trespass. | A | L | Establish a process event for eviction and trespass. | Mike Long, Ryan
h42 | 1 | b | High | OGC needs all the facts before hand to start having back-n-forth discussion loops. | A | S, L | 16. OGC shall outline expectations for writing style and substance depth. Let the manager or supervisor know if OGC is constantly is having issues with draft documents. As an interim measure OGC shall provide a library of NOV examples. OGC will finish updating the enforcement document forms in the enforcement manual. (same for barriers 66, 80, h19, h34, h38) | Alissa
h43 | 1 | b | High | Non-value added steps drain resources (certifies mail) excessive meetings, priority mail, informal conferences) | M | S | 13. A. with an attorney or consultant require all comments and tracked changes to consent order 5 business days prior to meeting for efficiency. Cancel meeting if they do not comply and go to NOV or CR. B. If unsophisticated respondent give 90 days from day of proposed CO to reach agreement (signed CO). C. If unresponsive respondent wait 30 days from date of 18-14 letter (call after 20) and initiate NOV or CR. (same for barriers 57, 87, 98, 101, h26, h37) | donna
Barrier Disposition Codes: (Dispo Code)
Map Change = M
Action Plan = A
Procedure Change = P
Already fixed = F
Dropped = D
Later = L
Timeline Term
Short - permanent fix in <30 days
Long - permanent fix in > 30 days
Temp - Temporary fix while waiting for long-term solution