## Notes
1. Metrics workbook was constructed on 051519 with project information submitted during the RAP process.
2. The projects in this workbook were based on eligible projects from the Lox River Master Project List Draft_042319.
3. Projects deemed ineligible were not included in the Lox Metrics workbook. This resulted in some entities having new project numbers assigned than what was originally presented.
4. 011420 Edited workbook and deleted NOI and charts tab
Metrics Questions from Edits - Keep FDOT4-07 Education Project?
5. In March 2021, Bud Howard provided changes for 2020/early 2021. March 2021 changes indicated in red text
6. On 3/25/21, Tiffany Busby filled in blank cells in red text, made the fonts consistent, assigned project numbers to new projects, reduced any long project descriptions to 255 characters or less, and refreshed the pivot tables summarzing the nutrient and FIB projects. Tiffany also added "Ongoing" as a project status option and adjusted those projects that were "ongoing" by being listed as "Completed" with "N/A" as the completion date, and changed their status to "Ongoing" and leaving the completion date as "N/A."
7. On 2/22/22, Tiffany Busby turned the changes from 2020 to black text, so the new changes for 2021 would stand out.

## All Nutrient Projects
ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | Structural, Non-structural, or Trade | (Original) Project Status | Year Project Added | Attachments | BMAP | Latitude | Longitude | Start Date | Comments
| DEP FPS | N/A | FPS-01 | Jonathan Dickinson State Park - Ditch Filling - FY 15/16 | In the RAP area, backfilled 177 acres of ditches which were ultimately discharging to the Loxahatchee River. Filling of the ditches restores the natural floodplain and retains runoff in the wetlands. | Wetland Restoration | Completed | 2016 | 151.3544 | 7.2777 | N/A | 178 | 265000 | N/A | Loxahatchee River Preservation Initiative (LRPI)/ Florida Fish and Wildlife Conservation Commission (FWC) Aquatic Habitat Restoration Enhancement Section (AHRES) | 265000 | N/A | Structural | Completed | 2019 | GIS files | Loxahatchee River 4e | N/A | N/A | 2016
| DEP FPS | N/A | FPS-02 | Jonathan Dickinson State Park - Wilson Creek | Ditch work to restore approximately 90 acres of pristine depression marshes. | Wetland Restoration | Completed | 2019 | 35.857 | 1.1028 | N/A | 69 | 150000 | N/A | North American Wetlands Conservation Act Grants | 150000 | N/A | Structural | Underway | 2019 | GIS files | Loxahatchee River 4e | N/A | N/A | Not provided
| DEP FPS | N/A | FPS-03 | Jonathan Dickinson State Park - Education Activities | Information pamphlets and website. | Education Efforts | Completed | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee River 4e | N/A | N/A | Not provided
| FDACS | Agricultural Producers | FDACS-01 | Agricultural Best Management Practices (BMPs) | Enrollment in FDACS BMP manuals for owner implemented BMPs as of April 2019. | Agricultural BMPs | Completed | N/A | 1019.518 | 239.1811 | N/A | 4980 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | PLSM Output | Loxahatchee River 4e | N/A | N/A | N/A
| FDACS | N/A | FDACS-02 | Agricultural Land Use Change | Land use change from citrus to sugar cane resulting in lower fertilizer use. | Land Use Change | Completed | N/A | 193.7928 | 493.2907 | N/A | 2788 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | PLSM Output | Loxahatchee River 4e | N/A | N/A | N/A
| FDOT District 4 | N/A | FDOT4-01A | I-95 From South of Donald Ross Rd to South of Indiantown Rd | Construction and operation of a surface water management system for this roadway widening project. | Grass swales with swale blocks or raised culverts | Completed | 2012 | 350.9064 | 24.3616 | Basins A-E | 191.76 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2019 | Loxahatchee River 4e | N/A | N/A | 2008-08-21 | Need GIS distinguishing part A from part B of the project
| FDOT District 4 | N/A | FDOT4-01B | I-95 From South of Donald Ross Rd to South of Indiantown Rd | Construction and operation of a surface water management system for this roadway widening project. | Dry Detention Pond | Completed | 2012 | 197.2555 | 13.6759 | Basins F, G | 79.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2019 | Loxahatchee River 4e | N/A | N/A | 2008-08-21 | Need GIS distinguishing part A from part B of the project
| FDOT District 4 | N/A | FDOT4-01C | I-95 From South of Donald Ross Rd to South of Indiantown Rd | Construction and operation of a surface water management system for this roadway widening project. | Dry Detention Pond | Completed | 2012 | 9.985 | 0.67502 | Basin H | 46.03 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2019 | Loxahatchee River 4e | N/A | N/A | 2008-08-21 | GIS layer FDOT1A_H
| FDOT District 4 | N/A | FDOT4-02 | US 1/SR 5 Bridges - Jupiter | Construction and operation of a surface water management system (French drains) for this bridge replacement project. | Off-line Retention BMPs | Completed | 2013 | 32.1221 | 4.6898 | Not provided | 6.75 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2019 | Loxahatchee River 4e | N/A | N/A | 2010-06-14 | N/A
| FDOT District 4 | Villages of Tequesta | FDOT4-03 | Tequesta Drive Bridge Replacement Project | Construction and operation of a surface water management system for this bridge replacement project. | Grass swales with swale blocks or raised culverts | Completed | 2010 | 6.9786 | 1.0655 | Not provided | 3.17 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2019 | Loxahatchee River 4e | N/A | N/A | 2009-11-18 | N/A
| FDOT District 4 | N/A | FDOT4-04 | I-95 Weigh-in-Motion Station | Construction and operation of a surface water management system. | Wet Detention Pond | Completed | 2009 | 111.707 | 11.4197 | Not provided | 66.54 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2019 | Loxahatchee River 4e | N/A | N/A | 2007-06-26 | N/A
| FDOT District 4 | N/A | FDOT4-05 | Street Sweeping | Estimated 1,648,053 kg/yr collected | Street Sweeping | Completed | N/A | 2046 | 1312 | Not provided | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | FSA Sheet in Credit Workbook | Loxahatchee River 4e | N/A | N/A | Not provided | N/A
| FDOT District 4 | N/A | FDOT4-06 | Catch Basin Cleanout | Weight of material collected not provided. | BMP Cleanout | Completed | N/A | TBD | TBD | Not provided | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee River 4e | N/A | N/A | Not provided | Need weight of material
| FDOT District 4 | N/A | FDOT4-07 | Public Education | Provided education outreach with joint NPDES group. Actions included public service announcements, FYN brochure, public information, and outreach. | Education Efforts | Completed | N/A | TBD | TBD | N/A | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee River 4e | N/A | N/A | Not provided | N/A
| Florida Turnpike Enterprise | AM Contractor | FTE-01 | Street Sweeping | Routine maintenance roadway street sweeping (12 months) 17 cycles, 46.5 curb or lane miles, approximately 146,567.0 lbs. dry weight. | Street Sweeping | Completed | N/A | 83 | 53 | N/A | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | FSA Tool | Loxahatchee River 4e | N/A | N/A | N/A | N/A
| Florida Turnpike Enterprise | AM Contractor | FTE-02 | Catch Basin Cleanout | 53 catch basins cleaned (12 month period). Contractor has been requested to collect information on weight of materials for calculations. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | TBD | TBD | N/A | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | Not provided | Loxahatchee River 4e | N/A | N/A | N/A | N/A
| Loxahatchee River District | SFWMD | LRD-01 | Loxahatchee River Oyster Reef Enhancement | Installed substrate for oyster attachment to promote oyster reef development. | Creating/ Enhancing Oyster Reefs | Completed | 2010 | N/A | N/A | N/A | N/A | 75000 | N/A | LRD/ LRPI | LRD - $37,500/ LRPI - $37,500 | N/A | Structural | Completed | 2019 | Not provided | Loxahatchee River 4e | Not provided | Not provided | 2008 | Project type is ineligible for credit.
| Loxahatchee River District | SFWMD | LRD-02 | Loxahatchee River Neighborhood Sewering Phase 1 | Convert 55 septic systems to sewer. | OSTDS Phase Out | Completed | 2008 | 359 | N/A | N/A | N/A | 196053 | Not provided | LRD/ LRPI | LRD - $200,000/ LRPI - $200,000 | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2019 | Loxahatchee River 4e | Not provided | Not provided | 2008 | N/A
| Loxahatchee River District | SFWMD | LRD-03 | Loxahatchee River Neighborhood Sewering Phase 2 | Convert 197 septic systems to sewer. | OSTDS Phase Out | Completed | 2009 | 391 | N/A | N/A | N/A | 1890579 | Not provided | LRD/ LRPI | LRD - $223,500/ LRPI - $223,500 | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2020 | Loxahatchee River 4e | Not provided | Not provided | 2009 | N/A
| Loxahatchee River District | Not provided | LRD-04 | Loxahatchee River Neighborhood Sewering Phase 3 | Convert 188 septic systems to sewer. | OSTDS Phase Out | Completed | 2010 | 329 | N/A | N/A | N/A | 952623 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2021 | Loxahatchee River 4e | Not provided | Not provided | 2010 | N/A
| Loxahatchee River District | Not provided | LRD-05 | Loxahatchee River Neighborhood Sewering Phase 4 | Convert 251 septic systems to sewer. | OSTDS Phase Out | Completed | 2011 | 2646 | N/A | N/A | N/A | 1397227 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2022 | Loxahatchee River 4e | Not provided | Not provided | 2011 | N/A
| Loxahatchee River District | DEP | LRD-06 | Loxahatchee River Neighborhood Sewering Phase 5 | Convert 57 septic systems to sewer. | OSTDS Phase Out | Completed | 2012 | 242 | N/A | N/A | N/A | 320830 | Not provided | LRD/ LRPI | LRD - $498,000/ LRPI - $498,000 | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2023 | Loxahatchee River 4e | Not provided | Not provided | 2012 | N/A
| Loxahatchee River District | DEP | LRD-07 | Loxahatchee River Neighborhood Sewering Phase 6 | Convert 155 septic systems to sewer. | OSTDS Phase Out | Completed | 2013 | 189 | N/A | N/A | N/A | 1477526 | Not provided | LRD/ LRPI | LRD - $896,000/ LRPI - $100,000 | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2024 | Loxahatchee River 4e | Not provided | Not provided | 2013 | N/A
| Loxahatchee River District | DEP | LRD-08 | Loxahatchee River Neighborhood Sewering Phase 7 | Convert 112 septic systems to sewer. | OSTDS Phase Out | Completed | 2014 | 740 | N/A | N/A | N/A | 2143261 | Not provided | LRD/ LRPI | LRD - $2,343,000/ LRPI - $200,000 | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2025 | Loxahatchee River 4e | Not provided | Not provided | 2014 | N/A
| Loxahatchee River District | Not provided | LRD-09 | Loxahatchee River Neighborhood Sewering Phase 8 | Convert 105 septic systems to sewer. | OSTDS Phase Out | Completed | 2015 | 37 | N/A | N/A | N/A | 550981 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2026 | Loxahatchee River 4e | Not provided | Not provided | 2015 | N/A
| Loxahatchee River District | Not provided | LRD-10 | Loxahatchee River Neighborhood Sewering Phase 9 | Convert 120 septic systems to sewer. | OSTDS Phase Out | Completed | 2016 | 234 | N/A | N/A | N/A | 1800728 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2027 | Loxahatchee River 4e | Not provided | Not provided | 2016 | N/A
| Loxahatchee River District | Not provided | LRD-11 | Loxahatchee River Neighborhood Sewering Phase 10 | Convert 104 septic systems to sewer. | OSTDS Phase Out | Completed | 2017 | 32 | N/A | N/A | N/A | 1087211 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_4-10-2028 | Loxahatchee River 4e | Not provided | Not provided | 2017 | N/A
| Loxahatchee River District | Not provided | LRD-12 | Loxahatchee River Neighborhood Sewering Phase 11 | Convert 74 septic systems to sewer. | OSTDS Phase Out | Completed | 2018 | 92 | N/A | N/A | N/A | 977726 | Not provided | Not provided | Not provided | N/A | Structural | Underway | 2019 | ArcNLET Results Log Rev_4-10-2029 | Loxahatchee River 4e | Not provided | Not provided | 2017 | N/A
| Loxahatchee River District | Not provided | LRD-13 | Loxahatchee River Neighborhood Sewering Phase 12 | Convert 232 septic systems to sewer - Whispering Trails (182), Island Country Estates (38), 188890 Country Club Dr (1), Gardiner Ln (2), Island Country Estates Ph 2 (9) | OSTDS Phase Out | Completed | 2019 | 1453 | N/A | N/A | N/A | TBD | Not provided | Not provided | Not provided | N/A | Structural | Planned | 2019 | ArcNLET Results Log Rev_4-10-2030 | Loxahatchee River 4e | Not provided | Not provided | 2019 | N/A
| Loxahatchee River District | Not provided | LRD-14 | Loxahatchee River Neighborhood Sewering Phase 13 | Convert 56 septic systems to sewer - Imperial Woods (47), 815 US 1 (1), Olympus Dr (2), Thelma (3), US1 Residential (3) | OSTDS Phase Out | Underway | 2021 | 15 | N/A | N/A | N/A | TBD | Not provided | Not provided | Not provided | N/A | Structural | Planned | 2019 | ArcNLET Results Log Rev_4-10-2031 | Loxahatchee River 4e | Not provided | Not provided | 2020 | N/A
| Loxahatchee River District | Not provided | LRD-15 | Loxahatchee River Neighborhood Sewering Remnant Parcels | Convert 117 septic systems to sewer. | OSTDS Phase Out | Completed | 2019 | 371 | N/A | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2019 | ArcNLET Results Log Rev_7-24-2019 | Loxahatchee River 4e | Not provided | Not provided | 2019 | N/A
| Martin County | SFWMD | MC-01 | Cypress Creek Restoration - Culpepper Ranch Wetland Restoration | Ditch plugs and fill berm breaches. | Hydrologic Restoration | Completed | 2011 | 1233.54 | 207.0424 | N/A | 1229.87 | 198811 | N/A | County/ LRPI | County - $99,406/ LRPI - $99,405 | N/A | Structural | Completed | 2019 | PLSM tool and GIS output | Loxahatchee River 4e | N/A | N/A | 2010 | Martin County provided information that 15.38" of retention were provided.
| Martin County | NRCS | MC-02 | Pal Mar East | Plug ditches throughout property that drain wetland areas. | Hydrologic Restoration | Completed | 2009 | 2127.8405 | 201.7629 | N/A | 2943.19 | 74497 | N/A | County/ NRCS | Not provided | N/A | Structural | Completed | 2019 | PLSM tool and GIS output | Loxahatchee River 4e | N/A | N/A | 2009 | N/A
| Martin County | N/A | MC-03 | Education Program | FYN; landscaping, irrigation, fertilizer, and pet waste ordinances; PSAs, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 2786 | 372 | N/A | N/A | Not provided | Not provided | County | 60000 | N/A | Non-structural | Completed | 2019 | PLSM tool and Education Credit Workbook | Loxahatchee River 4e | N/A | N/A | N/A | N/A
| Martin County | N/A | MC-04 | Cypress Creek Weir Project | Weir replacement. | Control Structure | Completed | 2019 | 1132.4849 | 422.5179 | N/A | 2004.8043 | 975000 | Not provided | County/ LRPI/ SFWMD | County - $725,000/ LRPI - $100,000/ SFWMD - $150,000 | N/A | Structural | Planned | 2019 | Not provided | Loxahatchee River 4e | Not provided | Not provided | 2019 | N/A
| Palm Beach County | SFWMD | PBC-01 | Cypress Creek Phases I-II; Cypress Creek Habitat Restoration | Exotic vegetation control, habitat restoration, and hydrologic restoration through increased retention. | Hydrologic Restoration | Completed | 2015 | 1043.74 | 36.91 | N/A | 2034.32 | 950000 | Not provided | County/ LRPI | County - $475,000/ LRPI - $475,000 | N/A | Structural | Completed | 2019 | GIS (pbcerm_cypresscreek) and PLSM Output | Loxahatchee River 4e | N/A | N/A | 2005 | N/A
| Palm Beach County | N/A | PBC-02 | Palm Beach County Street Sweeping | Street sweeping program. | Street Sweeping | Completed | N/A | 640 | 410 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | FSA Tool | Loxahatchee River 4e | N/A | N/A | Not provided | N/A
| Palm Beach County | N/A | PBC-03 | Palm Beach County Public Education | Public education program that includes FY&N Program; landscaping, irrigation, and fertilizer ordinances; PSAs; pamphlets; website; and inspection program. | Education Efforts | Completed | N/A | 3066 | 284 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | PLSM Output | Loxahatchee River 4e | N/A | N/A | 2009 | N/A
| SIRWCD | LRPI | SIRWCD-01 | Lateral Canal Improvements | Installation of 5 operable gates to increase detention, increase the groundwater elevation, and assist in pre-storm draw down when needed. | Wet Detention Pond | Completed | 2008 | 6218.0122 | 456.3351 | N/A | 8778 | 1488675 | 2000 | SFWMD/ SIRWCD | Not provided | N/A | Structural | Completed | 2019 | GIS file | Loxahatchee River 4e | N/A | N/A | 2005 | N/A
| Town of Jupiter | Not provided | TOJ-01 | Surface Water Recharge System Improvements II | Complete system to capture and retain up to 10 MGD of excess stormwater runoff from the C-18 basin in lieu of discharging to tide. | Dispersed Water Management (DWM) | Planned | 2021 | TBD | TBD | Not provided | Not provided | 1937926 | Not provided | Town | 1937926 | Not provided | Structural | Planned | 2019 | N/A | Loxahatchee River 4e | Not provided | Not provided | 2008 | Originally TOJ-10. TOJ is working with DEP to appropriately account for project.
| Town of Jupiter | SFWMD | TOJ-02 | Pine Gardens South Water Quality Improvements | Installation of exfiltration trenches to provide an average of 0.41 inches of treatment in the project area. | Exfiltration Trench | Completed | 2015 | 17.6465 | 2.0801 | Not provided | 12 | 328552 | Not provided | Town/ LRPI | Town - $200,000/ LRPI - $128,552 | Not provided | Structural | Completed | 2019 | Pine Gardens South Engineering Report | Loxahatchee River 4e | Not provided | Not provided | 2015 | Originally TOJ-15. Engineering report with retention submitted. Still need GIS file to clip to land use.
| Town of Jupiter | Not provided | TOJ-03 | Public Education | Includes fertilizer, landscape, pet waste, and irrigation ordinances; FYN; PSAs, pamphlets, website, and inspection program (6 % credit). Additional efforts including festivals, training, information distribution, and joint NPDES group activities. | Education Efforts | Completed | N/A | 2742.2214 | 281.6631 | N/A | N/A | Not provided | Not provided | Town | Not provided | Not provided | Non-structural | Underway | 2019 | N/A | Loxahatchee River 4e | Not provided | Not provided | 2008 | TOJ-18
| Town of Jupiter | Not provided | TOJ-04 | Maintenance Dredging | Dredging in Rio Vista Waterway. | Muck Removal/Restoration Dredging | Completed | 2012 | 74.1 | 18.6 | Not provided | Not provided | 70500 | Not provided | Town | 70500 | Not provided | Structural | Completed | 2019 | Calculations workbook provided 2018 | Loxahatchee River 4e | Not provided | Not provided | 2012 | TOJ-19
| Town of Jupiter | Not provided | TOJ-05 | Street Sweeping | Periodic street sweeping to enhance water quality. | Street Sweeping | Completed | N/A | 142 | 91 | N/A | N/A | Not provided | 49586 | Town | 49586 | Not provided | Non-structural | Completed | 2019 | MS4 Workbook | Loxahatchee River 4e | Not provided | Not provided | 2008 | TOJ-21
| Town of Jupiter | Not provided | TOJ-06 | Cinquez Park Drainage Improvements I | Construction of drainage system, swales and roadways (existing roads were shell rock). | BMP Treatment Train | Completed | 2011 | 36.1973 | 2.5816 | Not provided | 20 | 569518 | Not provided | Town | 569518 | Not provided | Structural | Completed | 2019 | Cinquez Park Area Calcs and Permit submitted in 2018 | Loxahatchee River 4e | Not provided | Not provided | 2009 | Originally TOJ-28 - Need GIS
| Town of Jupiter | Not provided | TOJ-07 | Cinquez Park Drainage Improvements II | Construction of new park stormwater management system to retain runoff. | On-line Retention BMPs | Completed | 2018 | 14.223 | 0.65148 | Not provided | 13 | 329400 | Not provided | Town | 329400 | Not provided | Structural | Underway | 2019 | Cinquez Park Drainage Improvement Area provided in 2018 | Loxahatchee River 4e | Not provided | Not provided | 2016 | Originally TOJ-29 - Need GIS and is it on or off-line.
| Town of Jupiter | Not provided | TOJ-08 | Water Plant Detention Pond Cleanout | Silt removal from wet detention pond located at the water plant. | Muck Removal/Restoration Dredging | Completed | 2017 | 165 | 67 | Not provided | Not provided | 10620 | Not provided | Town | 10620 | Not provided | Structural | Completed | 2019 | Dredge calculations workbook submitted in 2018 | Loxahatchee River 4e | Not provided | Not provided | 2017 | TOJ-30
| Town of Jupiter | Not provided | TOJ-09 | Stormwater Quality Improvement Grants (HOA Residential Grants) | Town cost-share program (50/50) with property owner and homeowner associations for storm water quality enhancements within their private systems. 28 grants awarded since 2008. Annual appropriation. | Stormwater System Rehabilitation | Underway | N/A | N/A | N/A | Not provided | N/A | 998229 | Not provided | Town | 998229 | Not provided | Non-structural | Underway | 2019 | Not provided | Loxahatchee River 4e | Not provided | Not provided | 2008 | Originally TOJ-31
| Town of Jupiter | Not provided | TOJ-09a | Indian Creek Exfiltration Trench | Indian Creek exfiltration trench funded as a part of the Town of Jupiter cost-share program (TOJ-09). | Exfiltration Trench | Completed | 2017 | 5.5189 | 0.55014 | Not provided | 1.63 | Not provided | Not provided | Town | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2019 | Loxahatchee River 4e | Not provided | Not provided | Not provided | N/A
| Town of Jupiter | Not provided | TOJ-09b | Boyd Medical Retention | Boyd Medical on-line retention BMPs funded as a part of the Town of Jupiter cost-share program (TOJ-09). | On-line Retention BMPs | Completed | 2016 | 1.8646 | 0.13011 | Not provided | 0.65 | Not provided | Not provided | Town | Not provided | N/A | Structural | Completed | 2019 | GIS files submitted in 2020 | Loxahatchee River 4e | Not provided | Not provided | Not provided | N/A
| Town of Jupiter | Not provided | TOJ-10 | Seminole Avenue Drainage Basin Improvements | Construct additional outfall and pump station to reroute discharge to FEC canal. | Stormwater System Rehabilitation | Planned | 2023 | 64.6162 | 5.6519 | Not provided | 86.78 | 2174461 | Not provided | Town | 2174461 | Not provided | Structural | Planned | 2019 | Not provided | Loxahatchee River 4e | Not provided | Not provided | 2018 | Not designed yet. Details will be provided when available. Originally TOJ-32
| Town of Jupiter | Not provided | TOJ-11 | Pine Gardens North Water Quality Improvements | Construct exfiltration trenches within existing right-of-way. | Exfiltration Trench | Planned | 2022 | 627.8982 | 69.3255 | Not provided | 169.17 | 719782 | Not provided | Town | 719782 | Not provided | Structural | Planned | 2019 | Map of proposed trench locations provided in 2018. | Loxahatchee River 4e | Not provided | Not provided | 2020 | Map of proposed exfil trenches provided. Need GIS file and design specifications when available. Originally TOJ-33.
| Town of Jupiter | Not provided | TOJ-12 | Stormwater System Redevelopment Grants | Renewal or improvement of existing privately owned stormwater systems under site redevelopment to ensure continued or enhanced functionality. Annual appropriation. | Stormwater System Rehabilitation | Completed | N/A | N/A | N/A | Not provided | Not provided | 432368 | Not provided | Town | 432368 | Not provided | Structural | Underway | 2019 | Not provided | Loxahatchee River 4e | Not provided | Not provided | 2013 | Benefits vary from project to project. Suggest the stakeholder provide details on significant projects as to be listed individually under the main number and credited. Originally TOJ-34.
| Town of Jupiter | Not provided | TOJ-13 | Pennock Industrial Park Drainage Improvements | Improvements to include additional exfiltration systems to enhance runoff water quality. | Exfiltration Trench | Planned | 2022 | 165.7755 | 22.6755 | Not provided | 36.92 | 463710 | Not provided | Town | 463710 | Not provided | Structural | Planned | 2019 | Not provided | Loxahatchee River 4e | Not provided | Not provided | 2021 | Design not completed yet. Originally TOJ-36.
| Town of Jupiter | Not provided | TOJ-14 | Sonoma Isles Stormwater Harvesting | Removal and replacement of existing Town-owned stormwater systems to ensure continued functionality. Annual appropriation. | Stormwater System Rehabilitation | Completed | 2016 | 123.812 | 220.5118 | Not provided | Not provided | Not provided | Not provided | Private Owner | N/A | Not provided | Structural | Completed | 2019 | Sonoma Isles Calculation Backup and LRD monitoring concentrations in 2018. | Loxahatchee River 4e | Not provided | Not provided | 2017 | Suggest calculating credit based on the TN/TP concentration change and the volume. TOJ-38
| Town of Jupiter | Not provided | TOJ-15 | Evernia Street Alley Improvements | Construction of drainage system, which will include 100 LF of exiltration trench | Exfiltration Trench | Completed | 2020 | 13.423 | 0.92795 | Not provided | 4.3 | Not provided | Not provided | Not provided | Not provided | Not provided | Structural | Planned | 2019 | GIS file | Loxahatchee River 4e | Not provided | Not provided | Not provided | N/A
| Village of Tequesta | N/A | VOT-01 | Education Program | FYN; landscaping, irrigation, and fertilizer ordinances; PSAs, pamphlets, website, illicit discharge program. FYN and PSAs through Palm Beach County. | Education Efforts | Completed | N/A | 385.5443 | 47.475 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | Not provided | Loxahatchee River 4e | N/A | N/A | N/A | N/A
| Village of Tequesta | N/A | VOT-02 | Street Sweeping | Street sweeping program. | Street Sweeping | Completed | N/A | 2.5 | 1.5 | N/A | N/A | N/A | 3555 | Villages of Tequesta | 3555 | N/A | Non-structural | Completed | 2019 | NPDES Part III.A.3 and MS4 Tool | Loxahatchee River 4e | N/A | N/A | N/A | N/A
| Loxahatchee River District | Town of Jupiter | LRD-16 | Storm Water Filter Box Evaluation | Study to evaluate the materials captured and effectiveness of Suntree Tech Gutter Bin storm water filter boxes. | Study | Underway | 2021 | N/A | N/A | Various locations in TOJ | N/A | Not provided | Not provided | Not provided | Not provided | Not provided | Non-structural | N/A | 2020 | N/A | Loxahatchee River 4e | Not provided | Not provided | Not provided | N/A
| Loxahatchee River District | N/A | LRD-17 | Loxahatchee River Neighborhood Sewering Phase 14 | Convert 28 septic systems to sewer - 181st St (12), Hobart St (13), 197 Pl (3). | OSTDS Phase Out | Underway | 2021 | TBD | TBD | Not provided | Not provided | Not provided | Not provided | Not provided | Not provided | Not provided | Structural | N/A | 2020 | N/A | Loxahatchee River 4e | Not provided | Not provided | Not provided | Need to run ArcNLET calculations
| Town of Jupiter | N/A | TOJ-16 | Dolphin Drive Infrastructure Improvements | Construction of drainage improvements into the southern portion of Dolphin Dr to alleviate flooding and enhance stormwater runoff inculding regrading of swales and installation of catch basins. | Stormwater System Rehabilitation | Planned | 2023 | TBD | TBD | Not provided | Not provided | 225495 | Not provided | Town of Jupiter | Not provided | Not provided | Structural | N/A | 2020 | N/A | Loxahatchee River 4e | Not provided | Not provided | Not provided | N/A
| Town of Jupiter | N/A | TOJ-17 | Bush Road Drainage Improvements | Construction of drainage improvements along the west side of Bush Road to alleviate flooding and enhance stormwater runoff including addition of drainage inlets, exfiltration trench, RCP and regrading of swales. | Exfiltration Trench | Planned | 2023 | TBD | TBD | Not provided | Not provided | 189000 | Not provided | Town of Jupiter | Not provided | Not provided | Structural | N/A | 2021 | N/A | Loxahatchee River 4e | Not provided | Not provided | Not provided | N/A
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Jan 2008 forward
Note on J28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Bud submitted ArcNLET as 2,367 with a note that the total includes 2,336 for Jupiter Inlet Colony which is outside the RAP boundary.
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: South Indian River Water Control District
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Loxahatchee River Preservation Initiative
Note on G47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Specifiy if on or off-line
Note on J56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TN and TP reductions for TOJ-14 are based on pre and post monitoring concentrations and PLSM modeled runoff volume. TP measured data showed a greater reduction than TN.

## All FIB Projects
Lead Entity | Partners | Project Number | Project Name | Project Description | Project Type | Project Status | Estimated Completion Date | Location | Cost Estimate | Cost Annual O&M | Funding Source | Funding Amount | DEP Contract Agreement Number | Structural, Non-structural, or Trade | (Original) Project Status | Year Project Added | Attachments | BMAP | Latitude | Longitude | Start Date | Comments
FDOT District 4 | N/A | FDOT-FIB-01 | Geographic Information Systems (GIS) Data Collection and Mapping | GIS collection and mapping of stormwater assets and infrastructure. | FIB- Stormwater | Ongoing | N/A | State roads throughout RAP boundary | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
FDOT District 4 | N/A | FDOT-FIB-02 | Litter Control | Routine maintenance roadway litter collection. | FIB- Trash Cleanup of Impaired Waterbody | Ongoing | N/A | State roads throughout RAP boundary | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
FDOT District 4 | N/A | FDOT-FIB-03 | Street Sweeping | Routine maintenance roadway street sweeping. | FIB- Stormwater | Ongoing | N/A | State roads throughout RAP boundary | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
FDOT District 4 | N/A | FDOT-FIB-04 | Illicit Detection Program (Inspections, Reporting, Investigations and Elimination) | All FDOT maintenance personnel and roadway contractors complete IDDE trainning (see trainning video link). | FIB- Stormwater | Ongoing | N/A | State roads throughout RAP boundary | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
FDOT District 4 | N/A | FDOT-FIB-05 | Walk the Waterbody/ Right Of Way | Walk the right of way to look for illicite discharges and sources of fecal bacteria such as wildlife, accumulated trash and homeless populations. | FIB- Source Identification Activities | Underway | 2020 | WBID 3226C | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
FDOT District 4 | N/A | FDOT-FIB-06 | Catch Basin Cleanout | TBD catch basins cleaned (12 month period). | FIB- Stormwater | Ongoing | N/A | State roads throughout RAP boundary | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
FDOT District 4 | N/A | FDOT-FIB-07 | Desilting of Stormwater Pipes | TBD LF cleaned (12 month period). | FIB- Stormwater | Ongoing | N/A | State roads throughout RAP boundary | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | AM Contractor | FTE-FIB-01 | GIS Data Collection and Mapping | GIS collection and mapping of stormwater assets & infrastructure. | FIB- Stormwater | Ongoing | N/A | FTP MP 112-125 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | AM Contractor | FTE-FIB-02 | Street sweeping | Routine maintenance roadway street sweeping (12 months) 17 cycles, 46.5 curb or lane miles, approximately 146,567.0 lbs. dry weight. | FIB- Stormwater | Ongoing | N/A | FTP MP 112-125 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | N/A | FTE-FIB-03 | Pet/Animal Management | West Palm Beach & Ft. Pierce Service plazas have pet waste areas with bags and waste receptacles. | FIB- Stormwater | Ongoing | N/A | West Palm Beach Service Plaza MP 94 & Ft. Pierce Service Plaza MP 145 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | AM Contractor | FTE-FIB-04 | Illicit Detection Program (Inspections, Reporting, Investigations and Elimination) | All roadway contractors must complete IDDE training. | FIB- Stormwater | Completed | N/A | FTP MP 112-125 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | N/A | FTE-FIB-05 | Walk the Waterbody/Rights-Of-Way | Walk the rights-of-way to look for illicit discharges and sources of fecal bacteria such as wildlife, accumulated trash, and homeless populations. | FIB- Source Identification Activities | Completed | 2020 | FTP MP 112-116 (WBID 3226C) | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | AM Contractor | FTE-FIB-06 | Catch Basin Cleanout | 53 catch basins cleaned (12 month period). | FIB- Stormwater | Ongoing | N/A | FTP MP 112-125 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | AM Contractor | FTE-FIB-07 | Desilting of Stormwater Pipes | 2,460 linear feet of stormwater pipe cleaned (12 month period). | FIB- Stormwater | Ongoing | N/A | FTP MP 112-125 | Not provided | N/A | Florida Legislature | Not provided | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Florida Turnpike Enterprise | N/A | FTE-FIB-08 | Education and Outreach | All service plazas have an E-poster on video screens. | FIB- Stormwater | Ongoing | N/A | West Palm Beach Service Plaza MP 94 & Ft. Pierce Service Plaza MP 145 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Florida Turnpike Enterprise | N/A | FTE-FIB-09 | GIS Data Collection and Mapping | GIS collection and mapping of stormwater assets & infrastructure. Capturing maintenance activity and inspections. | FIB- Stormwater | Underway | 2021 | FTP MP 112-125 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Loxahatchee River District | N/A | LRD-FIB-01 | Weekly Bacteria Sampling and Mapping | Weekly sampling of recreational waterways. | FIB- Source Identification Activities | Ongoing | N/A | 3226C, 3226, 3226D, 3226A | Not provided | Not provided | LRD | Not provided | N/A | Non-structural | Completed | 2019 | GIS maps provided | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Loxahatchee River District | DEP | LRD-FIB-02 | Short-term Source ID Partnership | Source identification sampling conducted in partnership with DEP on priority areas. | FIB- Source Identification Activities | Ongoing | N/A | 3226C, 3226 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Loxahatchee River District | N/A | LRD-FIB-03 | Wrack Study | Study of FIB in wrack sediments and surface water in the Loxahatchee River. | FIB- Source Identification Activities | Completed | 2018 | 3226C, 3226D, 3226 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
North Palm Beach County Improvement District | N/A | NPBC-FIB-01 | Develop BPCP for The Shores (Unit 23) | The district will develop a BPCP for 7 Units of Development within the plan boundary by March 2020. | FIB- Source Identification Activities | Completed | 2020 | WBID 3232 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Combined Report
North Palm Beach County Improvement District | N/A | NPBC-FIB-02 | Develop BPCP for North Fork (Unit 29) | The district will develop a BPCP for 7 Units of Development within the plan boundary by March 2020. Includes | FIB- Source Identification Activities | Completed | 2020 | WBIDs 3232A and 3224 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Combined Report
North Palm Beach County Improvement District | N/A | NPBC-FIB-03 | Develop BPCP for Palm Cove (Unit 32) | The district will develop a BPCP for 7 Units of Development within the plan boundary by March 2020. | FIB- Source Identification Activities | Completed | 2020 | WBID 3232 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Combined Report
North Palm Beach County Improvement District | N/A | NPBC-FIB-04 | Develop BPCP for Cypress Cove (Unit 33) | The district will develop a BPCP for 7 Units of Development within the plan boundary by March 2020. | FIB- Source Identification Activities | Completed | 2020 | WBID 3232 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Combined Report
North Palm Beach County Improvement District | N/A | NPBC-FIB-05 | Develop BPCP for Mystic Cove (Unit 41) | The district will develop a BPCP for 7 Units of Development within the plan boundary by March 2020. | FIB- Source Identification Activities | Completed | 2020 | WBID 3232 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Combined Report
North Palm Beach County Improvement District | N/A | NPBC-FIB-06 | Develop BPCP for Paseos (Unit 45) | The district will develop a BPCP for 7 Units of Development within the plan boundary by March 2020. | FIB- Source Identification Activities | Completed | 2020 | WBID 3226C | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Combined Report
North Palm Beach County Improvement District | N/A | NPBC-FIB-07 | Develop BPCP for Jupiter Isles (Unit 47) | The district will develop a BPCP for 7 Units of Development within the plan boundary by March 2020. | FIB- Source Identification Activities | Completed | 2020 | WBID 3230 | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Combined Report
Palm Beach County | N/A | PBC-FIB-01 | Public Education | Public education program that includes FY&N Program; landscaping, irrigation, and fertilizer ordinances; PSAs; pamphlets; website; and inspection program. | FIB- Stormwater | Ongoing | N/A |  | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-01 | Jones and Sims Creek Water Quality Master Plan | Master water quality plan to identify fecal bacteria contamination sources. | FIB- Source Identification Activities | Completed | 2015 | WBID 3226C | 57070 | Not provided | Town/ LRPI | 28535 | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-02 | Pine Gardens South Water Quality Improvements | Installation of exfiltration trenches to provide an average of 0.41 inches of treatment in the project area. | FIB- Stormwater | Completed | 2015 | WBID 3226W1 | 328552 | Not provided | Town/ LRPI | Town - $200,000/ LRPI - $128,552 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | Joint NPDES Group | TOJ-FIB-03 | Public Education | Public education efforts related to actions such as proper pet waste management. | FIB- Stormwater | Ongoing | N/A | Town of Jupiter | Not provided | Not provided | Town | Not provided | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-04 | Street Sweeping | Periodic street sweeping to enhance water quality. | FIB- Stormwater | Ongoing | N/A | Town of Jupiter | Not provided | 49586 | Town | 49586 | N/A | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-05 | Indian Creek Outfall Replacement and Canal Stabilization | Canal stabilization to reduced/prevent erosion of the canal banks. | FIB- Stormwater | Completed | 2013 | WBID 3234 | 199922 | Not provided | Town | 199922 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-06 | Cinquez Residential Area | Construction of drainage system to retain volume above what was required to offset the increase in impervious area. | FIB- Stormwater | Completed | 2011 | WBID 3226C | 569518 | Not provided | Town | 569518 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-07 | Cinquez Park Drainage Improvements | Construction of new park stormwater management system to retain runoff. | FIB- Stormwater | Underway | 2018 | WBID 3226C | 329400 | Not provided | Town | 329400 |  | Structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-08 | Stormwater Quality Improvement Grants | Town cost-share program (50/50) with property owner and homeowner associations for storm water quality enhancements within their private systems. 28 grants awarded since 2008. Annual appropriation. | FIB- Stormwater | Ongoing | N/A | Town of Jupiter | 432368 | Not provided | Town | 998229 |  | Non-structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-09 | Pennock Industrial Park Drainage Improvements | Improvements to include additional exfiltration systems to enhance runoff water quality. | FIB- Stormwater | Planned | 2022 | WBID 3226C | 463710 | Not provided | Town | 463710 | N/A | Structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-10 | Sonoma Isles Stormwater Harvesting | Retention of excess stormwater runoff from the Sonoma Isles community for use for irrigation purposes. | FIB- Stormwater | Completed | 2016 | WBID 3230 | Not provided | Not provided | Privately Funded | Not provided | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | LRD | TOJ-FIB-11 | Water Quality Monitoring in Jones and Sims Creeks | Surface water sampling of nutrients, chlorophyll a, and FIB to characterize conditions and identify trends in Jones and Sims Creeks tributaries. | FIB- Source Identification Activities | Ongoing | N/A | WBID 3226C | Not provided | 30000 | Town | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-12 | Datasonde Monitoring in Jones and Sims Creeks | Automated water quality equipment established at 3 stations to record water temperature, salinity, water depth, and dissolved oxygen. | FIB- Source Identification Activities | Ongoing | N/A | WBID 3226C | 47176 | 10000 | Town | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | Jupiter River Estates | TOJ-FIB-13 | Jupiter River Estates Community Clean-up | Clean-up and trash removal from Jones Creek tributary by volunteer residents in Jupiter River Estates Community. | FIB- Trash Cleanup of Impaired Waterbody | Ongoing | N/A | WBID 3226C | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-14 | Urban Stormwater Management System Rehabilitation - Phase III | Rehabilitation of swale systems within Maplewood Drive and North Palm Beach Heights. | FIB- Stormwater | Completed | 2008 | WBID 3226C | 259250 | Not provided | Town/ LRPI | Town - $129,625/ LRPI - $129,625 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-15 | Urban Stormwater Management System Rehabilitation - Phase IV | Rehabilitation of swale systems within Jupiter River Estates. | FIB- Stormwater | Completed | 2009 | WBID 3226C | 377486 | Not provided | Town/ LRPI | Town - $188,743/ LRPI - $188,743 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-16 | Urban Stormwater Management System Rehabilitation - Phase V | Rehabilitation of swale systems within North Palm Beach Heights. | FIB- Stormwater | Completed | 2010 | WBID 3226C | 355300 | Not provided | Town/ LRPI | Town - $177,650/ LRPI - $177,650 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-17 | Urban Stormwater Management System Rehabilitation - Phase VI | Rehabilitation of swale systems within Maplewood Drive and Toney Penna. | FIB- Stormwater | Completed | 2014 | WBID 3226C | 337170 | Not provided | Town/ LRPI | Town - $168,585/ LRPI - $168,585 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-18 | Maintenance Dredging in Rio Vista Waterway | Dredging and muck removal to restore Rio Vista Waterway. | FIB- Stormwater | Completed | 2012 | WBID 3226D | 70500 | Not provided | Town | 70500 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-19 | Water Plant Detention Pond Cleanout | Silt removal from wet detention pond located at the water plant. | FIB- Stormwater | Completed | 2017 | WBID 3226C | 10620 | Not provided | Town | 10620 | N/A | Structural | Completed | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | N/A | TOJ-FIB-20 | Pine Gardens North Water Quality Improvements | Construct exfiltration trenches within existing right-of-way. | FIB- Stormwater | Planned | 2022 | WBID 3226C | 719782 | Not provided | Town | 719782 | N/A | Structural | Planned | 2019 | N/A | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Town of Jupiter | Jupiter River Estates | TOJ-FIB-21 | Jupiter River Estates Canal Vegetation Trimming | Trimming along Jones Creek to remove of exotic vegetation to provide sunlight to reduce bacterial growth. Project is contigent upon a property assessment for reoccuring canal maintenance for at least of 10 years and receipt of grant funding. | FIB- Trash Cleanup of Impaired Waterbody | Planned | 2022 | WBID 3226C | 500000 | Not provided | Not provided | Not provided | Not provided | Non-structural | N/A | 2020 | Not provided | Loxahatchee 4e Plan | Not provided | Not provided | Not provided | N/A
Loxahatchee River District | FDEP | LRD-FIB-04 | Dubois Basin Study 2019-2020 | Partner project between FDEP and LRD to evaluate Fecal Indicator Bacteria (FIB), Genetic Markers and Chemical Indicators in the Dubois drainage basin. | FIB- Stormwater | Completed | 2021 | WBID 3226 & 3226W3 | Not provided | Not provided | Not provided | Not provided | FDEP Lab: PROP – Jones, Lox SW Fork – WBID 3226C and Dubois Customer: WPCS Project ID: PROP | Non-structural | N/A | 2021 | Not provided | Loxahatchee 4e Plan | 26.9371 | -80.0723 | Not provided | Genetic and Chemical markers negative; Unpublished lab reports
Loxahatchee River District | FDEP | LRD-FIB-05 | Jones Creek Study 2019-2020 | Partner project between FDEP and LRD to evaluate Fecal Indicator Bacteria (FIB), Genetic Markers, Chemical Indicators, and Turbidity in Jones Creek. | FIB- Stormwater | Completed | 2021 | WBID 3226C | Not provided | Not provided | Not provided | Not provided | FDEP Lab: PROP – Jones, Lox SW Fork – WBID 3226C and Dubois Customer: WPCS Project ID: PROP | Non-structural | N/A | 2021 | N/A | Loxahatchee 4e Plan | 26.929 | -80.1172 | Not provided | Final Report Completed 3/2021
Loxahatchee River District | FDEP, Town of Jupiter, Green Water Solutions, Dr. Peter Moeller, NOAA | LRD-FIB-06 | Nano Bubble Ozone Treatment Project Jones Creek | FDEP Innovative Technologies grant funded project to evaluate the use of Nano Bubble Ozone treatment to improve water quality by reducing perisistently high bacteria concentrations in the brackish, tidal influenced, Jones Creek. | FIB- Stormwater | Planned | 2021 | WBID 3226C | 375000 | N/A | FDEP | 350000 | TBD | Non-structural | N/A | 2021 | N/A | Loxahatchee 4e Plan | 26.929 | -80.1172 | 2021 | N/A
Florida Turnpike Enterprise | N/A | FTE-FIB-10 | Walk the Waterbody/Rights-Of-Way | Walk the rights-of-way to look for illicit discharges and sources of fecal bacteria such as wildlife, accumulated trash, and homeless populations. | FIB- Source Identification Activities | Underway | 2021 | FTP MP 116-125 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Underway | 2019 | N/A | Loxahatchee 4e Plan | N/A | N/A | Not provided | Previously FTE-FIB-05, broken up into two projects
Note on H39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need a completion date or, if the project happens every year (ongoing), we can say that the completion date is "N/A." Either way, we need to know what to list. The completion date is a required component of the project database.
Note on H40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need a completion date or, if the project happens every year (ongoing), we can say that the completion date is "N/A." Either way, we need to know what to list. The completion date is a required component of the project database.

## Nutrient Summary Info
ProjectStatus | Completed |  |  | Description | TN (lb/yr) | TP (lb/yr) | Project Type | TN Reduction (lbs/yr) | TP Reduction (lbs/yr)
|  |  |  | Revised PLSM Reduction Estimate | 36489 | 4129 | Agricultural BMPs | 1019.518 | 239.1811
Sum of CostEstimate | Sum of CostAnnualO&M | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | Reductions from Projects Completed | 31858.7223 | 5286.0514 | BMP Cleanout | 0 | 0
18712686 | 55141 | 31858.7223 | 5286.0514 | Reductions Remaining | 4630.2777 | -1157.0514 | BMP Treatment Train | 36.1973 | 2.5816
|  |  |  | Percentage of Reductions Achieved | 87.31% | 128% | Catch Basin Inserts/Inlet Filter Cleanout | 0 | 0
|  |  |  | Estimate to meet 5.5 ug/L chl-a |  |  | Control Structure | 1132.4849 | 422.5179
[7 empty] | Creating/ Enhancing Oyster Reefs | 0 | 0
[7 empty] | Dispersed Water Management (DWM) | 0 | 0
[7 empty] | Dry Detention Pond | 207.2405 | 14.3509
ProjectStatus | (Multiple Items) |  |  | Description | TN (lb/yr) | TP (lb/yr) | Education Efforts | 8979.7657 | 985.1381
|  |  |  | Revised PLSM Reduction Estimate | 36489 | 4129 | Exfiltration Trench | 830.2621 | 95.5592
Sum of CostEstimate | Sum of CostAnnualO&M | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | Reductions from All Projects | 34198.4351 | 5384.6323 | Grass swales with swale blocks or raised culverts | 357.885 | 25.4271
6294108 | 0 | 2339.7128 | 98.5809 | Reductions Remaining | 2290.5649 | -1255.6323 | Hydrologic Restoration | 4405.1205 | 445.7153
|  |  |  | Percentage of Reductions Achieved | 93.72% | 130.4% | Land Use Change | 193.7928 | 493.2907
|  |  |  | Estimate to meet 5.5 ug/L chl-a |  |  | Muck Removal/Restoration Dredging | 239.1 | 85.6
[7 empty] | Off-line Retention BMPs | 32.1221 | 4.6898
[7 empty] | On-line Retention BMPs | 16.0876 | 0.78159
[7 empty] | OSTDS Phase Out | 7130 | 0
[7 empty] | Stormwater System Rehabilitation | 188.4281 | 226.1637
[7 empty] | Street Sweeping | 2913.5 | 1867.5
[7 empty] | Wet Detention Pond | 6329.7192 | 467.7549
[7 empty] | Wetland Restoration | 187.2114 | 8.3805
[7 empty] | Grand Total | 34198.4351 | 5384.6323
INTERNAL
|  |  |  | Description | TN (lb/yr) | TP (lb/yr)
|  |  |  | Revised PLSM Reduction Estimate | 60220 | 6814
|  |  |  | Reductions from All Projects | 34198.4351 | 5384.6323
|  |  |  | Reductions Remaining | 26021.5649 | 1429.3677
|  |  |  | Percentage of Reductions Achieved | 56.79% | 79.02%
Estimate to meet 4 ug/L chl-a

## FIB Summary Info
FIB Summary Info
Project Types | Number of Projects
FIB- Source Identification Activities | 16
FIB- Stormwater | 30
FIB- Trash Cleanup of Impaired Waterbody | 2
Grand Total | 48
Lead Entity | Number of Projects
FDOT District 4 | 7
Florida Turnpike Enterprise | 10
Loxahatchee River District | 3
North Palm Beach County Improvement District | 7
Palm Beach County | 1
Town of Jupiter | 20
Grand Total | 48
2021 Status
Row Labels | Count of Project Status
Completed | 40
Planned | 4
Underway | 8
Grand Total | 52

## Project Types and Drop Downs
ProjectType |  | Project Type | Structural/Non Structural | Status
Wetland Restoration | Structural | 100% On-site Retention | Structural | Completed
Education Efforts | Non-structural | Agricultural BMPs | Use Past Designation | Planned
Agricultural BMPs | Use Past Designation | Alum Injection Systems | Structural | Canceled
Land Use Change | Non-structural | Aquatic Vegetation Harvesting | Non-structural | Underway
Grass swales with swale blocks or raised culverts | Structural | Baffle Boxes- First Generation (hydrodynamic separator) | Structural | Ongoing
Dry Detention Pond | Structural | Baffle Boxes- Second Generation | Structural
Off-line Retention BMPs | Structural | Baffle Boxes- Second Generation with Media | Structural
Wet Detention Pond | Structural | Biological/ Bacteria Treatment | Structural
Street Sweeping | Non-structural | Biosorption Activated Media (BAM) | Structural
BMP Cleanout | Non-structural | Bioswales | Structural
Catch Basin Inserts/Inlet Filter Cleanout | Non-structural | BMP Cleanout | Non-structural
Creating/ Enhancing Oyster Reefs | Structural | BMP Treatment Train | Structural
OSTDS Phase Out | Structural | Catch Basin Inserts/Inlet Filter Cleanout | Non-structural
Hydrologic Restoration | Structural | Closed Basin | Non-structural
Control Structure | Structural | Control Structure | Structural
Dispersed Water Management (DWM) | Structural | Creating/ Enhancing Living Shoreline | Structural
Exfiltration Trench | Structural | Creating/ Enhancing Oyster Reefs | Structural
Muck Removal/Restoration Dredging | Non-structural | Credit Trade | Trade
BMP Treatment Train | Structural | Dairy Remediation | Structural
On-line Retention BMPs | Structural | Decommission/ Abandonment | Non-structural
Stormwater System Rehabilitation | Structural | Deep Injection Well | Structural
|  | Denitrification Walls | Structural
|  | Dispersed Water Management (DWM) | Structural
|  | Dry Detention Pond | Structural
|  | Education Efforts | Non-structural
|  | Enhanced Public Education | Non-structural
|  | Exfiltration Trench | Structural
|  | Exotic Vegetation Removal | Non-structural
|  | Fertilizer Cessation | Non-structural
|  | Fertilizer Reduction | Non-structural
|  | Filter Marsh | Structural
|  | Fish Harvesting | Non-structural
|  | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Structural
|  | Floodplain Restoration | Structural
|  | Golf Course or Sports Field BMPs | Non-structural
|  | Grass swales with swale blocks or raised culverts | Structural
|  | Grass swales without swale blocks or raised culverts | Structural
|  | Hybrid wetland treatment technology (HWTT) | Structural
|  | Hydrodynamic Separators | Structural
|  | Hydrologic Restoration | Structural
|  | Impoundment | Structural
|  | Industrial Facility Upgrades | Structural
|  | Land Acquisition | Non-structural
|  | Land Preservation | Non-structural
|  | Land Use Change | Non-structural
|  | LID- Green Roofs | Structural
|  | LID- Other | Structural
|  | LID- Rain Gardens | Structural
|  | LID- Tree Boxes/Tree Wells | Structural
|  | Macroalgal Harvesting | Non-structural
|  | Monitoring/Data Collection | Non-structural
|  | Muck Removal/Restoration Dredging | Non-structural
|  | Natural Wetlands as Filters | Non-structural
|  | Non-contributing Basin | Non-structural
|  | Off-line Retention BMPs | Structural
|  | On-line Retention BMPs | Structural
|  | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Structural
|  | OSTDS Phase Out | Structural
|  | Pervious Pavement | Structural
|  | Pervious Pavers | Structural
|  | Plugging Artesian Wells | Structural
|  | Reclaimed Water | Structural
|  | Regional Stormwater Treatment | Structural
|  | Regulations, Ordinances, and Guidelines | Non-structural
|  | Retention/Detention BMP Retrofit with Nutrient Reducing Media | Structural
|  | Retention/Detention BMP with Nutrient Reducing Media | Structural
|  | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Structural
|  | Sanitary Sewer Inspections | Non-structural
|  | SAV Planting | Structural
|  | Shoreline Stabilization | Structural
|  | Stormwater Aeration System | Structural
|  | Stormwater Reuse | Structural
|  | Stormwater System Rehabilitation | Structural
|  | Stormwater Treatment Areas (STAs) | Structural
|  | Street Sweeping | Non-structural
|  | Study | Non-structural
|  | Turbidity Reducing Polymers (e.g., Floc logs ®) | Non-structural
|  | Vegetated Buffers | Non-structural
|  | Wastewater Service Area Expansion | Structural
|  | Wet Detention Pond | Structural
|  | Wetland Restoration | Structural
|  | Wetland Treatment | Structural
|  | WWTF Disposal Site | Structural
|  | WWTF Diversion to Reuse | Structural
|  | WWTF Nutrient Reduction | Structural
|  | WWTF Upgrade | Structural
|  | FIB- Stormwater | Bacteria
|  | FIB- Source Identification Activities | Bacteria
|  | FIB- Sanitary Sewer | Bacteria
|  | FIB- OSTDS | Bacteria
|  | FIB- Trash Cleanup of Impaired Waterbody | Bacteria
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Specifiy if on or off-line