## Table of Contents
Sheet Name | Contents
Milestones | Drop-down features to show TN & TP milestones, required reductions, and project reductions by entity.
Required Reductions | Table with TN and TP required reductions by entity and BMAP milestones.
Target Milestones | Target milestones for each BMAP.
All Projects | Project information for all projects from STAR.
All Projects Pivot | Pivot table of information from STAR.
Project Table | Table of TN & TP reductions by entity, sub-basin, & watershed.

## Milestones
For Total Nitrogen Reductions |  |  |  | For Total Phosphorus Reductions
BMAP: | Caloosahatchee |  |  | BMAP: | Caloosahatchee
Crediting Location: | East Caloosahatchee |  |  | Crediting Location: | West Caloosahatchee
Entity: | City of Moore Haven |  |  | Entity: | Total
Required Reduction (lbs/yr): | 1026.1704 |  |  | Basin: | Total
|  |  |  | Required Reduction (lbs/yr): | 24986
Year | Overall Requirement | Entity Requirement (lbs/yr) | Reductions Achieved/ Planned (lbs/yr) | Year | Overall Requirement | Entity Requirement (lbs/yr) | Total Entity Reductions Achieved/ Planned (lbs/yr)
2025 | 10% | 102.617 | 0 | 2025 | 10% | 2498.6 | N/A
2030 | 35% | 359.1597 | 1885 | 2030 | 35% | 8745.1 | N/A
2035 | 75% | 769.6278 | 1885 | 2035 | 75% | 18739.5 | N/A
2040 | 100% | 1026.1704 | 1885 | 2040 | 100% | 24986 | N/A

## Required Reductions
Tidal Subwatershed Reductions |  |  | East and West Caloosahatchee Subwatershed TN Reductions |  | East and West Caloosahatchee Subwatershed TP Reductions
Entity | TN Required Reduction (lbs/yr) |  | Entity | TN Required Reduction (lbs/yr) | Entity | C-19 Canal | Lake Hicpochee | Long Hammock | S-4 Basin | Townsend Canal | Total
FDACS | 208669.1 |  | FDACS | 1358401.3 | FDACS | 1276 | 25 | 11106 | 1782 | 8623 | 22811
Charlotte County | 5846.52 |  | Charlotte County | 643.8 | FDOT | 48 | 0 | 57 | 45 | 82 | 232
City of Cape Coral | 38964.6 |  | City of Clewiston | 3704.0083 | City of Clewiston | N/A | N/A | N/A | 316 | N/A | 316
City of Fort Myers | 19493.1 |  | City of LaBelle | 7642.8586 | Glades County | 133 | 2 | 51 | 199 | N/A | 386
FDOT District 1 | 5098.3 |  | City of Moore Haven | 1026.1704 | Hendry County/Port LaBelle CDD | N/A | N/A | 585 | 596 | 54 | 1235
LA-MSID (formerly ECWCD) | 34716.3 |  | Collier County | 38.041 | Collier County | N/A | N/A | N/A | N/A | 6 | 6
Lee County | 59559.4 |  | FDOT District 1 | 5333.1 | Total | 1457 | 27 | 11799 | 2938 | 8765 | 24986
Lucaya CDD | 88 |  | Glades County | 17439.1252
Moody River Estates CDD | 424 |  | Hendry County/Port LaBelle CDD | 40450.581
Sail Harbour CDD | 126.9 |  | LA-MSID (formerly ECWCD) | 31689.9
Verandah East CDD | 532.7 |  | Lee County | 4925
Verandah West CDD | 824.4 |  | Portico CDD | 784.561
Total | 374343.32 |  | River Hall CDD | 4343.1712
|  |  | Total | 1476421.6169
Do not delete. Need for Data Validation Substitute.
Tidal BMAP Subwatershed
East Caloosahatchee |  | EWCS
Tidal Caloosahatchee
West Caloosahatchee

## Target Milestones
Tidal Subwatershed - TN |  |  | East and West Subwatershed - TN and TP
Milestone | Year | % | Milestone | Year | %
5-year | 2017 | 50 | 5-year | 2025 | 10
10-year | 2022 | 75 | 10-year | 2030 | 35
15-year | 2027 | 95 | 15-year | 2035 | 75
20-year | 2032 | 100 | 20-year | 2040 | 100

## All Projects
LeadEntity | ProjectNumber | ProjectName | ProjectDescription | Project Type Category | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | CreditingLocation
Barron WCD | BD-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2019 | NA | 0 | 0 | East Caloosahatchee
Barron WCD | BD-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2019 | NA | 0 | 0 | East Caloosahatchee
Barron WCD | BD-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | East Caloosahatchee
Barron WCD | BD-04 | Canal/Ditch Bank Berms | Minimize sediment transport by constructing berms on top of canal/ditch banks and promoting vegetation cover. | Stormwater | Shoreline Stabilization | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Barron WCD | BD-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | East Caloosahatchee
Charlotte County | CH-01 | Education Efforts | Education efforts include: Florida Yards and Neighborhoods (FYN) Program, landscape, irrigation, fertilizer ordinances, pamphlets, public service announcements, website, and inspection/illicit discharge program. | Stormwater | Education Efforts | Ongoing | 2020 | NA | 1180 | 191 | Tidal Caloosahatchee
Charlotte County | CH-01 | Education Efforts | Education efforts include: Florida Yards and Neighborhoods (FYN) Program, landscape, irrigation, fertilizer ordinances, pamphlets, public service announcements, website, and inspection/illicit discharge program. | Stormwater | Education Efforts | Ongoing | 2020 | NA | 130 | 21 | West Caloosahatchee
City of Cape Coral | CC-01 | Education Efforts | FYN; landscape, irrigation, pet waste, and fertilizer ordinances; pamphlets, PSAs, website, and Illicit Discharge Program. | Stormwater | Education Efforts | Ongoing | TBD | NA | 9299 | 3448 | Tidal Caloosahatchee
City of Cape Coral | CC-02 | SE - 1 Swale/ Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-03 | SW - 1 Swale/ Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-04 | SW - 2 Swale/ Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-05 | SW - 3 Swale/ Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-06 | SW - 4 Swale/ Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-07 | SW - 5 Swale/ Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-08 | SE Pipe Replacement | SE pipe replacement. | Stormwater - Nutrient Projects Ineligible for Credit | Stormwater System Rehabilitation | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-09 | Unit 23 - SE 8th Street Drainage | Unit 23-SE 8th Street drainage. | Stormwater - Nutrient Projects Ineligible for Credit | Stormwater System Rehabilitation | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-10 | Freshwater Canal Detention | Regulation of freshwater canals through existing control structures. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 4416 | 3412 | Tidal Caloosahatchee
City of Cape Coral | CC-11 | Freshwater Canal Irrigation | Pump stormwater stored in canals into irrigation supply network. | Stormwater | Stormwater Reuse | Completed | TBD | Prior to 2012 | 796 | 141 | Tidal Caloosahatchee
City of Cape Coral | CC-12 | Weir #6 Elevation/ Basin 12 | Installed riser on weir in freshwater canal system to provide additional retention volume in canals. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-13 | Weir #1 Elevation/ Basin 15 | Installed riser on weir in freshwater canal system to provide additional retention volume in canals. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-14 | Street Sweeping | Street sweeping of downtown area, alleys, bicycle lanes and commercial roads. | Stormwater | Street Sweeping | Ongoing | 2015 | 2023 | 790.5 | 453.1 | Tidal Caloosahatchee
City of Cape Coral | CC-15 | Septic to Sewer Phase Out Project | Phase out septic tanks in Southwest 6/7 area. | Wastewater | OSTDS Phase Out | Completed | 2013 | 2015 | 24454 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-16 | Catch Basin Cleanout | Catch basin cleanouts from Caloosahatchee Watershed areas. | Stormwater | Catch Basin Inserts/Inlet Filter Cleanout | Ongoing | 2015 | 2023 | 109 | 56 | Tidal Caloosahatchee
City of Cape Coral | CC-17 | Unit 8 - SE 47th Terrace Streetscape Improvements Club Square | Suntree Technologies Skimboss and Bold and Gold Media - Club Square. | Stormwater | Baffle Boxes- Second Generation with Media | Completed | TBD | 2018 | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-18 | Ft Myers Cape Coral Wastewater Pipeline | Elimination of wastewater treatment plant effluent discharges to the river from Ft Myers by conveying wastewater to Cape Coral for reuse in Cape Coral water reclamation system. | Wastewater | WWTF Diversion to Reuse | Planned | TBD | TBD | 0 | 0 | Tidal Caloosahatchee
City of Cape Coral | CC-19 | Yellow Fever Creek Hydrologic Restoration | Transfer water from Gator Slough to a new reservoir in Yellow Fever Creek and slowly releasing the flow into the headwaters of Yellow Fever Creek, extending wetland hydroperiods. | Stormwater | Hydrologic Restoration | Underway | TBD | TBD | 14 | 19 | Tidal Caloosahatchee
City of Clewiston | CW-01 | Clewiston Public Education | Landscaping, irrigation, fertilizer, and stormwater ordinances; PSAs; pamphlets; website; illicit discharge program. | Stormwater | Education Efforts | Ongoing | NA | NA | 256 | 29 | East Caloosahatchee
City of Clewiston | CW-02 | Clewiston Street Sweeping | 529 miles swept. 86.93 tons swept. | Stormwater | Street Sweeping | Ongoing | 2000 | NA | 98 | 45 | East Caloosahatchee
City of Clewiston | CW-03 | Clewiston Inlet Maintenance | 43 inlets cleaned. 6.7 tones cleaned. | Stormwater | Catch Basin Inserts/Inlet Filter Cleanout | Ongoing | 2000 | NA | 13 | 7 | East Caloosahatchee
City of Clewiston | CW-04 | Reverse Osmosis WTP Dry Pond | Dry detention pond (volume required = 0.23 ac-ft, volume provided = 1.12 ac-ft). | Stormwater | Dry Detention Pond | Completed | 2006 | Prior to 2012 | 25 | 1 | East Caloosahatchee
City of Clewiston | CW-05 | Sweet Lake Villas Community Association, Inc. | Wet detention pond (volume required = 0.71 ac-ft, volume provided = 1.88 ac-ft). | Stormwater | Wet Detention Pond | Completed | 2006 | Prior to 2012 | 1 | 1 | East Caloosahatchee
City of Clewiston | CW-06 | East Ventura Water Quality | Constructed wetlands to treat runoff. | Stormwater | Stormwater Treatment Areas (STAs) | Completed | 2022 | 2023 | 50 | 6 | East Caloosahatchee
City of Fort Myers | FM-01 | Country Club Neighborhood Exfiltration Trenches | Exfiltration trenches. | Stormwater | Exfiltration Trench | Completed | 2009 | 2012 | 214 | 27 | Tidal Caloosahatchee
City of Fort Myers | FM-02 | Education Efforts | FYN, fertilizer ordinance, pamphlets, PSAs, website, illicit discharge program. | Stormwater | Education Efforts | Ongoing | 2009 | NA | 4652 | 1630 | Tidal Caloosahatchee
City of Fort Myers | FM-03 | Winkler Avenue Utility and Streetscape Improvements | Installation of StormceptorsTM. | Stormwater | Hydrodynamic Separators | Completed | 1999 | 2001 | 0 | 0 | Tidal Caloosahatchee
City of Fort Myers | FM-04 | Manuel's Branch Siltation Structures | Installation of siltation structure designed to receive incoming flow, reduce its velocity and allow for settling of suspended particles. Called sediment trap (near control structure). | Stormwater | Control Structure | Completed | 2011 | 2011 | 486 | 78 | Tidal Caloosahatchee
City of Fort Myers | FM-05 | Manuel's Branch Control Structures | Series of two weirs constructed along Manuel's Branch between Royal Palm Avenue and Grand Avenue that act as detention structures for purpose of increasing storage and attenuation in canal. | Stormwater | Control Structure | Completed | 2010 | 2012 | 981 | 311 | Tidal Caloosahatchee
City of Fort Myers | FM-06 | Billy's Creek Wetland | Filter marsh park. | Stormwater | Constructed Wetland Treatment | Completed | 2008 | 2010 | 1421 | 1211 | Tidal Caloosahatchee
City of Fort Myers | FM-07 | Brookhill Drive Utility Drainage Improvement | Installation of 2 Nutrient Baffle Boxes in parallel along Brookhill Dr. | Stormwater | Baffle Boxes- Second Generation with Media | Completed | 2012 | 2013 | 36 | 4 | Tidal Caloosahatchee
City of Fort Myers | FM-08 | Street Sweeping | All city roads with curb and gutter divided into four zones and swept at varying frequencies based on pollutant accumulation. | Stormwater | Street Sweeping | Ongoing | 2000 | NA | 1851 | 1174 | Tidal Caloosahatchee
City of Fort Myers | FM-09 | Ford Street Preserve | Constructed wetland treatment system that removes pollutants from Ford Street Canal, which serves 811 acres of highly urbanized watershed. | Stormwater | Constructed Wetland Treatment | Completed | 2014 | 2016 | 7916 | 1412 | Tidal Caloosahatchee
City of Fort Myers | FM-10 | Riverfront Development Phase 1 | Retention pond. | Stormwater | On-line Retention BMPs | Completed | 2011 | 2013 | 37 | 10 | Tidal Caloosahatchee
City of Fort Myers | FM-11 | Carrell Canal Water Quality Retrofit | Two detention areas, five filter marshes, and golf course renovation. | Stormwater | BMP Treatment Train | Completed | 2014 | 2015 | 640 | 218 | Tidal Caloosahatchee
City of Fort Myers | FM-12 | Aquashores Neighborhood | Installation of two StormceptorsTM. | Stormwater | Hydrodynamic Separators | Completed | 2014 | 2015 | 0 | 1 | Tidal Caloosahatchee
City of Fort Myers | FM-13 | Billy & High Street Drainage Improvement | Neighborhood improvement project. | Stormwater | BMP Treatment Train | Completed | 2021 | 2023 | 0 | 0 | Tidal Caloosahatchee
City of Fort Myers | FM-14 | Ridgewood Park Neighborhood Improvements | Neighborhood improvement projects to be done in phases. Design is completed. | Stormwater | BMP Treatment Train | Planned | 2024 | 2030 | 0 | 0 | Tidal Caloosahatchee
City of Fort Myers | FM-15 | Midtown Redevelopment | Area improvements including water quality improvements. | Stormwater | BMP Treatment Train | Planned | 2024 | 2028 | 0 | 0 | Tidal Caloosahatchee
City of Fort Myers | FM-16 | Edgewood Neighborhood Improvements | Neighborhood improvement projects to be done in phases. Stormwater design completed. | Stormwater | BMP Treatment Train | Planned | 2024 | 2030 | 0 | 0 | Tidal Caloosahatchee
City of Fort Myers | FM-17 | WTP RO Treatment Improvement | Construct diversion force main between Central and South WWTP. Upgrade South Plant to meet reuse quality. Provide reuse water to Cape Coral. | Wastewater | WWTF Diversion to Reuse | Underway | 2016 | 2025 | 0 | 0 | Tidal Caloosahatchee
City of LaBelle | LB-01 | City of LaBelle Zone J Septic Tank to Central Sewer | Septic tank conversion project that will consist of a pump station, force main and gravity sewer to provide an estimated 50 customers (area buildout) with sanitary sewer. | Wastewater | OSTDS Phase Out | Underway | 2019 | 2025 | 307 | 0 | West Caloosahatchee
City of LaBelle | LB-02 | City of LaBelle Zone A Septic Tank to Central Sewer | Septic tank conversion project that will consist of a pump station, force main and gravity sewer to provide an estimated 442 customers (area buildout) with sanitary sewer. | Wastewater | OSTDS Phase Out | Underway | 2019 | 2024 | 2771 | 0 | West Caloosahatchee
City of LaBelle | LB-03 | City of LaBelle Zone B Septic Tank to Central Sewer | Septic tank conversion project that will consist of a pump station, force main and gravity sewer to provide an estimated 315 customers (area buildout) with sanitary sewer. | Wastewater | OSTDS Phase Out | Underway | 2021 | 2025 | 1971 | 0 | West Caloosahatchee
City of LaBelle | LB-04 | City of LaBelle Zones C, D, and E WWTP System Improvements and Expansion Project | Septic tank conversion project that will consist of pump station additions and downstream improvements, force main and gravity sewer to provide an estimated 776 customers (area buildout) with sanitary sewer. | Wastewater | OSTDS Phase Out | Underway | 2022 | 2027 | 3462 | 0 | West Caloosahatchee
City of LaBelle | LB-05 | City of LaBelle Zones G, H, and I WWTP System Improvements and Expansion Project | Septic tank conversion project that will consist of pump station additions and downstream improvements, force main and gravity sewer to provide an estimated 262 customers (area buildout) with sanitary sewer. | Wastewater | OSTDS Phase Out | Underway | 2022 | 2027 | 1649 | 0 | West Caloosahatchee
City of Moore Haven | MH-01 | Glades County Caloosahatchee River and Estuary Area Wastewater Grant | Elimination of aging and/or failing existing septic systems in City of Moore Haven. Project also provides for additional conveyance capacity for additional homes and businesses. | Wastewater | OSTDS Phase Out | Planned | TBD | 2021 | 1654 | 0 | East Caloosahatchee
City of Moore Haven | MH-02 | Sanitary Sewer Hook-Up Project | Hook-up 14 residential housing units on Railroad Ave, Avenue F and 7th street currently on septic systems to central sewer. | Wastewater | OSTDS Phase Out | Completed | 2019 | 2020 | 231 | 0 | East Caloosahatchee
Clewiston Drainage District | CD-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2021 | NA | 0 | 0 | East Caloosahatchee
Clewiston Drainage District | CD-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2021 | NA | 0 | 0 | East Caloosahatchee
Clewiston Drainage District | CD-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | East Caloosahatchee
Clewiston Drainage District | CD-04 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2020 | NA | 0 | 0 | East Caloosahatchee
Clewiston Drainage District | CD-05 | Aquatic Vegetation Control | Mechanical removal of vegetation. | In Waterbody | Aquatic Vegetation Harvesting | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Collier County | TC-COL-01 | Collier County Pollution Prevention | Collier County pollution prevention programs through local illicit discharge ordinance and inspection/complaint program, fertilizer ordinance, pet waste ordinance, landscape ordinance, and education and outreach efforts. | Stormwater | Education Efforts | Ongoing | 2011 | NA | 3 | 0.4 | West Caloosahatchee
Collins Slough WCD | CS-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2021 | NA | 0 | 0 | East Caloosahatchee
Collins Slough WCD | CS-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2021 | NA | 0 | 0 | East Caloosahatchee
Collins Slough WCD | CS-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2021 | 2020 | 0 | 0 | East Caloosahatchee
Collins Slough WCD | CS-04 | Canal Cleaning Program | Review and field evaluation of sediment accumulation and scheduling of removal, when necessary. | In Waterbody | Muck Removal/Restoration Dredging | Planned | 2021 | NA | 0 | 0 | East Caloosahatchee
Collins Slough WCD | CS-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | East Caloosahatchee
County Line Drainage District | CL-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Ongoing | 2020 | NA | 0 | 0 | West Caloosahatchee
County Line Drainage District | CL-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Underway | 2020 | TBD | 0 | 0 | West Caloosahatchee
County Line Drainage District | CL-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | West Caloosahatchee
County Line Drainage District | CL-04 | Canal Cleaning Program | Review and field evaluation of sediment accumulation and scheduling of removal, when necessary. | In Waterbody | Muck Removal/Restoration Dredging | Underway | 2020 | TBD | 0 | 0 | West Caloosahatchee
County Line Drainage District | CL-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Underway | 2020 | TBD | 0 | 0 | West Caloosahatchee
Cow Slough WCD | CSW-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Cow Slough WCD | CSW-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Cow Slough WCD | CSW-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | West Caloosahatchee
Cow Slough WCD | CSW-04 | Canal/Ditch Bank Berms | Minimize sediment transport by constructing berms on top of canal/ditch banks and promoting vegetation cover. | Stormwater | Shoreline Stabilization | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Cow Slough WCD | CSW-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2020 | NA | 0 | 0 | West Caloosahatchee
Devil's Garden WCD | DG-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Devil's Garden WCD | DG-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Devil's Garden WCD | DG-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | West Caloosahatchee
Devil's Garden WCD | DG-04 | Canal Cleaning Program | Review and field evaluation of sediment accumulation and scheduling of removal, when necessary. | In Waterbody | Muck Removal/Restoration Dredging | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Devil's Garden WCD | DG-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | West Caloosahatchee
Disston Island Conservancy District | DI-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2021 | NA | 0 | 0 | East Caloosahatchee
Disston Island Conservancy District | DI-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Disston Island Conservancy District | DI-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | East Caloosahatchee
Disston Island Conservancy District | DI-04 | Slow Velocity in the Main Canal | Minimize sediment transport by slowing velocity in main canal near main discharge structure. | Stormwater | Control Structure | Planned | 2021 | TBD | 0 | 0 | East Caloosahatchee
Disston Island Conservancy District | DI-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | East Caloosahatchee
FDACS | FDACS-01 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Attenuated reductions based on FDACS OAWP December 2022 Enrollment and HSPF model. Acres treated based on FDACS OAWP December 2023 Enrollment and FSAID X. | Agriculture | Agricultural BMPs | Ongoing | 2012 | NA | 63475 | 2349 | Tidal Caloosahatchee
FDACS | FDACS-02 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Attenuated reductions based on FDACS OAWP December 2022 Enrollment and HSPF model. Acres treated based on FDACS OAWP December 2023 Enrollment and FSAID X. | Agriculture | Agricultural BMPs | Ongoing | 2012 | NA | 260337 | 10492 | West Caloosahatchee
FDACS | FDACS-03 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Attenuated reductions based on FDACS OAWP December 2022 Enrollment and HSPF model. Acres treated based on FDACS OAWP December 2023 Enrollment and FSAID X. | Agriculture | Agricultural BMPs | Ongoing | 2012 | NA | 155521 | 5171 | East Caloosahatchee
FDACS | FDACS-04 | Cost-Share BMP Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions estimated by DEP using 2019 BMAP LET. | Agriculture | Agricultural BMPs | Ongoing | 2012 | NA | 20203 | 1255 | Tidal Caloosahatchee
FDACS | FDACS-05 | Cost-Share BMP Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions estimated by DEP using 2019 BMAP LET. | Agriculture | Agricultural BMPs | Ongoing | 2012 | NA | 37622 | 1556 | West Caloosahatchee
FDACS | FDACS-06 | Cost-Share BMP Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions estimated by DEP using 2019 BMAP LET. | Agriculture | Agricultural BMPs | Ongoing | 2012 | NA | 24380 | 1069 | East Caloosahatchee
FDOT District 1 | FDOT-01 | Existing Stormwater Dry Ponds | Dry detention pond; Facility ID = 12010-3505-01. | Stormwater | Dry Detention Pond | Completed | 1997 | Prior to 2012 | 31 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-02 | Existing Stormwater Dry Ponds | Dry detention pond; Facility ID = 12060-3530-01. | Stormwater | Dry Detention Pond | Completed | 1996 | Prior to 2012 | 4 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-03 | Existing Stormwater Dry Ponds | Dry detention pond; Facility ID = 12060-3530-02. | Stormwater | Dry Detention Pond | Completed | 1996 | Prior to 2012 | 4 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-04 | Discontinue Fertilization | No longer fertilizing rights-of-way in watershed. | Stormwater | Fertilizer Cessation | Completed | 2005 | 2005 | 1811 | 454 | Tidal Caloosahatchee
FDOT District 1 | FDOT-05 | Education Efforts | Pamphlets, PSAs, illicit discharge program. | Stormwater | Education Efforts | Ongoing | 2005 | NA | 253 | 54 | Tidal Caloosahatchee
FDOT District 1 | FDOT-06 | Street Sweeping | Street sweeping. | Stormwater | Street Sweeping | Ongoing | 2002 | NA | 473 | 346 | Tidal Caloosahatchee
FDOT District 1 | FDOT-07 | Ditch Blocked Swales | Swales with ditch blocks. Facility ID = 12020-3538-02. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | 1990 | Prior to 2012 | 273 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-08 | Ditch Blocked Swales | Swales with ditch blocks. Facility ID = 12020-3541-01. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | 1989 | Prior to 2012 | 179 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-09 | Ditch Blocked Swales | Swales with ditch blocks. | Stormwater | Grass swales with swale blocks or raised culverts | Completed | NA | Prior to 2012 | 318 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-10 | Swales without Ditch Blocks | Swales without blocks. | Stormwater | Grass swales without swale blocks or raised culverts | Completed | NA | Prior to 2012 | 4617 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-11 | Existing Stormwater Wet Ponds | F12001-3516-01. | Stormwater | Wet Detention Pond | Completed | 1995 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-12 | Existing Stormwater Wet Ponds | F12001-3516-02. | Stormwater | Wet Detention Pond | Completed | 1995 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-13 | Existing Stormwater Wet Ponds | F12040-3514-01. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-14 | Existing Stormwater Wet Ponds | F12040-3515-01. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-15 | Existing Stormwater Wet Ponds | F12040-3515-02. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-16 | Existing Stormwater Wet Ponds | F12040-3515-03. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-17 | Existing Stormwater Wet Ponds | F12040-3515-04. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-18 | Existing Stormwater Wet Ponds | F12060-3530-03. | Stormwater | Wet Detention Pond | Completed | 1996 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-19 | Existing Stormwater Wet Ponds | F12060-3533-01. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-20 | Existing Stormwater Wet Ponds | F12060-3533-02. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-21 | Existing Stormwater Wet Ponds | F12060-3533-03. | Stormwater | Wet Detention Pond | Completed | 2002 | Prior to 2012 | 225 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-22 | State Road (SR) 78 Project | Wet detention pond. FM195705-1, Pond SMF 1A. | Stormwater | Wet Detention Pond | Completed | 2009 | Prior to 2012 | 36 | 10 | Tidal Caloosahatchee
FDOT District 1 | FDOT-23 | State Road (SR) 78 Project | Wet detention pond. FM195705-1, Pond SMF 1D. | Stormwater | Wet Detention Pond | Completed | 2009 | Prior to 2012 | 44 | 12 | Tidal Caloosahatchee
FDOT District 1 | FDOT-24 | State Road (SR) 78 Project | Wet detention pond. FM195705-1, Pond SMF 2B. | Stormwater | Wet Detention Pond | Completed | 2009 | Prior to 2012 | 67 | 18 | Tidal Caloosahatchee
FDOT District 1 | FDOT-25 | State Road (SR) 78 Project | Wet detention pond. FM195705-1, Pond SMF 4C. | Stormwater | Wet Detention Pond | Completed | 2009 | Prior to 2012 | 101 | 27 | Tidal Caloosahatchee
FDOT District 1 | FDOT-26 | SR 82 from Lee Blvd to Shawnee Road | Funding Partnership with LAMSID (formerly known as [fka] ECWCD) for SW Weirs Project. | Stormwater | Control Structure | Completed | TBD | 2017 | 0 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-27 | SR 82 from Lee Blvd to Shawnee Road | Funding Partnership with LAMSID (fka ECWCD) for West Marsh Preserve. | Stormwater | Stormwater Treatment Areas (STAs) | Completed | 2017 | 2020 | 0 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-28 | SR 82 from Shawnee Rd to Alabama Road | Funding Partnership with LAMSID (fka ECWCD) for Moving Water South PH II, Hendry Canal Widening. | Stormwater | Regional Stormwater Treatment | Completed | 2018 | 2020 | 0 | 0 | Tidal Caloosahatchee
FDOT District 1 | FDOT-29 | SR 80 from Dalton Lane to CR 833 (408286-5) | Widening project provided extra nutrient removal in treatment ponds. | Stormwater | Wet Detention Pond | Completed | 2017 | 2020 | 218 | 24 | West Caloosahatchee
FDOT District 1 | FDOT-30 | SR 82 from Gator Slough Lane to SR 29 (430849-1) | Widening project provided extra nutrient removal in treatment Pond 4. | Stormwater | Wet Detention Pond | Completed | 2019 | 2022 | 71 | 15 | West Caloosahatchee
FDOT District 1 | FDOT-31 | Six Mile Cypress Preserve North Hydrologic Restoration project | Hydrologic restoration project. | Stormwater | Hydrologic Restoration | Completed | 2003 | 2005 | 718 | 134 | Tidal Caloosahatchee
Flaghole Drainage District | FH-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Flaghole Drainage District | FH-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Flaghole Drainage District | FH-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | East Caloosahatchee
Flaghole Drainage District | FH-04 | Slow Velocity in the Main Canal | Minimize sediment transport by slowing the velocity in main canal near main discharge structure. | Stormwater | Control Structure | Planned | 2021 | TBD | 0 | 0 | East Caloosahatchee
Flaghole Drainage District | FH-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | East Caloosahatchee
Gerber Groves WCD | GG-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Gerber Groves WCD | GG-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2020 | NA | 0 | 0 | West Caloosahatchee
Gerber Groves WCD | GG-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | West Caloosahatchee
Gerber Groves WCD | GG-04 | Canal/Ditch Bank Berms | Minimize sediment transport by constructing berms on top of canal/ditch banks and promoting vegetation cover. | Stormwater | Shoreline Stabilization | Planned | 2021 | TBD | 0 | 0 | West Caloosahatchee
Gerber Groves WCD | GG-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | West Caloosahatchee
Glades County | GC-01 | Education and Outreach | FYN; landscaping, irrigation, and fertilizer ordinances; PSAs, pamphlets, website, and illicit discharge program. | Stormwater | Education Efforts | Completed | 2014 | 2015 | 1564 | 419 | West Caloosahatchee
Glades County | GC-02 | Glades County Caloosahatchee River & Estuary Area Wastewater Grant | Elimination of aging and/or failing existing septic systems in the City of Moore Haven. The Project also provides for additional conveyance capacity for additional homes and businesses. | Wastewater | OSTDS Phase Out | Underway | 2018 | 2024 | 1253 | 0 | East Caloosahatchee
Glades County | GC-03 | Glades County Business Park Wetlands | Wetland maintenance and planting agreement. | Stormwater | Constructed Wetland Treatment | Completed | 2019 | 2021 | 0 | 0 | East Caloosahatchee
Glades County | GC-04 | U.S. 27 Corridor Utility Infrastructure | Install wastewater infrastructure across the Caloosahatchee River to connect to existing force main at 8th St and U.S. 27 and to Sportsman Village RV package plant. | Wastewater | OSTDS Phase Out | Underway | 2021 | 2024 | 0 | 0 | East Caloosahatchee
Hendry County | HC-01 | Four Corners MSBU / County Line Ditch Widening | Residents near the project area experience frequent flooding due to the lack of drainage capacity. Improvements will allow the upstream watershed to pass through a system that will reduce nutrient loading prior to discharging to the river downstream. | Stormwater | Retention/Detention BMP Retrofit with Nutrient Reducing Media | Underway | 2023 | 2025 | 0 | 0 | West Caloosahatchee
Hendry County | HC-02 | North LaBelle Water Quality | Provide water quality components to treat stormwater along Mohawk Avenue prior to discharging into the Roy Brown Canal and flowing into the Caloosahatchee River. | Stormwater | Retention/Detention BMP Retrofit with Nutrient Reducing Media | Planned | 2025 | 2026 | 0 | 0 | West Caloosahatchee
Hendry County | HC-03 | Phase 1 of a Force Main Extension from Airglades Airport to the City of Clewiston | Hendry County will construct a force main to extend from the Airglades Airport to City of Clewiston. The work consists of constructing a wastewater transmission system to convey raw wastewater from the Airglades Airport WWTP to City of Clewiston. | Wastewater | WWTF Upgrade | Underway | 2016 | 2024 | 0 | 0 | East Caloosahatchee
Hendry County | HC-04 | Hendry County Port LaBelle Utility System Cast Iron Sewer Pipe Replacement | Repairing and/or replacing damaged or leaking pipe by installing a liner or replacement with new pipe. Mechanically cleaning a portion of the gravity sewer main that is cast iron pipe. The main will be inspected and clay and cast iron pipe will be lined. | Wastewater - Nutrient Projects Ineligible for Credit | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Completed | 2016 | 2023 | 0 | 0 | West Caloosahatchee
Hendry County | HC-05 | Hendry County Port LaBelle Utility System Wastewater Collection System - Port LaBelle Unit 1 | Design and permit and construction of a wastewater collection system and wastewater force main pumping system to serve the unsewered sections of Unit No. 1 of Port LaBelle. | Wastewater | OSTDS Phase Out | Underway | 2024 | 2027 | 0 | 0 | West Caloosahatchee
Hendry County | HC-06 | Hendry County Port LaBelle Utility System Gravity Sewer Line Rehabilitation - Port LaBelle Units 1, 4, & 5 | The rehabilitation of the existing gravity sewer system serving Port LaBelle Units 1, 4 and 5. The purpose is to reduce infiltration and inflow in the aging gravity sewer collection system by lining the piping within the gravity sewer collection system. | Wastewater - Nutrient Projects Ineligible for Credit | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Planned | 2024 | 2025 | 0 | 0 | West Caloosahatchee
Hendry County | HC-07 | Hendry County Port LaBelle Utility System Wastewater Collection System - Port LaBelle Units 2 & 3 | Design and permit of a wastewater collection system and wastewater force main pumping system to serve the unsewered sections of Unit Nos. 2 and 3 of Port LaBelle. And construction of the said system for Unit No. 2. | Wastewater | OSTDS Phase Out | Planned | 2024 | 2028 | 0 | 0 | West Caloosahatchee
Hendry County | HC-08 | Hendry County Port LaBelle Utility System Wastewater Treatment Plant Expansion | The Port LaBelle Utility System Wastewater Treatment Plant is in need of expansion to provide additional plant capacity as rapid growth is expected to continue in the Port LaBelle area and the eventual increase in residential connections that will occur. | Wastewater - Nutrient Projects Ineligible for Credit | Wastewater Service Area Expansion | Planned | 2024 | 2028 | 0 | 0 | West Caloosahatchee
Hendry-Hilliard WCD | HH-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Hendry-Hilliard WCD | HH-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Hendry-Hilliard WCD | HH-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | East Caloosahatchee
Hendry-Hilliard WCD | HH-04 | Slow Velocity in the Main Canal | Minimize sediment transport by slowing velocity in main canal near main discharge structure. | Stormwater | Control Structure | Planned | 2021 | TBD | 0 | 0 | East Caloosahatchee
Hendry-Hilliard WCD | HH-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | East Caloosahatchee
LA-MSID (formerly ECWCD) | LA-01 | Education/Pollution Prevention/Fertilizer | Pollution prevention and fertilizer education. | Stormwater | Education Efforts | Ongoing | TBD | NA | 982 | 144 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) |  | Education/Pollution Prevention/Fertilizer | Pollution prevention and fertilizer education. | Stormwater | Education Efforts | Ongoing | TBD | NA | 897 | 132 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-02 | Freshwater Canal Detention | Regulation of freshwater canals through existing control structures. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 5624 | 943 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) |  | Freshwater Canal Detention | Regulation of freshwater canals through existing control structures. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 5256 | 522 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-03 | Weir Elevation Improvements | Replacement of weir structures at increased control elevations to provide additional attenuation. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 5343 | 896 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) |  | Weir Elevation Improvements | Replacement of weir structures at increased control elevations to provide additional attenuation. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 4992 | 496 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-04 | Harn's Marsh Phases I and II | Replacement of weir structures and redirection of flows into filter marsh. | Stormwater | Control Structure | Completed | TBD | Prior to 2012 | 0 | 0 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-05 | Jim Flemming Eco-Park | Wetland rehydration and treatment. | Stormwater | Hydrologic Restoration | Completed | TBD | Prior to 2012 | 7942 | 1716 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-06 | Mirror Lake Phase I | Detention pond. | Stormwater | Wet Detention Pond | Completed | TBD | 2013 | 819 | 127 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-07 | Aquifer Benefit and Storage for Orange River Basin (Southwest Lehigh Weirs) | Increase canal control elevations and local groundwater levels by constructing 25 new weirs. | Stormwater | Control Structure | Completed | 2016 | 2017 | 5551 | 935 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-08 | S-AW-2 Weir Elevation Improvements | Replacement of weir structures at increase control elevations to provide additional attenuation. | Stormwater | Control Structure | Completed | 2016 | 2017 | 416 | 61 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-09 | Mirror Lake Phase 2 | Detention pond. | Stormwater | Wet Detention Pond | Completed | 2017 | 2018 | 739 | 109 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-10 | West Marsh Preserve | Wetland rehydration and treatment. | Stormwater | Hydrologic Restoration | Completed | 2017 | 2020 | 1302 | 217 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-11 | S-H-2 Weir Replacement | Replace failed fabriform weir. | Stormwater | Control Structure | Completed | 2018 | 2019 | 106 | 8 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-12 | Hendry Canal Widening | Widen three miles of Hendry Ext. Canal. Create additional stormwater storage within the canal system. | Stormwater | Hydrologic Restoration | Completed | 2020 | 2021 | 0 | 0 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-13 | CREST | Purchased 100 acres agricultural land to construct STA. | Load Tracking | Land Use Change | Completed | 2018 | 2018 | 528 | 70 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-14 | CREST | Construct STA. | Stormwater | Stormwater Treatment Areas (STAs) | Underway | 2021 | 2025 | 19958 | 2732 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-15 | GS-10 | Construct STA. | Stormwater | Stormwater Treatment Areas (STAs) | Planned | 2021 | 2031 | 0 | 0 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-16 | S-BH-2 | Replacement of weir structures at increase control elevations to provide additional attenuation. | Stormwater | Control Structure | Completed | 2021 | 2021 | 0 | 0 | West Caloosahatchee
LA-MSID (formerly ECWCD) | LA-17 | S-CP-1 | Replacement of weir structures at increase control elevations to provide additional attenuation. | Stormwater | Control Structure | Completed | 2021 | 2022 | 0 | 0 | Tidal Caloosahatchee
LA-MSID (formerly ECWCD) | LA-18 | S-R-1 | Replacement of weir structures at increase control elevations to provide additional attenuation. | Stormwater | Control Structure | Completed | 2020 | 2020 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-01 | Yellow Fever Creek Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 66 | 31 | Tidal Caloosahatchee
Lee County | LC-02 | Billy's Creek Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 47 | 2 | Tidal Caloosahatchee
Lee County | LC-03 | Six Mile Cypress Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 1626 | 59 | Tidal Caloosahatchee
Lee County | LC-05 | Buckingham Trails Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 1815 | 68 | Tidal Caloosahatchee
Lee County | LC-06 | Caloosahatchee Creeks Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 89 | 11 | Tidal Caloosahatchee
Lee County | LC-07 | Deep Lagoon Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 144 | 10 | Tidal Caloosahatchee
Lee County | LC-08 | Hickory Swamp Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 226 | 9 | Tidal Caloosahatchee
Lee County | LC-09 | Orange River Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 7 | 1 | Tidal Caloosahatchee
Lee County | LC-10 | Prairie Pines Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-11 | Telegraph Creek Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 4676 | 140 | Tidal Caloosahatchee
Lee County | LC-12 | West Marsh Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 148 | 41 | Tidal Caloosahatchee
Lee County | LC-13 | Yellow Fever Creek Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 34 | 48 | Tidal Caloosahatchee
Lee County | LC-15 | Education Efforts | FYN; landscape, irrigation, and fertilizer ordinances; pamphlets, PSAs, website, illicit discharge program; WETPLAN. | Stormwater | Education Efforts | Ongoing | Prior to 2012 | NA | 12957 | 4994 | Tidal Caloosahatchee
Lee County | LC-16 | Street Sweeping | Materials from roadway and gutter sweeping. | Stormwater | Street Sweeping | Ongoing | 2000 | NA | 572 | 374 | Tidal Caloosahatchee
Lee County | LC-17 | North Fort Myers Surface Water Restoration: Powell Creek Extension and Lost Lane Levee | Conveyance improvements to increase residence time, rehydrate offsite wetlands on adjacent properties, and accommodate offsite flows. | Stormwater | Hydrologic Restoration | Completed | Prior to 2012 | 2013 | 13638 | 3536 | Tidal Caloosahatchee
Lee County | LC-18 | Whiskey Creek Weir Reconstruction | Retention lake weir repairs to restore originally intended design and operation. | Stormwater | Control Structure | Completed | Prior to 2012 | Prior to 2012 | 27712 | 9113 | Tidal Caloosahatchee
Lee County | LC-19 | Caloosahatchee Creeks East | Hydrologic restoration. | Stormwater | Hydrologic Restoration | Completed | Prior to 2012 | Prior to 2012 | 248 | 20 | Tidal Caloosahatchee
Lee County | LC-20 | Powell Creek Filter Marsh | Created wetland areas, boardwalks, and trails and a stabilized crossing of Powell Creek. | Stormwater | Constructed Wetland Treatment | Completed | Prior to 2012 | 2013 | 5245 | 2053 | Tidal Caloosahatchee
Lee County | LC-21 | Nalle Grade Stormwater Park | Dry retention and wet detention ponds. | Stormwater | Stormwater Treatment Areas (STAs) | Completed | 2019 | 2021 | 12084 | 1027 | Tidal Caloosahatchee
Lee County | LC-22 | Deep Lagoon Hydrologic Restoration | Hydrologic restoration and enhancement, water conservation, wildlife habitat enhancement, and flood protection for surrounding area. | Stormwater | Hydrologic Restoration | Completed | Prior to 2012 | Prior to 2012 | 144 | 26 | Tidal Caloosahatchee
Lee County | LC-23 | Popash Creek Restoration | Hydrologic restoration to more natural flow regime by increasing water storage on property and improving both onsite and off-site flows. | Stormwater | Hydrologic Restoration | Completed | Prior to 2012 | Prior to 2012 | 272 | 44 | Tidal Caloosahatchee
Lee County | LC-24 | Billy's Creek Wetland | Billy Creek Filter Marsh Park. | Stormwater | Constructed Wetland Treatment | Completed | Prior to 2012 | Prior to 2012 | 948 | 807 | Tidal Caloosahatchee
Lee County | LC-25 | Caloosahatchee Creeks Preserve-West Restoration | Hydrologic restoration. | Stormwater | Hydrologic Restoration | Completed | 2015 | 2016 | 16185 | 1368 | Tidal Caloosahatchee
Lee County | LC-26 | Yellow Fever Creek - Gator Slough Transfer Facility | Return historical flow from Gator Slough Canal system to Yellow Fever Creek. There are 114 acres in the BMAP being treated by this project, there are additional areas being treated outside of the BMAP boundary. | Stormwater | Hydrologic Restoration | Completed | 2021 | 2022 | 102 | 118 | Tidal Caloosahatchee
Lee County | LC-27 | Prairie Pines Preserve Restoration | Restoration of historical flows and enhancement and restoration of wetlands. | Stormwater | Hydrologic Restoration | Completed | 2018 | 2018 | 10356 | 837 | Tidal Caloosahatchee
Lee County | LC-28 | BMAP Plan Development - Basin Study | Basin study to identify pollutant sources and identify further actions to reach reduction goals. | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Completed | 2016 | 2017 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-29 | Caloosahatchee River-North Fort Myers Nutrient and Bacteria Source Identification Study | Watershed study to investigate interactions between onsite sewage treatment and disposal systems (OSTDS), groundwater, and surface water in Caloosahatchee Estuary. | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Completed | 2017 | 2020 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-30 | Waterway Estates Wastewater Treatment Facility (WWTF) Closure | Closure of facility with direct discharge to Caloosahatchee. | Wastewater | WWTF Diversion to Reuse | Completed | 2012 | 2012 | 295 | 0 | Tidal Caloosahatchee
Lee County | LC-31 | Six Mile Cypress Preserve North Hydrologic Restoration | Wetland creation, addition of control structures, berms, berm breaches to connect natural and created wetlands, and restoration of historical hydrologic conditions to reduce discharge into Caloosahatchee River. | Stormwater | Hydrologic Restoration | Completed | 2013 | 2013 | 725 | 194 | Tidal Caloosahatchee
Lee County | LC-33 | Telegraph Creek Preserve | Ditch blocks and native plantings in conveyances. | Stormwater | Hydrologic Restoration | Completed | 2016 | 2017 | 421 | 44 | Tidal Caloosahatchee
Lee County | LC-34 | West Harnes Marsh | Creation and enhancement of wetland marsh ecosystem, including hydraulic connection for water quality improvement and stormwater attenuation. | Stormwater | Constructed Wetland Treatment | Completed | 2018 | 2021 | 558 | 93 | Tidal Caloosahatchee
Lee County | LC-35 | C-43 Water Quality Treatment and Testing Facility Project (*study/land acquisition) | Project to demonstrate and implement cost-effective, wetland-based strategies for reduction of dissolved organic nitrogen (DON). | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Underway | 2015 | TBD | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-38 | Deep Lagoon Pollutant Load Reduction Phase 2-Watershed Analysis Report | Basin study to identify pollutant sources and identify further actions to reach reduction goals. | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Completed | 2018 | 2018 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-39 | North Fort Myers Florida Power and Light (FPL) Feasibility Study | Study to identify areas of high nutrient loads and potential BMPs to improve water quality and reduce flooding. | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Completed | 2018 | 2019 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-40 | Sunniland/Nine Mile Run Drainage Improvements | Replacement of failing water control structures (WCS) and reconnection of flow-ways to Hickory Swamp and Buckingham Trails Preserve. | Stormwater | Hydrologic Restoration | Planned | 2021 | 2024 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-41 | Caloosahatchee Tributary Canal Rehabilitation: L-3 | Reshaping canal banks, littoral planting, and possible addition of control structure(s). | Stormwater | Regional Stormwater Treatment | Completed | 2021 | 2021 | 985 | 190 | Tidal Caloosahatchee
Lee County | LC-44 | Powell Creek / Old Bridge Park Restoration | Filter marsh creation and BMPs. | Stormwater | Constructed Wetland Treatment | Completed | 2021 | 2023 | 294 | 56.4 | Tidal Caloosahatchee
Lee County | LC-45 | Deep Lagoon Preserve Water Quality Improvement Project | Retention ponds, channel/ditch modifications, ditch blocks and pumped solutions. | Stormwater | BMP Treatment Train | Canceled | NA | NA | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-46 | Olga Shores Preserve Hydrological Restoration | Filter marsh creation. Best Management Practices (BMPs). | Stormwater | Hydrologic Restoration | Canceled | NA | NA | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-47 | Microbial Source Tracking in Lee County Waterways | Watershed study to investigate interactions between OSTDS and surface water in the Caloosahatchee Estuary. | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Completed | 2021 | 2022 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-48 | Olga Shores Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2017 | 2017 | 2 | 0 | Tidal Caloosahatchee
Lee County | LC-49 | Four Mile Cove | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2020 | 2020 | 24 | 6 | Tidal Caloosahatchee
Lee County | LC-51 | Master Wastewater Treatment Feasibility Analysis | Study to support the development of a County-wide Septic Conversion Master Plan (SCMP). | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Completed | 2021 | 2023 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-54 | Palm Creek Lower Filter Marsh | Development of a cellular pond and wetland network to assist in treatment of surface water for nutrient removal and related water quality improvement. | Stormwater | BMP Treatment Train | Planned | 2022 | 2025 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-04 | Bob Jane's Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 882 | 45 | Tidal Caloosahatchee
Lee County |  | Bob Jane's Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2012 | 2012 | 19365 | 450 | West Caloosahatchee
Lee County | LC-32 | Bob Jane's Preserve Environmental Restoration | Hydrologic improvements in portion of preserve via berms, beaches, and ditch blocks. | Stormwater | Hydrologic Restoration | Completed | TBD | 2017 | 207 | 20 | Tidal Caloosahatchee
Lee County |  | Bob Jane's Preserve Environmental Restoration | Hydrologic improvements in portion of preserve via berms, beaches, and ditch blocks. | Stormwater | Hydrologic Restoration | Completed | TBD | 2018 | 1413 | 99 | West Caloosahatchee
Lee County | LC-42 | Bob Janes Preserve Restoration Feasibility Study | Study to identify areas of high nutrient loads and potential BMPs to improve water quality, and restore historic hydrologic conditions. | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Completed | 2019 | 2020 | 0 | 0 | Tidal Caloosahatchee
Lee County | LC-43 | GS-10 | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2019 | 2019 | 20681 | 8915 | Tidal Caloosahatchee
Lee County |  | GS-10 | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2019 | 2019 | 14400 | 4954 | West Caloosahatchee
Lee County | LC-36 | Fichter's Creek Restoration Project | Restoration of hydroperiod and water quality in Fichter's Creek. | Stormwater | Hydrologic Restoration | Completed | 2018 | 2018 | 1705 | 114 | West Caloosahatchee
Lee County | LC-37 | Spanish Creek at Daniel's Preserve Restoration | Restoration of wetland hydroperiod and sheet flow attenuation. | Stormwater | Hydrologic Restoration | Completed | 2014 | 2014 | 1161 | 46 | West Caloosahatchee
Lee County | LC-50 | Alva Scrub Preserve | Land purchase and conversion to conservation land use. | Load Tracking | Land Use Change | Completed | 2000 | 2019 | 2674 | 164 | West Caloosahatchee
Lee County | LC-52 | Bob Janes Restoration | Two hydrologic modification projects to provide attenuation of peak flows and nutrient reduction in water discharging from the Bob Janes Preserve. | Stormwater | Hydrologic Restoration | Planned | 2023 | 2024 | 1439 | 225 | West Caloosahatchee
Lee County | LC-53 | Oak Hammock Preserve | Land purchased and conversion to conservation land use. | Load Tracking | Land Use Change | Planned | 2021 | 2024 | 0 | 0 | West Caloosahatchee
Lucaya CDD | LU-01 | Education/ Fertilizer | Education. | Stormwater | Education Efforts | Ongoing | TBD | NA | 2 | 0 | Tidal Caloosahatchee
Lucaya CDD | LU-02 | Education/ Pet Waste | Education. | Stormwater | Education Efforts | Ongoing | TBD | NA | 2 | 0 | Tidal Caloosahatchee
Mirada CDD | M-01 | Education/Fertilizer | Public education, training, codes and ordinances provided by Lee County. | Stormwater | Education Efforts | Ongoing | 2017 | NA | 0 | 0 | Tidal Caloosahatchee
Mirada CDD | M-02 | Education/Pet Waste | Public education and training provided by Lee County. | Stormwater | Education Efforts | Ongoing | 2017 | NA | 0 | 0 | Tidal Caloosahatchee
Port LaBelle CDD | PL-01 | Public Education and Outreach | Updates on BMAP and requirements during annual meeting. | Stormwater | Education Efforts | Planned | 2019 | NA | 81 | 14 | East Caloosahatchee
Portico CDD | PORT-01 | Education/Fertilizer | FYN; landscape, irrigation, and fertilizer ordinances; website, illicit discharge program; WETPLAN. | Stormwater | Education Efforts | Ongoing | 2022 | NA | 92 | 8 | West Caloosahatchee
Portico CDD | PORT-02 | Control Structures | CS-A1 is a Modified Type H Inlet, CS-A2 is a Modified Type E Inlet, CS-B1 is a Modified Type C Inlet. | Stormwater | Control Structure | Completed | 2006 | 2007 | 0 | 0 | West Caloosahatchee
Portico CDD | PORT-03 | Conservation Lands | Conversion of agricultural lands to natural conservation lands. | Load Tracking | Land Use Change | Completed | 2006 | 2006 | 0 | 0 | West Caloosahatchee
Portico CDD | PORT-04 | Stormwater Aeration System | Aeration systems on surface water management ponds A1, A2, A3, A4, A5, A9, A10, B1, and B2. | Stormwater - Nutrient Projects Ineligible for Credit | Stormwater Aeration System | Completed | 2017 | 2017 | 0 | 0 | West Caloosahatchee
SFWMD - Coordinating Agency | CA-01 | C-43 West Basin Storage Reservoir | Storage of 170,000 acre-feet of stormwater runoff and releases from Lake Okeechobee. It will reduce volume of lake discharges in wet season and provide freshwater flow to the estuary in dry season to aid in essential flows for more stable salinities. | Stormwater | Hydrologic Restoration | Underway | 2015 | 2025 | 0 | 0 | West Caloosahatchee
SFWMD - Coordinating Agency | CA-02 | Lake Hicpochee Hydrologic Enhancement, Phase I | Provide shallow water storage, rehydrate a portion of lake bed to promote habitat restoration storage, and increase capacity for ancillary water quality benefit. Project will deliver excess stormwater runoff from C-19 canal to north end of lake as needed. | Stormwater | Hydrologic Restoration | Completed | 2017 | 2019 | 0 | 0 | East Caloosahatchee
SFWMD - Coordinating Agency | CA-03 | Lake Hicpochee Expansion, Phase II | Building on Phase I efforts, project will expand regional storage in the Caloosahatchee River Watershed and reduce flows lost to tide on over 2,600 acres of District lands. | Stormwater | Hydrologic Restoration | Planned | 2022 | 2026 | 0 | 0 | East Caloosahatchee
SFWMD - Coordinating Agency | CA-04 | BOMA Flow Equalization Basin (FEB) | Expand regional storage in the Caloosahatchee River Watershed and reduce flows to the estuary on approximately 1,800 acres of SFWMD lands. | Stormwater | Hydrologic Restoration | Planned | 2024 | 2026 | 0 | 0 | East Caloosahatchee
SFWMD - Coordinating Agency | CA-05 | C-43 Water Quality Treatment and Testing Facility, Phase II - Test Cells | Located within the Boma FEB, the purpose of the project is to evaluate the effectiveness of wetland treatment systems in reducing nitrogen at a test-scale. | Nutrient Studies, Monitoring, and Enhanced Education - Ineligible for Credit | Study | Underway | 2022 | 2024 | 0 | 0 | East Caloosahatchee
SFWMD - Coordinating Agency | CA-06 | C-43 West Basin Storage Reservoir Water Quality Component | Construct and operate a water quality treatment component at the C-43 West Basin Storage Reservoir to reduce discharge of nutrients which may contribute to blue-green algal blooms. | Stormwater | Constructed Wetland Treatment | Planned | 2024 | 2024 | 0 | 0 | West Caloosahatchee
SFWMD - Coordinating Agency | CA-07 | Mudge Ranch | A 304-acre project area; estimated annual ac-ft of storage is 362 ac-ft. | Stormwater | Dispersed Water Management (DWM) | Completed | 2013 | 2014 | 0 | 0 | West Caloosahatchee
SFWMD - Coordinating Agency | CA-08 | Four Corners Rapid Infiltration | Project utilizes a minor above ground impoundment combined with rapid infiltration areas to provide storage of stormwater runoff captured from local contributory watersheds of the C-43 canal. | Stormwater | Dispersed Water Management (DWM) | Completed | 2022 | 2023 | 0 | 0 | West Caloosahatchee
Sugarland Drainage District | SD-01 | Public Education and Outreach | Updates on BMAP and requirements during annual landowner meetings. | Stormwater | Education Efforts | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Sugarland Drainage District | SD-02 | FDACS BMP Assistance | Provide assistance to FDACS, as needed, to encourage landowners to enroll in BMPs. | Agriculture | Agricultural BMPs | Planned | 2020 | NA | 0 | 0 | East Caloosahatchee
Sugarland Drainage District | SD-03 | Nutrient Controls | No application of fertilizer in district's rights-of-way. | Stormwater | Fertilizer Cessation | Completed | 2020 | 2020 | 0 | 0 | East Caloosahatchee
Sugarland Drainage District | SD-04 | Slow Velocity in the Main Canal | Minimize sediment transport by slowing velocity in main canal near main discharge structure. | Stormwater | Control Structure | Planned | 2021 | TBD | 0 | 0 | East Caloosahatchee
Sugarland Drainage District | SD-05 | Control Structures | Annual maintenance of water control structures. | Stormwater | Control Structure | Ongoing | 2021 | NA | 0 | 0 | East Caloosahatchee
Verandah East CDD | VE-01 | Education/Fertilizer | FYN; landscape, irrigation, and fertilizer ordinances; pamphlets, PSAs, website, illicit discharge program; WETPLAN. | Stormwater | Education Efforts | Ongoing | TBD | NA | 117 | 15 | Tidal Caloosahatchee
Verandah West CDD | VW-01 | Education/Fertilizer | FYN; landscape, irrigation, and fertilizer ordinances; pamphlets, PSAs, website, illicit discharge program; WETPLAN. | Stormwater | Education Efforts | Ongoing | TBD | NA | 180 | 29 | Tidal Caloosahatchee

## All Projects Pivot (hidden)
LeadEntity | CreditingLocation | EstimatedCompletionDate | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr)
Barron WCD | East Caloosahatchee | 2020 | 0 | 0
Barron WCD | East Caloosahatchee | NA | 0 | 0
Charlotte County | Tidal Caloosahatchee | NA | 1180 | 191
Charlotte County | West Caloosahatchee | NA | 130 | 21
City of Cape Coral | Tidal Caloosahatchee | 2015 | 24454 | 0
City of Cape Coral | Tidal Caloosahatchee | 2018 | 0 | 0
City of Cape Coral | Tidal Caloosahatchee | 2023 | 899.5 | 509.1
City of Cape Coral | Tidal Caloosahatchee | NA | 9299 | 3448
City of Cape Coral | Tidal Caloosahatchee | Prior to 2012 | 5212 | 3553
City of Cape Coral | Tidal Caloosahatchee | TBD | 14 | 19
City of Clewiston | East Caloosahatchee | 2023 | 50 | 6
City of Clewiston | East Caloosahatchee | NA | 367 | 81
City of Clewiston | East Caloosahatchee | Prior to 2012 | 26 | 2
City of Fort Myers | Tidal Caloosahatchee | 2001 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2010 | 1421 | 1211
City of Fort Myers | Tidal Caloosahatchee | 2011 | 486 | 78
City of Fort Myers | Tidal Caloosahatchee | 2012 | 1195 | 338
City of Fort Myers | Tidal Caloosahatchee | 2013 | 73 | 14
City of Fort Myers | Tidal Caloosahatchee | 2015 | 640 | 219
City of Fort Myers | Tidal Caloosahatchee | 2016 | 7916 | 1412
City of Fort Myers | Tidal Caloosahatchee | 2023 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2025 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2028 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2030 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | NA | 6503 | 2804
City of LaBelle | West Caloosahatchee | 2024 | 2771 | 0
City of LaBelle | West Caloosahatchee | 2025 | 2278 | 0
City of LaBelle | West Caloosahatchee | 2027 | 5111 | 0
City of Moore Haven | East Caloosahatchee | 2020 | 231 | 0
City of Moore Haven | East Caloosahatchee | 2021 | 1654 | 0
Clewiston Drainage District | East Caloosahatchee | 2020 | 0 | 0
Clewiston Drainage District | East Caloosahatchee | NA | 0 | 0
Collier County | West Caloosahatchee | NA | 3 | 0.4
Collins Slough WCD | East Caloosahatchee | 2020 | 0 | 0
Collins Slough WCD | East Caloosahatchee | NA | 0 | 0
County Line Drainage District | West Caloosahatchee | 2020 | 0 | 0
County Line Drainage District | West Caloosahatchee | NA | 0 | 0
County Line Drainage District | West Caloosahatchee | TBD | 0 | 0
Cow Slough WCD | West Caloosahatchee | 2020 | 0 | 0
Cow Slough WCD | West Caloosahatchee | NA | 0 | 0
Devil's Garden WCD | West Caloosahatchee | 2020 | 0 | 0
Devil's Garden WCD | West Caloosahatchee | NA | 0 | 0
Disston Island Conservancy District | East Caloosahatchee | 2020 | 0 | 0
Disston Island Conservancy District | East Caloosahatchee | NA | 0 | 0
Disston Island Conservancy District | East Caloosahatchee | TBD | 0 | 0
FDACS | East Caloosahatchee | NA | 179901 | 6240
FDACS | Tidal Caloosahatchee | NA | 83678 | 3604
FDACS | West Caloosahatchee | NA | 297959 | 12048
FDOT District 1 | Tidal Caloosahatchee | 2005 | 2529 | 588
FDOT District 1 | Tidal Caloosahatchee | 2017 | 0 | 0
FDOT District 1 | Tidal Caloosahatchee | 2020 | 0 | 0
FDOT District 1 | Tidal Caloosahatchee | NA | 726 | 400
FDOT District 1 | Tidal Caloosahatchee | Prior to 2012 | 8149 | 67
FDOT District 1 | West Caloosahatchee | 2020 | 218 | 24
FDOT District 1 | West Caloosahatchee | 2022 | 71 | 15
Flaghole Drainage District | East Caloosahatchee | 2020 | 0 | 0
Flaghole Drainage District | East Caloosahatchee | NA | 0 | 0
Flaghole Drainage District | East Caloosahatchee | TBD | 0 | 0
Gerber Groves WCD | West Caloosahatchee | 2020 | 0 | 0
Gerber Groves WCD | West Caloosahatchee | NA | 0 | 0
Gerber Groves WCD | West Caloosahatchee | TBD | 0 | 0
Glades County | East Caloosahatchee | 2021 | 0 | 0
Glades County | East Caloosahatchee | 2024 | 1253 | 0
Glades County | West Caloosahatchee | 2015 | 1564 | 419
Hendry County | East Caloosahatchee | 2024 | 0 | 0
Hendry County | West Caloosahatchee | 2023 | 0 | 0
Hendry County | West Caloosahatchee | 2025 | 0 | 0
Hendry County | West Caloosahatchee | 2026 | 0 | 0
Hendry County | West Caloosahatchee | 2027 | 0 | 0
Hendry County | West Caloosahatchee | 2028 | 0 | 0
Hendry-Hilliard WCD | East Caloosahatchee | 2020 | 0 | 0
Hendry-Hilliard WCD | East Caloosahatchee | NA | 0 | 0
Hendry-Hilliard WCD | East Caloosahatchee | TBD | 0 | 0
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2013 | 819 | 127
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2017 | 5967 | 996
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2018 | 739 | 109
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2020 | 1302 | 217
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2022 | 0 | 0
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | NA | 982 | 144
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | Prior to 2012 | 18909 | 3555
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2018 | 528 | 70
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2019 | 106 | 8
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2021 | 0 | 0
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2025 | 19958 | 2732
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2031 | 0 | 0
LA-MSID (formerly ECWCD) | West Caloosahatchee | NA | 897 | 132
LA-MSID (formerly ECWCD) | West Caloosahatchee | Prior to 2012 | 10248 | 1018
Lee County | Tidal Caloosahatchee | 2012 | 10055 | 465
Lee County | Tidal Caloosahatchee | 2013 | 19608 | 5783
Lee County | Tidal Caloosahatchee | 2016 | 16185 | 1368
Lee County | Tidal Caloosahatchee | 2017 | 630 | 64
Lee County | Tidal Caloosahatchee | 2018 | 10356 | 837
Lee County | Tidal Caloosahatchee | 2019 | 20681 | 8915
Lee County | Tidal Caloosahatchee | 2020 | 24 | 6
Lee County | Tidal Caloosahatchee | 2021 | 13627 | 1310
Lee County | Tidal Caloosahatchee | 2022 | 102 | 118
Lee County | Tidal Caloosahatchee | 2023 | 294 | 56.4
Lee County | Tidal Caloosahatchee | 2024 | 0 | 0
Lee County | Tidal Caloosahatchee | 2025 | 0 | 0
Lee County | Tidal Caloosahatchee | NA | 13529 | 5368
Lee County | Tidal Caloosahatchee | Prior to 2012 | 29324 | 10010
Lee County | Tidal Caloosahatchee | TBD | 0 | 0
Lee County | West Caloosahatchee | 2012 | 19365 | 450
Lee County | West Caloosahatchee | 2014 | 1161 | 46
Lee County | West Caloosahatchee | 2018 | 3118 | 213
Lee County | West Caloosahatchee | 2019 | 17074 | 5118
Lee County | West Caloosahatchee | 2024 | 1439 | 225
Lucaya CDD | Tidal Caloosahatchee | NA | 4 | 0
Mirada CDD | Tidal Caloosahatchee | NA | 0 | 0
Port LaBelle CDD | East Caloosahatchee | NA | 81 | 14
Portico CDD | West Caloosahatchee | 2006 | 0 | 0
Portico CDD | West Caloosahatchee | 2007 | 0 | 0
Portico CDD | West Caloosahatchee | 2017 | 0 | 0
Portico CDD | West Caloosahatchee | NA | 92 | 8
SFWMD - Coordinating Agency | East Caloosahatchee | 2019 | 0 | 0
SFWMD - Coordinating Agency | East Caloosahatchee | 2024 | 0 | 0
SFWMD - Coordinating Agency | East Caloosahatchee | 2026 | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2014 | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2023 | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2024 | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2025 | 0 | 0
Sugarland Drainage District | East Caloosahatchee | 2020 | 0 | 0
Sugarland Drainage District | East Caloosahatchee | NA | 0 | 0
Sugarland Drainage District | East Caloosahatchee | TBD | 0 | 0
Verandah East CDD | Tidal Caloosahatchee | NA | 117 | 15
Verandah West CDD | Tidal Caloosahatchee | NA | 180 | 29
(blank) | (blank) | (blank)
Grand Total |  |  | 885462.5 | 86837.9

## Project Table (hidden)
*Blue cells indicate estimated completion date is later than 2028.
LeadEntity | CreditingLocation | EstimatedCompletionDate | ISTEXT | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | Entity | CreditingLocation | TN Reductions Thru 2017 | TN Reductions 2018-2022 | TN Reductions 2023-2027 | TN Reductions 2028-2032 | TP Reductions Thru 2025 | TP Reductions 2026-2030 | TP Reductions 2030-2035 | TP Reductions 2035-2040
Barron WCD | East Caloosahatchee | 2020 | FALSE | 0 | 0 | Barron WCD | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Barron WCD | East Caloosahatchee | NA | TRUE | 0 | 0 | Charlotte County | Tidal Caloosahatchee | 1180 | 0 | 0 | 0 | 191 | 0 | 0 | 0
Charlotte County | Tidal Caloosahatchee | NA | TRUE | 1180 | 191 | Charlotte County | West Caloosahatchee | 130 | 0 | 0 | 0 | 21 | 0 | 0 | 0
Charlotte County | West Caloosahatchee | NA | TRUE | 130 | 21 | City of Cape Coral | Tidal Caloosahatchee | 38979 | 0 | 899.5 | 0 | 7529.1 | 0 | 0 | 0
City of Cape Coral | Tidal Caloosahatchee | 2015 | FALSE | 24454 | 0 | City of Clewiston | East Caloosahatchee | 393 | 0 | 50 | 0 | 89 | 0 | 0 | 0
City of Cape Coral | Tidal Caloosahatchee | 2018 | FALSE | 0 | 0 | City of Fort Myers | Tidal Caloosahatchee | 18234 | 0 | 0 | 0 | 6076 | 0 | 0 | 0
City of Cape Coral | Tidal Caloosahatchee | 2023 | FALSE | 899.5 | 509.1 | City of LaBelle | West Caloosahatchee | 0 | 0 | 10160 | 0 | 0 | 0 | 0 | 0
City of Cape Coral | Tidal Caloosahatchee | NA | TRUE | 9299 | 3448 | City of Moore Haven | East Caloosahatchee | 0 | 1885 | 0 | 0 | 0 | 0 | 0 | 0
City of Cape Coral | Tidal Caloosahatchee | Prior to 2012 | TRUE | 5212 | 3553 | Clewiston Drainage District | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Cape Coral | Tidal Caloosahatchee | TBD | TRUE | 14 | 19 | Collier County | West Caloosahatchee | 3 | 0 | 0 | 0 | 0.4 | 0 | 0 | 0
City of Clewiston | East Caloosahatchee | 2023 | FALSE | 50 | 6 | Collins Slough WCD | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Clewiston | East Caloosahatchee | NA | TRUE | 367 | 81 | County Line Drainage District | West Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Clewiston | East Caloosahatchee | Prior to 2012 | TRUE | 26 | 2 | Cow Slough WCD | West Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2001 | FALSE | 0 | 0 | Devil's Garden WCD | West Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2010 | FALSE | 1421 | 1211 | Disston Island Conservancy District | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2011 | FALSE | 486 | 78 | FDACS | East Caloosahatchee | 179901 | 0 | 0 | 0 | 6240 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2012 | FALSE | 1195 | 338 | FDACS | Tidal Caloosahatchee | 83678 | 0 | 0 | 0 | 3604 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2013 | FALSE | 73 | 14 | FDACS | West Caloosahatchee | 297959 | 0 | 0 | 0 | 12048 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2015 | FALSE | 640 | 219 | FDOT District 1 | Tidal Caloosahatchee | 11404 | 0 | 0 | 0 | 1055 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2016 | FALSE | 7916 | 1412 | FDOT District 1 | West Caloosahatchee | 0 | 289 | 0 | 0 | 39 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2023 | FALSE | 0 | 0 | Flaghole Drainage District | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2025 | FALSE | 0 | 0 | Gerber Groves WCD | West Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2028 | FALSE | 0 | 0 | Glades County | East Caloosahatchee | 0 | 0 | 1253 | 0 | 0 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | 2030 | FALSE | 0 | 0 | Glades County | West Caloosahatchee | 1564 | 0 | 0 | 0 | 419 | 0 | 0 | 0
City of Fort Myers | Tidal Caloosahatchee | NA | TRUE | 6503 | 2804 | Hendry County | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of LaBelle | West Caloosahatchee | 2024 | FALSE | 2771 | 0 | Hendry County | West Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of LaBelle | West Caloosahatchee | 2025 | FALSE | 2278 | 0 | Hendry-Hilliard WCD | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of LaBelle | West Caloosahatchee | 2027 | FALSE | 5111 | 0 | LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 26677 | 8008 | 0 | 0 | 5148 | 0 | 0 | 0
City of Moore Haven | East Caloosahatchee | 2020 | FALSE | 231 | 0 | LA-MSID (formerly ECWCD) | West Caloosahatchee | 11145 | 634 | 19958 | 0 | 3960 | 0 | 0 | 0
City of Moore Haven | East Caloosahatchee | 2021 | FALSE | 1654 | 0 | Lee County | Tidal Caloosahatchee | 89331 | 45420 | 294 | 0 | 34300.4 | 0 | 0 | 0
Clewiston Drainage District | East Caloosahatchee | 2020 | FALSE | 0 | 0 | Lee County | West Caloosahatchee | 20526 | 20192 | 1439 | 0 | 6052 | 0 | 0 | 0
Clewiston Drainage District | East Caloosahatchee | NA | TRUE | 0 | 0 | Lucaya CDD | Tidal Caloosahatchee | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collier County | West Caloosahatchee | NA | TRUE | 3 | 0.4 | Mirada CDD | Tidal Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Collins Slough WCD | East Caloosahatchee | 2020 | FALSE | 0 | 0 | Port LaBelle CDD | East Caloosahatchee | 81 | 0 | 0 | 0 | 14 | 0 | 0 | 0
Collins Slough WCD | East Caloosahatchee | NA | TRUE | 0 | 0 | Portico CDD | West Caloosahatchee | 92 | 0 | 0 | 0 | 8 | 0 | 0 | 0
County Line Drainage District | West Caloosahatchee | 2020 | FALSE | 0 | 0 | SFWMD - Coordinating Agency | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
County Line Drainage District | West Caloosahatchee | NA | TRUE | 0 | 0 | SFWMD - Coordinating Agency | West Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
County Line Drainage District | West Caloosahatchee | TBD | TRUE | 0 | 0 | Sugarland Drainage District | East Caloosahatchee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cow Slough WCD | West Caloosahatchee | 2020 | FALSE | 0 | 0 | Verandah East CDD | Tidal Caloosahatchee | 117 | 0 | 0 | 0 | 15 | 0 | 0 | 0
Cow Slough WCD | West Caloosahatchee | NA | TRUE | 0 | 0 | Verandah West CDD | Tidal Caloosahatchee | 180 | 0 | 0 | 0 | 29 | 0 | 0 | 0
Devil's Garden WCD | West Caloosahatchee | 2020 | FALSE | 0 | 0
Devil's Garden WCD | West Caloosahatchee | NA | TRUE | 0 | 0
Disston Island Conservancy District | East Caloosahatchee | 2020 | FALSE | 0 | 0
Disston Island Conservancy District | East Caloosahatchee | NA | TRUE | 0 | 0
Disston Island Conservancy District | East Caloosahatchee | TBD | TRUE | 0 | 0
FDACS | East Caloosahatchee | NA | TRUE | 179901 | 6240
FDACS | Tidal Caloosahatchee | NA | TRUE | 83678 | 3604
FDACS | West Caloosahatchee | NA | TRUE | 297959 | 12048
FDOT District 1 | Tidal Caloosahatchee | 2005 | FALSE | 2529 | 588
FDOT District 1 | Tidal Caloosahatchee | 2017 | FALSE | 0 | 0
FDOT District 1 | Tidal Caloosahatchee | 2020 | FALSE | 0 | 0
FDOT District 1 | Tidal Caloosahatchee | NA | TRUE | 726 | 400
FDOT District 1 | Tidal Caloosahatchee | Prior to 2012 | TRUE | 8149 | 67
FDOT District 1 | West Caloosahatchee | 2020 | FALSE | 218 | 24
FDOT District 1 | West Caloosahatchee | 2022 | FALSE | 71 | 15
Flaghole Drainage District | East Caloosahatchee | 2020 | FALSE | 0 | 0
Flaghole Drainage District | East Caloosahatchee | NA | TRUE | 0 | 0
Flaghole Drainage District | East Caloosahatchee | TBD | TRUE | 0 | 0
Gerber Groves WCD | West Caloosahatchee | 2020 | FALSE | 0 | 0
Gerber Groves WCD | West Caloosahatchee | NA | TRUE | 0 | 0
Gerber Groves WCD | West Caloosahatchee | TBD | TRUE | 0 | 0
Glades County | East Caloosahatchee | 2021 | FALSE | 0 | 0
Glades County | East Caloosahatchee | 2024 | FALSE | 1253 | 0
Glades County | West Caloosahatchee | 2015 | FALSE | 1564 | 419
Hendry County | East Caloosahatchee | 2024 | FALSE | 0 | 0
Hendry County | West Caloosahatchee | 2023 | FALSE | 0 | 0
Hendry County | West Caloosahatchee | 2025 | FALSE | 0 | 0
Hendry County | West Caloosahatchee | 2026 | FALSE | 0 | 0
Hendry County | West Caloosahatchee | 2027 | FALSE | 0 | 0
Hendry County | West Caloosahatchee | 2028 | FALSE | 0 | 0
Hendry-Hilliard WCD | East Caloosahatchee | 2020 | FALSE | 0 | 0
Hendry-Hilliard WCD | East Caloosahatchee | NA | TRUE | 0 | 0
Hendry-Hilliard WCD | East Caloosahatchee | TBD | TRUE | 0 | 0
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2013 | FALSE | 819 | 127
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2017 | FALSE | 5967 | 996
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2018 | FALSE | 739 | 109
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2020 | FALSE | 1302 | 217
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | 2022 | FALSE | 0 | 0
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | NA | TRUE | 982 | 144
LA-MSID (formerly ECWCD) | Tidal Caloosahatchee | Prior to 2012 | TRUE | 18909 | 3555
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2018 | FALSE | 528 | 70
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2019 | FALSE | 106 | 8
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2021 | FALSE | 0 | 0
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2025 | FALSE | 19958 | 2732
LA-MSID (formerly ECWCD) | West Caloosahatchee | 2031 | FALSE | 0 | 0
LA-MSID (formerly ECWCD) | West Caloosahatchee | NA | TRUE | 897 | 132
LA-MSID (formerly ECWCD) | West Caloosahatchee | Prior to 2012 | TRUE | 10248 | 1018
Lee County | Tidal Caloosahatchee | 2012 | FALSE | 10055 | 465
Lee County | Tidal Caloosahatchee | 2013 | FALSE | 19608 | 5783
Lee County | Tidal Caloosahatchee | 2016 | FALSE | 16185 | 1368
Lee County | Tidal Caloosahatchee | 2017 | FALSE | 630 | 64
Lee County | Tidal Caloosahatchee | 2018 | FALSE | 10356 | 837
Lee County | Tidal Caloosahatchee | 2019 | FALSE | 20681 | 8915
Lee County | Tidal Caloosahatchee | 2020 | FALSE | 24 | 6
Lee County | Tidal Caloosahatchee | 2021 | FALSE | 13627 | 1310
Lee County | Tidal Caloosahatchee | 2022 | FALSE | 102 | 118
Lee County | Tidal Caloosahatchee | 2023 | FALSE | 294 | 56.4
Lee County | Tidal Caloosahatchee | 2024 | FALSE | 0 | 0
Lee County | Tidal Caloosahatchee | 2025 | FALSE | 0 | 0
Lee County | Tidal Caloosahatchee | NA | TRUE | 13529 | 5368
Lee County | Tidal Caloosahatchee | Prior to 2012 | TRUE | 29324 | 10010
Lee County | Tidal Caloosahatchee | TBD | TRUE | 0 | 0
Lee County | West Caloosahatchee | 2012 | FALSE | 19365 | 450
Lee County | West Caloosahatchee | 2014 | FALSE | 1161 | 46
Lee County | West Caloosahatchee | 2018 | FALSE | 3118 | 213
Lee County | West Caloosahatchee | 2019 | FALSE | 17074 | 5118
Lee County | West Caloosahatchee | 2024 | FALSE | 1439 | 225
Lucaya CDD | Tidal Caloosahatchee | NA | TRUE | 4 | 0
Mirada CDD | Tidal Caloosahatchee | NA | TRUE | 0 | 0
Port LaBelle CDD | East Caloosahatchee | NA | TRUE | 81 | 14
Portico CDD | West Caloosahatchee | 2006 | FALSE | 0 | 0
Portico CDD | West Caloosahatchee | 2007 | FALSE | 0 | 0
Portico CDD | West Caloosahatchee | 2017 | FALSE | 0 | 0
Portico CDD | West Caloosahatchee | NA | TRUE | 92 | 8
SFWMD - Coordinating Agency | East Caloosahatchee | 2019 | FALSE | 0 | 0
SFWMD - Coordinating Agency | East Caloosahatchee | 2024 | FALSE | 0 | 0
SFWMD - Coordinating Agency | East Caloosahatchee | 2026 | FALSE | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2014 | FALSE | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2023 | FALSE | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2024 | FALSE | 0 | 0
SFWMD - Coordinating Agency | West Caloosahatchee | 2025 | FALSE | 0 | 0
Sugarland Drainage District | East Caloosahatchee | 2020 | FALSE | 0 | 0
Sugarland Drainage District | East Caloosahatchee | NA | TRUE | 0 | 0
Sugarland Drainage District | East Caloosahatchee | TBD | TRUE | 0 | 0
Verandah East CDD | Tidal Caloosahatchee | NA | TRUE | 117 | 15
Verandah West CDD | Tidal Caloosahatchee | NA | TRUE | 180 | 29
(blank)
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Validation for text. Any text in Column B-Estimated Completion Date will have data added to "Thru 2018" column