## Projects for 5-Year Review
Year Added | Completion Date | Lead Entity | Project Number | Project Name | Description | Project Type | Structural, Non-structural, or Trade | Original Project Status | Project Status | Deadline (if applicable) | Acres Treated | TN Reduction (lbs/yr) | TN Reduction (kg/yr) | TP Reduction (lbs/yr) | TP Reduction (kg/yr) | DEP Contract Agreement Number | Cost | Cost Annual O&M | Funding Source | Attachments | BMAP | Latitude | Longitude | Location | Partners | Start Date
2012 | Prior to 2012 | Charlotte County | CH-01 | Education Efforts | Florida Yards and Neighborhoods (FYN) Program, landscaping ordinance, irrigation ordinance, fertilizer ordinance, pamphlets, public service announcements (PSAs), website, inspection/illicit discharge program. | Education Efforts | Non-structural | Ongoing | Completed | - | N/A | 380.765 | 172.712 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-01 | Education Efforts | FYN,landscaping ordinance, irrigation ordinance, fertilizer ordinance, pet waste ordinance, pamphlets, PSAs, website, illicit discharge program. | Education Efforts | Non-structural | Ongoing | Completed | - | N/A | 15429 | 6998.471 | N/A | N/A | N/A | N/A | 2000 | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | IFAS | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-02 | SE-1 Swale/Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Grass Swales with Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-03 | SW-1 Swale/Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Grass Swales with Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-04 | SW-2 Swale/Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Grass Swales with Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-05 | SW-3 Swale/Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Grass Swales with Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-06 | SW-4 Swale/Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Grass Swales with Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-07 | SW-5 Swale/Inlet Replacement | Installed raised inlets to provide additional water quality in roadside swales. | Grass Swales with Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-08 | SE Pipe Replacement | SE pipe replacement. | Stormwater System Rehabilitation | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-09 | Unit 23–SE 8th St. Drainage | Unit 23–SE 8th St. drainage. | Stormwater System Rehabilitation | Structural | Completed | Completed | - | Information not provided | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-10 | Freshwater Canal Detention | Regulation of freshwater canals through existing control structures. | Control Structure | Structural | Completed | Completed | - | 10702 | 39971 | 18130.5258 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-11 | Freshwater Canal Irrigation | Pump stormwater stored in canals into irrigation supply network. | Stormwater Reuse | Structural | Completed | Completed | - | Information not provided | 27670 | 12550.8906 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-12 | Weir #6 Elevation/Basin 12 | Installed riser on weir in freshwater canal system to provide additional retention volume in canals. | Control Structure | Structural | Completed | Completed | - | 932 | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | City of Cape Coral | CC-13 | Weir #1 Elevation/Basin 15 | Installed riser on weir in freshwater canal system to provide additional retention volume in canals. | Control Structure | Structural | Completed | Completed | - | 1314 | 0 | 0 | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2014 | 2014 | City of Cape Coral | CC-14 | Street Sweeping | Street sweeping of downtown area, alleys, and commercial roads. | Street Sweeping | Non-structural | Ongoing | Completed | - | N/A | 1084 | 491.6937 | N/A | N/A | N/A | Information not provided | 360000 | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | 2015
2015 | 2015 | City of Cape Coral | CC-15 | Septic to Sewer Phase Out Project | Phase out septic tanks in Southwest 6/7 area. | Wastewater Service Area Epansion | Structural | Completed | Completed | - | 2560 | TBD | TBD | N/A | N/A | N/A | Information not provided | Information not provided | Cape Coral | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2016 | 2015 | City of Cape Coral | CC-16 | Catch Basin Cleanout | Catch basin cleanouts from Caloosahatchee Watershed areas. | Catch Basin Insert/Inlet Filter Cleanout | Structural |  | Completed |  | Information not provided | 590 | 267.6193 | N/A | N/A | N/A | Information not provided | 170000 | Cape Coral |  | Caloosahatchee |  |  | Tidal Caloosahatchee | N/A | 2015
2012 | Prior to 2012 | City of Fort Myers | FM-01 | Manuels Branch Watershed Improvements | Exfiltration trenches. | Exfiltration Trench | Structural | Completed | Completed | - | 124.6 | 836 | 379.2029 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | City of Fort Myers | FM-02 | Education Efforts | FYN, fertilizer ordinance, pamphlets, PSAs, website, illicit discharge program. | Education Efforts | Non-structural | Ongoing | Completed | - | N/A | 2101 | 952.9968 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | City of Fort Myers | FM-03 | Utility and Streetscape Improvements | Installation of Stormceptors™. | Stormceptor™ Unit | Structural | Completed | Completed | - | 117.9 | 40 | 18.1437 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | City of Fort Myers | FM-04 | Manuels Branch Siltation Structures | Installation of siltation structure designed to receive incoming flow, reduce its velocity and allow for settling of suspended particles. | Control Structure | Structural | Completed | Completed | - | 642.7 | 1078 | 488.9722 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | City of Fort Myers | FM-05 | Manuels Branch Control Structures | Series of two weirs constructed along Manuels Branch between Royal Palm Ave. and Grand Ave. that act as detention structures for purpose of increasing storage and attenuation in canal. | Control Structure | Structural | Completed | Completed | - | 437.9 | 2202 | 998.8096 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | City of Fort Myers | FM-06 | Billy's Creek Wetland | Filter marsh park. | Filter Marsh | Structural | Completed | Completed | - | 1631.6 | 4025 | 1825.7078 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | 2013 | City of Fort Myers | FM-07 | Brookhill Utility Drainage Improvement | Installation of Stormceptors™. | StormceptorTM Unit | Structural | Completed | Completed | - | Information not provided | 11 | 4.9895 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | City of Fort Myers | FM-08 | Street Sweeping | Four zones swept at varying frequencies based on pollutant accumulation. | Street Sweeping | Non-structural | Ongoing | Completed | - | N/A | 2582 | 1171.1745 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | 2015 | City of Fort Myers | FM-09 | Ford Street Preserve | Constructed wetland treatment system that removes pollutants from Ford Street Canal, which serves 811 acres of highly urbanized watershed. | Wetland Treatment | Structural | Completed | Completed | - | 811 | 7293 | 3308.0465 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | 2013 | City of Fort Myers | FM-10 | Riverfront Development Phase 1 | Wet detention pond. | Wet Detention Pond | Structural | Completed | Completed | - | Information not provided | 90 | 40.8233 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2014 | 2014 | City of Fort Myers | FM-11 | Carrell Canal Water Quality Retrofit | Two detention areas, five filter marshes, and golf course renovation. | BMP Treatment Trains | Structural | Completed | Completed | - | Information not provided | 1275 | 578.3298 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | LA-MSID (formerly ECWCD) | EC-01 | Education/Fertilizer | Education. | Education Efforts | Non-structural | Ongoing | Completed | - | N/A | 1646 | 746.6124 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | LA-MSID (formerly ECWCD) | EC-02 | Freshwater Canal Detention | Regulation of freshwater canals through existing control structures. | Control Structure | Structural | Completed | Completed | - | 32555 | 7940 | 3601.5205 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | LA-MSID (formerly ECWCD) | EC-03 | Weir Elevation Improvements | Replacement of weir structures at increase control elevations to provide additional attenuation. | Control Structure | Structural | Completed | Completed | - | 32555 | 7543 | 3421.4445 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | LA-MSID (formerly ECWCD) | EC-04 | Harn's Marsh Phases I and II | Replacement of weir structures and redirection of flows into filter marsh. | Control Structure | Structural | Completed | Completed | - | 32555 | 4682 | 2123.7177 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | LA-MSID (formerly ECWCD) | EC-05 | Jim Flemming Eco-Park | Wetland rehydration and treatment. | Hydrologic Restoration | Structural | Completed | Completed | - | 5.02 | 39.26 | 17.808 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | 2013 | LA-MSID (formerly ECWCD) | EC-06 | Mirror Lake Phase I | Detention pond. | Wet Detention Pond | Structural | Completed | Completed | - | 32555 | 1357 | 615.5243 | N/A | N/A | Information not provided | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2016 | 2017 | LA-MSID (formerly ECWCD) | EC-07 | Aquifer Benefit and Storage for Orange River Basin (ABSORB) (Southwest Lehigh Weirs) | Increase canal control elevations and local groundwater levels by constructing 25 new weirs. | Control Structure | Structural |  | Underway |  | 5760 | 1975 | 895.8442 | N/A | N/A | S0721 | 2532311.32 | Information not provided | DEP/FDOT |  | Caloosahatchee | 755817.2536 | 828743.8958 | Tidal Caloosahatchee | DEP/FDOT | 2016
2017 | 2017 | LA-MSID (formerly ECWCD) | EC-08 | S-AW-1 Weir Elevation Improvements | Replacement of weir structures at increase control elevations to provide additional attenuation. | Control Structure | Structural |  | Completed |  | 640 | 324.5 | 147.1906 | N/A | N/A | N/A | 400000 | 15000 | LA-MSID |  | Caloosahatchee |  |  | Tidal Caloosahatchee | N/A | 2016
2017 | 2018 | LA-MSID (formerly ECWCD) | EC-09 | Mirror Lake Phase 2 | Detention pond. | Wet Detention Pond | Structural | In Design | Underway |  | 32555 | 4938 | 2239.8373 | N/A | N/A | N/A | 500000 | TBD | LA-MSID/ SFWMD |  | Caloosahatchee |  |  | Tidal Caloosahatchee | SFWMD | 2017
2017 | 2020 | LA-MSID (formerly ECWCD) | EC-10 | West Marsh Preserve | Wetland rehydration and treatment. | Hydrologic Restoration/Filter Marsh | Structural |  | Underway |  | 32555 | 2015 | 913.9879 | N/A | N/A | N/A | 12000000 | TBD | LA-MSID/ FDOT/ Lee County |  | Caloosahatchee |  |  | Tidal Caloosahatchee | FDOT/ Lee County | 2017
2012 | Prior to 2012 | FDACS | FDACS-01 | BMP Enrollment | Agricultural BMPs. | Agricultural BMPs | Non-structural | Ongoing | Completed |  | 18628 | 30744 | 13945.2324 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | N/A
2012 | Prior to 2012 | FDOT | FDOT-01 | Existing Stormwater Dry Ponds | Dry detention pond. | Dry Detention Pond | Structural | Completed | Completed | - | 6 | 55 | 24.9476 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | FDOT | FDOT-02 | Discontinuing Fertilization | No longer fertilizing rights-of-way in watershed. | Fertilizer Cessation | Non-structural | Completed | Completed | - | 465 | 1941 | 880.4221 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | FDOT | FDOT-03 | Education Efforts | Pamphlets, PSAs, illicit discharge program. | Education Efforts | Non-structural | Ongoing | Completed | - | N/A | 232 | 105.2333 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | FDOT | FDOT-04 | Street Sweeping | 2,992 pavement miles swept annually. | Street Sweeping | Non-structural | Ongoing | Completed | - | N/A | 577 | 261.7226 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | FDOT | FDOT-05 | Ditch Blocked Swales | Swales with ditch blocks. | Grass Swales with Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | 166 | 826 | 374.667 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | FDOT | FDOT-06 | Swales without Ditch Blocks | Swales without blocks. | Grass Swales without Swale Blocks or Raised Culverts | Structural | Completed | Completed | - | 1353 | 4949 | 2244.8268 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | FDOT | FDOT-07 | Existing Stormwater Wet Ponds | Wet detention pond. | Wet Detention Pond | Structural | Completed | Completed | - | 155 | 2646 | 1200.2044 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | FDOT | FDOT-08 | State Road (SR) 78 Project | Wet detention pond. | Wet Detention Pond | Structural | Completed | Completed | - | 79.5 | 264 | 119.7483 | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided
2012 | Prior to 2012 | Lee County | LC-01 | Yellow Fever Creek Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 220 | 32 | 14.5149 | N/A | N/A | N/A | $3,323.506.74 | 11703 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-02 | Billy's Creek Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 50.7 | 17 | 7.7111 | N/A | N/A | N/A | 2500000 | N/A | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-03 | Six Mile Cypress Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 1219 | 13 | 5.8967 | N/A | N/A | N/A | 71475196 | 149212 | Lee County/SFWMD | - | Caloosahatchee | - | - | Tidal Caloosahatchee | SFWMD | Information not provided
2012 | Prior to 2012 | Lee County | LC-04 | Bob Jane's Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 1978.9 | 0 | 0 | N/A | N/A | N/A | 41538620 | 639924 | Lee County/SFWMD/National Oceanic and Atmospheric Administration (NOAA) | - | Caloosahatchee | - | - | Tidal Caloosahatchee | SFWMD/NOAA | Information not provided
2012 | Prior to 2012 | Lee County | LC-05 | Buckingham Trails Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 575.5 | 13 | 5.8967 | N/A | N/A | N/A | 12584000 | 18708 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-06 | Caloosahatchee Creeks Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 911.3 | 15 | 6.8039 | N/A | N/A | N/A | 8175706 | 81323 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Florida Communities Trust | Information not provided
2012 | Prior to 2012 | Lee County | LC-07 | Deep Lagoon Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 117 | 3 | 1.3608 | N/A | N/A | N/A | 4475664.23 | 9915 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-08 | Hickory Swamp Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 67.2 | 3 | 1.3608 | N/A | N/A | N/A | 467000 | 3856 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-09 | Orange River Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 59.1 | 3 | 1.3608 | N/A | N/A | N/A | 1755000 | 2966 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-10 | Prairie Pines Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 330.9 | 3 | 1.3608 | N/A | N/A | N/A | 11790529.95 | 190454 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Florida Communities Trust | Information not provided
2012 | Prior to 2012 | Lee County | LC-11 | Telegraph Creek Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 1715.1 | 0 | 0 | N/A | N/A | N/A | 23900000 | 54639 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-12 | West Marsh Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 218.1 | 3 | 1.3608 | N/A | N/A | N/A | 4631625 | N/A | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-13 | Yellow Fever Creek Preserve | Land purchase and conversion to conservation land use. | Land Acquisition | Non-structural | Completed | Completed | - | 117.8 | 0 | 0 | N/A | N/A | N/A | 3323506.74 | 11703 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-15 | Education Efforts | FYN, landscaping ordinance, irrigation ordinance, fertilizer ordinance, pamphlets, PSAs, website, illicit discharge program. | Education Efforts | Non-structural | Ongoing | Completed | - | N/A | 20445 | 9273.6884 | N/A | N/A | N/A | 392441 | N/A | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | University of Florida Institute of Food and Agricultural Sciences (UF–IFAS–Lee County Extension) | Information not provided
2012 | Prior to 2012 | Lee County | LC-16 | Street Sweeping | Materials from roadway and gutter sweeping. | Street Sweeping | Non-structural | Ongoing | Completed | - | N/A | 490 | 222.2601 | N/A | N/A | N/A | 694176 | N/A | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | 2013 | Lee County | LC-17 | North Fort Myers Surface Water Restoration: Powell Creek Extension and Lost Lane Levee | Conveyance improvements to increase residence time, rehydrate offsite wetlands on adjacent properties, and accommodate offsite flows. | Hydrologic Restoration | Structural | Completed | Completed | - | 397.1 | 2976 | 1349.8898 | N/A | N/A | N/A | 3485817 | 17101 | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-18 | Whiskey Creek Weir Reconstruction | Retention lake weir repairs to restore originally intended design and operation. | Control Structure | Structural | Completed | Completed | - | 549.6 | 3364 | 1525.8835 | N/A | N/A | N/A | Information not provided | Information not provided | Lee County | - | Caloosahatchee | - | - | Tidal Caloosahatchee | N/A | Information not provided
2012 | Prior to 2012 | Lee County | LC-19 | Caloosahatchee Creeks | Hydrologic restoration. | Hydrologic Restoration | Structural | Completed | Completed | - | 6567.4 | 4251 | 1928.2196 | N/A | N/A | N/A | Information not provided | Information not provided | Lee County/SFWMD/U.S. Fish and Wildlife Service (FWS) | - | Caloosahatchee | - | - | Tidal Caloosahatchee | SFWMD/FWS | Information not provided
2012 | 2013 | Lee County | LC-20 | Powell Creek Filter Marsh | Created wetland areas, boardwalks, and trails and a stabilized crossing of Powell Creek. | Filter Marsh | Structural | Completed | Completed | - | 1169.6 | 1693 | 767.9313 | N/A | N/A | S0606 | 1440000 | 38395 | Lee County/SFWMD/DEP | - | Caloosahatchee | - | - | Tidal Caloosahatchee | DEP/SFWMD | Information not provided
2012 | TBD | Lee County | LC-21 | Nalle Grade Stormwater Park | Dry retention and wet detention ponds. | Stormwater Treatment Area | Structural | Future | Underway | - | 720.36 | TBD | TBD | N/A | N/A | S0727 | 3500000 | TBD | Lee County/DEP | - | Caloosahatchee | - | - | Tidal Caloosahatchee | DEP | Information not provided
2012 | Prior to 2012 | Lee County | LC-22 | Deep Lagoon Hydrologic Restoration | Hydrologic restoration and enhancement, water conservation, wildlife habitat enhancement, and flood protection for surrounding area. | Hydrologic Restoration | Structural | Completed | Completed | - | 1022.1 | 3097 | 1404.7744 | N/A | N/A | N/A | 210959 | Information not provided | Lee County/SFWMD | - | Caloosahatchee | - | - | Tidal Caloosahatchee | SFWMD | Information not provided
2012 | Prior to 2012 | Lee County | LC-23 | Popash Creek Restoration | Hydrologic restoration to more natural flow regime by increasing water storage on property and improving both onsite and off-site flows. | Hydrologic Restoration | Structural | Completed | Completed | - | 3517 | 6596 | 2991.8928 | N/A | N/A | LP6838 | 1726625 | 16920 | Lee County/DEP | - | Caloosahatchee | - | - | Tidal Caloosahatchee | DEP | Information not provided
2012 | Prior to 2012 | Lee County | LC-24 | Billy's Creek Wetland | Billy Creek Filter Marsh Park. | Filter Marsh | Structural | Completed | Completed | - | 1632 | 2684 | 1217.4409 | N/A | N/A | N/A | 2500000 | N/A | Lee County/City of Fort Myers | - | Caloosahatchee | - | - | Tidal Caloosahatchee | City of Fort Myers | Information not provided
2015 | 2016 | Lee County | LC-25 | Caloosahatchee Creeks Preserve–West Restoration | Hydrologic restoration. | Hydrologic Restoration | Structural | Future | Completed | - | 1295 | 110 | 49.8951 | N/A | N/A | S0849 | 250000 | Information not provided | Lee County/DEP | - | Caloosahatchee | - | - | Tidal Caloosahatchee | DEP | 2015
2015 | TBD | Lee County | LC-26 | Yellow Fever Creek – Gator Slough Transfer Facility | Return historical flow from Gator Slough Canal system to Yellow Fever Creek. | Hydrologic Restoration | Structural | Future | Underway | - | TBD | TBD | TBD | N/A | N/A | S0840 | TBD | TBD | Lee County/DEP | - | Caloosahatchee | - | - | Tidal Caloosahatchee | DEP | Information not provided
2016 | TBD | Lee County | LC-27 | Prairie Pines Preserve Restoration | Restoration of historical flows and enhancement and restoration of wetlands. | Hydrologic Restoration | Structural | Construction in 2017 | Planned |  | 2334 | TBD | TBD | N/A | N/A | S0895 | 500000 | 28295 | Lee County/DEP |  | Caloosahatchee |  |  | Tidal Caloosahatchee | DEP | 2017
2016 | 2017 | Lee County | LC-28 | BMAP Plan Development – Basin Study | Basin study to identify pollutant sources and identify further actions to reach reduction goals. | Studies | Non-structural |  | Completed |  | N/A | N/A | N/A | N/A | N/A | N/A | 195831 | N/A | Lee County |  | Caloosahatchee |  |  | Tidal Caloosahatchee | N/A | 2016
2016 | TBD | Lee County | LC-29 | Caloosahatchee River-North Fort Myers Nutrient and Bacteria Source Identification Study | Watershed study to investigate interactions between onsite sewage treatment and disposal systems (OSTDS), groundwater, and surface water in Caloosahatchee Estuary. | Studies | Non-structural |  | Underway |  | N/A | N/A | N/A | N/A | N/A | N/A | 181352 | N/A | Lee County |  | Caloosahatchee |  |  | Tidal Caloosahatchee | N/A | 2017
2017 | 2012 | Lee County | LC-30 | Waterway Estates WWTF Closure | Closure of facility with direct discharge to Caloosahatchee. | WWTF Diversion to Reuse | Structural |  | Completed |  | N/A | 307 | 139.2527 | N/A | N/A | N/A | 61565 | N/A | Lee County |  | Caloosahatchee |  |  | Tidal Caloosahatchee | N/A | Information not provided
2017 | 2017 | Lee County | LC-31 | Six Mile Cypress Preserve North Hydrologic Restoration | Wetland creation, addition of control structures, berms, berm breaches to connect natural and created wetlands, and restoration of historical hydrologic conditions to reduce discharge into Caloosahatchee River. | Hydrologic Restoration | Structural |  | Completed |  | Information not provided | TBD | TBD | N/A | N/A | N/A | TBD | TBD | Lee County/SFWMD/FDOT |  | Caloosahatchee |  |  | Tidal Caloosahatchee | SFWMD/FDOT | Information not provided
2017 | 2017 | Lee County | LC-32 | Bob Jane's Preserve Environmental Restoration | Hydrologic improvements in portion of preserve via berms, beaches, and ditch blocks. | Hydrologic Restoration | Structural |  | Completed |  | Information not provided | TBD | TBD | N/A | N/A | S0871 | Information not provided | Information not provided | Lee County/DEP/SFWMD |  | Caloosahatchee |  |  | Tidal Caloosahatchee | DEP/SFWMD | Information not provided
2017 | 2017 | Lee County | LC-33 | Telegraph Creek Preserve | Ditch blocks and native plantings in conveyances. | Hydrologic Restoration | Structural |  | Completed |  | Information not provided | TBD | TBD | N/A | N/A | S0873 | 107337 | 54639 | Lee County/DEP |  | Caloosahatchee |  |  | Tidal Caloosahatchee | DEP | Information not provided
2017 | TBD | Lee County | LC-34 | West Marsh Preserve Filter Marsh | Creation and enhancement of wetland marsh ecosystem, including hydraulic connection for water quality improvement and stormwater attenuation. | Filter Marsh | Structural |  | Underway |  | TBD | TBD | TBD | N/A | N/A | N/A | TBD | TBD | Lee County/ LA-MSID |  | Caloosahatchee |  |  | Tidal Caloosahatchee | LA-MSID/FDOT | Information not provided
2017 | TBD | Lee County | LC-35 | C-43 Water Quality Treatment and Testing Facility Project (*study/land acquisition) | Project to demonstrate and implement cost-effective, wetland-based strategies for reduction of DON. | Studies | Structural |  | Underway |  | N/A | N/A | N/A | N/A | N/A | N/A | 10000000 | N/A | Lee County/ DEP/ SFWMD |  | Caloosahatchee |  |  | Upstream of Estuary BMAP | SFWMD/DEP | Information not provided
2017 | TBD | Lee County | LC-36 | Fichter's Creek Restoration Project | Restoration of hydroperiod and water quality in Fichter's Creek. | Hydrologic Restoration | Structural |  | Underway |  | TBD | 1453 | 659.0692 | N/A | N/A | S0893 | 2000000 | TBD | Lee County/DEP/SFWMD |  | Caloosahatchee |  |  | Upstream of Estuary BMAP | DEP/SFWMD | Information not provided
2017 | TBD | Lee County | LC-37 | Spanish Creek at Daniel's Preserve Restoration | Restoration of wetland hydroperiod and sheetflow attenuation. | Hydrologic Restoration | Structural |  | Underway |  | TBD | 112 | 50.8023 | N/A | N/A | S0732 | 400000 | TBD | Lee County/DEP |  | Caloosahatchee |  |  | Upstream of Estuary BMAP | DEP | Information not provided
2017 | TBD | Lee County | LC-38 | Deep Lagoon Pollutant Load Reduction Phase 2-Watershed Analysis Report | Basin study to identify pollutant sources and identify further actions to reach reduction goals. | Studies | Non-structural |  | Underway |  | N/A | N/A | N/A | N/A | N/A | N/A | 70000 | N/A | Lee County |  | Caloosahatchee |  |  | Tidal Caloosahatchee | Information not provided | Information not provided
2017 | TBD | Lee County | LC-39 | North Fort Myers FPL Feasibility Study | Study to identify areas of high nutrient loads and potential BMPs to improve water quality and reduce flooding. | Studies | Non-structural |  | Underway |  | N/A | 0 | 0 | N/A | N/A | S0894 | 200000 | N/A | Lee County/DEP |  | Caloosahatchee |  |  | Tidal Caloosahatchee | DEP | Information not provided
2017 | TBD | Lee County | LC-40 | Sunniland/Nine Mile Run Drainage Improvements | Replacement of failing water control structures and reconnection of flowways to Hickory Swamp and Buckingham Trails Preserve. | Hydrologic Restoration | Structural |  | Planned |  | TBD | TBD | TBD | N/A | N/A | LP3602B | 2000000 | TBD | Lee County/DEP |  | Caloosahatchee |  |  | Tidal Caloosahatchee | DEP | Information not provided
2017 | TBD | Lee County | LC-41 | Caloosahatchee Tributary Canal Rehabilitation: L-3 | Reshaping canal banks, littoral planting, and possible addition of control structure(s). | Regional Stormwater Treatment | Structural |  | Planned |  | TBD | TBD | TBD | N/A | N/A | N/A | 500000 | TBD | Lee County/ City of Fort Myers |  | Caloosahatchee |  |  | Tidal Caloosahatchee | City of Fort Myers | Information not provided
2012 | Prior to 2012 | Lucaya CDD | LU-01 | Education/Fertilizer | Education | Education Efforts | Non-structural | Completed | Completed | - | N/A | 0 | Information not provided | N/A | N/A | N/A | Information not provided | Information not provided | Information not provided | - | Caloosahatchee | - | - | Tidal Caloosahatchee | Information not provided | Information not provided