## ROCK-24
BMAP | Lead Entity | Project Number | Project Name | Project Type | Proposed TN Reduction (lbs./yr.) | Awarded TN Reduction (lbs./yr.) | Proposed TP Reduction (lbs./yr.) | Awarded TP Reduction (lbs./yr.) | Date Verification Completed | Status | Notes
NIRL | Rockledge | ROCK-24 | Huntington Lakes II | Wet Detention Pond | 555 |  | 103 |  |  | Incomplete | Assigned 100% credit for a wet pond with no discharge - but did not confirm there was no discharge. No staging/draw-down information. No supporting documentation of initial loading - missing land use map/file. Not stormwater reuse. Did not show calc for %Reduction for treatment basin. No PLSM model - though referenced.
Wood Log:
Date | Contact | Date Received | Data Received | Data Reviewed By | Status Update | Comments
2019-02-04 | Kevin Williams |  | Initial Data Request | Sarah Faraji | Incomplete | See Notes Above
2019-02-12 | Kevin Williams | 2019-02-11 | PLSM Model | Sarah Faraji | Incomplete | Still missing reduction percentage calculation for bmps, pond treatment volume/retention, and loading reduction calculation.
Assigned 100% for a wet detention pond, without providing retention (in) or storage volume.
Need evidence that this pond provides sufficient storage for the drainage basin.
PLSM model reported for Rock-24 that TN was 742 (lb/yr.) and TP was 182.2 (lb/yr.) for initial loading.
Engineering Report stated: TN Loading-662 lbs. and TP Loading- 88lbs.
This does not match the report.
*Final engineering report (nov 2017) was reference but not provided.

## ROCK-27
BMAP | Lead Entity | Project Number | Project Name | Project Type | Proposed TN Reduction (lbs./yr.) | Awarded TN Reduction (lbs./yr.) | Proposed TP Reduction (lbs./yr.) | Awarded TP Reduction (lbs./yr.) | Date Verification Completed | Status | Notes
NIRL | Rockledge | ROCK-27 | River Ridge Non Discharge | 100% On-site Retention | 328 |  | 68 |  |  | Incomplete | Assigned 100% credit for a wet pond with no discharge - did not confirm no discharge: " it appears that there is no discharge from this basin, though heavy underbrush prevented a complete no discharge determination." No supporting documentation of initial loading - missing land use map/file. Not stormwater reuse. Did not identify pond/acreage - only provided map of aerial.
Wood Log:
Date | Contact | Date Received | Data Received | Data Reviewed By | Status Update | Comments
2019-02-04 | Kevin Williams |  | Initial Data Request | Sarah Faraji | Incomplete | See Notes Above
2019-02-12 | Kevin Williams | 2019-02-11 | PLSM Model | Sarah Faraji | Incomplete | The provided report, though titled Rock-27, actually refers to a project called Rock -29. But they have the same project description "River Ridge No Discharge Area"
Still missing reduction calculations, pond treatment volume/retention, engineering reports/calculations.
Need evidence that this pond provides sufficient storage for the drainage basin - missing retention (in).
PLSM model reported for Rock-27 that TN was 208 (lb/yr.) and TP was 46.50 (lb/yr.) for initial loading.
This does not match the report.

## ROCK-32
BMAP | Lead Entity | Project Number | Project Name | Project Type | Proposed TN Reduction (lbs./yr.) | Awarded TN Reduction (lbs./yr.) | Proposed TP Reduction (lbs./yr.) | Awarded TP Reduction (lbs./yr.) | Date Verification Completed | Status | Notes
NIRL | Rockledge | ROCK-32 | School Triangle Pond | Dry Detention Pond | 8 |  | 2 |  |  | Incomplete | Missing initial loading, reduction calculation, model, pond size. No supporting documentation or drawings. No land use file/map or percentages.
Wood Log:
Date | Contact | Date Received | Data Received | Data Reviewed By | Status Update | Comments
2019-02-04 | Kevin Williams |  | Initial Data Request | Sarah Faraji | Incomplete | See Notes Above
2019-02-12 | Kevin Williams | 2019-02-11 | PLSM Model | Sarah Faraji | Incomplete | The provided report, though titled Rock-32, actually refers to a project called Rock -36. But they have the same project description "School Triangle Pond"
Still missing reduction calculations, pond treatment volume/retention, engineering reports/calculations.
Need evidence that this pond provides sufficient storage for the drainage basin.
PLSM model reported for Rock-32: TN was 16 (lb/yr.) and TP was 4.40 (lb/yr.) for initial loading.
For 10% treatment (FDEP BMP List) - this does not match reduction credit listed above or what is in the report
|  |  | TN Load (lbs./yr.) | Adjusted TP (lbs./yr.)
|  | Load | 16 | 4.4 | PLSM Model
|  | Reduction | 1.6 | 0.44

## Rock-34
BMAP | Lead Entity | Project Number | Project Name | Project Type | Proposed TN Reduction (lbs./yr.) | Awarded TN Reduction (lbs./yr.) | Proposed TP Reduction (lbs./yr.) | Awarded TP Reduction (lbs./yr.) | Date Verification Completed | Status | Notes
NIRL | Rockledge | ROCK-34 | Winchester Cove Non Discharge | 100% On-site Retention | 44 |  | 5 |  |  | Incomplete | Assigned 100% credit for a wet pond with no discharge. Need to confirm "no discharge". No supporting documentation of initial loading - missing land use file/map or percentages. Not stormwater reuse. Only provided a handrawn map - not confirming treatment area.
Wood Log:
Date | Contact | Date Received | Data Received | Data Reviewed By | Status Update | Comments
2019-02-04 | Kevin Williams |  | Initial Data Request | Sarah Faraji | Incomplete | See Notes Above
2019-02-12 | Kevin Williams | 2019-02-11 | PLSM Model | Sarah Faraji | Incomplete | The provided report, though titled Rock-34, actually refers to a project called Rock -30. But they have the same project description "Winchester Grove Nondischarge"
Still missing reduction calculations, pond treatment volume/retention, engineering reports/calculations.
Need evidence that this pond provides sufficient storage for the drainage basin - missing retention (in).
PLSM model reported for Rock-34: TN was 13 (lb/yr.) and TP was 1.60 (lb/yr.) for initial loading.
This does not match the report.

## ROCK-35
BMAP | Lead Entity | Project Number | Project Name | Project Type | Proposed TN Reduction (lbs./yr.) | Awarded TN Reduction (lbs./yr.) | Proposed TP Reduction (lbs./yr.) | Awarded TP Reduction (lbs./yr.) | Date Verification Completed | Status | Notes
NIRL | Rockledge | ROCK-35 | Florida Ave and Dixie Lane Swale | Grass swales with swale blocks or raised culverts | TBD |  | TBD |  |  | TBD - Incomplete | Claims > 100% retention for a swale+swale block - to be calculated as on-line retention. Claimed 12 inch of retention, but did not provide any staging or draw-down information. No design drawings. No land use maps/files or percentages.
Wood Log:
Date | Contact | Date Received | Data Received | Data Reviewed By | Status Update | Comments
2019-02-04 | Kevin Williams |  | Initial Data Request | Sarah Faraji | Incomplete | See Notes Above
2019-02-12 | Kevin Williams | 2019-02-11 | PLSM Model | Sarah Faraji | TBD- Incomplete | The PLSM Model for Rock-35 states initial loading as: TN- 229 (lbs./yr.) and TP - 42.2 (lbs./yr.)
This does not match the report for Rock-35: TN- 134.66 lbs. and TP -32.33 lbs.
Must provide pond drawings or engineering report to confirm that the pond provides 12 inches of retention and 100% treatment.