## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile | ProvideAdditionalInfoToCredit
BIRL | 2433 | City of Cape Canaveral | N/A | CC-17 | Central Ditch Dredging Project | Dredging of southern portion of Central Ditch. | Muck Removal/Restoration Dredging | Canceled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2446 | City of Cape Canaveral | Brevard County/ SOIRL | CC-21 | Holman Road Swale | Swales and biosorption activated media (BAM). | BMP Treatment Train | Canceled | 2019 | 2021 | N/A | N/A | N/A | N/A | 28000 | 500 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2486 | City of Cape Canaveral | Brevard County/ SOIRL | CC-22 | Cocoa Palms LID | Exfiltration and BAM wall. | BMP Treatment Train | Canceled | 2018 | 2021 | N/A | N/A | N/A | N/A | 85000 | 1000 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2485 | City of Cape Canaveral | N/A | CC-23 | Cherrie Down Park | Swale with biosorption activated media (BAM). | BMP Treatment Train | Canceled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2484 | City of Cape Canaveral | Brevard County/ SOIRL | CC-24 | Carver Cove Swale | Swale with biosorption activated media (BAM). | BMP Treatment Train | Canceled | 2018 | 2021 | N/A | N/A | N/A | N/A | 20340 | 1000 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2483 | City of Cape Canaveral | Brevard County/ SOIRL | CC-25 | Cape Shores Swales (3 count) | Swale with biosorption activated media (BAM). | BMP Treatment Train | Canceled | 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2481 | City of Cape Canaveral | Brevard County/ SOIRL | CC-27 | Justamere Road Swale | Dry detention swale without blocks or raised culverts and media filter. | BMP Treatment Train | Canceled | 2018 | 2021 | N/A | N/A | N/A | N/A | 7800 | 1000 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2480 | City of Cape Canaveral | Brevard County/ SOIRL | CC-28 | Hitching Post Berm | Berm and associated grass swale without blocks or raised culverts and media filter. | BMP Treatment Train | Canceled | 2018 | 2021 | N/A | N/A | N/A | N/A | 40300 | 1000 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2478 | City of Cape Canaveral | Brevard County/ SOIRL | CC-30 | Holman Road Pond | Wet detention pond. | Wet Detention Pond | Canceled | 2021 | 2022 | N/A | N/A | N/A | N/A | 235630 | 2500 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2477 | City of Cape Canaveral | Brevard County/ SOIRL | CC-31 | Costa Del Sol Pond | Dry detention swale without blocks or raised culverts and media filter. | Dry Detention Pond | Canceled | 2019 | 2021 | N/A | N/A | N/A | N/A | 58120 | 2500 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 2476 | City of Cape Canaveral | Brevard County/ SOIRL | CC-32 | Costa del Sol Denitrificaiton Wall | Exfiltration and BAM wall. | BMP Treatment Train | Canceled | 2021 | 2021 | N/A | N/A | N/A | N/A | 18800 | 1000 | City/ County | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
BIRL | 4328 | City of Cape Canaveral | Cape Canaveral/ Save Our Indian River Lagoon (SOIRL) | BC-33 | Central Blvd Baffle Box | 2nd generation baffle box, SOIRL-13. | Baffle Boxes- Second Generation | Completed | Not provided | 2017 | TBD | TBD | B | 213.4 | 41700 | 41700 | SOIRL/ DEP | 34700 | NF025 | Not provided | 28.3961 | -80.6081 | N/A | Y | Y
BIRL | 2464 | City of Cape Canaveral | SJRWMD | CC-01 | Holman Road Baffle Box | First generation baffle box installation near Holman Road outfall. | Baffle Boxes- First Generation | Completed | 2005 | 2006 | 1.6497 | 1.2769 | B | 32.8211 | 75000 | 1200 | SJRWMD/ City | SJRWMD - $45,000/ City - $30,000 | N/A | Not provided | 28.3749 | -80.6063 | N/A | N | N
BIRL | 2465 | City of Cape Canaveral | SJRWMD | CC-02 | Center Street Baffle Box | First generation baffle box installation near Center Street outfall. | Baffle Boxes- First Generation | Completed | 2005 | 2006 | 4.5486 | 3.2915 | B | 96.2315 | 75000 | 1200 | SJRWMD/ City | SJRWMD - $45,000/ City - $30,000 | N/A | Not provided | 28.382 | -80.6039 | N/A | N | N
BIRL | 2466 | City of Cape Canaveral | SJRWMD | CC-03 | International Drive Baffle Box | First generation baffle box installation near International Drive outfall. | Baffle Boxes- First Generation | Completed | 2005 | 2006 | 8.6102 | 6.4443 | B | 181.0013 | 75000 | 1200 | SJRWMD/ City | SJRWMD - $45,000/ City - $30,000 | N/A | Not provided | 28.3882 | -80.6029 | N/A | N | N
BIRL | 2467 | City of Cape Canaveral | SJRWMD | CC-04 | Angel Isles Baffle Box | First generation baffle box installation near Angel Isles outfall. | Baffle Boxes- First Generation | Completed | 2005 | 2006 | 1.5074 | 1.0208 | B | 40.0239 | 75000 | 1200 | SJRWMD/ City | SJRWMD - $45,000/ City - $30,000 | N/A | Not provided | 28.3961 | -80.6156 | N/A | N | N
BIRL | 2468 | City of Cape Canaveral | N/A | CC-05 | WWTP Baffle Box | First generation baffle box installation at WWTP. | Baffle Boxes- First Generation | Completed | 2003 | 2004 | 0.38266 | 0.247 | B | 11.6258 | 15000 | 1200 | City | City - $15,000 | N/A | Not provided | 28.3925 | -80.6177 | N/A | N | N
BIRL | 2469 | City of Cape Canaveral | SJRWMD | CC-06 | West Central Boulevard Baffle Box | First generation baffle box installation at West Central Boulevard outfall to Central Ditch. | Baffle Boxes- First Generation | Completed | 2004 | 2005 | 12.4026 | 9.1458 | B | 273.0267 | 75000 | 1200 | SJRWMD/ City | SJRWMD - $45,000/ City - $30,000 | N/A | Not provided | 28.3972 | -80.6015 | N/A | N | N
BIRL | 2470 | City of Cape Canaveral | DEP | CC-07 | Central Ditch Baffle Box (3 count) | Second generation baffle box installations (3) in northern portion of Central Ditch. | Baffle Boxes- Second Generation | Completed | 2008 | 2009 | 175.7113 | 22.3601 | B | 119.1307 | 443003 | 3600 | City/ DEP | DEP - $263,402/ City - $179,601 | G0136 | Not provided | 28.4007 | -80.6071 | N/A | N | N
BIRL | 2487 | City of Cape Canaveral | N/A | CC-09 | Shorewood Drainage Subbasin | Basin with no stormwater discharge. | 100% On-site Retention | Completed | Not provided | Prior to 2013 | 314.5991 | 45.1548 | B | 42.6905 | Not provided | 0 | Private Developer | Not provided | N/A | Not provided | 28.4035 | -80.5974 | N/A | N | N
BIRL | 2610 | City of Cape Canaveral | N/A | CC-11 | Manatee Park Stormwater Improvements | Wet detention pond and swales. | Wet Detention Pond | Completed | 2012 | 2013 | 3.3629 | 0.73025 | B | 11.8824 | 193000 | 5000 | City | City - $193,000 | N/A | Not provided | 28.3944 | -80.6183 | N/A | N | N
BIRL | 2438 | City of Cape Canaveral | N/A | CC-12 | Banana River Park Stormwater Improvements | Stormwater swales. | Grass Swales without Swale Blocks or Raised Culverts | Completed | 2012 | 2013 | 10.2376 | 1.465 | B | 5.5893 | 38000 | 2500 | City | City - $38,000 | N/A | Not provided | 28.3976 | -80.6188 | N/A | N | N
BIRL | 2437 | City of Cape Canaveral | N/A | CC-13 | Exfiltration on North Atlantic Ave | Stormwater swales. | Grass Swales without Swale Blocks or Raised Culverts | Completed | 2014 | 2016 | 39.4808 | 5.987 | B | 36.5412 | 436000 | 5000 | City | City - $436,000 | N/A | Not provided | 28.3963 | -80.6048 | N/A | N | N
BIRL | 2436 | City of Cape Canaveral | DEP | CC-14 | Exfiltration at Canaveral City Park | Stormwater/wastewater vault system. | Exfiltration Trench | Completed | 2015 | 2017 | 108.898 | 18.3246 | B | 31.0944 | 1820500 | 3500 | City/ DEP | DEP - $1,162,662/ City - $657,838 | WW050500/ LP05052 | Not provided | 28.3871 | -80.6018 | N/A | N | N
BIRL | 2434 | City of Cape Canaveral | N/A | CC-18 | Exfiltration Piping Installations | Exfiltration piping installations – 8 locations. | Exfiltration Trench | Completed | N/A | 2014 | N/A | N/A | B | 4500 | 0 | N/A | City | City - $4,500 | N/A | Not Provided | N/A | N/A | N/A | Y | Y
BIRL | 2472 | City of Cape Canaveral | SJRWMD | CC-19 | Reclaimed Water Tank | Reclaimed water system improvements (2.5 million gallon reclaimed water tank). | WWTF Upgrade | Completed | 2014 | 2016 | 2151 | 158 | B | N/A | 3030000 | 10000 | SJRWMD/ City | SJRWMD - $75,000/ City - $2,955,000 | WW050500 | Not provided | 28.3925 | -80.6178 | Not provided | N | N
BIRL | 2444 | City of Cape Canaveral | DEP/ Brevard County/ SOIRL | CC-20 | Central Boulevard Baffle Box Upgrade | Baffle box upgrade to 2nd generation - Central Ditch Baffle Box | Baffle Boxes- Second Generation | Completed | 2017 | 2017 | 327.7941 | 42.8846 | B | 186.8575 | 43700 | 1200 | DEP/ City/ County | DEP - $41,700/ City - $2,000 | NF025 | Not provided | 28.3961 | -80.608 | N/A | N | N
BIRL | 4340 | City of Cape Canaveral | N/A | CC-33 | WWTF SHORELINE RESTORATION | Armor shoreline at WWTF. | Shoreline Stabilization | Completed | Not provided | 2018 | N/A | N/A | B | N/A | 193850 | 1000 | City | City - $193,850 | N/A | Not Provided | 28.3817 | -80.6079 | N/A | Y | Y
BIRL | 4343 | City of Cape Canaveral | N/A | CC-36 | LS #2 SEWER LINE REPLACEMENT | Replacement of sewer line for LS #2. | WWTF Upgrade | Completed | Not provided | 2018 | N/A | N/A | B | N/A | N/A | N/A | N/A | N/A | N/A | Not Provided | 28.3817 | -80.6079 | Not Provided | N/A | N/A
BIRL | 4344 | City of Cape Canaveral | N/A | CC-37 | FORCE MAIN #3 REPLACEMENT | Replacement and relocation of Force Main #3. | WWTF Upgrade | Completed | Not provided | 2018 | N/A | N/A | B | N/A | N/A | N/A | N/A | N/A | N/A | Not Provided | 28.3964 | -80.608 | Not Provided | N/A | N/A
BIRL | 4347 | City of Cape Canaveral | DEP | CC-40 | PARKS SHORELINE RESTORATION | Armor shorelines at two City parks. | Creating/ Enhancing Living Shoreline | Completed | Not provided | 2016 | N/A | N/A | B | 1 | 232664 | 1000 | City/ DEP | DEP - $65,600/ City - $167,064 | NF012 | Not Provided | 28.3945 | -80.6191 | N/A | Y | Y
BIRL | 2471 | City of Cape Canaveral | N/A | CC-08 | Street Sweeping | Sweeping of streets/pedways. | Street Sweeping | Ongoing | 2002 | N/A | 353.0616 | 226.0882 | B | N/A | 12322 | N/A | City | City - $12,322 | N/A | Not provided | N/A | N/A | N/A | N | N
BIRL | 2473 | City of Cape Canaveral | N/A | CC-10 | Education Efforts | FYN (Blue Life); landscape, irrigation, fertilizer, and pet waste ordinances; public service announcements (PSAs); pamphlets; website; Illicit Discharge Program. | Education Efforts | Ongoing | 2013 | N/A | 534.9 | 85.14 | B | N/A | 3100 | 500 | City | City - $3,100 | N/A | Not provided | N/A | N/A | N/A | N | N
BIRL | 2435 | City of Cape Canaveral | N/A | CC-16 | Clean Out of Baffle Boxes | Maintenance of baffle boxes. | BMP Cleanout | Ongoing | 2014 | N/A | 88.1879 | 53.896 | B | N/A | 4500 | 1500 | City | City - $4,500 | N/A | Not provided | N/A | N/A | N/A | N | N
BIRL | 4342 | City of Cape Canaveral | N/A | CC-35 | OXIDATION DITCH REFURBISHMENT | Oxidation Ditch rehab. | BMP Cleanout | Ongoing | Not provided | 2018 | TBD | TBD | B | N/A | N/A | N/A | N/A | N/A | N/A | Not provided | N/A | N/A | N/A | N | N
BIRL | 2405 | City of Cape Canaveral | TBD | CC-15 | Stormwater Pond on West Central Blvd | Wet detention pond and swales. | Wet Detention Pond | Planned | 2021 | 2022 | 232.3409 | 66.1841 | B | 61.3211 | 3130200 | 10000 | TBD | TBD | TBD | TBD | 28.3964 | -80.6029 | N/A | N | N
BIRL | 2482 | City of Cape Canaveral | FDOT | CC-26 | International Drive | Wet detention pond as part of SR A1A Streetscape Project. | Wet Detention Pond | Planned | 2021 | 2022 | TBD | TBD | B | 93.9218 | 708450 | 2500 | FDOT | FDOT - $708,450 | N/A | TBD | 28.3889 | -80.6012 | N/A | Y | Y
BIRL | 2479 | City of Cape Canaveral | Brevard County/ SOIRL | CC-29 | Center Street Pond | Wet detention pond. | Wet Detention Pond | Planned | 2020 | 2021 | TBD | TBD | B | 84.7146 | 277850 | 2500 | City/ County | TBD | N/A | TBD | 28.3822 | -80.6032 | N/A | Y | Y
BIRL | 4341 | City of Cape Canaveral | N/A | CC-34 | BEEMATS INSTALLATION (4 COUNT) | Beemats installation. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Underway | TBD | TBD | 0.026297 | 0.0036572 | B | 1 | 15000 | 2500 | City | City - $15,000 | N/A | TBD | 28.3925 | -80.6186 | N/A | N | N
BIRL | 4345 | City of Cape Canaveral | N/A | CC-38 | CANAVERAL CITY PARK EXFILTRATION SYSTEM EXPANSION | Improvements for discharge of reuse water (same as CC-14). | WWTF Disposal Site | Underway | TBD | TBD | TBD | TBD | B | N/A | N/A | N/A | N/A | N/A | N/A | TBD | 28.3875 | -80.6015 | TBD | Y | Y
BIRL | 4346 | City of Cape Canaveral | SJRWMD | CC-39 | ESTUARY PROPERTY RESTORATION | Habitat and water quality improvements. | Exotic Vegetation Removal | Underway | TBD | 2021 | N/A | N/A | B | 10 | TBD | TBD | SJRWMD/ City | TBD | N/A | TBD | 28.39 | -80.6114 | N/A | N/A | N/A
BIRL | 5159 | City of Cape Canaveral | N/A | CC-41 | Carbon (Micro C) Feed System Installation | WWTF Effluent Polishing System. | WWTF Upgrade | Underway | TBD | 2021 | TBD | TBD | B | N/A | TBD | TBD | City | TBD | N/A | TBD | 28.3925 | -80.6177 | TBD | N/A | N/A

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody