## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile | ProvideAdditionalInfoToCredit
NIRL | 3177 | City of Cocoa | N/A | CC-18 | John Garren Street Realignment & Parking | Roadway and stormwater improvements. | BMP Treatment Train | Canceled | N/A | N/A | N/A | N/A | B | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIRL | 3168 | City of Cocoa | N/A | CC-19 | Brevard Ave. Bioretention and Tree Preservation | Roadway and stormwater improvements. | BMP Treatment Train | Canceled | N/A | N/A | N/A | N/A | B | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIRL | 3053 | City of Cocoa | SOIRL | BC-82 | Stormwater Project - NIRL - Cocoa - Church St Type II Baffle Box | SOIRL-14. See CC-17. | Baffle Boxes- Second Generation | Completed | Not provided | 2018 | TBD | TBD | B | 75.2033 | 233455 | Not provided | DEP TMDL | DEP TMDL - $20,856 | NF025 | Not provided | 28.3534 | -80.72379 | N/A | Y | Y
NIRL | 3072 | City of Cocoa | SJRWMD | CC-01 | Bracco Pond B | SOIRL-01. | Wet Detention Pond | Completed | Not provided | 2014 | 1608.6405 | 491.0925 | B | 630.168 | 35000 | 12000 | City/ SJRWMD | City - $250,000/ SJRWMD - $250,000 | N/A | Not provided | 28.3611985497873 | -80.7322637125207 | N/A | N | N
NIRL | 2999 | City of Cocoa | SJRWMD | CC-02 | Bracco Expansion Area | Provide the community with a park along the ponds. | Wet Detention Pond | Completed | Not provided | 2014 | 103.7369 | 28.3413 | B | 880.6833 | 570762 | 5000 | City/ SJRWMD | City - $262,500/ SJRWMD - $262,500 | N/A | Not provided | 28.3969147778384 | -80.7491260407421 | N/A | N | N
NIRL | 3204 | City of Cocoa | EPA/ SJRWMD | CC-03 | Cocoa Village Park | Subsurface detention storage that is part of a redevelopment project of the Cocoa Village Park and Riverwalk Esplanade areas. | Dry Detention Pond | Completed | 2014 | 2018 | 13.8144 | 1.8293 | B | 13.5 | 330000 | 35000 | City/ SJRWMD | City - $1,250,000/ SJRWMD - $1,250,000 | WM736 | Not provided | 28.3542830404074 | -80.7249888675671 | N/A | N | N
NIRL | 3162 | City of Cocoa | Rockledge/ SOIRL | CC-04 | Morris Pond | Joint project with the City of Rockledge to accommodate previously untreated runoff. | Wet Detention Pond | Completed | Not provided | 2014 | 59.6003 | 16.4524 | B | 16.2 | 247480 | N/A | City of Rockledge | N/A | N/A | Not provided | 28.3499519225776 | -80.727630279036 | N/A | N | N
NIRL | 2778 | City of Cocoa | N/A | CC-05 | North Brevard Avenue Stormwater Treatment Facility | Hydrodynamic separators that remove sediment, trap debris and separate floating oils from runoff. | Hydrodynamic Separators | Completed | Not provided | 2014 | N/A | 1.8241 | B | 11.3 | N/A | N/A | City of Titusville | N/A | N/A | Not provided | 28.3572166853689 | -80.7280586746575 | N/A | N | N
NIRL | 2766 | City of Cocoa | SJRWMD | CC-06 | North Fiske Stormwater Retention Facility | Wet detention pond to reduce the discharge of stormwater runoff into surface waters in the state by complete on-site storage. | 100% On-site Retention | Completed | Not provided | 2014 | 16.2847 | 2.1582 | B | 33.9 | 330000 | 5000 | City | City - $250,000/ SJRWMD - $250,000 | N/A | Not provided | 28.3830836678646 | -80.7426851825722 | N/A | N | N
NIRL | 2765 | City of Cocoa | N/A | CC-07 | Suntree Baffle Box #1 on 2116 IRD | Capture previously untreated runoff. | Baffle Boxes- Second Generation | Completed | Not provided | 2014 | 10.9649 | 1.3334 | B | 5.9 | 80000 | 3500 | City | City - $40,000 | N/A | Not provided | 28.3919676139863 | -80.7433458320404 | N/A | N | N
NIRL | 2763 | City of Cocoa | N/A | CC-09 | Bracco Supplemental Water Supply | Joint project with the WWTP to provide reclaimed water. | WWTF Diversion to Reuse | Completed | Not provided | 2014 | 1102.8964 | 107.7542 | B | N/A | 1200000 | N/A | City | City - $250,000 | N/A | Not provided | 28.36361 | -80.73917 | Not provided | N | N
NIRL | 2762 | City of Cocoa | Community Development Block Grant (CDBG) | CC-10 | Diamond Square Stormwater Improvements | Retrofit existing storm sewer in Dimond Square, including the construction of a wet detention pond. | Wet Detention Pond | Completed | Not provided | 2011 | 41.0353 | 4.2167 | B | 98.6996 | 210000 | 2500 | City | City - $450,000 | N/A | Not provided | 28.3508076803161 | -80.7324508936752 | N/A | N | N
NIRL | 2787 | City of Cocoa | Space Coast Transportation Planning Organization (SCTPO)/ FDOT | CC-12 | Peachtree St. Reconstruction | Roadway and stormwater improvements. | Stormwater System Rehabilitation | Completed | Not provided | 2016 | N/A | N/A | B | 3 | 1700000 | N/A | City/ FDOT | City - $161,250/ FDOT - $1,387,500 | N/A | Not provided | 28.35778 | -80.73889 | N/A | N/A | N/A
NIRL | 2767 | City of Cocoa | N/A | CC-13 | Cocoa Riverfront Park | Amphitheatre and stormwater improvements. Same as Project Number CC-03 where information is captured. Recommend removing from list. | Stormwater System Rehabilitation | Completed | Not provided | 2016 | N/A | N/A | B | 12 | 162000 | N/A | City | N/A | N/A | Not provided | 28.35417 | -80.72417 | N/A | N/A | N/A
NIRL | 3163 | City of Cocoa | N/A | CC-14 | Control Gate | Flood control gate installed at Bracco pond outfall. | Control Structure | Completed | Not provided | 2016 | TBD | TBD | B | N/A | Not provided | N/A | City | City - $50,000 | N/A | Not provided | 28.435 | -80.73806 | N/A | Y | Y
NIRL | 3164 | City of Cocoa | SCTPO/ FDOT | CC-15 | Florida Avenue Improvements | Infiltration through pervious pavers and then ultimately to the AT&T pond. | BMP Treatment Train | Completed | 2016 | 2017 | TBD | TBD | B | 6.9 | 3344222 | 1500 | City/ FDOT | City - $2,587,000/ FDOT - $913,000 | N/A | Not provided | 28.353298 | -80.727723 | N/A | Y | Y
NIRL | 3165 | City of Cocoa | SJRWMD | CC-16 | AT&T Detention Pond Retrofit | Incoming inlets will have 2nd generation baffle boxes. | BMP Treatment Train | Completed | 2016 | 2017 | 391.2669 | 53.9088 | B | 75.0966 | 297877 | 1500 | City/ SJRWMD | City - $199,578/ SJRWMD - $98,299 | N/A | Not provided | 28.351983 | -80.727381 | N/A | N | N
NIRL | 3166 | City of Cocoa | SJRWMD/ SOIRL | CC-17 | Church Street Baffle Box | The goal of this project is to capture and treat stormwater that flows untreated and directly into the Indian River Lagoon. | Baffle Boxes- Second Generation with Media | Completed | TBD | 2018 | 323.0418 | 41.5415 | B | 75 | 173620 | 1500 | City/ SJRWMD/ SOIRL | City - $116,326/ SJRWMD - $50,000/ SOIRL - $20,000 | N/A | Not provided | 28.35333 | -80.72611 | N/A | N | N
NIRL | 4458 | City of Cocoa | TBD | CC-22 | Cocoa Waterfront Stormwater Study | Stormwater Study for the Cocoa waterfront. | Study | Completed | 2018 | 2019 | N/A | N/A | B | N/A | TBD | N/A | City | N/A | N/A | Not provided | N/A | N/A | N/A | N/A | N/A
NIRL | 2764 | City of Cocoa | N/A | CC-08 | Street Sweeping | Pavement cleaning by sweeping, vacuum, or cleaning. | Street Sweeping | Ongoing | Not provided | N/A | 405 | 260 | B | N/A | 80000 | 100000 | City | N/A | N/A | Not provided | N/A | N/A | N/A | N/A | N
NIRL | 2761 | City of Cocoa | N/A | CC-11 | Education Efforts | Fertilizer ordinance. | Education Efforts | Ongoing | Not provided | N/A | 636.615 | 92.575 | B | N/A | N/A | N/A | City | N/A | N/A | Not provided | N/A | N/A | N/A | N/A | N
NIRL | 5360 | City of Cocoa | N/A | CC-24 | Annual Sewer Inspection | Annual sewer inspection and maintenance. | Sanitary Sewer Inspections | Ongoing | Not provided | N/A | N/A | N/A | B | N/A | N/A | 335000 | City | N/A | N/A | Not provided | N/A | N/A | N/A | N/A | N
NIRL | 4457 | City of Cocoa | SJRWMD | CC-21 | Broadmoor Acres and Fiske Blvd. Drainage Improvements | Roadway and stormwater improvements. | Stormwater System Rehabilitation | Planned | Not provided | 2020 | N/A | N/A | B | 7 | TBD | TBD | City/ SJRWMD | TBD | TBD | TBD | 28.36222 | -80.74361 | N/A | N/A | N/A
NIRL | 3160 | City of Cocoa | TBD | CC-20 | U.S. 1 and Forrest Ave. Stormwater Treatment Facility | Develop a dry detention stormwater facility adjacent to U.S. 1. | Dry Detention Pond | Underway | 2018 | 2021 | TBD | TBD | B | 16.39 | TBD | TBD | City | TBD | N/A | TBD | 28.36917 | -80.73444 | N/A | Y | Y
NIRL | 5359 | City of Cocoa | Brevard County | CC-23 | Septic to Sewer Indian River Drive | Design and Install new sewer along Indian River to provide sewer service and remove septic tank use. | OSTDS Phase Out | Underway | Not provided | 2021 | TBD | TBD | B | N/A | 3000000 | N/A | City/SOIRL Tax | N/A | N/A | TBD | TBD | TBD | TBD | Y | Y
NIRL | 5361 | City of Cocoa | N/A | CC-25 | Diamond Square Stormwater PS Feasibility Study | PS study for pumping stormwater across US 1 to Church Street baffle box. | Study | Underway | Not provided | 2020 | N/A | N/A | B | N/A | 26620 | N/A | City | N/A | N/A | TBD | TBD | TBD | N/A | N/A | N/A

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody