## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile
CIRL | 2662 | Indian River County | DEP | IRC-01 | Vero Lake Estates Stormwater Improvements - Phase 1 | Series of swales and canals in a large development leading to large stormwater detention ponds. | Wet Detention Pond | Completed | Not provided | 2002 | 7655.2342 | 1992.618 | SEB | 2407.11 | 1572829 | Not provided | DEP | Not provided | WM803 |  | 27.7486 | -80.5301 | N/A
CIRL | 2661 | Indian River County | DEP | IRC-02 | East Roseland Stormwater Improvements | A stormwater detention pond receiving water from swale systems in a subdivision. | Wet Detention Pond | Completed | Not provided | 2005 | 215.8167 | 57.6154 | SEB | 73.66 | 433134 | 2176 | DEP | Not provided | G0061 |  | 27.8344 | -80.4881 | N/A
CIRL | 2660 | Indian River County | DEP | IRC-03 | East Gifford Stormwater Improvements | A stormwater detention pond receiving water from swale systems in a subdivision. | Wet Detention Pond | Completed | Not provided | 2004 | 129.2243 | 39.2202 | B | 44.11 | 686136 | 2471 | DEP | Not provided | WM836 |  | 27.6699 | -80.41 | N/A
CIRL | 2659 | Indian River County | DEP | IRC-04 | PC Main Screening System | Nutrient removal from measured data. | Regional Stormwater Treatment | Completed | Not provided | 2009 | 1739 | 476 | B | 22800.5042 | 5331908 | 63260 | DEP | Not provided | G0182 |  | 27.6219 | -80.4825 | N/A
CIRL | 2658 | Indian River County | DEP | IRC-05 | Egret Marsh Stormwater Park | Nutrient removal from measured data. | Regional Stormwater Treatment | Completed | Not provided | 2010 | 13406 | 3005 | B | 10104.2434 | 7563274 | 200189 | DEP | Not provided | G0143 |  | 27.5996 | -80.5117 | N/A
CIRL | 2657 | Indian River County | DEP | IRC-06 | PC South (Osprey Marsh) Algal Nutrient Removal Facility | Nutrient removal from measured data. | Regional Stormwater Treatment | Completed | Not provided | 2016 | 6091 | 604 | B | 9781.8789 | 10000000 | 600000 | DEP | Not provided | G0353 |  | 27.5831 | -80.4445 | N/A
CIRL | 2620 | Indian River County | N/A | IRC-07 | Moorhen Marsh Low Energy Aquatic Plant System | This is a managed aquatic plant system that will remove sediment and suspended solids through settling and filtration by aquatic plant roots. The aquatic plants will be harvested on a regular basis. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Underway | 2018 | 2021 | 4888.8244 | 680.4636 | B | 6301.1543 | 8705000 | 84000 | County/ SJRWMD/Florida Legislature | Not provided | LPA0018 |  | 27.6983 | -80.4611 | N/A
CIRL | 5587 | Indian River County | N/A | IRC-07a | Moorhen Marsh Low Energy Aquatic Plant System | This is a managed aquatic plant system that will remove sediment and suspended solids through settling and filtration by aquatic plant roots. The aquatic plants will be harvested on a regular basis. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Underway | 2018 | 2021 | 52.1771 | 6.6673 | SEB | 6301.1543 | 8705000 | 84000 | County/ SJRWMD/Florida Legislature | Not provided | LPA0018 |  | 27.6983 | -80.4611 | N/A
CIRL | 2585 | Indian River County | N/A | IRC-08 | Education Efforts | Fertilizer ordinance, PSAs, website, pamphlets, Illicit Discharge Program, and signs along Indian River Farms WCD canals. | Education Efforts | Ongoing | Not provided | N/A | 16157.7 | 2351.94 | B | N/A | N/A | 52000 | Not provided | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 5588 | Indian River County | N/A | IRC-08a | Education Efforts | Fertilizer ordinance, PSAs, website, pamphlets, Illicit Discharge Program, and signs along Indian River Farms WCD canals. | Education Efforts | Ongoing | Not provided | N/A | 5276.52 | 761.76 | SEB | N/A | N/A | 52000 | Not provided | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 2633 | Indian River County | N/A | IRC-09 | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Not provided | N/A | 273.75 | 175.5 | B | N/A | Not provided | 22050 | Not provided | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 5589 | Indian River County | N/A | IRC-09a | Street Sweeping | Street sweeping. | Street Sweeping | Ongoing | Not provided | N/A | 91.25 | 58.5 | SEB | N/A | Not provided | 22050 | Not provided | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 2605 | Indian River County | N/A | IRC-10 | Storm Drain Cleaning with Vacuum Trucks | Nutrient removal from measured data. | BMP Cleanout | Planned | Not provided | TBD | TBD | TBD | B | TBD | TBD | 19067 | TBD | TBD | N/A |  | Not provided | Not provided | N/A
CIRL | 5590 | Indian River County | N/A | IRC-10a | Storm Drain Cleaning with Vacuum Trucks | Nutrient removal from measured data. | BMP Cleanout | Planned | Not provided | TBD | TBD | TBD | SEB | TBD | TBD | 19067 | TBD | TBD | N/A |  | Not provided | Not provided | N/A
CIRL | 2604 | Indian River County | N/A | IRC-11 | Floating Aquatic Plant Islands in County Stormwater Ponds and Lakes | Nutrient removal from measured data. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Planned | Not provided | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | N/A |  | Not provided | Not provided | N/A
CIRL | 5591 | Indian River County | N/A | IRC-11a | Floating Aquatic Plant Islands in County Stormwater Ponds and Lakes | Nutrient removal from measured data. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Planned | Not provided | TBD | TBD | TBD | SEB | TBD | TBD | TBD | TBD | TBD | N/A |  | Not provided | Not provided | N/A
CIRL | 2603 | Indian River County | N/A | IRC-12 | Spoonbill Marsh Project | Nutrient removal from measured data. | Constructed Wetland Treatment | Completed | Not provided | 2010 | 5700 | 247 | B | 359.4497 | 4200000 | 329143 | Not provided | Not provided | N/A |  | 27.6992 | -80.4032 | N/A
CIRL | 2602 | Indian River County | N/A | IRC-13 | North Relief Canal Mechanical Vegetation/Debris Removal | Removal of aquatic vegetation containing nitrogen and phosphorus that otherwise, would enter IRL and die, releasing nutrients into the lagoon. | Aquatic Vegetation Harvesting | Planned | Not provided | TBD | TBD | TBD | SEB | 6301.1543 | 1000000 | 50000 | County/ Grants | TBD | N/A |  | 27.6983 | -80.4611 | N/A
CIRL | 2718 | Indian River County | N/A | IRC-14 | South Relief Canal Mechanical Vegetation/Debris Removal | Removal of aquatic vegetation containing nitrogen and phosphorus that otherwise, would enter IRL and die, releasing nutrients into the lagoon. | Aquatic Vegetation Harvesting | Planned | Not provided | TBD | TBD | TBD | B | 7154.841 | 1000000 | 50000 | County/ Grants | Not provided | N/A |  | 27.59 | -80.4586 | N/A
CIRL | 2706 | Indian River County | SJRWMD/ DEP/ EPA | IRC-15 | Osprey Acres Floway and Nature Preserve | This is a managed aquatic plant system that will remove nutrients using aquatic vegetation that will be harvested on a regular basis. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Completed | 2017 | 2019 | 8058.4051 | 1129.4708 | B | 9783.6114 | 7500000 | 50000 | DEP/ SJRWMD/ Florida Legislature | 3634536 | NS027 |  | 27.5832 | -80.4445 | N/A

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody