## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile
CIRL | 2860 | City of Melbourne | N/A | MEL-01 | Fee & Apollo Drainage Improvements | No treatment is provided within the existing development; completely a water quality addition. | Wet Detention Pond | Completed | Not provided | 2011 | 27.5373 | 39.5307 | A | 77 | 525161 | Not provided | City | City - $525,161 | N/A |  | 28.0823 | -80.6177 | N/A
CIRL | 2859 | City of Melbourne | N/A | MEL-02 | Education Efforts | Irrigation, fertilizer, pet waste management, and landscaping ordinances; pamphlets, presentations, website, illicit discharge program. | Education Efforts | Ongoing | Not provided | N/A | 3794.7 | 543.42 | A | N/A | Not provided | Not provided | City | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 2858 | City of Melbourne | N/A | MEL-03 | Street Sweeping | Street sweeping in the basin and debris removal. | Street Sweeping | Ongoing | Not provided | N/A | 378 | 187 | A | N/A | N/A | 87500 | City | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 2857 | City of Melbourne | N/A | MEL-04 | Participation in FYN | Participation in FYN Program. Credited in MEL-02. | Education Efforts | Canceled | Not provided | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2846 | City of Melbourne | N/A | MEL-05 | South Croton Baffle Box | Dry retention and baffle box. | BMP Treatment Train | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2925 | City of Melbourne | N/A | MEL-06 | Southwest Park Improvements near Florida Avenue | Installation of baffle box along with pipe replacement. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2017 | TBD | TBD | A | 48 | 582152.62 | Not provided | City | City - $582,153 | N/A |  | 28.0559 | -80.6256 | N/A
CIRL | 2974 | City of Melbourne | N/A | MEL-07 | Melbourne Avenue Existing Baffle Box Upgrade | Upgrade existing 1st generation baffle boxes to 2nd generation baffle boxes with BAM. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2016 | TBD | TBD | A | 12.9 | 12000 | Not provided | City | City - $12,000 | N/A |  | 28.0785 | -80.6012 | N/A
CIRL | 2973 | City of Melbourne | SOIRL | MEL-08 | Penwood Septic to Sewer Conversion | Providing for 12 lots (4 existing and 8 proposed) to be converted to municipal sewer. | Wastewater Service Area Expansion | Underway | 2018 | 2020 | TBD | TBD | A | TBD | 60000 | TBD | City/ SOIRL | 40632 | N/A |  | 28.0751 | -80.6349
CIRL | 2980 | City of Melbourne | SOIRL | MEL-09 | Riverview Park Living Shoreline | Construction of a living shoreline with an oyster breakwater. | Creating/ Enhancing Living Shoreline | Underway | TBD | 2021 | TBD | TBD | A | TBD | 440000 | TBD | City/ SOIRL | 108790 | N/A |  | 28.0717 | -80.5935 | N/A
CIRL | 2959 | City of Melbourne | SOIRL | MEL-10 | Hoag Septic to Sewer Conversion | Providing for 12 lots (7 existing and 5 proposed) to be converted to municipal sewer. | Wastewater Service Area Expansion | Underway | TBD | 2021 | TBD | TBD | A | TBD | 105000 | TBD | City/ SOIRL | 86031 | N/A |  | 28.0655 | -80.5967
CIRL | 2957 | City of Melbourne | SOIRL | MEL-11 | Grant Place Baffle Box | 2nd Generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Underway | 2018 | 2020 | TBD | TBD | A | 103 | 400000 | TBD | City/ SOIRL | 82481 | N/A |  | 28.0761 | -80.6083 | N/A
CIRL | 2979 | City of Melbourne | SOIRL | MEL-12 | Roxy Septic to Sewer Conversion | Five lots with septic systems to be converted to municipal sewer. | Wastewater Service Area Expansion | Planned | 2018 | 2021 | TBD | TBD | A | TBD | 265000 | TBD | City/ SOIRL | 88944 | N/A |  | 28.0764 | -80.6136
CIRL | 4381 | City of Melbourne | SOIRL | MEL-13 | Espanolia Baffle Box | Installation of baffle box along with pipe replacement. | Baffle Boxes- Second Generation with Media | Planned | Not provided | 2022 | 457.8521 | 73.4398 | A | 61 | 550000 | TBD | City/ SOIRL | 105000 | N/A |  | 28.0829 | -80.6302 | N/A
CIRL | 5231 | City of Melbourne | SOIRL/SRF Loan | MEL-14 | Grant Street Water Reclamation Facility Improvements | Improvements include rehabilitation of major treatment elements and structures of facility. | WWTF Nutrient Reduction | Planned | Not provided | TBD | TBD | TBD | A | TBD | 10038000 | Not provided | City of Melbourne/ SOIRL/ SRF | 5415600 | N/A |  | Not provided | Not provided

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody