## NIRL STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile | ProvideAdditionalInfoToCredit
NIRL | 3152 | City of Melbourne | N/A | MEL-06 | Garfield Street Ponds - Lot 12 (North) | Two small dry detention ponds within an existing subdivision (with MEL-7). | Dry Detention Pond | Canceled | N/A | N/A | N/A | N/A | B | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIRL | 3169 | City of Melbourne | N/A | MEL-07 | Garfield Street Ponds - Lot 24 (South) | Two small dry detention ponds within an existing subdivision (with MEL-6). | Dry Detention Pond | Canceled | N/A | N/A | N/A | N/A | B | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIRL | 3146 | City of Melbourne | N/A | MEL-11 | Participation in FYN | Future participation in FYN Program. Credited in MEL-08. | Education Efforts | Canceled | Not provided | N/A | N/A | N/A | B | N/A | N/A | N/A | City | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
NIRL | 3171 | City of Melbourne | N/A | MEL-01 | Fee and Apollo Drainage Improvements | No treatment is provided within the existing development; complete a water quality addition. | Wet Detention Pond | Completed | Not provided | 2010 | 17.0526 | 23.979 | B | 43.6 | 525161 | Not provided | City | Not provided | N/A | Not provided | 28.0854935559057 | -80.6183468185909 | N/A | N | N
NIRL | 3172 | City of Melbourne | N/A | MEL-02 | Dove Street Pond | No treatment is provided within the existing development; complete a water quality addition. | Wet Detention Pond | Completed | Not provided | 2003 | 39.2445 | 10.4326 | B | 14.9 | 156164 | Not provided | City | Not provided | N/A | Not provided | 28.1407618937741 | -80.6372981165378 | N/A | N | N
NIRL | 3173 | City of Melbourne | N/A | MEL-03 | Charles Drive Pipe Replacement | Replaced failing stormwater pipe and created wet detention pond; little to no treatment is provided within existing developments. | Wet Detention Pond | Completed | Not provided | 2010 | 149.5285 | 89.8771 | B | 143.3 | 462644 | Not provided | City | Not provided | N/A | Not provided | 28.1083863336182 | -80.6230686997807 | N/A | N | N
NIRL | 3174 | City of Melbourne | N/A | MEL-04 | Wickham Park Pond | Ponds along with piping upgrades help eliminate flooding within the area along with treatment. | Wet Detention Pond | Completed | Not provided | 2004 | 4180.6711 | 1111.0837 | B | 1796.9 | 250000 | Not provided | City | City - $250,000 | N/A | Not provided | 28.1658908107587 | -80.6716100956786 | N/A | N | N
NIRL | 3175 | City of Melbourne | N/A | MEL-05 | Babcock Street Realignment | Additional treatment was provided for the adjacent drainage basins. | On-line Retention BMPs | Completed | Not provided | 2005 | 133.9586 | 18.8782 | B | 42.3 | 1757186 | Not provided | City | Not provided | N/A | Not provided | 28.1137628090592 | -80.6228893621516 | N/A | N | N
NIRL | 3145 | City of Melbourne | DEP | MEL-10 | Autumn Woods | Construction of a wet detention pond for water quality treatment. | Wet Detention Pond | Completed | 2017 | 2016 | 0 | 0 | B | 56.9096 | 879220 | Not provided | City/ DEP | Not provided | LP05094 | Not provided | 28.1319192062629 | -80.6447698645152 | N/A | N | N
NIRL | 3147 | City of Melbourne | DEP | MEL-12 | South Croton Baffle Box | Dry retention and baffle box. | BMP Treatment Train | Completed | 2016 | 2017 | TBD | TBD | B | 14.8 | 487296 | Not provided | City/ DEP | 191100 | LP05092 | Not provided | 28.1197321226282 | -80.6550285635007 | N/A | Y | Y
NIRL | 3148 | City of Melbourne | DEP | MEL-13 | Bell Street Baffle Box | Construction of a new baffle box. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2017 | 994.6079 | 171.8716 | B | 127.2 | 300000 | Not provided | City/ DEP | 517050 | LP05093 | Not provided | 28.1190836152988 | -80.6502721321051 | N/A | N | N
NIRL | 3149 | City of Melbourne | N/A | MEL-14 | Paradise Baffle Box | Retrofit existing baffle box to upgrade to second generation. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2016 | TBD | TBD | B | 125.6 | 19000 | Not provided | City | City - $19,000 | N/A | Not provided | 28.12111 | -80.5875 | N/A | Y | Y
NIRL | 3159 | City of Melbourne | DEP | MEL-15 | Garfield North Baffle Box | Construction of a new baffle box. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2017 | 501.2342 | 80.2904 | B | 67 | 350000 | Not provided | City/ DEP | Not provided | LP05093 | Not provided | 28.1247575465803 | -80.6275 | N/A | N | N
NIRL | 3151 | City of Melbourne | DEP | MEL-16 | Garfield South Baffle Box | Construction of a new baffle box. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2017 | 92.0878 | 14.6722 | B | 11.8 | 150000 | Not provided | City/ DEP | Not provided | LP05093 | Not provided | 28.1230907475358 | -80.6496455631695 | N/A | N | N
NIRL | 3153 | City of Melbourne | SJRWMD | MEL-18 | Croton Road (Lime) Baffle Box | Installation of baffle box. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2016 | 98.055 | 16.8765 | B | 70 | 260660 | Not provided | City/ SJRWMD | 72752 | Not provided | Not provided | 28.1303537025119 | -80.6565617170867 | N/A | N | N
NIRL | 3154 | City of Melbourne | N/A | MEL-19 | Young Street Existing Baffle Box Upgrade | Upgrade existing 1st generation baffle boxes to 2nd generation baffle boxes with BAM. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2016 | TBD | TBD | B | 7.04 | 20000 | Not provided | City | City - $20,000 | N/A | Not provided | 28.12639 | -80.6275 | N/A | Y | Y
NIRL | 3150 | City of Melbourne | N/A | MEL-24 | South Sarno Drainage Improvements | Retrofit existing ditch system to include dry detention shelves. | Dry Detention Pond | Completed | 2017 | 2015 | 1238.7457 | 173.3101 | B | 1475 | 2227000 | Not provided | City | City - $2,227,000 | N/A | Not provided | 28.11389 | -80.63667 | N/A | N | N
NIRL | 3176 | City of Melbourne | N/A | MEL-25 | Sarno Road Turn Lane | Dry detention above needs for turn lane construction. | Dry Detention Pond | Completed | 2017 | 2018 | 7.2011 | 1.0357 | B | 6.79 | 560000 | Not provided | City | City - $560,000 | N/A | Not provided | 28.12139 | -80.63139 | N/A | N | N
NIRL | 3167 | City of Melbourne | N/A | MEL-08 | Education Efforts | FYN, Irrigation, fertilizer, pet waste management, and landscaping ordinances; pamphlets, presentations, website, Illicit Discharge Program. | Education Efforts | Ongoing | Not provided | N/A | 4667.46 | 685.2 | B | N/A | Not provided | Not provided | City | Not provided | N/A | Not provided | N/A | N/A | N/A | N/A | N
NIRL | 3144 | City of Melbourne | N/A | MEL-09 | Street Sweeping | Street sweeping in the basin and debris removal. | Street Sweeping | Ongoing | Not provided | N/A | 701 | 378 | B | N/A | N/A | 162500 | City | Not provided | N/A | Not provided | N/A | N/A | N/A | N/A | N
NIRL | 3073 | City of Melbourne | SOIRL | BC-87 | Stormwater Project - NIRL - Melbourne - Thrush Dr Baffle Box | SOIRL-35. | Baffle Boxes- Second Generation | Planned | TBD | 2019 | TBD | TBD | B | 422.9518 | 322200 | TBD | SOIRL/ City | 322200 | N/A | TBD | Not provided | Not provided | N/A | Y | Y
NIRL | 3061 | City of Melbourne | SOIRL | BC-90 | Stewart Rd Dry Retrofit | Stormwater Project - CIRL - Melbourne, SOIRL-39. | Dry Detention Pond | Planned | TBD | 2020 | TBD | TBD | B | TBD | 18344 | TBD | SOIRL/ City | 18344 | N/A | TBD | 28.15588 | -80.67001 | N/A | Y | Y
NIRL | 3179 | City of Melbourne | SOIRL | MEL-23 | Leewood Forest Wetland and Baffle Box | The proposed project consists of construction a wetland treatment area and baffle box to provide stormwater quality treatment. | Constructed Wetland Treatment | Planned | TBD | TBD | TBD | TBD | B | 149.5 | 2590000 | TBD | City/ SOIRL | TBD | N/A | TBD | 28.1348 | -80.6649 | N/A | Y | Y
NIRL | 3180 | City of Melbourne | SOIRL | MEL-26 | Apollo/GA Baffle Box | 2nd generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Planned | 2019 | 2019 | TBD | TBD | B | 854 | 825000 | TBD | City/ SOIRL | 297522 | N/A | TBD | 28.1125 | -80.63361 | N/A | Y | Y
NIRL | 3181 | City of Melbourne | SOIRL | MEL-27 | Stewart Road WQ Project | Installation of BAM filter box on existing culvert. | Biosorption Activated Media (BAM) | Planned | 2020 | 2020 | TBD | TBD | B | 36 | 435000 | TBD | City/ SOIRL | 18344 | N/A | TBD | 28.14722 | -80.64694 | N/A | Y | Y
NIRL | 5362 | City of Melbourne | SOIRL/ SRF Loan | MEL-31 | Grant Street Water Reclamation Facility Improvements | Improvements include rehabilitation of major treatment elements and structures of facility. | WWTF Nutrient Reduction | Planned | N/A | TBD | TBD | TBD | B | TBD | 10038000 | TBD | City/ SOIRL/ SRF | 5415600 | N/A | TBD | N/A | N/A | TBD | N | Y
NIRL | 5363 | City of Melbourne | TBD | MEL-32 | Dove Street Pond Retrofit | Retrofting of existing pond to enhance treatment potential. | BMP Treatment Train | Planned | N/A | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | N/A | TBD | N/A | N/A | N/A | Y | Y
NIRL | 5364 | City of Melbourne | TBD | MEL-33 | Melbourne Cemetery Baffle Box | 2nd generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Planned | N/A | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | N/A | TBD | N/A | N/A | N/A | Y | Y
NIRL | 5365 | City of Melbourne | TBD | MEL-34 | Funeral Home Baffle Box | 2nd generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Planned | N/A | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | N/A | TBD | N/A | N/A | N/A | Y | Y
NIRL | 5366 | City of Melbourne | TBD | MEL-35 | Melbourne High Baffle Box | 2nd generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Planned | N/A | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | N/A | TBD | N/A | N/A | N/A | Y | Y
NIRL | 3057 | City of Melbourne | SOIRL | BC-86 | Stormwater Project - NIRL - Melbourne - Cliff Creek Baffle Box | SOIRL-34. | Baffle Boxes- Second Generation | Underway | TBD | 2019 | TBD | TBD | B | 515.41 | 347781 | TBD | SOIRL/ City | 347781 | N/A | TBD | 28.15738 | -80.64935 | N/A | Y | Y
NIRL | 3143 | City of Melbourne | DEP | MEL-17 | Sherwood Stormwater Quality Project | Construction of a new wet detention pond for a subdivision without any treatment. | Wet Detention Pond | Underway | 2016 | 2020 | TBD | TBD | B | 246.1714 | 2168800 | TBD | City/ DEP | 400000 | NS013 | TBD | 28.1755849842337 | -80.6627036800513 | N/A | Y | Y
NIRL | 3155 | City of Melbourne | SOIRL | MEL-20 | Thrush Drive Baffle Box | Baffle Box - 2nd generation with media filter. | Baffle Boxes- Second Generation with Media | Underway | 2018 | TBD | TBD | TBD | B | 422 | 450000 | TBD | City/ SOIRL | 322200 | N/A | TBD | 28.1561 | -80.6504 | N/A | Y | Y
NIRL | 3156 | City of Melbourne | SOIRL | MEL-21 | Cliff Creek Baffle Box | Baffle Box - 2nd generation with media filter. | Baffle Boxes- Second Generation with Media | Underway | 2016 | TBD | TBD | TBD | B | 515 | 450000 | TBD | City/ SOIRL | 347781 | N/A | TBD | 28.1444 | -80.6349 | N/A | Y | Y
NIRL | 3157 | City of Melbourne | SOIRL | MEL-22 | Riverside Drive Septic to Sewer Conversion | Providing for 12 lots to be converted to municipal sewer. | Wastewater Service Area Expansion | Underway | 2016 | TBD | TBD | TBD | B | TBD | 215000 | TBD | City/ SOIRL | 265960 | N/A | TBD | 28.1691 | -80.6451 | TBD | Y | Y
NIRL | 4459 | City of Melbourne | SOIRL | MEL-28 | Cherry Street Baffle Box | 2nd generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Underway | Not provided | 2020 | 1017.3906 | 161.0921 | B | 1307 | 550000 | Not provided | City/ SOIRL | 92120 | N/A | TBD | 28.100253 | -80.617162 | N/A | N | N
NIRL | 4460 | City of Melbourne | SOIRL | MEL-29 | Spring Creek Baffle Box | 2nd generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Underway | Not provided | 2020 | 812.9534 | 123.1028 | B | 110 | 450000 | Not provided | City/ SOIRL | 99358 | N/A | TBD | 28.133253 | -80.635986 | N/A | N | N
NIRL | 4461 | City of Melbourne | SOIRL | MEL-30 | Brevard County Partnership Projects | Project approved by the SOIRL Project Plan not built by the City of Melbourne. | BMP Treatment Train | Underway | TBD | TBD | TBD | TBD | B | TBD | TBD | TBD | SOIRL | TBD | N/A | TBD | TBD | TBD | N/A | Y | Y

## CIRL STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile | ProvideAdditionalInfoToCredit
CIRL | 2857 | City of Melbourne | N/A | MEL-04 | Participation in FYN | Participation in FYN Program. Credited in MEL-02. | Education Efforts | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CIRL | 2846 | City of Melbourne | N/A | MEL-05 | South Croton Baffle Box | Dry retention and baffle box. | BMP Treatment Train | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
CIRL | 2860 | City of Melbourne | N/A | MEL-01 | Fee & Apollo Drainage Improvements | No treatment is provided within the existing development; completely a water quality addition. | Wet Detention Pond | Completed | Not provided | 2011 | 27.5373 | 39.5307 | A | 77 | 525161 | Not provided | City | City - $525,161 | N/A | Not provided | 28.0823 | -80.6177 | N/A | N | N
CIRL | 2925 | City of Melbourne | N/A | MEL-06 | Southwest Park Improvements near Florida Avenue | Installation of baffle box along with pipe replacement. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2017 | TBD | TBD | A | 48 | 582152.62 | Not provided | City | City - $582,153 | N/A | Not provided | 28.0559 | -80.6256 | N/A | Y | Y
CIRL | 2974 | City of Melbourne | N/A | MEL-07 | Melbourne Avenue Existing Baffle Box Upgrade | Upgrade existing 1st generation baffle boxes to 2nd generation baffle boxes with BAM. | Baffle Boxes- Second Generation with Media | Completed | 2016 | 2016 | TBD | TBD | A | 12.9 | 12000 | Not provided | City | City - $12,000 | N/A | Not provided | 28.0785 | -80.6012 | N/A | Y | Y
CIRL | 2859 | City of Melbourne | N/A | MEL-02 | Education Efforts | Irrigation, fertilizer, pet waste management, and landscaping ordinances; pamphlets, presentations, website, illicit discharge program. | Education Efforts | Ongoing | Not provided | N/A | 3794.7 | 543.42 | A | N/A | Not provided | Not provided | City | Not provided | N/A | Not provided | N/A | N/A | N/A | N/A | N
CIRL | 2858 | City of Melbourne | N/A | MEL-03 | Street Sweeping | Street sweeping in the basin and debris removal. | Street Sweeping | Ongoing | Not provided | N/A | 378 | 187 | A | N/A | N/A | 87500 | City | Not provided | N/A | Not provided | N/A | N/A | N/A | N/A | N
CIRL | 2979 | City of Melbourne | SOIRL | MEL-12 | Roxy Septic to Sewer Conversion | Five lots with septic systems to be converted to municipal sewer. | Wastewater Service Area Expansion | Planned | 2018 | 2021 | TBD | N/A | A | TBD | 265000 | TBD | City/ SOIRL | 88944 | N/A | TBD | 28.0764 | -80.6136 | TBD | Y | Y
CIRL | 4381 | City of Melbourne | SOIRL | MEL-13 | Espanolia Baffle Box | Installation of baffle box along with pipe replacement. | Baffle Boxes- Second Generation with Media | Planned | TBD | 2022 | 457.8521 | 73.4398 | A | 61 | 550000 | TBD | City/ SOIRL | 105000 | N/A | TBD | 28.0829 | -80.6302 | N/A | N | N
CIRL | 5231 | City of Melbourne | SOIRL/SRF Loan | MEL-14 | Grant Street Water Reclamation Facility Improvements | Improvements include rehabilitation of major treatment elements and structures of facility. | WWTF Nutrient Reduction | Planned | TBD | TBD | TBD | TBD | A | TBD | 10038000 | TBD | City of Melbourne/ SOIRL/ SRF | 5415600 | N/A | TBD | TBD | TBD | TBD | N | Y
CIRL | 2973 | City of Melbourne | SOIRL | MEL-08 | Penwood Septic to Sewer Conversion | Providing for 12 lots (4 existing and 8 proposed) to be converted to municipal sewer. | Wastewater Service Area Expansion | Underway | 2018 | 2020 | TBD | N/A | A | TBD | 60000 | TBD | City/ SOIRL | 40632 | N/A | TBD | 28.0751 | -80.6349 | TBD | Y | Y
CIRL | 2980 | City of Melbourne | SOIRL | MEL-09 | Riverview Park Living Shoreline | Construction of a living shoreline with an oyster breakwater. | Creating/ Enhancing Living Shoreline | Underway | TBD | 2021 | TBD | TBD | A | TBD | 440000 | TBD | City/ SOIRL | 108790 | N/A | TBD | 28.0717 | -80.5935 | N/A | Y | Y
CIRL | 2959 | City of Melbourne | SOIRL | MEL-10 | Hoag Septic to Sewer Conversion | Providing for 12 lots (7 existing and 5 proposed) to be converted to municipal sewer. | Wastewater Service Area Expansion | Underway | TBD | 2021 | TBD | N/A | A | TBD | 105000 | TBD | City/ SOIRL | 86031 | N/A | TBD | 28.0655 | -80.5967 | TBD | Y | Y
CIRL | 2957 | City of Melbourne | SOIRL | MEL-11 | Grant Place Baffle Box | 2nd Generation baffle box with BAM. | Baffle Boxes- Second Generation with Media | Underway | 2018 | 2020 | TBD | TBD | A | 103 | 400000 | TBD | City/ SOIRL | 82481 | N/A | TBD | 28.0761 | -80.6083 | N/A | Y | Y

## CIRL Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## NIRL Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody