## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile
CIRL | 2948 | City of Palm Bay | N/A | PB-01 | Basin 11 | Not provided. | Muck Removal/Restoration Dredging | Completed | Not provided | 2009 | Not provided | Not provided | A | Not provided | 1866695 | Not provided | Not provided | Not provided | N/A |  | Not provided | Not provided | N/A
CIRL | 2949 | City of Palm Bay | N/A | PB-02 | Chace Lane Pond Modifications | Not provided. | Dry Detention Pond | Completed | Not provided | 2001 | 77.5697 | 11.138 | A | 91.1934 | 20290 | Not provided | Not provided | Not provided | N/A |  | 28.0208 | -80.5879 | N/A
CIRL | 2950 | City of Palm Bay | N/A | PB-03 | Glenham Drive Sidewalks Improvements | Not provided. | Dry Detention Pond | Completed | Not provided | 2014 | 10.6929 | 1.5252 | A | 12.2 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0322 | -80.5932 | N/A
CIRL | 2951 | City of Palm Bay | N/A | PB-04 | Basin 7 Stormwater Improvements Phase II | Not provided. | Wet Detention Pond | Completed | Not provided | 2009 | 351.9083 | 101.1494 | A | 146.5 | 79109 | Not provided | Not provided | Not provided | N/A |  | 28.0334 | -80.5906 | N/A
CIRL | 2952 | City of Palm Bay | N/A | PB-05 | Boundary Canal Trail Phase 3 | Not provided. | Baffle Boxes- First Generation | Completed | Not provided | 2014 | 17.3373 | 11.6538 | A | 365.9 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0164 | -80.5821 | N/A
CIRL | 2953 | City of Palm Bay | N/A | PB-06 | Boundary Canal Phase II Stormwater Improvement | Not provided. | On-line Retention BMPs | Completed | Not provided | 2014 | 3276.0116 | 382.8013 | A | 632.7 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0076 | -80.5796 | N/A
CIRL | 2954 | City of Palm Bay | N/A | PB-07 | Boundary Canal Phase I Baffle Box Installation | Not provided. | Baffle Boxes- First Generation | Completed | Not provided | 2014 | 0.14756 | 0.079316 | A | 632.7 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0076 | -80.5796 | N/A
CIRL | 2956 | City of Palm Bay | N/A | PB-08 | Norwood Street Baffle Box Installation | Not provided. | Baffle Boxes- First Generation | Completed | Not provided | 2014 | 16.4716 | 11.8261 | A | 528.8 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0272 | -80.6283 | N/A
CIRL | 2970 | City of Palm Bay | N/A | PB-09 | Basin 1 Drainage Improvements Phase 1 (East of US 1) | Not provided. | Wet Detention Pond | Completed | Not provided | 2007 | 109.6134 | 9.5358 | A | 136.54 | 22247 | Not provided | Not provided | Not provided | N/A |  | 28.0593 | -80.597 | N/A
CIRL | 2958 | City of Palm Bay | N/A | PB-10 | Basin 13 Stormwater Improvements | Not provided. | Wet Detention Pond | Completed | Not provided | 2006 | 143.4578 | 36.9496 | A | 42.38 | 200419 | Not provided | Not provided | Not provided | N/A |  | 28.0248 | -80.613 | N/A
CIRL | 2946 | City of Palm Bay | N/A | PB-11 | Powell's Subdivision Paving & Drainage Improvements | Not provided. | Wet Detention Pond | Completed | Not provided | 2000 | 176.0512 | 82.4304 | A | 123.557 | 147478 | Not provided | Not provided | Not provided | N/A |  | 28.0536 | -80.6008 | N/A
CIRL | 2960 | City of Palm Bay | N/A | PB-12 | Port Malabar Unit 40 Drainage Improvements North | Not provided. | Wet Detention Pond | Completed | Not provided | 2015 | 736.6567 | 181.7822 | A | 224.327 | 23778 | Not provided | Not provided | Not provided | N/A |  | 27.991 | -80.6181 | N/A
CIRL | 2947 | City of Palm Bay | N/A | PB-13 | Mandarin Ditch (South) | Not provided. | Grass swales without swale blocks or raised culverts | Completed | Not provided | 2006 | 212.9422 | 29.7689 | A | 73.04 | 308797 | Not provided | Not provided | Not provided | N/A |  | 28.0242 | -80.5961 | N/A
CIRL | 2969 | City of Palm Bay | N/A | PB-14 | Basin 3 Main Street Parking Lot | Treatment train with PB-15. | Pervious Pavement Systems | Completed | Not provided | 2008 | 1427.6758 | 205.6032 | A | 346.0507 | 4845 | Not provided | Not provided | Not provided | N/A |  | 28.043 | -80.5901 | N/A
CIRL | 2968 | City of Palm Bay | N/A | PB-15 | Basin 3 Main Street Improvements Channel Alignment | Treatment train with PB-14. | BMP Treatment Train | Completed | Not provided | 2010 | 1604.1442 | 231.0168 | A | 358.6 | 403561 | Not provided | Not provided | Not provided | N/A |  | 28.043 | -80.5901 | N/A
CIRL | 2967 | City of Palm Bay | N/A | PB-16 | Street Sweeping | Not provided. | Street Sweeping | Ongoing | Not provided | N/A | 57 | 36 | A | N/A | 8900 | Not provided | Not provided | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 2966 | City of Palm Bay | N/A | PB-17 | Turkey Creek Maintenance Dredging | Not provided. | Muck Removal/Restoration Dredging | Completed | Not provided | 2007 | Not provided | Not provided | A | Not provided | 255241 | Not provided | Not provided | Not provided | N/A |  | Not provided | Not provided | N/A
CIRL | 2965 | City of Palm Bay | N/A | PB-18 | Turkey Creek Maintenance Dredging - Sump | Not provided. | Muck Removal/Restoration Dredging | Completed | Not provided | 2014 | Not provided | Not provided | A | Not provided | Not provided | Not provided | Not provided | Not provided | N/A |  | Not provided | Not provided | N/A
CIRL | 2964 | City of Palm Bay | N/A | PB-19 | Anglers Drive | Not provided. | Baffle Boxes- First Generation | Completed | Not provided | 2008 | 0.85041 | 0.57537 | A | 12.12 | 85000 | Not provided | Not provided | Not provided | N/A |  | 28.0343 | -80.5782 | N/A
CIRL | 2963 | City of Palm Bay | N/A | PB-20 | Worth Court | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 2014 | 0.13 | 0.1 | A | 5.0008 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0319 | -80.5769 | N/A
CIRL | 2962 | City of Palm Bay | SJRWMD/ DEP | PB-21 | Basin 9 (Harris Pond) | Not provided. | Wet Detention Pond | Completed | Not provided | 2010 | TBD | TBD | A | 442.5173 | 294519 | Not provided | SJRWMD/ DEP | Not provided | Not provided |  | 28.0349 | -80.5982 | N/A
CIRL | 2961 | City of Palm Bay | N/A | PB-22 | Wild Rose BMP | Not provided. | Baffle Boxes- First Generation | Completed | Not provided | 2014 | 0.21198 | 0.14325 | A | 4.5881 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0284 | -80.5835 | N/A
CIRL | 2975 | City of Palm Bay | N/A | PB-24 | Port Malabar Inlet Inserts | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 2010 | Not provided | Not provided | A | 29.2521 | 19518 | Not provided | Not provided | Not provided | N/A |  | 28.0168 | -80.5919 | N/A
CIRL | 2976 | City of Palm Bay | N/A | PB-25 | Kent Street Baffle Box | Not provided. | Baffle Boxes- First Generation | Completed | Not provided | 2009 | 1.0641 | 0.7129 | A | 20.77 | 50000 | Not provided | Not provided | Not provided | N/A |  | 28.0071 | -80.612 | N/A
CIRL | 2977 | City of Palm Bay | N/A | PB-26 | PMU1 North (Florin Pond) | Not provided. | Dry Detention Pond | Completed | Not provided | 2000 | TBD | TBD | A | 25.86 | 150000 | Not provided | Not provided | Not provided | N/A |  | Not provided | Not provided | N/A
CIRL | 2978 | City of Palm Bay | N/A | PB-27 | Education Efforts | FYN, ordinances, pamphlets, PSAs, website, illicit discharge program. | Education Efforts | Ongoing | Not provided | N/A | 12342.78 | 1787.1 | A | N/A | 1866695 | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2971 | City of Palm Bay | N/A | PB-28 | Vance Circle-Drainage Improvements | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2972 | City of Palm Bay | DEP | PB-29 | Basin 1 Drainage Improvements Phase 1 | Baffle box, modular wetlands, and upward filter. | BMP Treatment Train | Completed | Not provided | 2017 | Not provided | Not provided | A | 175.0182 | 250000 | Not provided | DEP | DEP - $250,000 | S0876 |  | 28.0593 | -80.597 | N/A
CIRL | 2955 | City of Palm Bay | N/A | PB-30 | Troutman/ Clearmond Drainage Pond | Roadway widening from rural to urban section with underground drainage. | Dry Detention Pond | Completed | Not provided | 2014 | 7.0428 | 0.97944 | A | 7.89 | 5400000 | Not provided | Not provided | Not provided | N/A |  | 28.0285 | -80.6048 | N/A
CIRL | 2911 | City of Palm Bay | N/A | PB-31 | Port Malabar Drainage Improvements Central | Modification of existing drainage system redesigned to promote infiltration of stormwater runoff. The system has perforated piping, baffles, and infiltration trenches to encourage percolation. | Exfiltration Trench | Completed | Not provided | 2013 | 11.8426 | 1.6686 | A | 11.84 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.023 | -80.5749 | N/A
CIRL | 2926 | City of Palm Bay | N/A | PB-32 | Kingswood Drainage Pond | Modification and expansion of existing drainage pond to provide additional stormwater capacity, attenuation, and treatment. | Dry Detention Pond | Completed | Not provided | 2015 | 60.6058 | 8.3199 | A | 62.42 | Not provided | Not provided | Not provided | Not provided | N/A |  | 28.0555 | -80.5918 | N/A
CIRL | 2937 | City of Palm Bay | DEP | PB-33 | Basin 3 Bayfront Community SW Improvements (Koske Pond Phase 1) | Baffle box, modular wetlands, and upward filter. | BMP Treatment Train | Completed | Not provided | 2017 | TBD | TBD | A | Not provided | 500000 | Not provided | DEP | DEP - $500,000 | S0801 |  | 28.039 | -80.585 | N/A
CIRL | 2924 | City of Palm Bay | SJRWMD/ DEP | PB-34 | Stormwater Treatment at City Marina | Baffle box, modular wetlands, and upward filter. | BMP Treatment Train | Planned | Not provided | TBD | TBD | TBD | A | TBD | 890050 | TBD | SJRWMD/ DEP | TBD | LP05073 |  | Not provided | Not provided | N/A
CIRL | 2922 | City of Palm Bay | N/A | PB-35 | Education Efforts | FYN, ordinances, pamphlets, PSAs, website, illicit discharge program. | Education Efforts | Ongoing | Not provided | N/A | 185.22 | 24.78 | SEB | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2921 | City of Palm Bay | N/A | PB-37 | Norwood Baffle Box Retrofit | N/A | Baffle Boxes- First Generation | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2920 | City of Palm Bay | N/A | PB-38 | Victoria Pond | N/A | Baffle Boxes- First Generation | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2910 | City of Palm Bay | N/A | PB-39 | Goode Park | N/A | Baffle Boxes- First Generation | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2918 | City of Palm Bay | N/A | PB-40 | Florin Pond | N/A | Baffle Boxes- First Generation | Canceled | N/A | N/A | N/A | N/A | A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2927 | City of Palm Bay | N/A | PB-41 | Turkey Creek Shoreline Restoration | Bayfront shoreline restoration to place fill addressing hurricane erosion damage from 2016 and 2017. | Shoreline Stabilization | Completed | 2018 | 2018 | TBD | TBD | A | TBD | 180000 | TBD | DEO | DEO - $177,300/ City - $2,700 | N/A |  | 28.036 | -80.582 | N/A
CIRL | 2916 | City of Palm Bay | N/A | PB-42 | Unit 48 Drainage Improvements - Emerson | Expansion of wet detention system and adjustment of control structures. | Wet Detention Pond | Planned | TBD | 2019 | TBD | TBD | A | TBD | TBD | TBD | City | TBD | N/A |  | 28.03 | -80.691 | N/A
CIRL | 2915 | City of Palm Bay | Brevard County/ Brevard Zoo | PB-43 | Bayfront/Palm Bay Living Shoreline at Turkey Creek | Installation of oyster mats and plantings to uptake nutrients from sheet flow. | Creating/ Enhancing Living Shoreline | Canceled | 2018 | 2019 | N/A | N/A | A | TBD | 113000 | TBD | Brevard County | Brevard County - $113,000 | N/A |  | 28.036 | -80.582 | N/A
CIRL | 2914 | City of Palm Bay | N/A | PB-44 | Basin 3 Bayfront Community SW Improvements (Koske Pond Phases 2 and 3) | Expansion of wet pond. | Wet Detention Pond | Planned | TBD | 2019 | TBD | TBD | A | TBD | TBD | 200 | TBD | TBD | N/A |  | 28.039 | -80.585 | N/A
CIRL | 2913 | City of Palm Bay | N/A | PB-45 | Basin 1 Drainage Improvements Phase 2B Victoria Pond (West of U.S. 1) | Baffle box and upflow filter. | BMP Treatment Train | Planned | TBD | 2019 | TBD | TBD | A | 175 | TBD | TBD | TBD | TBD | N/A |  | 28.061 | -80.596 | N/A

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody