## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile | ProvideAdditionalInfoToCredit
NIRL | 3107 | City of Rockledge | Not provided | ROCK-22 | Treatment Missing from Model | Wet detention ponds – missing from model. Project canceled after model update. | BMP Missing from Model | Canceled | 1986 | Prior to 2013 | N/A | N/A | B | 383.2 | Not provided | Not provided | Not provided | Not provided | N/A | N/A | Not provided | Not provided | N/A | N/A | N/A
NIRL | 3050 | City of Rockledge | SOIRL | BC-79 | Breeze Swept Septic to Sewer | Hood up to sewer - SOIRL-01. | Wastewater Service Area Expansion | Completed | Not provided | 2017 | TBD | TBD | B | Not provided | 3400000 | Not provided | City/ SOIRL | 880530 | N/A | Not provided | 28.14488 | -80.63526 | Not provided | Y | Y
NIRL | 3182 | City of Rockledge | SOIRL | ROCK-01 | Orange Avenue Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2009 | 18.6639 | 2.3266 | B | 10.4 | 8600 | 2555 | Not provided | Not provided | N/A | Not provided | 28.3358844529754 | -80.7191337236133 | N/A | N | N
NIRL | 3183 | City of Rockledge | SOIRL | ROCK-02 | Barton Avenue Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2009 | 50.7479 | 6.6243 | B | 27.1 | 9350 | 2555 | Not provided | Not provided | N/A | Not provided | 28.3344067956925 | -80.7185547816069 | N/A | N | N
NIRL | 3184 | City of Rockledge | Not provided | ROCK-03 | Hardee Circle Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2009 | 26.3799 | 3.1567 | B | 14.5995 | 43420 | 2555 | Not provided | Not provided | N/A | Not provided | 28.3450210169474 | -80.7233373119782 | N/A | N | N
NIRL | 3194 | City of Rockledge | Not provided | ROCK-04 | Rockledge Avenue Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2004 | 69.9682 | 8.4536 | B | 40.9738 | 21448 | 3682 | Not provided | Not provided | N/A | Not provided | 28.3395133018598 | -80.7222970327956 | N/A | N | N
NIRL | 3186 | City of Rockledge | Not provided | ROCK-05 | Bougainvillea Drive Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2000 | 58.0213 | 6.7048 | B | 35.7392 | 29495 | 2566 | Not provided | Not provided | N/A | Not provided | 28.3428566283423 | -80.7236854677754 | N/A | N | N
NIRL | 3178 | City of Rockledge | Not provided | ROCK-06 | Park Avenue Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2007 | 23.4704 | 2.77 | B | 13.1825 | 52529 | 2555 | Not provided | Not provided | N/A | Not provided | 28.3220234729787 | -80.7129191180079 | N/A | N | N
NIRL | 3188 | City of Rockledge | Not provided | ROCK-07 | Little John Lane Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2004 | 21.5932 | 2.5627 | B | 11.8698 | 60000 | 2555 | Not provided | Not provided | N/A | Not provided | 28.3470602607763 | -80.7239221412234 | N/A | N | N
NIRL | 3189 | City of Rockledge | Not provided | ROCK-08 | Fernwood Drive Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | Prior to 2013 | 23.3714 | 2.8507 | B | 12.8809 | 55750 | Not provided | Not provided | Not provided | N/A | Not provided | 28.3377094925977 | -80.7199146805068 | N/A | N | N
NIRL | 3190 | City of Rockledge | Not provided | ROCK-09 | Valencia Drive Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2008 | 41.627 | 4.9661 | B | 22.8785 | 58960 | 2555 | Not provided | Not provided | N/A | Not provided | 28.3364789605983 | -80.721467032622 | N/A | N | N
NIRL | 3191 | City of Rockledge | Not provided | ROCK-10 | Knollwood Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2002 | 44.1547 | 5.2796 | B | 24.3 | 68248 | 3682 | Not provided | Not provided | N/A | Not provided | 28.3248052088542 | -80.7147073069673 | N/A | N | N
NIRL | 3192 | City of Rockledge | Not provided | ROCK-11 | Sutton Street Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2011 | 14.999 | 1.943 | B | 8 | Not provided | Not provided | Not provided | Not provided | N/A | Not provided | 28.3489002160579 | -80.7239852006912 | N/A | N | N
NIRL | 3193 | City of Rockledge | Not provided | ROCK-12 | River Groves Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2011 | 13.1252 | 1.5685 | B | 7.4 | Not provided | Not provided | Not provided | Not provided | N/A | Not provided | 28.3157608983968 | -80.709712527472 | N/A | N | N
NIRL | 3126 | City of Rockledge | Not provided | ROCK-13 | Summer Place Baffle Box | The second generation (nutrient separating) baffle box includes a wire mesh box that captures vegetative debris, litter, and other materials from settling in the water in the bottom of the box, thereby preventing leaching of the nutrients. | Baffle Boxes- Second Generation | Completed | Not provided | 2011 | 17.1487 | 2.0211 | B | 9.8 | 35000 | Not provided | Not provided | Not provided | N/A | Not provided | 28.32066271625 | -80.7120550940693 | N/A | N | N
NIRL | 3075 | City of Rockledge | Not provided | ROCK-14 | Sweet Street Swale | Swales are designed to infiltrate a defined quantity of runoff (the treatment volume) through the permeable soils of the swale floor and side slopes into the shallow ground water aquifer immediately following a storm event. | Grass Swales without Swale Blocks or Raised Culverts | Completed | Not provided | 2011 | 27.7853 | 4.1038 | B | 8 | 10000 | Not provided | Not provided | Not provided | N/A | Not provided | 28.3479926808053 | -80.7239701099827 | N/A | N | N
NIRL | 3158 | City of Rockledge | Not provided | ROCK-15 | Community Park of Rockledge Regional Facility Phase 1 | "Wet detention" means the collection and temporary storage of stormwater in a permanently wet impoundment in such a manner as to provide for treatment through physical, chemical, and biological processes with subsequent gradual release of the stormwater. | Wet Detention Pond | Completed | Not provided | 2004 | 13.5089 | 1.6891 | B | 25.6 | 50000 | 23974 | Not provided | Not provided | N/A | Not provided | 28.3063587940788 | -80.7141055742677 | N/A | N | N
NIRL | 3093 | City of Rockledge | Not provided | ROCK-16 | Pineland Park Unit Three | "Wet detention" means the collection and temporary storage of stormwater in a permanently wet impoundment in such a manner as to provide for treatment through physical, chemical, and biological processes with subsequent gradual release of the stormwater. | Wet Detention Pond | Completed | Not provided | 2009 | 0.45083 | 0 | B | 54.3 | 100000 | 6234 | Not provided | Not provided | N/A | Not provided | 28.3197590816274 | -80.7240310122594 | N/A | N | N
NIRL | 3094 | City of Rockledge | DEP | ROCK-17 | Barton Park Regional Detention System | "Wet detention" means the collection and temporary storage of stormwater in a permanently wet impoundment in such a manner as to provide for treatment through physical, chemical, and biological processes with subsequent gradual release of the stormwater. | Wet Detention Pond | Completed | Not provided | 2010 | 2597.5141 | 670.0999 | B | 757 | 2600000 | 40000 | DEP | Not provided | S0538 | Not provided | 28.3418660790948 | -80.7285111576339 | N/A | N | N
NIRL | 3095 | City of Rockledge | Not provided | ROCK-18 | Florida Avenue Stormwater Facility | "Wet detention" means the collection and temporary storage of stormwater in a permanently wet impoundment in such a manner as to provide for treatment through physical, chemical, and biological processes with subsequent gradual release of the stormwater. | Wet Detention Pond | Completed | Not provided | 2010 | 37.6972 | 18.376 | B | 25.2 | 435000 | 40950 | Not provided | Not provided | N/A | Not provided | 28.3475981329594 | -80.7270431448797 | N/A | N | N
NIRL | 3092 | City of Rockledge | Not provided | ROCK-19 | Police Department Pond | "Wet detention" means the collection and temporary storage of stormwater in a permanently wet impoundment in such a manner as to provide for treatment through physical, chemical, and biological processes with subsequent gradual release of the stormwater. | Wet Detention Pond | Completed | Not provided | 2010 | 12.7248 | 2.5178 | B | 39.1 | 350000 | 7035 | Not provided | Not provided | N/A | Not provided | 28.3272497274533 | -80.7201771340042 | N/A | N | N
NIRL | 3097 | City of Rockledge | Not provided | ROCK-20 | Huntington Lakes I | "Wet detention" means the collection and temporary storage of stormwater in a permanently wet impoundment in such a manner as to provide for treatment through physical, chemical, and biological processes with subsequent gradual release of the stormwater. | Wet Detention Pond | Completed | Not provided | 2014 | 15.4012 | 3.9013 | B | 36.9 | 950000 | Not provided | Not provided | Not provided | N/A | Not provided | 28.3385852833507 | -80.7349897622933 | N/A | N | N
NIRL | 3091 | City of Rockledge | Not provided | ROCK-24 | Huntington Lakes II | Project provides treatment to some of the basin that leads into ROCK-17. | Wet Detention Pond | Completed | Not provided | 2016 | 298.4588 | 34.2433 | B | 133.5 | 900000 | 15000 | Not provided | Not provided | N/A | Not provided | 28.3423799707035 | -80.7346392372396 | N/A | N | N
NIRL | 3101 | City of Rockledge | Not provided | ROCK-25 | Aquatic Harvesting | Data is collected by location in yards; determining method to convert to dry weight. | Aquatic Vegetation Harvesting | Completed | Not provided | 2015 | TBD | TBD | B | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Not provided | Not provided | Not provided | N/A | N | Y
NIRL | 3161 | City of Rockledge | Not provided | ROCK-26 | Breeze Swept Septic Phase-out | Estimates will be calculated using the latest version of ArcNLET for the septic tank phase out. | Wastewater Service Area Expansion | Completed | Not provided | 2017 | TBD | TBD | B | 39.6 | 3700000 | 20000 | DEP, SJRWMD, 1/2 cent Lagoon Tax | 2580000 | N/A | Not provided | Not provided | Not provided | Not provided | Y | Y
NIRL | 3123 | City of Rockledge | Not provided | ROCK-27 | River Ridge Non Discharge | Nondisharge dry retention basin. | 100% On-site Retention | Completed | Not provided | 2015 | 304.8869 | 44.0024 | B | 35.2598 | Not provided | Not provided | Not provided | Not provided | N/A | Not provided | 28.3317223956173 | -80.719322273585 | N/A | N | N
NIRL | 3120 | City of Rockledge | Not provided | ROCK-30 | Public Works Pond 1 | Enlarge current retention area. | Dry Detention Pond | Completed | 2017 | 2017 | 5.0422 | 0.70584 | B | 5.6879 | 5000 | 600 | Not provided | Not provided | N/A | Not provided | 28.3340244752464 | -80.7258925736122 | N/A | N | N
NIRL | 3119 | City of Rockledge | Not provided | ROCK-31 | Public Works Pond 2 | Enlarge current retention area. | Dry Detention Pond | Completed | 2018 | 2017 | 6.511 | 0.87818 | B | 6.9616 | 10000 | 600 | Not provided | Not provided | N/A | Not provided | 28.3319102668024 | -80.7244180545605 | N/A | N | N
NIRL | 3118 | City of Rockledge | Not provided | ROCK-32 | School Triangle Pond | Create dry detention pond on city-owned land. | Dry Detention Pond | Completed | 2018 | 2017 | 1.0237 | 0.14469 | B | 1.22 | 20300 | 1000 | Not provided | Not provided | N/A | Not provided | 28.3388736540273 | -80.7230514871838 | N/A | N | N
NIRL | 3116 | City of Rockledge | Not provided | ROCK-34 | Winchester Cove Non Discharge | Nondisharge dry retention basin. | 100% On-site Retention | Completed | Not provided | 2015 | 17.9416 | 2.638 | B | 1.9 | Not provided | Not provided | Not provided | Not provided | N/A | Not provided | 28.3141006057383 | -80.7089130781029 | N/A | N | N
NIRL | 4462 | City of Rockledge | Not provided | ROCK-35 | Florida Ave and Dixie Lane Swale | Grass swale with blocks or culverts. | Grass swales with swale blocks or raised culverts | Completed | Not provided | 2018 | 94.8947 | 12.96 | B | 9.6 | 5000 | Not provided | Not provided | Not provided | N/A | Not provided | 28.345568 | -80.726635 | N/A | N | N
NIRL | 3001 | City of Rockledge | Not provided | ROCK-21 | Street Sweeping | Pavement cleaning by sweeping, vacuum, or washing. | Street Sweeping | Ongoing | Not provided | N/A | 794 | 337 | B | N/A | Not provided | 54000 | Not provided | Not provided | N/A | Not provided | N/A | N/A | N/A | N/A | N
NIRL | 3099 | City of Rockledge | Not provided | ROCK-23 | Education Efforts | Irrigation, fertilizer, pet waste management, and landscaping ordinances; pamphlets, presentations, website, illicit discharge program. Video "Know Your Waterways". | Education Efforts | Ongoing | Not provided | N/A | 1660.14 | 238.92 | B | N/A | 7385 | 0 | Not provided | Not provided | N/A | Not provided | N/A | N/A | N/A | N/A | N
NIRL | 3121 | City of Rockledge | TBD | ROCK-29 | Gus Hipp Pond | Conversion of borrow pit to a wet detention pond. | Wet Detention Pond | Planned | TBD | TBD | TBD | TBD | B | TBD | 335000 | TBD | TBD | TBD | N/A | TBD | Not provided | Not provided | N/A | Y | Y
NIRL | 3108 | City of Rockledge | TBD | ROCK-33 | Barton Park Irrigation | Use wet pond (Barton Lake) for irrigation. | Stormwater Reuse | Planned | TBD | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | N/A | Y | Y
NIRL | 5367 | City of Rockledge | TBD | ROCK-36 | WWTP EQ Basin Nutrient Uptake | Modification of WWTP Process. | WWTF Upgrade | Planned | TBD | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Not provided | Not provided | N/A | N/A | Y
NIRL | 5368 | City of Rockledge | TBD | ROCK-37 | WWTP Biosolids | Modification of WWTP Process. | WWTF Upgrade | Planned | TBD | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Not provided | Not provided | TBD | N/A | Y
NIRL | 5369 | City of Rockledge | TBD | ROCK-38 | Rockled Indian River Dr | Septic to Sewer. | Wastewater Service Area Expansion | Planned | TBD | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | TBD | TBD | Not provided | Not provided | TBD | Y | Y
NIRL | 3122 | City of Rockledge | TBD | ROCK-28 | Southwest Gus Hipp Conveyance | Add BAM for denitrification to major canal in the city. | BMP Treatment Train | Underway | 2017 | 2019 | TBD | TBD | B | TBD | 17000 | TBD | TBD | TBD | TBD | TBD | Not provided | Not provided | N/A | Y | Y

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody