## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile
CIRL | 2645 | Sebastian River Improvement District | N/A | SRID-01 | 2-Inch Rule | Establishment of two-inch discharge rule. | Regulations, Ordinances, and Guidelines | Ongoing | Not provided | N/A | N/A | N/A | SEB | N/A | N/A | N/A | N/A | N/A | N/A |  | Not provided | Not provided | N/A
CIRL | 2632 | Sebastian River Improvement District | Not provided | SRID-02 | Control Gates | Radial arm control gates. | Control Structure | Planned | Not provided | TBD | TBD | TBD | SEB | 9000 | TBD | TBD | SRID | TBD | N/A |  | Not provided | Not provided | N/A
CIRL | 2643 | Sebastian River Improvement District | N/A | SRID-03 | Muck Removal | Vegetation and sediment/muck removal from canals. | Stormwater System Rehabilitation | Ongoing | Not provided | N/A | Not provided | Not provided | SEB | Not provided | Not provided | Not provided | SRID | Not provided | N/A |  | Not provided | Not provided | N/A
CIRL | 2655 | Sebastian River Improvement District | N/A | SRID-04 | Education Efforts | Permit manual on website that encourages the use of BMPs. | Education Efforts | Ongoing | Not provided | N/A | N/A | N/A | SEB | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2641 | Sebastian River Improvement District | N/A | SRID-05 | Water Conservation | Large regional water conservation/ storage areas. | Off-line Retention BMPs | Planned | Not provided | TBD | TBD | TBD | SEB | TBD | TBD | TBD | SRID | TBD | N/A |  | Not provided | Not provided | N/A
CIRL | 2640 | Sebastian River Improvement District | Groves Brothers/ SJRWMD | SRID-06 | 200-Acre Water Dispersion Project | Construction of berms and two pump stations to remove water from outfall canals and store on land. | Dispersed Water Management (DWM) | Underway | 2018 | 2020 | TBD | TBD | SEB | 7700 | 5650000 | TBD | SJRWMD | SJRWMD - $5,650,000 | N/A |  | 27.7403 | -80.4903 | N/A
CIRL | 2639 | Sebastian River Improvement District | N/A | SRID-07 | Lateral D System Stormwater Management | Lateral D system stormwater discharge limitation. | Regulations, Ordinances, and Guidelines | Planned | TBD | TBD | N/A | N/A | SEB | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 5601 | Sebastian River Improvement District | FDACS | SRID-08 | Assist FDACS with BMP Enrollment Outreach | Assist FDACS, where needed, with identifying and contacting producers within the district boundaries for purposes of participating in the relevant FDACS BMP programs. | Agricultural BMPs | Ongoing | Not provided | N/A | N/A | N/A | SEB | N/A | Not provided | Not provided | Not provided | Not provided | Not provided |  | Not provided | Not provided | N/A

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody