## STAR 2020
BMAPID | ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedStartDate | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | WMDContractAgreementNumber | Latitude | Longitude | Proposed5YearFundingPlan | GISShapefile
CIRL | 2638 | St. Lucie County | N/A | SLC-01 | Education Efforts | FYN; landscaping, irrigation, fertilizer, and pet waste ordinances; PSAs, pamphlets, website, and illicit discharge program. | Education Efforts | Ongoing | Not provided | N/A | 6241.26 | 1006.38 | SIRL | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A
CIRL | 2808 | St. Lucie County | N/A | SLC-02 | Street Sweeping | 470 tons/yr collected. | Street Sweeping | Ongoing | Not provided | N/A | 664 | 299.1 | SIRL | N/A | Not provided | Not provided | Not provided | Not provided | N/A |  | N/A | N/A | N/A
CIRL | 2818 | St. Lucie County | DEP/ SFWMD/ IRL National Estuary Program (NEP) | SLC-03 | Paradise Park Stormwater Improvement | Construction of drainage system providing 75 % treatment of first 1-inch runoff. | Dry Detention Pond | Completed | Not provided | 2014 | 170.7785 | 28.4539 | SIRL | 168.1 | 10000000 | Not provided | DEP/ SFWMD/ IRL NEP | DEP - $225,000/ SFWMD - $304,448/ IRL NEP - $125,000 | LP56020 |  | 27.4722 | -80.3446 | N/A
CIRL | 2806 | St. Lucie County | N/A | SLC-04 | Harmony Heights Stormwater Improvement | Construction of drainage system providing 75 % treatment of first 1-inch runoff. | Dry Detention Pond | Underway | Not provided | 2015 | 252.7679 | 43.5131 | SIRL | 238.743 | 10000000 | TBD | TBD | 511838 | N/A |  | 27.4731 | -80.3723 | N/A
CIRL | 2805 | St. Lucie County | N/A | SLC-05 | Taylor Creek Dredging | Three-phase sediment/muck removal project totaling approximately 200,000 cubic yards. | Muck Removal/Restoration Dredging | Completed | Not provided | 2015 | Not provided | Not provided | SIRL | Not provided | 7500000 | N/A | Not provided | Not provided | N/A |  | 27.4667 | -80.3302 | N/A
CIRL | 2804 | St. Lucie County | N/A | SLC-06 | Stan Blum Memorial Boat Launch | Not provided. | Wet Detention Pond | Completed | Not provided | Prior to 2013 | Not provided | Not provided | SIRL | 6.1296 | Not provided | N/A | Not provided | Not provided | N/A |  | 27.4734 | -80.3217 | N/A
CIRL | 2803 | St. Lucie County | IRL NEP | SLC-07 | San Lucie Plaza Stormwater Master Plan | Construction of drainage system providing 75 % treatment of first 1-inch runoff. | On-line Retention BMPs | Underway | Not provided | 2018 | 1210.0139 | 214.4157 | SIRL | 157.0803 | 20000000 | TBD | TBD | 650325 | N/A |  | 27.4824 | -80.3476 | N/A
CIRL | 2802 | St. Lucie County | N/A | SLC-08 | Georgia Ave. Basin WQ Improvement | Baffle box and control weir. | Baffle Boxes- Second Generation | Canceled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | 27.4432 | -80.3266 | N/A
CIRL | 2801 | St. Lucie County | N/A | SLC-09 | North Hutchinson Island Septic to Sewer Project | 538 Homes converted to Central Sewer | Wastewater Service Area Expansion | Underway | N/A | Not provided | TBD | TBD | SIRL | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A
CIRL | 2827 | St. Lucie County | N/A | SLC-10 | Port of Fort Pierce | Stormwater management system. | Stormwater System Rehabilitation | Completed | Not provided | 2018 | N/A | N/A | SIRL | Not provided | TBD | TBD | Not provided | Not provided | N/A |  | Not provided | Not provided | N/A
CIRL | 4382 | St. Lucie County | N/A | SLC-11 | Swales Material Collected | Roadside swale cleanout and reprofiling. | BMP Cleanout | Underway | 2018 | TBD | TBD | TBD | SIRL | N/A | TBD | TBD | TBD | TBD | N/A |  | N/A | N/A | N/A
CIRL | 5238 | St. Lucie County | N/A | SLC-12 | St. Lucie County Stormwater Needs Assessment Study | Report that will provide information on identified project opportunities to reduce nutrients, estimated benefits, and costs. | Study | Underway | Not provided | TBD | N/A | N/A | SIRL | TBD | 142380 | TBD | TBD | TBD | N/A |  | Not provided | Not provided | N/A

## Wish List Projects
WLProjID | BMAPID | WLLeadEntity | WLPartners | WLProjectNumber | WLProjectName | WLDescription | WLProjectType | WLProjectStatus | WLEstimatedStartDate | WLTNReduction(lbs/yr) | WLTPReduction(lbs/yr) | WLCostEstimate | WLCostAnnualO&MEst | WLFundingSources | WLFundingAmounts | WLFundingStillNeeded | WLBasin/Location | WLLatitudeApproximate | WLLongitudeApproximate | Notes

## DropDowns
Project Type | Project Staus | GIS Shapefile
100% On-site Retention | Planned | Y
Agricultural BMPs | Underway | N
Aquatic Vegetation Harvesting | Completed
Baffle Boxes- First Generation | Canceled
Baffle Boxes- Second Generation | Ongoing
Baffle Boxes- Second Generation with Media
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Missing from Model
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Constructed Wetland Treatment
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
In Waterbody - Alum Injection System
In Waterbody - Biological/ Bacteria Treatment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement Systems
Plugging Artesian Wells
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer - Alum Injection System
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater - Alum Injection System
Stormwater - Biological/ Bacteria Treatment
Stormwater - Deep Injection Well
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater System Upgrade
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater - Deep Injection Well
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- OSTDS
FIB- Sanitary Sewer
FIB- Source Identification Activities
FIB- Stormwater
FIB- Trash Cleanup of Impaired Waterbody