## Sheet1
ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | TO DO | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | Structural, Non-structural, or Trade | (Original) Project Status | Year Project Added | BMAP | Latitude | Longitude | Start Date | DEP has Treatment Area Shapefile | DEP needs Treatment Area Shapefile | credit available?
2536 | Brevard County | N/A | BC-01 | Education Efforts | Florida Yards and Neighbors (FYN); landscape, irrigation, fertilizer, and pet waste ordinances; public service announcements (PSAs); pamphlets; website; Illicit Discharge Program. | Education Efforts | Apply New Information | Completed | N/A | 79 | 14 | A | N/A | N/A | 40000 | Utility Fee | N/A | N/A | Non-structural | Ongoing | 2013 | Banana River Lagoon | Not provided | Not provided | Not provided | no | no
2547 | Brevard County | SJRWMD/ Environmentally Endangered Lands (EELS) | BC-02 | Pine Island Phase I and II | Regional Stormwater Management System includes two wet ponds (80-acres & 23 acres) with gravity flow and pump station. | Regional Stormwater Treatment | Keep original calcs | Completed | 2015 | 160 | 102 | A | 15.3 | 3140824 | 19235 | EPA/ DEP TMDL | 1677079 | G0288/ G0344 | Structural | Completed | 2013 | Banana River Lagoon | 28.456 | -80.6767 | Not provided | yes | yes
2559 | Brevard County | DEP | BC-03 | Florida Blvd. Pond | Construction of a 2.3 acre wet detention pond to proivide treatment to a residential area in Merritt Island. | Wet Detention Pond | Update with SWIL #s | Completed | 2013 | 324 | 126.4 | B | 73.6 | 350384 | Not provided | DEP | DEP - $350,384 | WM744 | Structural | Completed | 2013 | Banana River Lagoon | 28.3908 | -80.7035 | Not provided | yes | yes
2545 | Brevard County | DEP | BC-04 | Hampton North (Riverside) | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2013 | 1 | 1.4 | B | 15.3 | 27000 | 1500 | DEP | DEP - $27,000 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.3677 | -80.6917 | Not provided | yes | yes
2544 | Brevard County | DEP | BC-05 | Hampton South (Needle Blvd) | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2013 | 1 | 1.6 | B | 18.1 | 29000 | 1500 | DEP | DEP - $29,000 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.366 | -80.6916 | Not provided | yes | yes
2543 | Brevard County | DEP | BC-06 | Albatross | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2013 | 1 | 1.5 | B | 21.8 | 33000 | 1500 | DEP | DEP - $33,000 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.3659 | -80.6679 | Not provided | yes | yes
2789 | Brevard County | DEP | BC-07 | Surfside | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2013 | 2 | 2.2 | B | 22.8 | 31500 | 1500 | DEP | DEP - $31,500 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.3818 | -80.6711 | Not provided | yes | yes
2457 | Brevard County | DEP | BC-08 | West Scots | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2013 | 30 | 5.9 | B | 9.7 | 41000 | 1500 | DEP | DEP - $41,000 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.3957 | -80.675 | Not provided | yes | yes
2428 | Brevard County | DEP | BC-09 | Johns Circle | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2013 | 2 | 1.8 | B | 19.5 | 31000 | 1500 | DEP | DEP - $31,000 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.4007 | -80.6738 | Not provided | yes | yes
2393 | Brevard County | DEP | BC-10 | Farrington Drive | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2013 | 24 | 4.9 | B | 7.8 | 37500 | 1500 | DEP | DEP - $37,500 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.3915 | -80.6725 | Not provided | yes | yes
2394 | Brevard County | DEP | BC-11 | Porpoise Street | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2013 | 25 | 4.9 | B | 7.8 | 42000 | 1500 | DEP | DEP - $42,000 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.388 | -80.6735 | Not provided | yes | yes
2402 | Brevard County | DEP | BC-12 | Angler Street | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2013 | 1 | 0.9 | B | 10.2 | 30700 | 1500 | DEP | DEP - $30,700 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.3799 | -80.6722 | Not provided | yes | yes
2396 | Brevard County | DEP | BC-13 | Diana Shores | Installing a Vortech Unit to treat runoff form an old residential, multi family and commercial area. | Hydrodynamic Separators | Update with SWIL #s | Completed | 2013 | 0 | 17 | B | 38.6 | 102000 | 1500 | DEP | DEP - $102,000 | G0268 | Structural | Completed | 2013 | Banana River Lagoon | 28.3846 | -80.6999 | Not provided | yes | yes
2389 | Brevard County | N/A | BC-14 | Education Efforts | FYN; landscape, irrigation, fertilizer, and pet waste ordinances; public service announcements (PSAs); pamphlets; website; Illicit Discharge Program. | Education Efforts | Apply New Information | Completed | N/A | 3854 | 825 | B | N/A | Not provided | Not provided | N/A | N/A | N/A | Non-structural | Ongoing | 2013 | Banana River Lagoon | N/A | N/A | Not provided | no | no
2398 | Brevard County | N/A | BC-15 | Street Sweeping | Street sweeping on 786 miles eight times per year. | Street Sweeping | Apply Rolling Average | Completed | N/A | 525 | 336 | A | N/A | N/A | 50000 | N/A | N/A | N/A | Non-structural | Ongoing | 2013 | Banana River Lagoon | N/A | N/A | Not provided | no | no
2399 | Brevard County | DEP | BC-16 | Fortenberry Pond | 22.3 Acre Regional Stormwater Detention Pond designed to accommodate water quality treatment for pre-existing development as well as for future build-out of commercial properties through the purchase of stormwater credits. | Wet Detention Pond | Update with SWIL #s | Completed | 2015 | 847 | 364.6 | B | 164.5 | 10900000 | 35000 | DEP TMDL | DEP TMDL - $340,533 | S0646 | Structural | Completed | 2013 | Banana River Lagoon | 28.353 | -80.6893 | Not provided | yes | yes
2400 | Brevard County | DEP | BC-17 | Merritt Island Airport Pond | Redirection of run-off from a drainage basin with no treatment through a swale and to a pond that was expanded to provide water quality. | Wet Detention Pond | Update with SWIL #s | Completed | 2013 | 458 | 160 | B | 148.2 | 652056 | Not provided | DEP | DEP - $652,056 | S0439 | Structural | Completed | 2013 | Banana River Lagoon | 28.3391 | -80.6901 | Not provided | yes | yes
2542 | Brevard County | Not provided | BC-18 | Florida Boulevard | Installation of floating vegetation islands to remove nitrogen from an existing wet detention pond. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | 2013 | 117 | 14.3 | B | 73.6 | 40772 | 18295 | Not provided | 40772 | Not provided | Structural | Completed | 2013 | Banana River Lagoon | 28.3908 | -80.7035 | Not provided | yes | yes
2541 | Brevard County | DEP | BC-19 | Third Ave Baffle Box | Upgrading a 1st generation baffle box to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2015 | 93 | 10 | B | 53.1 | 31452 | Not provided | DEP | DEP - $31,452 | S0648 | Structural | Completed | 2013 | Banana River Lagoon | 28.1999 | -80.6011 | Not provided | yes | yes
2540 | Brevard County | Not provided | BC-20 | Bes Management Practice (BMP) Cleanout | Cleaning out the BMP such as baffle boxes, inlet baskets, and sediment basins. | BMP Cleanout | Apply Rolling Average | Completed | N/A | 1 | 1 | B | N/A | 95069 | 55300 | N/A | 95069 | N/A | Non-structural | Ongoing | 2013 | Banana River Lagoon | Not provided | Not provided | Not provided | no | no
2539 | Brevard County | DEP | BC-21 | Fourth Place Baffle Box | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2015 | 146 | 25.7 | B | 57 | 34037 | Not provided | DEP | DEP - $34,037 | S0648 | Structural | Completed | 2013 | Banana River Lagoon | 28.3635 | -80.6977 | Not provided | yes | yes
2538 | Brevard County | DEP | BC-22 | Thrush 405 Baffle Box | Upgrading a 1st generation to a 2nd generatrion baffle box by adding the nutrient separating screen. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2015 | 7 | 0.7 | B | 4.3 | 12507 | Not provided | DEP | DEP - $12,507 | S0648 | Structural | Completed | 2013 | Banana River Lagoon | 28.2105 | -80.6127 | Not provided | yes | yes
2546 | Brevard County | DEP | BC-24 | Merritt Ridge Pond 3A | Installation of floating vegetation islands to remove nitrogen from an existing wet detention pond. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | Prior to 2013 | 210 | 48.7 | B | 84.4 | 114914 | 25091 | DEP | DEP - $114,914 | G0430 | Structural | Funded | 2013 | Banana River Lagoon | 28.352 | -80.6939 | Not provided | yes | yes
2548 | Brevard County | Satellite Beach | BC-25 | Cassia Phase 3 | Landscape buffer/ drainage swale along the adjoining roadway. Improvements include the construction of a dry detention area within an existing ditch and construction of roadside swales in the location of the existing bike/ pedestrian lane. | On-line Retention BMPs | Update with SWIL #s | Completed | 2013 | 100 | 0 | B | 18.4 | 100000 | Not provided | DEP/ Satellite Beach/ Brevard County | Not provided | N/A | Structural | Completed | 2013 | Banana River Lagoon | 28.1719 | -80.5976 | Not provided | yes | yes
2582 | Brevard County | SJRWMD | BC-26 | South Patrick Drive Baffle Box | 2nd generation baffle box with denitrification bioreactor. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2017 | 132 | 16.9 | B | 73.9 | 320256 | 2100 | SJRWMD/ DEP | SJRWMD - $57,750/ DEP - $136,000 | LP05111 | Structural | Funded | 2013 | Banana River Lagoon | 28.2106 | -80.603 | Not provided | yes | yes
2581 | Brevard County | Not provided | BC-27 | Kelly Park Reuse | Not provided. | Stormwater Reuse | Update with SWIL #s | Completed | 2013 | 19 | 1.3 | B | 32.9 | Not provided | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2013 | Banana River Lagoon | 28.3998 | -80.666 | Not provided | yes | yes
2580 | Brevard County | Not provided | BC-28 | Patrick Air Force Base Golf Course Pond Stormwater Reuse | Conversion of a retention pond into a reusue pond to irrigate the golf course. | Stormwater Reuse | Update with SWIL #s | Completed | 2016 | 359.1 | 0 | B | 88.3312 | Not provided | Not provided | Not provided | Not provided | N/A | Structural | Planned, Not Funded | 2013 | Banana River Lagoon | 28.2106 | -80.6029 | Not provided | yes | yes
2578 | Brevard County | N/A | BC-30 | Street Sweeping | Monthly street sweeping. | Street Sweeping | Apply Rolling Average | Completed | N/A | 0 | 0 | A | N/A | N/A | 47064 | N/A | N/A | N/A | Non-structural | Started | 2015 | Banana River Lagoon | N/A | N/A | Not provided | yes
2577 | Brevard County | Not provided | BC-31 | BMP Cleanout | Quarterly baffle box/ sediment trap cleaning. | BMP Cleanout | Apply Rolling Average | Completed | N/A | 0 | 0 | A | N/A | N/A | 52000 | N/A | N/A | N/A | Non-structural | Started | 2015 | Banana River Lagoon | N/A | N/A | Not provided | yes | no
2576 | Brevard County | DEP | BC-32 | Cocoa Beach Canal Dredging | Muck removal of 84,000 cubic yards of material. | Muck Removal/Restoration Dredging | Not Provided | Completed | 2017 | 0 | 0 | B | Not provided | 20000000 | Not provided | DEP | DEP - $10,000,000 | S0714 | Non-structural | Completed | 2017 | Banana River Lagoon | Not provided | Not provided | Not provided | no | no
4330 | Brevard County | All Cities | BC-35 | Education Efforts | Fertilizer video, rainbarrel workshops, Facebook page, bus wrap, and billboard. | Education Efforts | Apply New Information | Underway | N/A | N/A | N/A | B | N/A | N/A | 42000 | N/A | N/A | N/A | Non-structural | Underway | 2018 | Banana River Lagoon | 28.381 | -80.7015 | Not provided | no | no
4331 | Brevard County | N/A | BC-36 | Merritt Island Airport | Two wet detention ponds (80-acres & 23 acres) with gravity flow and pump station. | Wet Detention Pond | Update with SWIL #s | Completed | 2011 | 458 | 160 | B | 184.2 | 672464.37 | N/A | DEP TMDL | DEP TMDL - $307,333.86 | S0439 | Structural | Completed | 2018 | Banana River Lagoon | 28.34 | -80.686 | Not provided | no | yes
4332 | Brevard County | DEP | BC-37 | Artemis Blvd. - BB #979 | Biosorption Activated Media installed within existing Merritt Island drainage ditch system to remove nitrogen from groundwater baseflow with phosphorus removal media. | Biosorption Activated Media (BAM) | Update with SWIL #s | Completed | 2019 | TBD | TBD | B | 789 | 150000 | 2500 | Legislative Funding | Legislative Funding - $35,000 | LP0511A | Structural | Underway | 2018 | Banana River Lagoon | 28.381 | -80.7015 | Not provided | yes | yes
4333 | Brevard County | DEP | BC-38 | Oceana Drive - BB#997A | Biosorption Activated Media installed within existing Merritt Island drainage ditch system to remove nitrogen from groundwater baseflow. | Biosorption Activated Media (BAM) | Update with SWIL #s | Completed | 2019 | TBD | TBD | B | 68 | 50000 | 1000 | Legislative Funding | Legislative Funding - $35,000 | LP0511A | Structural | Underway | 2018 | Banana River Lagoon | 28.3654 | -80.6658 | Not provided | yes | yes
4334 | Brevard County | DEP | BC-39 | Georgiana Drive - BB#997C | Biosorption Activated Media installed within existing Merritt Island drainage ditch system to remove nitrogen from groundwater baseflow. | Biosorption Activated Media (BAM) | Update with SWIL #s | Completed | 2019 | TBD | TBD | B | 68 | 50000 | 1000 | Legislative Funding | Legislative Funding - $35,000 | LP0511A | Structural | Underway | 2018 | Banana River Lagoon | 28.3634 | -80.6649 | Not provided | yes | yes
4335 | Brevard County | DEP | BC-40 | Savannah Drive - BB#997B | Biosorption Activated Media installed within existing Merritt Island drainage ditch system to remove nitrogen from groundwater baseflow. | Biosorption Activated Media (BAM) | Update with SWIL #s | Completed | 2019 | TBD | TBD | B | 68 | 50000 | 1000 | Legislative Funding | Legislative Funding - $35,000 | LP0511A | Structural | Underway | 2018 | Banana River Lagoon | 28.3644 | -80.6659 | Not provided | yes | yes
4336 | Brevard County | DEP | BC-41 | Needle Blvd. - BB #998 | Biosorption Activated Media installed within existing Merritt Island drainage ditch system to remove nitrogen from groundwater baseflow. | Biosorption Activated Media (BAM) | Update with SWIL #s | Completed | 2019 | TBD | TBD | B | 273 | 55000 | 1000 | Legislative Funding | Legislative Funding - $35,000 | LP0511A | Structural | Underway | 2018 | Banana River Lagoon | 28.3649 | -80.6955 | Not provided | yes | yes
4338 | Brevard County | DEP/ SOIRL | BC-43 | Seagull Drive Pond Pond BAM Train BB#1304 (D-4) | Media will be installed along side slope of existing pond and will include solar panels. | BMP Treatment Train | Update with SWIL #s | Underway | 2020 | TBD | TBD | N/A | Not provided | 96000 | Not provided | LF/ SOIRL | 125000 | LP0511A | Structural | Underway | 2018 | Banana River Lagoon | 28.2036 | -80.6039 | Not provided | yes | yes
5146 | Brevard County | MIRA/ SJRWMD/ SOIRL/ DEP | BC-44 | MIRA Phase 2 Septic to Sewer (S. Tropical Tr.) | Connect 80 commercial properties to sewer. | OSTDS Phase Out | Not Provided | Completed | 2020 | TBD | N/A | B | N/A | Not provided | Not provided | SJRWMD/ SOIRL/ DEP | Not provided | 28731 | Structural | Completed | 2019 | Banana River Lagoon | 28.3109 | -80.639 | Not provided | no | yes
5147 | Brevard County | SOIRL/ Brevard Zoo | BC-45 | Bettinger Oyster Bar | Construct 120-linear foot oyster bar. | Creating/ Enhancing Oyster Reefs | Credit Unavailable | Completed | 2019 | TBD | TBD | B | Not provided | 101680 | Not provided | Not provided | 10680 | N/A | Structural | Completed | 2019 | Banana River Lagoon | 28.3322 | -80.615 | Not provided | yes | yes
5148 | Brevard County | SOIRL/ Brevard Zoo | BC-46 | Gitlin Oyster Bar | Construct 180 linear foot oyster reef. | Creating/ Enhancing Oyster Reefs | Credit Unavailable | Completed | 2019 | TBD | TBD | B | Not provided | 16020 | Not provided | SOIRL | 16020 | N/A | Structural | Completed | 2019 | Banana River Lagoon | 28.1724 | -80.6086 | Not provided | no | yes
5149 | Brevard County | SOIRL/ Brevard Zoo | BC-47 | Marina Isles Oyster Restoration | Construct 1500 linear foot oyster reef. | Creating/ Enhancing Oyster Reefs | Credit Unavailable | Completed | 2019 | TBD | TBD | B | Not provided | 26700 | Not provided | SOIRL | 26700 | N/A | Structural | Completed | 2019 | Banana River Lagoon | 28.1526 | -80.6065 | Not provided | no | no | no
5150 | Brevard County | SOIRL/ MRC | BC-48 | Cocoa Beach Living Shoreline | Plant 200 mangroves and 1000 spartina along shoreline of Cocoa Beach Country Club. | Creating/ Enhancing Living Shoreline | Credit Unavailable | Completed | 2018 | TBD | TBD | B | Not provided | 16080 | Not provided | SOIRL | 16080 | N/A | Structural | Completed | 2019 | Banana River Lagoon | 28.3109 | -80.639 | Not provided | no | no | no
5151 | Brevard County | SOIRL/ Cocoa Beach | BC-49 | Cocoa Beach Muck Dredging Phase III | Remove 300,000 cubic yards of muck. | Muck Removal/Restoration Dredging | Not Provided | Completed | 2019 | TBD | TBD | B | Not provided | 2236566 | Not provided | SOIRL/ DEP/ SJRWMD | Not provided | N/A | Non-structural | Completed | 2019 | Banana River Lagoon | Not provided | Not provided | Not provided | no | no | no
5152 | Brevard County | SOIRL | BC-50 | Education Efforts | Fertilizer, grass clippings, and septic system maintenance. | Education Efforts | Apply New Information | Underway | 2027 | TBD | TBD | A | N/A | 375000 | Not provided | SOIRL | 375000 | N/A | Non-structural | Underway | 2019 | Banana River Lagoon | Not provided | Not provided | Not provided | no | yes
5153 | Brevard County | SOIRL | BC-50a | Education Efforts | Fertilizer, grass clippings, and septic system maintenance. | Education Efforts | Apply New Information | Underway | 2027 | TBD | TBD | B | N/A | 375000 | Not provided | SOIRL | 375000 | N/A | Non-structural | Underway | 2019 | Banana River Lagoon | Not provided | Not provided | Not provided | no | no
5154 | Brevard County | DEP | BC-51 | Andrix Blvd. - BB#973 | Biosorption Activated Media installed within existing Merritt Island drainage ditch system to remove nitrogen from groundwater baseflow. | Biosorption Activated Media (BAM) | Update with SWIL #s | Completed | 2019 | TBD | TBD | B | Not provided | 55000 | 1500 | Legislative Funding | 35000 | LP0511A | Structural | Completed | 2019 | Banana River Lagoon | 28.3912 | -80.7134 | Not provided | yes | yes
5155 | Brevard County | MIRA/ SJRWMD/ SOIRL/ DEP | BC-52 | MIRA Phase 2 Bioswale Treatment Train (Merritt Ridge Pond) | Modification of existing wet pond to include bioswale with BAM. | BMP Treatment Train | Update with SWIL #s | Completed | 2019 | TBD | TBD | B | 210 | Not provided | Not provided | Not provided | Not provided | 28731 | Structural | Completed | 2019 | Banana River Lagoon | Not provided | Not provided | Not provided | yes | yes
5156 | Brevard County | MIRA/ SJRWMD/ SOIRL/ DEP | BC-53 | MIRA Phase 3 Septic to Sewer (Cone Rd) | Connect 30+ commercial properties to sewer. | OSTDS Phase Out | Not Provided | Underway | 2020 | TBD | TBD | B | N/A | Not provided | Not provided | Not provided | Not provided | 28731 | Structural | Underway | 2019 | Banana River Lagoon | Not provided | Not provided | Not provided | yes | yes
5157 | Brevard County | SOIRL | BC-54 | Grass Clippings Campaign Phase 1 | Marketing and surveying. | Education Efforts | Apply New Information | Completed | 2019 | TBD | TBD | A | N/A | 6666.66 | N/A | SOIRL | 20000 | N/A | Non-structural | Completed | 2019 | Banana River Lagoon | Not provided | Not provided | Not provided | yes | yes
5158 | Brevard County | SOIRL | BC-54a | Grass Clippings Campaign Phase 1 | Marketing and surveying. | Education Efforts | Apply New Information | Completed | 2020 | TBD | TBD | B | N/A | 6667.66 | N/A | SOIRL | 20001 | N/A | Non-structural | Completed | 2019 | Banana River Lagoon | Not provided | Not provided | Not provided | yes | yes
2769 | Brevard County | N/A | BC-001 | Old Dixie Highway 601 | Sediment trap. | BMP Cleanout | Take Rolling Average | Completed | 2014 | Not provided | Not provided | A | Not provided | 2000 | 2000 | County | County - $2,000 | N/A | Non-structural |  | 2013 | North Indian River Lagoon | Not provided | Not provided | 2010 | no | no
2797 | Brevard County | DEP/ Titusville | BC-002 | Chain of Lakes Pond | Wet detention Regional Pond. | Wet Detention Pond | Update with SWIL #s | Completed | 2010 | 2699 | 1109.4 | A | 1072.5 | 2051405 | Not provided | DEP | Not provided | WM804 | Structural |  | 2013 | North Indian River Lagoon | 28.6332408150473 | -80.8310185764948 | 2010 | no | no
2796 | Brevard County | West Melbourne/ Grant-Valkaria/ Malabar/ Melbourne/ Cocoa/ Indian Harbour Beach (IHB)/ Satellite Beach/ Cocoa Beach/ Cape Canaveral | BC-003 | Education Efforts | FYN; landscape, irrigation, fertilizer, and pet waste ordinances; PSAs; pamphlets; website, Illicit Discharge Program. | Education Efforts | Apply New Information | Completed | N/A | 1660 | 214 | A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural |  | 2013 | North Indian River Lagoon | N/A | N/A | Not provided
2795 | Brevard County | TBD | BC-004 | Scottsmoor I | Advanced denitrification and baffle box treatment train. | BMP Treatment Train | Update with SWIL #s | Underway | TBD | TBD | TBD | A | 530.9 | 601664 | 1000 | Legislative Funds | Legislative Funds - $286,648 | LP05118 | Structural |  | 2013 | North Indian River Lagoon | 28.7327895474711 | -80.8640955551483 | TBD
2794 | Brevard County | DEP/ City of Titusville | BC-005 | Chain of Lakes Southern Expansion Phase 1 | Completion of additional detention. | Wet Detention Pond | Update with SWIL #s | Completed | 2014 | 1325 | 440.6 | A | 575.2 | 3200000 | 1000 | DEP | Not provided | S0620 | Structural |  | 2013 | North Indian River Lagoon | 28.6273789688255 | -80.8322909258089 | 2014
2793 | Brevard County | Not provided | BC-006 | Chain of Lakes Reuse | Installing reuse from the pond. | Stormwater Reuse | Update with SWIL #s | Completed | 2005 | 498 | 63.2 | A | Not provided | Not provided | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.6332408150473 | -80.8310185764948 | Not provided
2792 | Brevard County | TBD | BC-007 | Scottsmoor C | Advanced denitrification and baffle box treatment train. | BMP Treatment Train | Update with SWIL #s | Underway | 2019 | TBD | TBD | A | 463 | TBD | 1000 | Legislative Funds | Legislative Funds - $33,7043 | LP05114 | Structural |  | 2015 | North Indian River Lagoon | 28.74381050624 | -80.8594264327632 | TBD
2791 | Brevard County | Not provided | BC-008 | Twin Lakes North | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2014 | 10 | 1 | B | 7.7 | Not provided | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.4128064458657 | -80.7520253074758 | Not provided
2790 | Brevard County | Not provided | BC-009 | Twin Lakes South | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2014 | 10 | 1 | B | 8.5 | 20082 | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.4119087868403 | -80.7519535776597 | Not provided
3058 | Brevard County | DEP | BC-010 | Lucas Place 640 Baffle Box | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2003 | 8 | 0.8 | B | 5.2 | 36835 | 1000 | DEP/ County | Not provided | S0620 | Structural |  | 2013 | North Indian River Lagoon | 28.3759208043569 | -80.711887550185 | 2017
3041 | Brevard County | DEP | BC-011 | Rockledge Drive 2055 | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2008 | 2 | 0.1 | B | 2.4 | 61094 | 1000 | DEP | Not provided | S0620 | Structural |  | 2013 | North Indian River Lagoon | 28.2906374761108 | -80.6960502627134 | 2017
3042 | Brevard County | Not provided | BC-012 | Rockledge and Riverwoods Baffle Box | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2000 | 3 | 0.3 | B | 3.8 | 47686 | 1000 | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.2800750902802 | -80.690668715772 | 2017
3043 | Brevard County | DEP | BC-013 | Anchor Lane | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2000 | 47 | 5.4 | B | 29.4 | 49560 | 1000 | DEP | Not provided | S0620 | Structural |  | 2013 | North Indian River Lagoon | 28.2471398671558 | -80.6784491178469 | 2017
3044 | Brevard County | Not provided | BC-014 | Kelmore Baffle Box | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2003 | 10 | 1.8 | B | 9.7 | 21817 | 1000 | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.1212612559775 | -80.636711042106 | Not provided
3040 | Brevard County | DEP | BC-015 | Puesta Del Sol 735 Baffle Box | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2003 | 2 | 0.2 | B | 2.2 | 24953 | 1000 | DEP | Not provided | S0620 | Structural |  | 2013 | North Indian River Lagoon | 28.1219641693395 | -80.5901203630795 | 2017
3039 | Brevard County | SJRWMD | BC-016 | Tequesta Harbor Baffle Box | Construction of a bafffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Update with SWIL #s | Completed | 2009 | 21 | 2.4 | B | 13.1 | 27582 | 1000 | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.2477356421776 | -80.6592294499719 | 2010
3038 | Brevard County | NRCS | BC-017 | Broadway Boulevard Pond | Constructon of a detention pond to treat runoff. | Wet Detention Pond | Update with SWIL #s | Completed | 2000 | 272 | 55.7 | B | 85.7 | 553169 | 14972.5 | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.4600166770728 | -80.7684122511537 | Not provided
3037 | Brevard County | Not provided | BC-018 | Fairglen Elementary School Pond | Constructon of a detention pond to treat runoff. | Wet Detention Pond | Update with SWIL #s | Completed | 2003 | 350 | 111.1 | B | 80.2 | 730869 | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.4355622936804 | -80.7625301673938 | Not provided
3036 | Brevard County | DEP | BC-019 | Lake George | Constructon of a detention pond to treat runoff. | Wet Detention Pond | Update with SWIL #s | Completed | 2010 | 1261 | 414.6 | B | 719 | 347255 | 17750 | DEP | Not provided | LP8952 | Structural |  | 2013 | North Indian River Lagoon | 28.4553943410101 | -80.6868569308333 | Not provided
3035 | Brevard County | Not provided | BC-020 | Merritt Island Courthouse Pond | Constructon of a detention pond to treat runoff. | Wet Detention Pond | Update with SWIL #s | Completed | 2003 | 8 | 2.5 | B | 7 | 95584 | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.4032557765221 | -80.7067833796016 | Not provided
3034 | Brevard County | Not provided | BC-021 | Parkway Drive Phase 2 Pond | Constructon of a detention pond to treat runoff. | Wet Detention Pond | Update with SWIL #s | Completed | 2004 | 4041 | 1598.9 | B | 1796.9 | 1817720 | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.1658908107587 | -80.6716100956786 | Not provided
3033 | Brevard County | Not provided | BC-022 | Street Sweeping | Monthly Street Sweeping 786 curb lane miles. | Street Sweeping | Take Rolling Average | Completed | N/A | 636 | 408 | B | N/A | 106665.04 | Not provided | Not provided | Not provided | N/A | Non-structural |  | 2013 | North Indian River Lagoon | N/A | N/A | Not provided
3018 | Brevard County | Not provided | BC-023 | Education Efforts | FYN; landscape, irrigation, fertilizer, and pet waste ordinances; PSAs; pamphlets; website, Illicit Discharge Program. | Education Efforts | Apply New Information | Completed | N/A | 6339 | 1035 | B | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural |  | 2013 | North Indian River Lagoon | N/A | N/A | Not provided
3031 | Brevard County | DEP | BC-024 | Pine Island Phase I and II | Two Wet Detention Ponds (80-acres & 23 acres) with Gravity Flow and Pump Station. | Wet Detention Pond | Update with SWIL #s | Completed | 2015 | 10948 | 3217.9 | B | 6232.9 | 4131255 | 34705 | DEP TMDL/ EPA 319 | DEP TDML/ EPA 319 - $1,677,079 | G0288/ G0344 | Structural |  | 2013 | North Indian River Lagoon | 28.4649053684489 | -80.699361745544 | Not provided
3045 | Brevard County | Not provided | BC-025 | Merritt Island Airport | Not provided. | Wet Detention Pond | Update with SWIL #s | Canceled | N/A | N/A | N/A | B | N/A | N/A | N/A | N/A | N/A | N/A | Structural |  | N/A | North Indian River Lagoon | 28.3404799067651 | -80.6936499371813 | N/A
3029 | Brevard County | DEP | BC-026 | Pines Industrial | Construction of a pond to treat runoff where no treatment was provided. | Wet Detention Pond | Update with SWIL #s | Underway | 2020 | 801.5 | 101 | B | 71 | 822000 | TBD | DEP | Not provided | NF003 | Structural |  | 2013 | North Indian River Lagoon | 28.291550162039 | -80.7047917774634 | TBD
3028 | Brevard County | DEP | BC-027 | Johnson Junior High | Discharge regulation, phosphorus reduction, and denitrification. Biosorption activated media added. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | 2017 | 187.14 | 27.04 | B | 133.4 | 499416.43 | Not provided | DEP | DEP - $489,200 | G0430 | Structural |  | 2013 | North Indian River Lagoon | 28.1436163757864 | -80.6514863823303 | TBD
3027 | Brevard County | DEP | BC-028 | Florida Boulevard | Installation of floating vegetative islands for Nutrient uptake. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | 2014 | 197 | 21 | B | 88.4 | 40772 | 18295 | DEP | Not provided | G0430 | Structural |  | 2013 | North Indian River Lagoon | 28.3911795884785 | -80.7061173869847 | Not provided
3026 | Brevard County | DEP | BC-029 | Fairglen Elementary | Installation of floating vegetative islands for Nutrient uptake. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | 2017 | 123 | 12.2 | B | 80.2 | 34996 | 15703 | DEP | Not provided | G0430 | Structural |  | 2013 | North Indian River Lagoon | 28.4355622936804 | -80.7625301673938 | Not provided
3025 | Brevard County | DEP | BC-030 | Port St. John B | Installation of floating vegetative islands for Nutrient uptake. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | Prior to 2013 | 237 | 41.5 | B | 57.9 | 16308 | 7315 | DEP | Not provided | G0430 | Structural |  | 2013 | North Indian River Lagoon | 28.481042842166 | -80.7741216614766 | Not provided
3024 | Brevard County | DEP | BC-031 | Wickham Park North | Installation of floating vegetative islands for Nutrient uptake. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | 2017 | 2804 | 597.8 | B | 1796.9 | 75428 | 24175 | DEP | Not provided | G0430 | Structural |  | 2013 | North Indian River Lagoon | 28.1658908107587 | -80.6716100956786 | Not provided
3023 | Brevard County | DEP | BC-032 | West Avenue 6600 | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2017 | 120 | 12 | B | 50.7 | 15000 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.474674300938 | -80.7702500834108 | Not provided
3022 | Brevard County | DEP | BC-033 | Lucas Place | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 8 | 0.7 | B | 2.7 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.37576 | -80.71335 | Not provided
3021 | Brevard County | DEP | BC-034 | Indian River Isles | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 63 | 7.8 | B | 7.3 | 30844 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.2456066318426 | -80.6807931992876 | Not provided
3020 | Brevard County | DEP | BC-035 | Granada Street 1030 East | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 99 | 16.4 | B | 38.6 | 15000 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.3403962500458 | -80.6977294924022 | Not provided
3071 | Brevard County | DEP | BC-036 | Haverhill Avenue | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 80 | 8 | B | 47.5 | 35857 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.4766812925972 | -80.7757188638679 | Not provided
3070 | Brevard County | DEP | BC-037 | Manth Avenue | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 226 | 29 | B | 69.1 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.4858563892688 | -80.7780358987526 | Not provided
3069 | Brevard County | Not provided | BC-038 | Rockledge and Riverwoods Boulevard Rockledge | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 3 | 0.2 | B | 3.8 | 15000 | 2140 | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.2800750902802 | -80.690668715772 | Not provided
2990 | Brevard County | DEP | BC-039 | Alamanda Indian Harbour Beach | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 3 | 0.3 | B | 2.8 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.1112527216627 | -80.5850920219407 | Not provided
2997 | Brevard County | DEP | BC-040 | River Shore 1848 Indialantic | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 3 | 0.3 | B | 2.7 | 31751 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.1087174777292 | -80.5857226938728 | Not provided
2988 | Brevard County | DEP | BC-041 | River Shore 1925 Indialantic | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 7 | 0.8 | B | 7.4 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.1100983771568 | -80.5851276841474 | Not provided
2987 | Brevard County | DEP | BC-042 | Cedar Lane Indialantic | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 6 | 0.6 | B | 3.8 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.1028679100412 | -80.5827657581731 | Not provided
2983 | Brevard County | DEP | BC-043 | Riverview 9856 Indialantic | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 9 | 0.9 | B | 5.7 | 15000 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.1013652817158 | -80.5828682995247 | Not provided
2985 | Brevard County | DEP | BC-044 | Riverview 9864 Indialantic | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 202 | 33.4 | B | 98.5 | 15000 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.1012668999919 | -80.5772017990645 | Not provided
2984 | Brevard County | DEP | BC-045 | Oak Ridge Indialantic | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | Prior to 2013 | 257 | 38.8 | B | 126.5 | 15000 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2013 | North Indian River Lagoon | 28.1019106232559 | -80.5758663070259 | Not provided
2981 | Brevard County | SOIRL | BC-046 | Kingsmill-Aurora Phase 2 | Expansion of a Wet Detention Pond and adding Denitrifcation to pond slope. | Wet Detention Pond | Update with SWIL #s | Planned | 2022 | 4059 | 1589.8 | B | 1220.4 | 1600000 | 1000 | SOIRL | TBD | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.1427614962516 | -80.6778035873237 | TBD
2982 | Brevard County | N/A | BC-047 | Sediment Trap, Grated Inlet Basket, Inlet Weir Cleaning | Annual maintenance, removing captured debris from structures. | BMP Cleanout | Update with SWIL #s | Underway | Prior to 2013 | TBD | TBD | B | N/A | 392105 | 250000 | N/A | N/A | N/A | Non-structural |  | 2013 | North Indian River Lagoon | Not provided | Not provided | 2013
2986 | Brevard County | DEP | BC-048 | Merritt Ridge 3A | Alum pond. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | Prior to 2013 | 138 | 27 | B | 32.1 | 100362 | 41817.5 | DEP/ County | Not provided | G0430 | Structural |  | 2013 | North Indian River Lagoon | 28.3549515004408 | -80.6983512328677 | Not provided
2989 | Brevard County | DEP | BC-049 | Lake George | Construction of a regional wet detention pond. | Wet Detention Pond | Update with SWIL #s | Completed | 2017 | 505 | 51.3 | B | 719 | 51200 | Not provided | DEP/ County | Not provided | LP852 | Structural |  | 2013 | North Indian River Lagoon | 28.4553943410101 | -80.6868569308333 | Not provided
3008 | Brevard County | Not provided | BC-050 | Wickham Park | The provided treatment volume is .17 ac-It. | Stormwater Reuse | Update with SWIL #s | Completed | 2010 | 75 | 4.6 | B | Not provided | Not provided | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.1619906106918 | -80.6679901540891 | Not provided
3016 | Brevard County | Not provided | BC-051 | Ellington Park | Construction of a wet detention pond. | Stormwater Reuse | Update with SWIL #s | Completed | 2005 | 409 | 87 | B | Not provided | Not provided | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.4317554274821 | -80.7131145409253 | Not provided
3015 | Brevard County | Not provided | BC-052 | Rockledge Barton Park Reuse | Barton Park Pond was constructed by Rockledge. Brevard Parks withdraws water for irrigation for Rockledge Park. | Stormwater Reuse | Update with SWIL #s | Completed | 2009 | 262 | 24.1 | B | Not provided | Not provided | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.33243 | -80.73757 | Not provided
3014 | Brevard County | Not provided | BC-053 | Florida Boulevard Pond | Construction of a wet detention pond. | Wet Detention Pond | Update with SWIL #s | Completed | 2002 | 545 | 185.4 | B | 88.4 | 350384 | Not provided | Not provided | Not provided | N/A | Structural |  | 2013 | North Indian River Lagoon | 28.3897981636262 | -80.7053651710951 | Not provided
3006 | Brevard County | DEP | BC-054 | McGiver South | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2013 | 6 | 0.7 | B | 2.8 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2014 | North Indian River Lagoon | 28.2879510396651 | -80.6958981800002 | Not provided
3013 | Brevard County | DEP | BC-055 | 651 Franklyn | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2013 | 15 | 1.6 | B | 13.7 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2014 | North Indian River Lagoon | 28.0990862589316 | -80.5824334401226 | Not provided
2991 | Brevard County | Not provided | BC-056 | Fountainhead | Removing vegetation from a wet detention pond. | Aquatic Vegetation Harvesting | Keep original calcs | Completed | 2014 | 401 | 64.7 | B | 125.458 | 39274 | Not provided | Not provided | Not provided | N/A | Non-structural |  | 2014 | North Indian River Lagoon | 28.1237873544048 | -80.6702140646093 | Not provided
3012 | Brevard County | DEP | BC-057 | Fiske | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2014 | 317.2 | 55.7 | B | 126.2 | 12507 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2015 | North Indian River Lagoon | 28.3165803880435 | -80.7246078029694 | Not provided
3000 | Brevard County | Not provided | BC-058 | Street Sweeping | Monthly street sweeping. | Street Sweeping | Apply Rolling Average | Completed | N/A | 110 | 71 | A | N/A | N/A | 21000 | County | N/A | N/A | Non-structural |  | 2015 | North Indian River Lagoon | N/A | N/A | Not provided
3002 | Brevard County | N/A | BC-059 | Baffle Box/Sediment Trap Cleaning | Quarterly baffle box/sediment trap cleaning. | BMP Cleanout | Apply Rolling Average | Completed | 2015 | Not provided | Not provided | A | N/A | 250000 | 250000 | County | County - $250,000 | N/A | Non-structural |  | 2015 | North Indian River Lagoon | N/A | N/A | 2010
3003 | Brevard County | DEP | BC-060 | Huntington Road | Installation of vegetative floating island into an exiting detention pond. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | 2016 | 520 | 47 | A | 354.6415 | 45788 | 9997.5 | DEP/County | Not provided | G0430 | Structural |  | 2016 | North Indian River Lagoon | 28.7667743725469 | -80.8638293742923 | Not provided
3004 | Brevard County | DEP | BC-061 | Port St. John C | Installation of vegetative floating island into an exiting detention pond. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Update with SWIL #s | Completed | 2016 | 62 | 10.5 | B | 19.9881 | 14062 | 3070.5 | DEP/County | Not provided | G0430 | Structural |  | 2016 | North Indian River Lagoon | 28.4785448767231 | -80.7730351941441 | Not provided
3017 | Brevard County | DEP | BC-062 | Shoreview Circle | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2015 | Not provided | Not provided | B | Not provided | 11270 | 2140 | DEP | DEP - $275,000 | S0648 | Structural |  | 2016 | North Indian River Lagoon | 28.1075809774619 | -80.5845053688769 | Not provided
3007 | Brevard County | DEP | BC-063 | Granada West | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2015 | Not provided | Not provided | B | Not provided | 11220 | 2140 | DEP | DEP - $275,000 | S0649 | Structural |  | 2016 | North Indian River Lagoon | 28.3368291905656 | -80.6997091027625 | Not provided
2998 | Brevard County | DEP | BC-064 | Shoreview Lane | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2015 | Not provided | Not provided | B | Not provided | 24543.44 | 2140 | DEP | DEP - $275,000 | S0650 | Structural |  | 2016 | North Indian River Lagoon | 28.1088048130158 | -80.5841896061234 | Not provided
3009 | Brevard County | DEP | BC-065 | Sunset Park North | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2015 | Not provided | Not provided | B | Not provided | 11170 | 2140 | DEP | DEP - $275,000 | S0651 | Structural |  | 2016 | North Indian River Lagoon | 28.0967269129133 | -80.5758464395432 | Not provided
3010 | Brevard County | DEP | BC-066 | Oak Street | Upgrading a 1st Generation to a 2nd generation baffle box by adding the nutrient separating screen. | Baffle Boxes- Second Generation | Update with SWIL #s | Completed | 2015 | Not provided | Not provided | B | Not provided | 10895 | 2140 | DEP | DEP - $275,000 | S0652 | Structural |  | 2016 | North Indian River Lagoon | 28.05792 | -80.55826 | Not provided
3011 | Brevard County | DEP | BC-067 | Fountainhead Advanced Denitrification | Phosphorus reduction & denitrification. | Denitrification Walls |  | Underway | 2020 | 488 | TBD | B | 234.65 | 381000 | Not provided | DEP | Not provided | LP05115 | Structural |  | 2017 | North Indian River Lagoon | 28.4819040653135 | -80.7704608143167 | Not provided
3096 | Brevard County | DEP | BC-068 | Multiple Ditch Outfall Denitrification D1 | Providing base flow/grondwater treatment in open drainage basins. | Biosorption Activated Media (BAM) |  | Canceled | 2019 | TBD | TBD | A | Not provided | 900000 | Not provided | Florida Legislature/ Brevard County | 900600 | LP0511A | Structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | Not provided
2992 | Brevard County | DEP | BC-068a | Multiple Ditch Outfall Denitrification D1 | Providing base flow/grondwater treatment in open drainage basins. | Biosorption Activated Media (BAM) |  | Canceled | 2019 | TBD | TBD | B | Not provided | Not provided | Not provided | DEP | Not provided | LP0511A | Structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | Not provided
2993 | Brevard County | DEP | BC-069 | Multiple Ditch Outfall Denitrification D4 (replace by individual Basin #s/names) | Providing base flow/grondwater treatment in open drainage basins. | Biosorption Activated Media (BAM) |  | Planned | 2019 | TBD | TBD | B | Not provided | 2140000 | Not provided | DEP | Not provided | LP0511A | Structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | Not provided
2994 | Brevard County | Not provided | BC-070 | Otter Creek Basin D4 | Providing base flow/grondwater treatment in open drainage basins. | Biosorption Activated Media (BAM) |  | Planned | 2019 | TBD | TBD | B | Not provided | 130000 | Not provided | Not provided | Not provided | N/A | Structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | Not provided
2995 | Brevard County | SJRWMD | BC-071 | Suntree In-Channel Denitrification D4 | Providing base flow/grondwater treatment in open drainage basins. | Biosorption Activated Media (BAM) |  | Planned | 2018 | TBD | TBD | B | Not provided | 71000 | Not provided | SJRWMD | Not provided | N/A | Structural |  | 2017 | North Indian River Lagoon | 28.22371 | -80.67458 | Not provided
2996 | Brevard County | DEP | BC-072 | Multiple Ditch Outfall Denitrification D5 (replace by individual Basin#s/names) | Providing base flow/grondwater treatment in open drainage basins. | Biosorption Activated Media (BAM) |  | Underway | 2019 | TBD | TBD | B | Not provided | 100000 | Not provided | DEP | DEP - $100,000 | LP0511A | Structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | Not provided
3005 | Brevard County | SOIRL | BC-073 | EauGallie Area Muck Dredging | Not provided. | Muck Removal/Restoration Dredging | Not Provided | Completed | 2017 | TBD | TBD | B | Not provided | 26250000 | N/A | SOIRL | SOIRL - $26,250,000 | N/A | Non-structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | 2018
3060 | Brevard County | SOIRL | BC-074 | Flounder Creek Pond Denitrification Retrofit | Stormwater traditional BMP. | Biosorption Activated Media (BAM) |  | Planned | TBD | 856 | N/A | A | 320 | 157500 | 12307.5 | Not provided | Not provided | N/A | Structural |  | 2017 | North Indian River Lagoon | 28.75022 | -80.85404 | TBD
3047 | Brevard County | Not provided | BC-075 | Huntington Creek Pond Denitrification Retrofit | Not provided. | Biosorption Activated Media (BAM) |  | Planned | TBD | TBD | TBD | A | 355 | 180000 | 16662.5 | Not provided | Not provided | N/A | Structural |  | 2017 | North Indian River Lagoon |  |  | TBD
3048 | Brevard County | Not provided | BC-077 | Merritt Ridge 2B D2 | Not provided. | Grass Swales without Swale Blocks or Raised Culverts | Update with SWIL #s | Completed | 2016 | Not provided | Not provided | B | 2 | 45000 | Not provided | Not provided | Not provided | N/A | Structural |  | 2017 | North Indian River Lagoon | 28.35449 | -80.70376 | Not provided
3049 | Brevard County | Not provided | BC-078 | Merritt Ridge 2E D2 | Wet detention pond construction. | Wet Detention Pond |  | Planned | TBD | TBD | TBD | B | Not provided | 720000 | Not provided | Not provided | Not provided | N/A | Structural |  | 2017 | North Indian River Lagoon | 28.35206 | -80.70145 | TBD
3051 | Brevard County | N/A | BC-080 | Wickham Park Solar Bee | Installing a mixer to reduce the amount of algae and cyanobacteria on an existing pond. | BMP Treatment Train |  | Planned | TBD | TBD | TBD | B | TBD | TBD | TBD | TBD | TBD | N/A | Structural |  | 2017 | North Indian River Lagoon | 28.15881 | -80.65674 | TBD
3052 | Brevard County | All Cities | BC-081 | Education Efforts | Fertilizer video, rain barrel workshops, Facebook page, bus wrap, and billboard. | Education Efforts | Apply New Information | Completed | N/A | N/A | N/A | A | N/A | 50000 | TBD | SOIRL | SOIRL - $50,000 | N/A | Non-structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | 2017
3019 | Brevard County | All Cities | BC-081a | Education Efforts | Fertilizer video, rain barrel workshops, Facebook page, bus wrap, and billboard. | Education Efforts | Apply New Information | Completed | N/A | N/A | N/A | B | N/A | Not provided | TBD | SOIRL | Not provided | N/A | Non-structural |  | 2017 | North Indian River Lagoon | Not provided | Not provided | 2017
3059 | Brevard County | N/A | BC-088 | Septic Removal - NIRL -MIRA | SOIRL-44. | OSTDS Phase Out |  | Underway | 2020 | TBD | N/A | B | Not provided | 2130852 | Not provided | SOIRL | SOIRL - $2,130,852 | N/A | Structural |  | 2017 | North Indian River Lagoon | 28.72321 | -80.84407 | Not provided
3062 | Brevard County | SOIRL | BC-091 | Kingsmill Aurora Phase II | Construction of 5 ac pond with weirs, drop structures, etc. | Wet Detention Pond |  | Underway | 2019 | 6264 | 814 | A | 1212.8 | 990000 | N/A | SOIRL/ BC | Not provided | N/A | Structural |  | 2017 | North Indian River Lagoon | 28.135 | -80.67001 | 2017
3063 | Brevard County | N/A | BC-092 | Baffle Box/Sediment Trap Cleaning | Increasing cleanout frequency to quarterly. | BMP Cleanout | Apply Rolling Average | Completed | N/A | 1 | 1 | A | N/A | Not provided | 276303.28 | County | Not provided | N/A | Non-structural |  | 2015 | North Indian River Lagoon | Not provided | Not provided | 2008
4451 | Brevard County | N/A | BC-093 | N. Wickham Road Upflow Filter - BB#1298 | Upflow filter with Biosorption Activated Media installed within existing detention pond system to remove nitrogen from baseflow. | Biosorption Activated Media (BAM) |  | Underway | 2019 | 917 | 116 | B | 170 | 125000 | 2500 | Legislative Funding | Legislative Funding - $35,000 | LP0511A | Structural |  | 2018 | North Indian River Lagoon | 28.20805 | -80.67363 | Not provided
4452 | Brevard County | SOIRL | BC-094 | Johns Rd Pond BAM - BB#62 (Actually located in 51) | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | 245 | 37 | A | Not provided | 172000 | Not provided | LF/SOIRL | 58030 | N/A | Structural |  | 2018 | North Indian River Lagoon | 28.75624 | -80.8612 | Not provided
4453 | Brevard County | SOIRL | BC-095 | Burkholm Rd BAM - BB#100 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | 685 | 104 | A | Not provided | 161000 | Not provided | LF/SOIRL | 99390 | N/A | Structural |  | 2018 | North Indian River Lagoon | 28.72321 | -80.84407 | Not provided
4454 | Brevard County | SOIRL | BC-096 | Carter Rd BAM- BB#115 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | 665 | 101 | A | Not provided | 176000 | Not provided | LF/SOIRL | 97510 | N/A | Structural |  | 2018 | North Indian River Lagoon | 28.71043 | -80.84092 | Not provided
4455 | Brevard County | SOIRL | BC-097 | Wiley Rd BAM - BB#193 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | 954 | 144 | A | Not provided | 179000 | Not provided | LF/SOIRL | 117735 | N/A | Structural |  | 2018 | North Indian River Lagoon | 28.67395 | -80.8519 | Not provided
4456 | Brevard County | SOIRL | BC-098 | Broadway Pond BAM - BB#832 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | 456 | 69 | A | Not provided | 290000 | Not provided | LF/SOIRL | 77864 | N/A | Structural |  | 2018 | North Indian River Lagoon | 28.46001 | -80.76361 | Not provided
5347 | Brevard County | SOIRL/ Brevard Zoo | BC-100 | Bomalaski Oyster Bar | Construct 100 linear foot oyster reef. | Creating/ Enhancing Oyster Reefs |  | Completed | 2018 | TBD | TBD | B | Not provided | 8900 | Not provided | SOIRL | SOIRL - $8,900 | N/A | Structural |  | 2019 | North Indian River Lagoon | 28.146442 | -80.60597 | Not provided
5348 | Brevard County | SOIRL/ MRC | BC-101 | Grass Clippings Campaign Phase 1 | Not provided. | Education Efforts | Apply New Information | Completed | 2019 | TBD | TBD | A | N/A | 6667 | N/A | SOIRL | SOIRL - $20,000 | N/A | Non-structural |  | 2019 | North Indian River Lagoon | Not provided | Not provided | Not provided
5349 | Brevard County | SOIRL/ MRC | BC-101a | Grass Clippings Campaign Phase 1 | Not provided. | Education Efforts | Apply New Information | Completed | 2019 | TBD | TBD | B | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural |  | 2019 | North Indian River Lagoon | Not provided | Not provided | Not provided
5350 | Brevard County | SOIRL | BC-102 | Education Efforts | Fertilizer, grass clippings, and septic system maintenance. | Education Efforts |  | Underway | 2027 | TBD | TBD | A | Not provided | 375000 | Not provided | SOIRL | SOIRL - $375,000 | N/A | Non-structural |  | 2019 | North Indian River Lagoon | Not provided | Not provided | Not provided
5351 | Brevard County | SOIRL | BC-102a | Education Efforts | Fertilizer, grass clippings, and septic system maintenance. | Education Efforts |  | Underway | 2027 | TBD | TBD | B | Not provided | N/A | N/A | N/A | N/A | N/A | Non-structural |  | 2019 | North Indian River Lagoon | Not provided | Not provided | Not provided
5352 | Brevard County | SOIRL | BC-103 | Mims Muck Removal: Outflow Water Nutrient Removal | Not provided. | Muck Removal/Restoration Dredging | Not Provided | Completed | N/A | TBD | TBD | A | Not provided | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural |  | 2019 | North Indian River Lagoon | Not provided | Not provided | Not provided
5353 | Brevard County | LF/ SOIRL | BC-104 | Countyline Ditch Road - BB#10 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | TBD | TBD | A | Not provided | 200000 | Not provided | LF/SOIRL | 107773 | N/A | Structural |  | 2019 | North Indian River Lagoon | 28.79108 | -80.88132 | Not provided
5354 | Brevard County | LF/ SOIRL | BC-105 | BB#141 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | TBD | TBD | A | Not provided | 164000 | Not provided | LF/SOIRL | 104174 | N/A | Structural |  | 2019 | North Indian River Lagoon | 28.69575 | -80.84406 | Not provided
5355 | Brevard County | LF | BC-106 | Huntington Road BAM - BB#22 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2020 | TBD | TBD | A | Not provided | TBD | Not provided | LF/SOIRL | 35000 | N/A | Structural |  | 2019 | North Indian River Lagoon | 28.76936 | -80.8519 | Not provided
5356 | Brevard County | Not provided | BC-107 | Sunste Ave BAM - BB#26 | Adding a media to remove nitrogen by denitrification. The media will be added to the side slope of the pond or the bottom of the swale. | Biosorption Activated Media (BAM) |  | Underway | 2021 | TBD | TBD | A | Not provided | TBD | Not provided | Not provided | Not provided | N/A | Structural |  | 2019 | North Indian River Lagoon | 28.77429 | -80.85429 | Not provided
5357 | Brevard County | SOIRL/ SJRWMD | BC-108 | MIRA Phase 1 Septic to Sewer | Connect approximately 11 properties to a central sewer system. | OSTDS Phase Out | Not Provided | Completed | 2017 | TBD | N/A | B | N/A | 320000 | Not provided | SOIRL/ SJWMD | Not provided | N/A | Structural |  | 2019 | North Indian River Lagoon | Not provided | Not provided | Not provided
5358 | Brevard County | N/A | BC-109 | Denitrifcation Basin - 1329 | Upflow filter through a BAM media to treat baseflow. | Biosorption Activated Media (BAM) |  | Underway | 2020 | TBD | TBD | B | Not provided | 155113 | Not provided | LF/ SOIRL | 70000 | LP0511A | Structural |  | 2019 | North Indian River Lagoon | 28.18338 | -80.60114 | Not provided