## BMAP Projects
ProjectNumber | LeadEntity | Partners | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | GIS_Shapefile
AFR-01 | Avon Park Air Force Range | N/A | Cancellation of Cattle Lease | Land use change from agriculture to natural. | Land Use Change | Completed | 2018 | TBD | TBD | Upper Kissimmee | 23975 | N/A | N/A | N/A | N/A | N/A | PDF map provided
AP-01 | City of Avon Park | N/A | Avon Park Street Sweeping | Street sweeping. | Street Sweeping | Canceled | N/A | 25 | 10 | Lake Istokpoga | N/A | Not provided | Not provided | City of Avon Park | Not provided | N/A
AP-02 | City of Avon Park | N/A | Lake Tulane Stormwater Improvement Project | Runoff will be captured in a series of swales that will allow the runoff to percolate into the sandy soils, preventing further degradation of Lake Tulane. | Grass Swales Without Swale Blocks or Raised Culverts | Canceled | TBD | 36 | 4 | Lake Istokpoga | 32.1 | Not provided | Not provided | City of Avon Park/ Southwest Florida Water Management District (SWFWMD) | Not provided | N/A
AP-03 | City of Avon Park | N/A | Lake Isis Stormwater Improvement Project | Runoff will be captured in a lakeside swale and a redesigned pond that will allow the runoff to percolate into the sandy soils, preventing further degradation of Lake Isis. | Wet Detention Pond | Completed | Completed | 11 | 1 | Lake Istokpoga | 37.1 | Not provided | Not provided | City of Avon Park/ SWFWMD | Not provided | N/A
CA-01 | Coordinating Agency | N/A | Brighton Valley Dispersed Water Management (DWM) | This NE-PPP project is estimated to provide a net annual average benefit of 39,765 ac-ft of treated water via a passthrough system. | Dispersed Water Management (DWM) | Underway | 2019 | 60186 | 7055 | Indian Prairie | 8200 | 42642088 | 3125000 | FDACS/ Florida Legislature | $11,500,000.00 | N/A
CA-02 | Coordinating Agency | N/A | Inactive Dairies - Lagoon Remediation | FDACS worked with a dairy in the LOW to partially remediate its lagoon. Soil was spread on the field for the crops to use the nutrients, and stormwater routed to remediated pond and reused to minimize discharges and groundwater withdrawls. | Dairy Remediation | Completed | Not provided | Not provided | Not provided | Taylor Creek/ Nubbin Slough | Not provided | Not provided | Not provided | FDACS | Not provided | N/A
CA-03 | Coordinating Agency | N/A | Inactive Dairies - Lagoon Remediation | See CA-02. | Dairy Remediation | Completed | Not provided | Not provided | Not provided | Indian Prairie | Not provided | Not provided | Not provided | FDACS | Not provided | N/A
CA-04 | Coordinating Agency | N/A | Lakeside Ranch Phase II | Phase II Includes southern STA and pump station (S-191), also known as Phase III in 2018 Ops Plan, to manage rim canal levels during high flow and potentially recirculate lake water back to STA for further TP removal. | Stormwater Treatment Areas (STAs) | Underway | 2021 | TBD | 16755 | Taylor Creek/ Nubbin Slough | 788 | 58000000 | N/A | Florida Legislature | Florida Legislature - $58,000,000 | N/A
CA-05 | Coordinating Agency | N/A | El Maximo Ranch DWM (formerly Latt Maxcy DWM) | This NE-PPP project is estimated to provide a net annual average benefit of 32,675 ac-ft of treated water via a pass-through system. | Dispersed Water Management (DWM) | Underway | 2020 | TBD | 4409 | Lower Kissimmee | 7030 | Not provided | Not provided | FDACS | Not provided | N/A
CA-06 | Coordinating Agency | N/A | Legislative Cost-Share Appropriation Program (Dairy Projects) | FDACS conducted 3 rounds of solicitations for dairy project proposals. The first solicitation was in fall 2014. Seven projects were funded, of which one is still under construction. The second solicitation for dairy projects occurred in fall 2015. Four pr | Dairy Remediation | Underway | TBD | TBD | TBD | Fisheating Creek | TBD | Not provided | Not provided | FDACS | Not provided | N/A
CA-07 | Coordinating Agency | N/A | Legislative Cost-Share Appropriation Program (Dairy Projects) | See CA-07. | Dairy Remediation | Underway | TBD | TBD | TBD | Indian Prairie | TBD | Not provided | Not provided | FDACS | Not provided | N/A
CA-08 | Coordinating Agency | N/A | Legislative Cost-Share Appropriation Program (Dairy Projects) | See CA-07. | Dairy Remediation | Underway | TBD | TBD | TBD | Lake Istokpoga | TBD | Not provided | Not provided | FDACS | Not provided | N/A
CA-09 | Coordinating Agency | N/A | Legislative Cost-Share Appropriation Program (Dairy Projects) | See CA-07. | Dairy Remediation | Underway | TBD | TBD | TBD | Lower Kissimmee | TBD | Not provided | Not provided | FDACS | Not provided | N/A
CA-10 | Coordinating Agency | N/A | Legislative Cost-Share Appropriation Program (Dairy Projects) | See CA-07. | Dairy Remediation | Underway | TBD | TBD | TBD | Taylor Creek/ Nubbin Slough | TBD | Not provided | Not provided | FDACS | Not provided | N/A
CA-11 | Coordinating Agency | N/A | Legislative Cost-Share Appropriation Program (Dairy Projects) | See CA-07. | Dairy Remediation | Underway | TBD | TBD | TBD | Upper Kissimmee | TBD | Not provided | Not provided | FDACS | Not provided | N/A
CA-12 | Coordinating Agency | NRCS | PL-566 Funded/Fisheating Creek Structure | USACE was working NRCS to develop alternatives. After staffing and priority changes at the USACE the NRCS took lead. Currently a scope of work has been developed with original contractor who will begin work again once approval and paperwork is done. | Control Structure | Planned | TBD | TBD | 1947 | Indian Prairie | TBD | TBD | TBD | TBD | TBD | N/A
CA-13 | Coordinating Agency | N/A | Rolling Meadows Wetland Restoration Phase II | Land has been acquired and a conceptual plan has been recommended. Implementation of Phase II is contingent upon the success of Phase I and future legislative funding. Schedule: If approved and funded, project completion is anticipated in 2 to 3 yrs. | Wetland Restoration | Planned | TBD | TBD | 20 | Upper Kissimmee | 580 | TBD | TBD | TBD | TBD | N/A
CA-14 | Coordinating Agency | FDOT | SR 710 Regional Project | The feasibility study was completed. FDOT is reviewing several conceptual designs. The Coordinating Agencies are also reviewing to determine whether multiple program initiatives can be aligned for a greater project impact. | Stormwater System Rehabilitation | Completed | TBD | TBD | TBD | Taylor Creek/ Nubbin Slough | TBD | TBD | TBD | FDOT | TBD | N/A
CA-15 | Coordinating Agency | FDOT | SR 710 Regional Project | See FDOT project | Stormwater System Rehabilitation | Canceled | TBD | TBD | TBD | Indian Prairie | TBD | TBD | TBD | FDOT | TBD | N/A
CO-01 | City of Okeechobee | SFWMD/ DEP | Centennial Park Stormwater Drainage Construction | Upgrade stormwater infrastructure by constructing a nutrient separating baffle box, bioswale, and removal and replacement of pipe. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2018 | 32 | 6 | Taylor Creek/ Nubbin Slough | 15 | 411412 | 8000 | City of Okeechobee/ SFWMD/ DEP | DEP - $183,630/ City - $227,782 | NS018
CO-02 | City of Okeechobee | N/A | South 4th Street Stormwater Drainage Construction | Upgrade stormwater infrastructure by constructing a nutrient separating baffle box, bioswale, and removal and replacement of pipe. | Baffle Boxes- First Generation (hydrodynamic separator) | Planned | TBD | TBD | TBD | Taylor Creek/ Nubbin Slough | 170 | 300000 | 10000 | TBD | 300000 | N/A
CO-03 | City of Okeechobee | DEP | SE 8th Stormwater Drainage Construction | Upgrade stormwater infrastructure by constructing a nutrient separating baffle box, bioswale, and removal and replacement of pipe. | Baffle Boxes- First Generation (hydrodynamic separator) | Planned | 2020 | TBD | TBD | Taylor Creek/ Nubbin Slough | 10 | 219000 | 8000 | City of Okeechobee/ DEP | DEP 80%/ City 20% | Not provided
CO-04 | City of Okeechobee | N/A | Citywide Street Sweeping | Removal of turbidity and excess nutrients from runnoff | Street Sweeping | Completed | N/A | TBD | TBD | Taylor Creek/ Nubbin Slough | 650 | 75000 | 75000 | City of Okeechobee | 100% City of Okeechobee | N/A
EW-01 | City of Edgewood | N/A | Water Quality Awareness Program | Water quality education and awareness articles in the city quarterly newsletter. Water quality-related informational brochures, fliers and other publications displayed at city hall for the public. | Education Efforts | Completed | N/A | 38 | 1 | Upper Kissimmee | N/A | N/A | 1000 | City of Edgewood | $1,000 | N/A
EW-02 | City of Edgewood | Orange County | Street Sweeping | Orange County performs weekly sweeping of approximately 15.6 miles of streets within the City limits | Street Sweeping | Completed | N/A | 55.13 | 35.35 | Upper Kissimmee | 45 | N/A | N/A | Orange County | N/A | N/A
EW-03 | City of Edgewood | Orange County | Catch Basin Inlet Cleaning | Orange County performs monthly cleaning of storm inlet baskets for debris removal | Catch Basin Inserts | Completed | N/A | 7.31 | 4.49 | Upper Kissimmee | N/A | N/A | N/A | Orange County | N/A | N/A
FDACS-01 | FDACS | SFWMD | Lemkin Creek | HWTT is a combination of wetland and chemical treatment technologies designed mainly to remove phosphorus at the subbasin and parcel scales. | Hybrid wetland treatment technology (HWTT) | Completed | 2009 | 1815 | 669 | Lemkin Creek | 1522 | 635970 | 417000 | FDACS | Not provided | N/A | Not provided
FDACS-02 | FDACS | SFWMD | Wolff Ditch | HWTT is a combination of wetland and chemical treatment technologies designed mainly to remove phosphorus at the subbasin and parcel scales. | Hybrid wetland treatment technology (HWTT) | Completed | 2009 | 2505 | 740 | Wolff Ditch | 1930 | 1036070 | 495000 | FDACS | Not provided | N/A | Not provided
FDACS-03 | FDACS | SFWMD | Grassy Island | HWTT is a combination of wetland and chemical treatment technologies designed mainly to remove phosphorus at the subbasin and parcel scales. | Hybrid wetland treatment technology (HWTT) | Completed | 2010 | 11557 | 3218 | Taylor Creek/Nubbin Slough | 37802 | 5041338 | 1611000 | FDACS | Not provided | N/A | Not provided
FDACS-04 | FDACS | Private Landowner | Fisheating Creek | FAVT is a floating aquatic vegetation treatment. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Completed | 2016 | 24204 | 5581 | Fisheating Creek | 45000 | 3311070 | 1945000 | FDACS | Not provided | N/A | Not provided
FDACS-05 | FDACS | Private Landowner | Nubbin Slough | HWTT is a combination of wetland and chemical treatment technologies designed mainly to remove phosphorus at the subbasin and parcel scales. | Hybrid wetland treatment technology (HWTT) | Completed | 2008 | 1994 | 1554 | Taylor Creek/Nubbin Slough | 2000 | 900260 | 352000 | FDACS | Not provided | N/A | Not provided
FDACS-06 | FDACS | Private Landowner | Mosquito Creek | HWTT is a combination of wetland and chemical treatment technologies designed mainly to remove phosphorus at the subbasin and parcel scales. | Hybrid wetland treatment technology (HWTT) | Completed | 2008 | 5429 | 2049 | Taylor Creek/Nubbin Slough | 5000 | 1263920 | 483000 | FDACS | Not provided | N/A | Not provided
FDACS-07 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - Fisheating Creek. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | 149372 | 15388 | Fisheating Creek | 65017.688 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-08 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - Indian Prairie. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | 267483 | 14824 | Indian Prairie | 213487.2255 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-09 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - Lake Istokpoga. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | 265404 | 3783 | Lake Istokpoga | 168306.2293 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-10 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - Lower Kissimmee. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | 208106 | 14528 | Lower Kissimmee | 289807.1723 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-11 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - Taylor Creek/Nubbin Slough. Acres treated based on FDACS OAWP December 2018 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | 111389 | 17044 | Taylor Creek/Nubbin Slough | 144556.5993 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-12 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - Upper Kissimmee. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | 370827 | 7851 | Upper Kissimmee | 179607.0646 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-13 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - East Lake Okeechobee. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | TBD after LET updated | TBD after LET updated | East Lake Okeechobee | 71004 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-14 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - South Lake Okeechobee. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | TBD after LET updated | TBD after LET updated | South Lake Okeechobee | 298158.9155 | N/A | N/A | FDACS | TBD | N/A | Yes
FDACS-15 | FDACS | Agricultural Producers | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers - West Lake Okeechobee. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID V. Reductions were estimated using 2019 BMAP LET. | Agricultural BMPs | Completed | N/A | TBD after LET updated | TBD after LET updated | West Lake Okeechobee | 153720.2535 | N/A | N/A | FDACS | TBD | N/A | Yes
FDOT1-01 | FDOT District 1 | N/A | State Road 70 from 34th Avenue to 80th Avenue | Six wet detention ponds. | Wet Detention Pond | Completed | 2018 | 94 | 50 | Taylor Creek/ Nubbin Slough | 57.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT1-02 | FDOT District 1 | N/A | State Road 70 from 80th Avenue to St. Lucie County Line | Three wet detention ponds and three dry retention swales. | Wet Detention Pond | Completed | 2018 | 87 | 39 | Taylor Creek/ Nubbin Slough | 31.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT1-03 | FDOT District 1 | N/A | Street Sweeping | Street sweeping. | Street Sweeping | Completed | N/A | 152 | 240 | Taylor Creek/ Nubbin Slough | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT4-01 | FDOT District 4 | N/A | FM# 432705-1 / SR 710 | SR-710/Beeline Highway widening from two to four lanes. | Grass swales without swale blocks or raised culverts | Underway | 2019 | TBD | TBD | East Lake Okeechobee | 159 | Not provided | Not provided | Not provided | Not provided | N/A | 432705_RoW_area.shp
FDOT4-02 | FDOT District 4 | N/A | Public Education | Pamphlets. | Education Efforts | Completed | N/A | TBD | TBD | East Lake Okeechobee | N/A | Not provided | Not provided | Not provided | Not provided | N/A
FDOT4-03 | FDOT District 4 | N/A | Street Sweeping | Continued sweeping. | Street Sweeping | Completed | N/A | TBD | TBD | East Lake Okeechobee | 3104 | Not provided | Not provided | Not provided | Not provided | N/A
FDOT4-04 | FDOT District 4 | N/A | Catch Basin Clean-out | Continued cleanout. | BMP Cleanout | Completed | N/A | TBD | TBD | East Lake Okeechobee | N/A | Not provided | Not provided | Not provided | Not provided | N/A
FDOT5-01 | FDOT District 5 | N/A | 239266-B State Road 15 (Hoffner Road) from north of Lee Vista Boulevard to west of State Road 436 (Pond 2) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2019 | 2.59 | 0.76 | Upper Kissimmee | 6.3 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-02 | FDOT District 5 | N/A | 239266-A State Road 15 Hoffner Ave from east of State Road 436 to Conway Road (Pond 1) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2019 | 3.96 | 1.04 | Upper Kissimmee | 9.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-03 | FDOT District 5 | N/A | 239266-C State Road 15 Hoffner Avenue from west of State 436 to Conway Road (Pond 3) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2019 | 10.45 | 2.66 | Upper Kissimmee | 26.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-04 | FDOT District 5 | N/A | 239266-D State Road 15 Hoffner Avenue from west of State Road 436 to Conway Road (Pond 4) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2019 | 8.83 | 2.7 | Upper Kissimmee | 23.94 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-05 | FDOT District 5 | N/A | 239535-F State Road 50 from Good Homes Road to Pine Hills Road (Pond 4) | Add lanes and reconstruct. | Dry Detention Pond | Completed | 2014 | 9 | 2 | Upper Kissimmee | 16.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-06 | FDOT District 5 | N/A | 416518-A Interstate (I) 4 Braided Ramp from US 192 Interchange to Osceola Parkway Interchange (Pond SE-1) | New road construction. | Wet Detention Pond | Completed | 2014 | 5 | 1 | Upper Kissimmee | 13.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-07 | FDOT District 5 | N/A | 416518-B Interstate-4 Braided Ramp from US 192 Interchange to Osceola Parkway Interchange (Pond SE-2) | New road construction. | Wet Detention Pond | Completed | 2014 | 2 | 0 | Upper Kissimmee | 6.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-08 | FDOT District 5 | N/A | 239682-A State Road 500 (US 17-92) from Aeronautical Drive to Budinger Avenue (Pond 1) | Add lanes and rehabilitate pavement. | Wet Detention Pond | Underway | 2020 | 13 | 2 | Upper Kissimmee | 26.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-09 | FDOT District 5 | N/A | 239682-B State Road 500 (US 17-92) from Aeronautical Drive to Budinger Avenue (Pond 2) | Add lanes and rehabilitate pavement. | Wet Detention Pond | Underway | 2020 | 8 | 1 | Upper Kissimmee | 13.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-10 | FDOT District 5 | N/A | 239682-C State Road 500 (US 17-92) from Aeronautical Drive to Budinger Avenue (Pond 3) | Add lanes and rehabilitate pavement. | Wet Detention Pond | Underway | 2020 | 7 | 1 | Upper Kissimmee | 15.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-11 | FDOT District 5 | N/A | 239682-D State Road 500 (US 17-92) from Aeronautical Drive to Budinger Avenue (Pond 4) | Add lanes and rehabilitate pavement. | Wet Detention Pond | Underway | 2020 | 15 | 2 | Upper Kissimmee | 33.7 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-12 | FDOT District 5 | N/A | 418403-A, B State Road 600 (US 17/92) John Young Parkway (JYP) from south of Portage Street to north of Vine Street (US192) (Ponds East and West) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2019 | 19.01 | 1.94 | Upper Kissimmee | 45.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-13 | FDOT District 5 | N/A | 239454-A widening of SR 436 from SR 528 to SR 552 (Pond A) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2010 | 2 | 1 | Upper Kissimmee | 38.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-14 | FDOT District 5 | N/A | 239635-A New Bridge State Road 500 at Reedy Creek (Pond 1) | New bridge. | Dry Detention Pond | Completed | 2010 | 1 | 0 | Upper Kissimmee | 4.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-15 | FDOT District 5 | N/A | 239635-B New Bridge State Road 500 at Reedy Creek (Pond 2) | New bridge. | Wet Detention Pond | Completed | 2010 | 7 | 0 | Upper Kissimmee | 7.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-16 | FDOT District 5 | N/A | 239663-A Widening of State Road 530 from State Road 535 to Hoagland Boulevard (Pond 1) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2010 | 5 | 1 | Upper Kissimmee | 14.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-17 | FDOT District 5 | N/A | 239663-B Widening of State Road 530 from State Road 535 to Hoagland Boulevard (Pond 2) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2010 | 6 | 2 | Upper Kissimmee | 17.9 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-18 | FDOT District 5 | N/A | 239663-C Widening of State Road 530 from State Road 535 to Hoagland Boulevard (Pond 3) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2010 | 5 | 2 | Upper Kissimmee | 16.9 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-19 | FDOT District 5 | N/A | 239663-D Widening of State Road 530 from State Road 535 to Hoagland Boulevard (Pond 4) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2010 | 5 | 1 | Upper Kissimmee | 12.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-20 | FDOT District 5 | N/A | 242436-A State Road 400 Ramps at Gore Avenue Retention Pits (Ponds 1 and 2) | Ramps. | Dry Detention Pond | Completed | 2011 | 6 | 0 | Upper Kissimmee | 9.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-21 | FDOT District 5 | N/A | 242484-A Widening of State Road 400 from Universal Boulevard to South Street (Pond 4) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2011 | 7 | 1 | Upper Kissimmee | 21.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-22 | FDOT District 5 | N/A | 405515-A and B State Road 400 Wet Detention Pond (Ponds 1 and 2) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2011 | 3 | 0 | Upper Kissimmee | 14.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-23 | FDOT District 5 | N/A | 410732-B State Road 400 Swales | Add lanes and reconstruct. | Grass Swales Without Swale Blocks or Raised Culverts | Completed | 2010 | 3 | 0 | Upper Kissimmee | 32.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-24 | FDOT District 5 | N/A | Street Sweeping | Street sweeping to collect 1,507,453 lbs/yr of material. | Street Sweeping | Completed | N/A | 229 | 147 | Upper Kissimmee | Varies | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-25 | FDOT District 5 | N/A | Education and Outreach | Funding for Orange County Water Atlas website, and illicit discharge inspection and training program. | Education Efforts | Completed | N/A | 44 | 4 | Upper Kissimmee | Varies | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-26 | FDOT District 5 | N/A | 2396831 Pond 6 (SR 500 widening from Eastern Ave. to Nova Road) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2017 | 198 | 22 | Upper Kissimmee | 19.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-27 | FDOT District 5 | N/A | 2396831 Pond 7 (SR 500 widening from Eastern Ave. to Nova Road) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2017 | 240 | 13 | Upper Kissimmee | 23.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-28 | FDOT District 5 | N/A | 407143-4 Ponds WDA 2A and 2B (SR 482 widening from west of Turkey Lake Rd. to east of Universal Blvd.) | Add lanes and reconstruct. | Wet Detention Pond | Underway | 2019 | 128 | 3 | Upper Kissimmee | 23 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-29 | FDOT District 5 | N/A | 407143-4 Pond WDA 3 (SR 482 widening from west of Turkey Lake Rd. to east of Universal Blvd.) | Add lanes and reconstruct. | Wet Detention Pond | Underway | 2019 | 35 | 1 | Upper Kissimmee | 23 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-30 | FDOT District 5 | N/A | 407143-4 Pond WDA 4 (SR 482 widening from west of Turkey Lake Rd. to east of Universal Blvd.) | Add lanes and reconstruct. | Wet Detention Pond | Underway | 2019 | 159 | 4 | Upper Kissimmee | 23 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-31 | FDOT District 5 | N/A | 407143-6 State Road 482 (Sand Lake Rd) at John Young Parkway - Overpass over Sand Lake | Overpass over Sand Lake at John Young Parkway (2 wet detention Ponds for FM 407143-1). | Wet Detention Pond | Underway | 2019 | 15 | 1 | Upper Kissimmee | 38.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-32 | FDOT District 5 | N/A | 239714-SR 600 from W of Poinciana to CR 535 (Pond 1) | Add lanes and reconstruct. | Wet Detention Pond | Underway | 2021 | 5.1 | 1.99 | Upper Kissimmee | 13 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-33 | FDOT District 5 | N/A | 239714-SR 600 from W of Poinciana to CR 535 (Pond 2) | Add lanes and reconstruct. | Wet Detention Pond | Underway | 2021 | 4.33 | 1.44 | Upper Kissimmee | 13.3 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-34 | FDOT District 5 | N/A | 239714-SR 600 from W of Poinciana to CR 535 (Pond 3) | Add lanes and reconstruct. | Wet Detention Pond | Underway | 2021 | 1.15 | 0.3 | Upper Kissimmee | 4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-35 | FDOT District 5 | N/A | 239304-SR 530 from Lake C/L to E of Secret Lake Dr (Pond 1) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2014 | 3.3 | 0.82 | Upper Kissimmee | 11 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-36 | FDOT District 5 | N/A | 239304-SR 530 from Lake C/L to E of Secret Lake Dr (Pond 5) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2014 | 3.23 | 0.67 | Upper Kissimmee | 11.9 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-37 | FDOT District 5 | N/A | 238422- SR 25 from Boggy Marsh Rd to N of Lake Louisa Rd (Pond A) | Add lanes and reconstruct. | Dry Detention Pond | Completed | 2018 | 0.65 | 0.08 | Upper Kissimmee | 18.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-38 | FDOT District 5 | N/A | 238422- SR 25 from Boggy Marsh Rd to N of Lake Louisa Rd (Pond B) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2018 | 7.49 | 1.67 | Upper Kissimmee | 29.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-39 | FDOT District 5 | N/A | 238422- SR 25 from Boggy Marsh Rd to N of Lake Louisa Rd (Pond C) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2018 | 0.47 | 0.14 | Upper Kissimmee | 7.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-40 | FDOT District 5 | N/A | 238422- SR 25 from Boggy Marsh Rd to N of Lake Louisa Rd (Pond D) | Add lanes and reconstruct. | Wet Detention Pond | Completed | 2018 | 1.54 | 0.54 | Upper Kissimmee | 30.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT5-41 | FDOT District 5 | N/A | 238422- SR 25 from Boggy Marsh Rd to N of Lake Louisa Rd (Pond E) | Add lanes and reconstruct. | Dry Detention Pond | Completed | 2018 | 0.3 | 0.04 | Upper Kissimmee | 30.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
GC-01 | Glades County | N/A | Education and Outreach | FYN; landscaping, irrigation, and fertilizer ordinances; PSAs, pamphlets, website, and illicit discharge program. | Education Efforts | Completed | N/A | 174 | 30 | Fisheating Creek | N/A | Not provided | 5500 | Glades County | Not provided | N/A
GC-02 | Glades County | N/A | Education and Outreach | FYN; landscaping, irrigation, and fertilizer ordinances; PSAs, pamphlets, website, and illicit discharge program. | Education Efforts | Completed | N/A | 915 | 65 | Indian Prairie | N/A | Not provided | 5500 | Glades County | Not provided | N/A
GC-03 | Glades County | N/A | Glades County Caloosahatchee River & Estuary Area Wastewater Grant | Elimination of aging and/or failing existing septic systems in the City of Moore Haven. The Project also provides for additional conveyance capacity for additional homes and businesses. | OSTDS Phase Out | Planned | 2021 | TBD | TBD | West Lake Okeechobee | 86.5 | 891848 | 12240 | GAA | $891,848.00 | LP22023
GC-04 | Glades County | N/A | Glades County Business Park Wetlands | Wetland Maintenance and Planting Agreement | Wetland Restoration | Planned | 2021 | TBD | TBD | West Lake Okeechobee | 8.84 | 42395 | Not provided | Glades County | 42395 | N/A
HC-01 | Highlands County | UF-IFAS | Education and Outreach | FYN, landscaping and irrigation ordinances, PSAs, and pamphlets. | Education Efforts | Completed | N/A | 799 | 65 | Fisheating Creek | N/A | Not provided | Not provided | Highlands County | Not provided | N/A
HC-02 | Highlands County | UF-IFAS | Education and Outreach | FYN, landscaping and irrigation ordinances, PSAs, and pamphlets. | Education Efforts | Completed | N/A | 915 | 65 | Indian Prairie | N/A | Not provided | Not provided | Highlands County | Not provided | N/A
HC-03 | Highlands County | UF-IFAS | Education and Outreach | FYN, landscaping and irrigation ordinances, PSAs, and pamphlets. | Education Efforts | Completed | N/A | 14508 | 342 | Lake Istokpoga | N/A | Not provided | Not provided | Highlands County | Not provided | N/A
HC-04 | Highlands County | UF-IFAS | Education and Outreach | FYN, landscaping and irrigation ordinances, PSAs, and pamphlets. | Education Efforts | Completed | N/A | 1187 | 300 | Lower Kissimmee | N/A | Not provided | Not provided | Highlands County | Not provided | N/A
HC-05 | Highlands County | FDOT/ SWFWMD | Lake June Stormwater Project | Installation of 450 feet of 24-inch French drain in four contributing basins. | On-line Retention BMPs | Completed | 2018 | 880 | 15 | Lake Istokpoga | 94 | 530000 | Not provided | SWFWMD/ Highlands County | SWFWMD - $440,000/ County - $90,000 | N/A
HC-06 | Highlands County | SWFWMD | Lake Clay Stormwater Project | 600 feet of 24-inch on-line French drain for parking lot subbasin; 300 feet of 24-inch on-line French drain will treat the street subbasin. | On-line Retention BMPs | Completed | 2013 | 53 | 3 | Lake Istokpoga | 26.6 | 330000 | 1973 | SWFWMD/ Highlands County | SWFWMD - $330,000/ County - $1,973 | N/A
HC-07 | Highlands County | Highlands Soil and Water Conservation District/ FDOT/ SWFWMD | Lake McCoy Stormwater Project | Replacement of 420 feet of concrete sluceway with grassy swales, ditch blocks and a drop box. | On-line Retention BMPs | Completed | 2018 | 26 | 3 | Lake Istokpoga | 12 | 134479 | TBD | Highlands Soil and Water Conservation District/ FDOT/ SWFWMD | SWFMWD - $100,859/ Soil and Water District - $33,620 | N/A
IMWID-01 | Istokpoga Marsh Watershed Improvement District | DEP/ SFWMD/ FDACS/ Istokpoga Marsh Watershed Improvement District | IMWID Phase I (DWM Project in Two Phases) | Construct above ground impoundment with storage capacity of 950 acre-feet/year. | Dispersed Water Management (DWM) | Underway | 2020 | TBD | 1874 | Indian Prairie | 308 | 15437146 | TBD | DEP/ SFWMD/ FDACS | DEP funding $4,600,000; FDACS funding $2,414,000; SFWMD fundng $8,423,146 | S0650
IMWID-02 | Istokpoga Marsh Watershed Improvement District | DEP/ SFWMD/ FDACS/ Istokpoga Marsh Watershed Improvement District | IMWID Phase II (DWM Project in Two Phases) | Construct above ground impoundment with storage capacity of 1,200 acre-feet/year. | Dispersed Water Management (DWM) | Underway | 2023 | TBD | 2359 | Indian Prairie | 400 | 4450000 | TBD | DEP/ FDACS | DEP funding $450,000, FDACS funding $4,000,000 | NF023
KS-01 | City of Kissimmee | N/A | Education and Outreach | PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 441 | 18 | Upper Kissimmee | N/A | 65000 | 45000 | City of Kissimmee | $110,000 | N/A
KS-02 | City of Kissimmee | N/A | Street Sweeping | Complete 6,573 miles of street sweeping and collect approximately 3,100 cubic yards of debris. | Street Sweeping | Completed | N/A | 612 | 221 | Upper Kissimmee | N/A | 50000 | 50000 | City of Kissimmee | $100,000 | N/A
KS-03 | City of Kissimmee | TBD | Lake Tivoli | Treatment for older existing development as well as future online development; treatment provides 2.5 times the proposed percent impervious area. | On-line Retention BMPs | Underway | TBD | TBD | TBD | Upper Kissimmee | 132.8 | 300000 | TBD | TBD | TBD | N/A
KS-04 | City of Kissimmee | N/A | Lakefront Park Redevelopment - Swales/ Rain Gardens | Swale/rain garden system with 2.07 acres of dry detention. | Grass Swales Without Swale Blocks or Raised Culverts | Completed | 2015 | 13 | 0 | Upper Kissimmee | 14.2 | 500000 | Not provided | City of Kissimmee | $500,000 | N/A
KS-05 | City of Kissimmee | N/A | Lakefront Park Redevelopment Baffle Boxes | Three nutrient separating baffle boxes and 3 filter boxes within the lakefront park area. wILL install up to additional two baffle boxes in the next 5 years. | Baffle Boxes- Second Generation | Completed | 2015 | 22 | 0 | Upper Kissimmee | 14.2 | 394267 | Not provided | City of Kissimmee | $394,267 | N/A
KS-06 | City of Kissimmee | N/A | Martin Luther King Boulevard Phase III from Thacker Avenue to Dyer Boulevard | Construction of dry detention with SPECIFIC standards (side slopes, littoral zones) per the Federal Aviation Administration for reduction of bird strikes. | Grass Swales Without Swale Blocks or Raised Culverts | Completed | 2015 | 3 | 0 | Upper Kissimmee | 5.5 | 1500000 | 1500 | City of Kissimmee | $1,501,500 | N/A
KS-07 | City of Kissimmee | DEP | Emory Avenue Stormwater Management Pond | An off-line stormwater pond to provide extra storage to alleviate flooding. The pond shall also catch the first flush during rain events to help provide water quality treatment to the West City Ditch. | Wet Detention Pond | Completed | 2017 | TBD | TBD | Upper Kissimmee | TBD | 500000 | 1000 | DEP | $500,000 | S0725
KS-08 | City of Kissimmee | NRCS | Mill Slough Restoration | Mill Slough restored erroded banks and removed excess silt that was washed from the bank along with removal of down trees. | Shoreline Stabilization | Underway | 2019 | TBD | TBD | Upper Kissimmee | TBD | 1857026 | TBD | NRCS/ City of Kissimmee | $1,434,974 | N/A
KS-09 | City of Kissimmee | DEP | Woodside Drainage Improvement | The project would reduce flooding and improve the water quality that goes into Shingle Creek basin. | Wet Detention Pond | Planned | 2021 | TBD | TBD | Upper Kissimmee | TBD | TBD | TBD | DEP/ City of Kissimmee | TBD | TBD
OC-01 | Orange County | N/A | Education and Outreach | FYN; landscaping, irrigation, fertilizer, and pet waste management ordinances; PSAs; pamphlets; Water Atlas website; and illicit discharge program. | Education Efforts | Completed | N/A | 29206 | 1292 | Upper Kissimmee | N/A | 225000 | 6988 | Orange County | $225,000 and $6,988 annually | N/A
OC-02 | Orange County | N/A | Lake Conway Street Sweeping | Street sweeping of 5,011 curb miles annually. | Street Sweeping | Completed | N/A | 645 | 298 | Upper Kissimmee | N/A | 94216.8616 | 94216.8616 | Lake Conway Taxing District (MSTU) | $94,217 annually | N/A
OC-03 | Orange County | N/A | Lake Holden Street Sweeping | Street sweeping of 829 curb miles annually. | Street Sweeping | Completed | N/A | 107 | 49 | Upper Kissimmee | N/A | 15586.8646 | 15586.8646 | Lake Holden Taxing District (MSTU) | $15,587 annually | N/A
OC-04 | Orange County | N/A | Lake Jessamine Street Sweeping | Street sweeping of 734 curb miles annually. | Street Sweeping | Completed | N/A | 94 | 44 | Upper Kissimmee | N/A | 13800.6738 | 13800.6738 | Lake Jessamine Taxing District (MSTU) | $13,801 annually | N/A
OC-05 | Orange County | N/A | Shingle/Boggy/Hart Basin Street Sweeping | Countywide street sweeping (about 13,000 curb miles). | Street Sweeping | Completed | N/A | 534 | 246 | Upper Kissimmee | N/A | 404000 | 404000 | Orange County | $404,000 Annually | N/A
OC-07 | Orange County | N/A | Lake Conway Curb Inlet Basket (CIB) Existing | Curb or grate inlet filter baskets (116) to collect 16,169 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2015 | 11 | 7 | Upper Kissimmee | 71 | 112000 | 13269 | Lake Conway Taxing District (MSTU) | Not provided | N/A
OC-09 | Orange County | N/A | Lake Pineloch CIB | Curb or grate inlet filter baskets (23) to collect 4,158 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 2.8 | 1.7 | Upper Kissimmee | 14 | 18000 | 2677 | Orange County | Not provided | N/A
OC-10 | Orange County | N/A | Lake Anderson CIB | Curb or grate inlet filter baskets (11) to collect 3,364 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Canceled | 2011 | 0 | 0 | Upper Kissimmee | 7 | 10000 | 1280 | Lake Anderson MSTU | Not provided | N/A
OC-11 | Orange County | N/A | Lake Holden CIB | Curb or grate inlet filter baskets (115) to collect 27,602 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 18.7 | 11.5 | Upper Kissimmee | 72 | 41000 | 13386 | Lake Holden Taxing District (MSTU) | Not provided | N/A
OC-12 | Orange County | N/A | Lake Jessamine CIB | Curb or grate inlet filter baskets (92) to collect 13,025 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 8.8 | 5.5 | Upper Kissimmee | 63 | 110000 | 10708 | Lake Jessamine Taxing District (MSTU) | Not provided | N/A
OC-13 | Orange County | N/A | Lake Floy CIB | Curb or grate inlet filter baskets (10) to collect 4,835 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 3.3 | 2 | Upper Kissimmee | 6 | 10000 | 1164 | Lake Floy MSTU | Not provided | N/A
OC-14 | Orange County | N/A | Lake Cane CIB | Curb or grate inlet filter baskets (14) to collect 3,845 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 2.6 | 1.5 | Upper Kissimmee | 11 | 14000 | 1629 | Orange County | Not provided | N/A
OC-15 | Orange County | N/A | Lake Odell CIB | Curb or grate inlet filter baskets (3) to collect 904 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 0.7 | 0.4 | Upper Kissimmee | 2 | 3000 | 349 | Orange County | Not provided | N/A
OC-16 | Orange County | Not provided | Lake Tyler CIB | Curb or grate inlet filter baskets (10). | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 3.3 | 2 | Upper Kissimmee | 7 | 11000 | 1164 | Not provided | Not provided | Not provided
OC-17 | Orange County | N/A | Lake Down/Windermere CIB | Curb or grate inlet filter baskets (51) to collect 16,934 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2014 | 11.5 | 7.1 | Upper Kissimmee | 34 | 56000 | 16063 | Windermere Water and Navigation Control District (MSTU) | Not provided | N/A
OC-18 | Orange County | N/A | Lake Tibet CIB | Curb or grate inlet filter baskets (92) to collect 13,494 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 9.3 | 5.7 | Upper Kissimmee | 58 | 31000 | Not provided | Windermere Water and Navigation Control District (MSTU) | Not provided | N/A
OC-19 | Orange County | N/A | Lisa Waterway Continuous Deflective Seperation (CDS) Unit | Treats runoff from Orange Avenue. | Hydrodynamic Separators | Completed | 2008 | 3 | 1 | Upper Kissimmee | Not provided | 225000 | 6988 | Lake Conway Taxing District (MSTU) | Not provided | N/A
OC-20 | Orange County | Not provided | Randolph Avenue CDS Unit | Treats runoff from Randolph Avenue. | Hydrodynamic Separators | Completed | Not provided | 0 | 0 | Upper Kissimmee | Not provided | Not provided | Not provided | Not provided | Not provided | Not provided
OC-21 | Orange County | Not provided | Randolph Avenue Stormceptor™ | Stormceptor™. | Hydrodynamic Separators | Completed | Prior to 2014 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | Not provided | Not provided | Not provided | Not provided
OC-22 | Orange County | Not provided | Randolph (Hansel) Avenue Pond | Retrofit of wet detention pond - increased residence time, pond depth. | Wet Detention Pond | Completed | 2019 | 1 | 0 | Upper Kissimmee | Not provided | Not provided | Not provided | Orange County Public Works/Lake Conway Taxing District (MSTU) | Not provided | Not provided
OC-23 | Orange County | FDOT District 5/ City of Edgewood | Lake Mary Jess Pond | Wet retention pond created from canal. | Wet Detention Pond | Completed | 2013 | 29 | 6 | Upper Kissimmee | 31.2 | 534795 | 6000 | FDOT District 5/ City of Edgewood | Not provided | N/A
OC-24 | Orange County | N/A | Lake Odell Sediment Sump | Small sump collects sediment from roadway, with an estimate of 12,000 lbs/yr of material. | Control Structure | Completed | 2014 | 3 | 1 | Upper Kissimmee | Not provided | 33300 | 1500 | Orange County | Not provided | N/A
OC-25 | Orange County | SJRWMD | Construct second generation nutrient separating baffle box (NSBB) containing media. Improve headwall and fore bay prior to discharge to the lake. | Construct NSBB containing media. | Baffle Boxes- Second Generation with Media | Completed | 2018 | 141 | 2 | Upper Kissimmee | 9.1 | 312511.29 | 2500 | SJRWMD/ Orange County | SJRWMD - $119,600/ County - $192,911 | N/A
OC-26 | Orange County | N/A | Lake Anderson Alum Treatment System | Storm pond enhancement with alum. | Alum Injection Systems | Completed | 2017 | 568 | 27 | Upper Kissimmee | 173 | 345166 | 16900 | Orange County/ Lake Anderson MSBU | Not provided | N/A
OC-27 | Orange County | N/A | Lake Jessamine Surface Alum | Whole-lake alum treatment. | Alum Injection Systems | Completed | 2013 | 158 | 10 | Upper Kissimmee | Not provided | 246000 | Not provided | Lake Jessamine Taxing District (MSTU) | Not provided | N/A
OC-28 | Orange County | DEP | Lake Down Alum Treatment Facility | Installation of offline alum injection facility on the upstream portion of the Butler Chain of Lakes to address phosphorus loading to the chain and downstream. | Alum Injection Systems | Completed | 2016 | 1224 | 47 | Upper Kissimmee | 378.8 | 2000000 | 15000 | Windermere Water and Navigation Control District (MSTU)/ DEP | MSTU - $1,053,000 DEP319 - $790,000 | G0335
OC-29 | Orange County | N/A | Lake Conway Hydrologic and Nutrient Study | Identify nutrient sources. | Study | Underway | 2019 | TBD | TBD | Upper Kissimmee | N/A | 172000 | N/A | Lake Conway Taxing District (MSTU) | 224097 | N/A
OC-30 | Orange County | N/A | Lake Jennie Jewel CIB Installation | Install baskets in stormwater inlets. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2015 | 2 | 2 | Upper Kissimmee | 6 | 9360 | 1200 | Orange County | $93,60 and $1,200 annually | N/A
OC-31 | Orange County | N/A | Jewell-Gatlin NSBB | Construct NSBB containing media. | Baffle Boxes- Second Generation with Media | Canceled | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OC-32 | Orange County | N/A | Lake Gem Mary Loading Assessment | Identify impairment sources and provide BMP recommendations. | Study | Underway | 2019 | N/A | N/A | Upper Kissimmee | N/A | 162517 | N/A | Orange County | $162,517 | N/A
OC-33 | Orange County | DEP | Lake Conway Old Dominion Road NSBB | Treat stormwater from Lake Conway Woods. | Baffle Boxes- Second Generation with Media | Completed | 2015 | 30 | 4 | Upper Kissimmee | 39.5 | 173513 | 4258 | Lake Conway Taxing District (MSTU) | DEP - $141,679/ MSTU - $31,834 | LP4803F
OC-34 | Orange County | N/A | Lake Conway Pershing CDS | Treat stormwater from Pershing Avenue. | Hydrodynamic Separators | Completed | Not provided | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 5072 | Lake Conway Taxing District (MSTU) | MSTU - $5,072 annually | N/A
OC-35 | Orange County | N/A | Lake Conway Cullen Lakeshore CDS | Treat stormwater from Cullen Lakeshore. | Hydrodynamic Separators | Completed | Prior to 2007 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 5677 | Lake Conway Taxing District (MSTU) | MSTU - $5,677 annually | N/A
OC-36 | Orange County | N/A | Lake Jessamine 608 Viscaya NSB1 | Treat stormwater from Viscaya Avenue. | Baffle Boxes- Second Generation with Media | Completed | 2015 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 1175 | Lake Jessamine Taxing District (MSTU) | MSTU - $1,175 annually | N/A
OC-37 | Orange County | N/A | Lake Jessamine 616 Viscaya NSB1 | Treat stormwater from Viscaya Avenue. | Baffle Boxes- Second Generation with Media | Completed | 2015 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 1404 | Lake Jessamine Taxing District (MSTU) | MSTU - $1,404 annually | N/A
OC-38 | Orange County | N/A | Lake Jessamine Silvera Avenue NSB1 | Treat stormwater from Silvera Avenue. | Baffle Boxes- Second Generation with Media | Completed | 2015 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 2076 | Lake Jessamine Taxing District (MSTU) | MSTU - $2,076 annually | N/A
OC-39 | Orange County | N/A | Lake Tyler Apts. 8 CDS | Treat stormwater from Lake Tyler Apts. | Hydrodynamic Separators | Completed | 2008 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 2952 | Orange County | County - $2,952 annually | N/A
OC-40 | Orange County | N/A | Lake Tyler Apts. 9 CDS | Treat stormwater from Lake Tyler Apts. | Hydrodynamic Separators | Completed | 2008 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 5445 | Orange County | County - $5,445 annually | N/A
OC-41 | Orange County | N/A | Hidden Cove Apts. 7 CDS | Treat stormwater from Hidden Cove Apts. | Hydrodynamic Separators | Completed | 2008 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 3333 | Orange County | County - $3,333 annually | N/A
OC-42 | Orange County | N/A | Lake Tibet Houston Pl. NSBB | Treat stormwater from Houston Place. | Baffle Boxes- Second Generation with Media | Completed | 2017 | 0 | 0 | Upper Kissimmee | Not provided | Not provided | 2329 | Butler MSTU | MSTU - $2,329 annually | N/A
OC-43 | Orange County | N/A | Lake Down Subbasin 9 NSBB | Treat stormwater from subbasin 9 in Lake Down. | Baffle Boxes- Second Generation | Completed | 2017 | 202 | 25 | Upper Kissimmee | 411 | 390000 | 8125 | Butler MSTU/ SFWMD | Not provided | N/A
OC-44 | Orange County | N/A | Lake Jessamine Hydrologic Nutrient Budget Study | Hydrologic and nutrient budget study. | Study | Completed | 2012 | N/A | N/A | Upper Kissimmee | N/A | 105886 | N/A | Lake Jessamine Taxing District (MSTU) | Not provided | N/A
OC-45 | Orange County | N/A | Anderson Street Sweeping | Sweeping of 31.8 curb miles annually. | Street Sweeping | Canceled | N/A | 0 | 0 | Upper Kissimmee | N/A | Not provided | 770 | Lake Anderson Taxing District (MSTU) | MSTU - $770 annually | N/A
OC-46 | Orange County | N/A | Bass Lake CIB | Collect 1,572 lbs/yr of material in 6 CIBs. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2008 | 1 | 1 | Upper Kissimmee | 4 | 5430 | 470 | Bass Lake Taxing District (MSTU) | MSTU - $5,430 plus $470 annually | N/A
OC-47 | Orange County | N/A | Jennie Jewel Alum | In-lake application of alum and buffer. | Alum Injection Systems | Completed | 2019 | TBD | TBD | Upper Kissimmee | 66.4 | 138605.02 | N/A | OCBCC/ SJRWMD | $119,600.00 (Bundled with OC-25) | N/A
OC-48 | Orange County | N/A | LaGrange CIB | Collect 2,290 lbs/yr of material. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | 2014 | 1 | 2 | Upper Kissimmee | 5 | 7200 | 940 | LaGrange Taxing District (MSTU) | MSTU - $7,200 plus $940 annually | N/A
OC-49 | Orange County | N/A | Lake Christie NSBB | Install nutrient separating baffle box fitted with bioactivated media. | Baffle Boxes- Second Generation with Media | Completed | 2018 | 26 | 15 | Upper Kissimmee | 81.5 | 150000 | 1500 | Orange County | $151,500.00 | N/A
OC-50 | Orange County | N/A | Lake Pineloch NSBB | Construct a treatment train consisting of an on-line nutrient separating baffle box and off-line upflow filter | Baffle Boxes- Second Generation with Media | Planned | 2020 | 531 | 79 | Upper Kissimmee | 109 | 841992 | 1500 | TBD | TBD | N/A
OC-51 | Orange County | N/A | Shingle Creek Hydro/ Nutrient Assessment | Conduct a nutrient/hydro assessment producing a ranked list of BMPs. | Study | Underway | 2019 | N/A | N/A | Upper Kissimmee | N/A | 134958 | N/A | Orange County | $134,958 | N/A
OC-52 | Orange County | N/A | Boggy Creek B-14 Pipeline (Segment B) | Replace structures and failing 60-inch corrugated metal pipe. | Stormwater System Rehabilitation | Completed | 2016 | N/A | N/A | Upper Kissimmee | N/A | 172840 | N/A | Orange County | $172,840 | N/A
OC-53 | Orange County | N/A | Bonnie Brook Erosion Control | Removed failing fabriform revetment and install new reinforced concrete channel lining and riprap within segments of the Lake Ellenor Outfall Canal and Westridge Outfall Canal. | Shoreline Stabilization | Completed | 2017 | Not provided | Not provided | Upper Kissimmee | Not provided | 387412 | N/A | Orange County | $387,412 | N/A
OC-54 | Orange County | N/A | B-14 Wheatberry Court | Repair existing slope failure areas and install turf reinforcement mat to stabilize slope. | Shoreline Stabilization | Underway | 2019 | TBD | TBD | Upper Kissimmee | TBD | 60000 | N/A | Orange County | $113,710 | N/A
OC-55 | Orange County | N/A | Boggy Creek B-14 Pipeline (Segments A, C, and D) | Replace 4,500 LF of failing 60-inch corrugated metal pipe. | Stormwater System Rehabilitation | Underway | 2021 | TBD | TBD | Upper Kissimmee | TBD | 3100000 | N/A | Orange County | $3,100,000 | N/A
OC-55 | Orange County | N/A | Lake Hickorynut Hydro/Nutrient Source Assessment | Assess hydrological and nutrient pollutant sources, allocate source loading, produce a ranked list of BMPs for consideration. | Study | Underway | 43983 | N/A | N/A | Upper Kissimmee | 800 | 199179.12 | 0 | Orange County Board of County Commissioners | 199179.12 | N/A
OC-55 | Orange County | N/A | Lake Gem Mary Alum Treatment Design | Size the alum application of Lake Gem Mary. | Alum Injection Systems | Underway | 43800 | TBD | TBD | Upper Kissimmee | 14 | 63671.64 | 0 | Orange County Board of County Commissioners | 63671.64 | N/A
OC-55 | Orange County | N/A | Lake Gem Mary Alum Treatment | In-lake alum surface water treatment. | Alum Injection Systems | Proposed | TBD | TBD | TBD | Upper Kissimmee | 14 | TBD | 0 | Orange County Board of County Commissioners | TBD | N/A
OC-55 | Orange County | N/A | Shingle Creek Feasibility Study | Determine constructability of BMPs intended to improve water quality and / or impound water. | Study | Underway | TBD | N/A | N/A | Upper Kissimmee | TBD | 197354.17 | 0 | Orange County Board of County Commissioners | 197354.17 | N/A
OC-55 | Orange County | N/A | Holden Heights Community Improvements Phase IV | Project includes new gravity sewer to replace aging septic tank systems. This is a joint OCU, OCPW, OCHCD and OUC project with CDBG funding provided through OCHCD. | OSTDS Phase Out | Underway | 2019 | TBD | TBD | Upper Kissimmee | N/A | Not provided | N/A | CDBG funding provided through OCHCD | Not provided | N/A
OC-55 | Orange County | N/A | Hamlin Water Reclamation Facility (WRF) | The Hamlin Water Reclamation Facility (WRF) project consists of the design and construction of new physical, biological and chemical treatment facilities for raw sewage with an Annual Average Daily Flow capacity of 5 MGD. Designing the WRF to meet the effluent golas of an Advanced WRF (annual average 5 mg/L TSS, 5 mg/L cBOD5, 3 mg/L TN, and 1 mg/L TP). | WWTF Nutrient Reduction | Underway | 2022 | TBD | TBD | Upper Kissimmee | N/A | Not provided | N/A | OCUD Capital Improvements Program Budget | Not provided | N/A
OK-01B | Okeechobee County | DEO | Douglas Park South | Addition of dry detention area to serve 73.5 acres of original 150-acre drainage area. | Dry Detention Pond | Completed | 2009 | 30 | 5 | Taylor Creek/ Nubbin Slough | 73.5 | 643593 | Not provided | DEO | Not provided | N/A
OK-02 | Okeechobee County | FEMA/ DEO | Oak Park | Roadside swales with raised inlets and two hydrodynamic separators. | Grass Swales With Swale Blocks or Raised Culverts | Completed | 2016 | 32 | 5 | Taylor Creek/ Nubbin Slough | 56.4 | 1112005 | Not provided | FEMA/ DEO | Not provided | N/A
OK-03 | Okeechobee County | FEMA/ City of Okeechobee | Southwest 21st Street | Dry detention roadside swales with raised inlets and one hydrodynamic separator. | Grass Swales With Swale Blocks or Raised Culverts | Completed | 2013 | 1 | 0 | Taylor Creek/ Nubbin Slough | 2.1 | 483893 | Not provided | FEMA/ City of Okeechobee/ County | Not provided | N/A
OK-04 | Okeechobee County | FEMA | Southwest Drainage Area Improvements | Dry detention roadside swales with raised inlets and two hydrodynamic separators. | Grass Swales With Swale Blocks or Raised Culverts | Completed | 2011 | 1 | 1 | Taylor Creek/ Nubbin Slough | 32.2 | 1485917 | Not provided | FEMA | Not provided | N/A
OK-05 | Okeechobee County | DEO | Okeechobee County 2008 Disaster Recovery Community Development Block Grant | Culvert upgrades and dry detention area to improve water quality and alleviate funding. | Stormwater System Rehabilitation | Completed | 2014 | 9 | 0 | Taylor Creek/ Nubbin Slough | 17.2 | 786665 | Not provided | DEO | Not provided | N/A
OK-06 | Okeechobee County | Not provided | Southwest Drainage Area Improvements Whidden Ditch (Phase III) | Ditch and culvert upgrades to improve stormwater conveyance to Rim Canal. | Stormwater System Rehabilitation | Completed | 2017 | 2 | 0 | Taylor Creek/ Nubbin Slough | 20 | 749410 | Not provided | Florida Legislature | Not provided | N/A
OK-07 | Okeechobee County | Not provided | Lock 7 Bypass Culvert System | Installation of parallel culvert system along the Rim Canal to improve conveyance. | Stormwater System Rehabilitation | Completed | 2016 | 0 | 0 | Taylor Creek/ Nubbin Slough | 0 | 157143 | Not provided | Florida Legislature | Not provided | N/A
ORL-01 | City of Orlando | SFWMD | 18th Street/Parramore Ave Baffle Box | Baffle box installed to remove gross pollutants, including organic debris, sediment and litter. 1.5 cubic yards/yr of material collected. | Baffle Boxes- Second Generation | Completed | 2009 | 3 | 1 | Upper Kissimmee | 4.6 | 578138 | Not provided | SFWMD/ City of Orlando Streets and Stormwater Division | City - $289,069/ SFWMD - $289,069 | N/A
ORL-02 | City of Orlando | SFWMD | 19th Street/Parramore Avenue Baffle Box | Baffle box installed to remove gross pollutants, including organic debris, sediment and litter. 1 cubic yard/yr of material collected. | Baffle Boxes- Second Generation | Completed | 2009 | 2 | 1 | Upper Kissimmee | 9.9 | N/A | Not provided | SFWMD/ City of Orlando Streets and Stormwater Division | N/A | N/A
ORL-03 | City of Orlando | DEP | Pine Street/Orange Blossom Trail Corridor Stormwater Improvements | Installation of 1,800 LF of stormwater pipe from Pine Street to Lake Lorna Doone, which includes a baffle box. | Baffle Boxes- Second Generation | Completed | 2010 | 6 | 1 | Upper Kissimmee | 11.5 | 942710 | Not provided | DEP/ City of Orlando Streets and Stormwater Division | City - $471,355/ DEP - $471,355 | Not provided
ORL-04 | City of Orlando | OUC | Lake Holden Terrace/Albert Shores Sanitary Components | Sanitary infrastructure installed for septic tank conversions. 11 of 77 homes converted. | Wastewater Service Area Expansion | Completed | 2012 | Not provided | Not provided | Upper Kissimmee | Not provided | 3522911 | Not provided | City of Orlando/ OUC | Not provided | N/A
ORL-05 | City of Orlando | OUC | Lake Holden Terrace/Albert Shores Stormwater Components | Two baffle boxes and one Storm Flo unit installed within stormwater infrastructure for capturing organic debris, sediment and litter; stormwater infrastructure added to alleviate flooding. 20.5 cubic yards/yr of material collected. | Baffle Boxes- Second Generation | Completed | 2012 | 44 | 18 | Upper Kissimmee | 76.4 | N/A | Not provided | City of Orlando/ OUC | Not provided | N/A
ORL-06 | City of Orlando | DEP | Lake Angel Drainage Improvements | Expand the permanent pool volume of Lake Angel and install three baffle boxes in the main inflow pipes. | Wet Detention Pond | Completed | 2015 | 37 | 1 | Upper Kissimmee | 87 | 1239249 | Not provided | DEP/ City of Orlando Streets and Stormwater Division | City - $948,249/ DEP - $291,000 | Not provided
ORL-07 | City of Orlando | N/A | CEMEX - South Division Avenue Roadway and Drainage Improvements | Pave unimproved access road to industrial park and install baffle box to capture sediment; install curbing along additional areas of Division Avenue to allow street sweepers to effectively capture more sediment in the Lake Holden Basin. | Baffle Boxes- Second Generation | Canceled | N/A | N/A | N/A | Upper Kissimmee | N/A | N/A | N/A | N/A | N/A | N/A
ORL-08 | City of Orlando | N/A | Lake Pineloch Basin Inlet Baskets | 32 inlet baskets installed to remove gross pollutants, including organic debris, sediment and litter. 44 cubic yards/yr of material collected. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 68 | 42 | Upper Kissimmee | Not provided | 40480 | 11735 | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-09 | City of Orlando | N/A | Clear Lake Basin Inlet Baskets | 29 inlet baskets installed to remove gross pollutants, including organic debris, sediment and litter. 25.25 cubic yards/yr of material collected. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 40 | 24 | Upper Kissimmee | Not provided | 8550 | 8332 | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-10 | City of Orlando | N/A | Lake Lorna Doone Basin Inlet Baskets | 16 inlet baskets installed to remove gross pollutants, including organic debris, sediment and litter. 32.6 cubic yards/yr of material collected. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 51 | 31 | Upper Kissimmee | Not provided | 17755 | 8673 | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-11 | City of Orlando | N/A | Lake Mann Basin Inlet Baskets | 44 inlet baskets installed to remove gross pollutants, including organic debris, sediment and litter. 23 cubic yards/yr of material collected. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 35 | 22 | Upper Kissimmee | Not provided | 48826 | 3566 | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-13 | City of Orlando | N/A | Rock Lake Basin Inlet Baskets | Ten inlet baskets installed to remove gross pollutants, including organic debris, sediment and litter. 21 cubic yards/yr of material collected. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 33 | 20 | Upper Kissimmee | Not provided | 8550 | 9706 | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-14 | City of Orlando | N/A | Lake Sunset Basin Inlet Baskets | Eight inlet baskets installed to remove gross pollutants, including organic debris, sediment and litter. 15 cubic yards/yr of material collected. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 22 | 13 | Upper Kissimmee | Not provided | 8550 | 11451 | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-15 | City of Orlando | N/A | Walker Lagoon Basin Inlet Baskets | Sixteen inlet baskets installed to remove gross pollutants, including organic debris, sediment and litter. 35.1 cubic yards/yr of material collected. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | Not provided | 55 | 33 | Upper Kissimmee | Not provided | 17755 | 7049 | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-16 | City of Orlando | N/A | Street Sweeping | Street sweeping within all public roads in City limits. 22,325.2 cubic yards/yr of material collected. | Street Sweeping | Completed | N/A | 6986 | 2430 | Upper Kissimmee | N/A | Not provided | 850000 | City of Orlando Streets and Stormwater Division | $850,000 | N/A
ORL-17 | City of Orlando | N/A | Education and Outreach | FYN; landscaping, irrigation, fertilizer, and pet waste management ordinances; PSAs; pamphlets; website; and illicit discharge program. | Education Efforts | Completed | N/A | 7584 | 456 | Upper Kissimmee | N/A | 51500 | Not provided | City of Orlando Streets and Stormwater Division | Not provided | N/A
ORL-18 | City of Orlando | N/A | Lizzie Rogers Park Baffle Box | Relocation of drainage outfall into Lake Sunset with addition of baffle box. | Baffle Boxes- Second Generation | Planned | 2020 | 0.66 | 9.02 | Upper Kissimmee | 7.2 | TBD | TBD | City of Orlando Streets and Stormwater Division | Not provided | N/A
OSC-01 | Osceola County | N/A | Narcoossee Road IB Ponds 2 and 3 | Roadway widening. | Wet Detention Pond | Completed | 2011 | 13 | 0 | Upper Kissimmee | 29.3 | Not provided | 4195 | Osceola County | Not provided | N/A
OSC-02 | Osceola County | N/A | Narcoossee Road III Ponds C3A & C3B | Roadway widening. | Wet Detention Pond | Completed | 2012 | 8 | 0 | Upper Kissimmee | 20.5 | Not provided | 4195 | Osceola County | Not provided | N/A
OSC-03 | Osceola County | N/A | Narcoossee Road III Pond D3 | Roadway widening. | Wet Detention Pond | Completed | 2012 | 8 | 0 | Upper Kissimmee | 24.3 | Not provided | 4195 | Osceola County | Not provided | N/A
OSC-04 | Osceola County | N/A | Narcoossee Road III Pond E1 | Roadway widening. | Wet Detention Pond | Completed | 2012 | 5 | 0 | Upper Kissimmee | 22.4 | Not provided | 4195 | Osceola County | Not provided | N/A
OSC-05 | Osceola County | N/A | Neptune Road I - Ponds 100, 200, and 300 | Road improvement. | Wet Detention Pond | Completed | 2010 | 483 | 18 | Upper Kissimmee | 226.8 | Not provided | 4195 | Osceola County | Not provided | N/A
OSC-06 | Osceola County | N/A | Old Wilson Road Pond D002-P | Road improvement. | On-line Retention BMPs | Completed | 2012 | 42 | 1 | Upper Kissimmee | 55.8 | Not provided | Not provided | Osceola County | Not provided | N/A
OSC-07 | Osceola County | N/A | Old Wilson Road Pond D004-P | Road improvement. | On-line Retention BMPs | Completed | 2012 | 44 | 1 | Upper Kissimmee | 18.7 | Not provided | Not provided | Osceola County | Not provided | N/A
OSC-08 | Osceola County | N/A | Old Wilson Road Pond E002-P | Road improvement. | On-line Retention BMPs | Completed | 2012 | 47 | 2 | Upper Kissimmee | 12.5 | Not provided | Not provided | Osceola County | Not provided | N/A
OSC-09 | Osceola County | N/A | Stewart Street Regional Pond Retrofit | Regional pond retrofit. | Wet Detention Pond | Completed | 2009 | 3851 | 155 | Upper Kissimmee | 2249.2 | Not provided | Not provided | Osceola County | Not provided | N/A
OSC-10 | Osceola County | N/A | Education and Outreach | FYN; landscaping, irrigation, fertilizer, and pet waste management ordinances; PSAs; pamphlets; website; and illicit discharge program. | Education Efforts | Completed | N/A | 23396 | 709 | Upper Kissimmee | N/A | Not provided | 60000 | Osceola County | $60,000 | N/A
OSC-11 | Osceola County | N/A | Education and Outreach | FYN; landscaping, irrigation, fertilizer, and pet waste management ordinances; PSAs; pamphlets; website; and illicit discharge program. | Education Efforts | Completed | N/A | 54 | 6 | Lower Kissimmee | N/A | Not provided | 5000 | Osceola County | $5,000 | N/A
OSC-12 | Osceola County | HOA | East Lake Reserve Stormwater Reuse | Stormwater reuse for landscape irrigation from pond A1 (9.1A). | Stormwater Reuse | Completed | Not provided | 806 | 12 | Upper Kissimmee | 130.8 | Not provided | Not provided | HOA | Not provided | N/A
OSC-13 | Osceola County | N/A | Neptune Rd. Stormwater Reuse | Stormwater reuse for landscape irrigation from Ponds 100/101 and 300. | Stormwater Reuse | Completed | Not provided | 55 | 2 | Upper Kissimmee | 35.7 | 640690 | 26000 | Osceola County | Not provided | N/A
OSC-14 | Osceola County | HOA | Bellalago and Isles of Bellalago Stormwater Reuse | Stormwater reuse for landscape irrigation (197A). | Stormwater Reuse | Completed | Not provided | 6772 | 141 | Upper Kissimmee | 1386.8 | Not provided | Not provided | HOA | Not provided | N/A
OSC-15 | Osceola County | Private | Poinciana Commerce Center Reuse | Stormwater reuse for landscape irrigation from Pond 1. | Stormwater Reuse | Completed | Not provided | 30 | 1 | Upper Kissimmee | 10.2 | Not provided | Not provided | Private | Not provided | N/A
OSC-16 | Osceola County | Private | Kissimmee Bay Reuse | Stormwater reuse; 20-year duration for 84.5 acres of golf course and five-year duration for 45.5 acres of landscape irrigation. | Stormwater Reuse | Completed | Not provided | 2006 | 43 | Upper Kissimmee | 271 | Not provided | Not provided | Private | Not provided | N/A
OSC-17 | Osceola County | Private | Remington Reuse | Stormwater reuse for golf course irrigation from Ponds 12, 13, 14A, and 14B. | Stormwater Reuse | Completed | Not provided | 1154 | 27 | Upper Kissimmee | 149.4 | Not provided | Not provided | Private | Not provided | N/A
OSC-18 | Osceola County | Private | Eagle Lake Reuse | Stormwater reuse for turf irrigation. | Stormwater Reuse | Completed | Not provided | 1927 | 42 | Upper Kissimmee | 435.1 | Not provided | Not provided | Private | Not provided | N/A
OSC-19 | Osceola County | Private | La Quinta Inn Reuse | Stormwater reuse for turf irrigation. | Stormwater Reuse | Completed | Not provided | 31 | 4 | Upper Kissimmee | 12.5 | Not provided | Not provided | Private | Not provided | N/A
OSC-20 | Osceola County | DEP/ SFWMD | Lake Toho Regional Water Storage Facility (Judge Farms) | Construction of a regional stormwater pond and an alternative water supply reservoir. | Stormwater Treatment Areas (STAs) | Underway | 2020 | 25500 | 2700 | Upper Kissimmee | 5883 | TBD | TBD | County/ DEP/ SFWMD/Toho Water Authority | County - $32,850,000/ DEP - $1,750,000 SFWMD - $400,000 | LP49021 and S0806
OSC-21 | Osceola County | N/A | Street Sweeping | Monthly street sweeping. | Street Sweeping | Completed | N/A | 102 | 35 | Upper Kissimmee | N/A | Not provided | 60000 | Osceola County | $60,000 | N/A
OSC-22 | Osceola County | N/A | Buenaventura Lakes Golf Course Ponds | Two new lakes at golf course. | Wet Detention Pond | Completed | Not provided | 13 | 4 | Upper Kissimmee | 517.7 | Not provided | Not provided | Osceola County | Not provided | N/A
OSC-23 | Osceola County | N/A | Slaman | Conservation areas. | Land Preservation | Completed | 2008 | 1 | 0 | Upper Kissimmee | 32.2 | Not provided | 1500 | Osceola County | $1,500 | N/A
OSC-24 | Osceola County | N/A | Jim Yates | Conservation areas. | Land Preservation | Completed | 2009 | 7 | 1 | Upper Kissimmee | 5.3 | Not provided | 3750 | Osceola County | $3,750 | N/A
OSC-25 | Osceola County | N/A | Udstad | Conservation areas. | Land Preservation | Completed | 2008 | 17 | 1 | Upper Kissimmee | 5.9 | Not provided | 3500 | Osceola County | $3,500 | N/A
OSC-26 | Osceola County | N/A | Proctor | Conservation areas. | Land Preservation | Completed | 2009 | 1 | 0 | Upper Kissimmee | 0.7 | Not provided | 1750 | Osceola County | $1,750 | N/A
OSC-27 | Osceola County | N/A | Twin Oaks | Conservation areas. | Land Preservation | Completed | 2009 | 584 | 104 | Upper Kissimmee | 399.6 | Not provided | 16500 | Osceola County | $16,500 | N/A
OSC-28 | Osceola County | N/A | Cherokee Point | Conservation areas. | Land Preservation | Completed | 2005 | 15 | 3 | Upper Kissimmee | 178.6 | Not provided | 21800 | Osceola County | $21,800 | N/A
OSC-29 | Osceola County | HOA | Encatada Resort | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 73 | 7 | Upper Kissimmee | 57.6 | Not provided | Not provided | HOA | Not provided | N/A
OSC-30 | Osceola County | HOA | Cypress Palms Condos | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 23 | 2 | Upper Kissimmee | 12.4 | Not provided | Not provided | HOA | Not provided | N/A
OSC-31 | Osceola County | HOA | Lake Pointe | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 711 | 13 | Upper Kissimmee | 150.2 | Not provided | Not provided | HOA | Not provided | N/A
OSC-32 | Osceola County | HOA | Traditions at Westside | Stormwater reuse for landscape irrigation from pond. | Stormwater Reuse | Completed | Not provided | 43 | 5 | Upper Kissimmee | 21.7 | Not provided | Not provided | HOA | Not provided | N/A
OSC-33 | Osceola County | N/A | Hoagland Blvd Phase III | Road Widening | Hydrodynamic Separators | Underway | 2020 | N/A | 0 | Upper Kissimmee | 14.6 | 16000 | 2400 | Osceola County | $16,000.00 | N/A
PC-01 | Polk County | Extension Office/ County Utilities/ Lakes Education Action Drive/ Municipal Agencies | Education and Outreach | FYN, fertilizer ordinance, PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 2396 | 86 | Lake Istokpoga | N/A | N/A | 2000 | Polk County | $2,000 | N/A
PC-02 | Polk County | Extension Office/ County Utilities/ Lakes Education Action Drive/ Municipal Agencies | Education and Outreach | FYN, fertilizer ordinance, PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 901 | 50 | Lower Kissimmee | N/A | N/A | 3000 | Polk County | $3,000 | N/A
PC-03 | Polk County | Extension Office/ County Utilities/ Lakes Education Action Drive/ Municipal Agencies | Education and Outreach | FYN, fertilizer ordinance, PSAs, pamphlets, website, and Illicit Discharge Program. | Education Efforts | Completed | N/A | 9784 | 262 | Upper Kissimmee | N/A | N/A | 2000 | Polk County | $2,000 | N/A
PC-04 | Polk County | SFWMD | Sumica Preserve Water Storage/Hydrologic Restoration | Construction of a gravel berm to store water onsite for wetland restoration. | Wetland Restoration | Completed | 2010 | TBD | 17 | Upper Kissimmee | 4077.4 | 42850 | 13000 | Polk County/ SFWMD | County - $21,425/ SFWMD - $21,245 | N/A
RCID-01 | Reedy Creek Improvement District | Walt Disney World | Education and Outreach | Landscaping, irrigation, and fertilizer ordinances; PSAs, pamphlets, website, Illicit Discharge Program, inspection program; equivalent FYN program to address needs of visitors, Walt Disney World employees, and neighboring property owners. | Education Efforts | Completed | N/A | 1396 | 115 | Upper Kissimmee | N/A | Not provided | Not provided | RCID | Not provided | N/A
RCID-02 | Reedy Creek Improvement District | Walt Disney World | Property Wide Street Sweeping | Street Sweeping of more than 220,000 lane miles annually. | Street Sweeping | Completed | N/A | 491 | 171 | Upper Kissimmee | N/A | Not provided | Not provided | RCID | Not provided | N/A
SEB-01 | City of Sebring | DEP/ SWFWMD/ Highlands County | Little Lake Jackson Off-line Alum Injection Stormwater Treatment | Stormwater diverted through underground culvert, alum injected and the water settles for seven days in a detention pond. Treated water is released to Little Lake Jackson. | Alum Injection Systems | Completed | 2011 | 192 | 112 | Lake Istokpoga | Not provided | 231494 | 18500 | DEP/ SWFWMD/ City of Sebring/ Highlands County | Not provided | N/A
SEB-02 | City of Sebring | Not provided | Street Sweeping | Street sweeping to collect 602,940 lbs/yr of material. In 2018, 992,000 lbs of material was collected. | Street Sweeping | Completed | N/A | 261 | 112 | Lake Istokpoga | N/A | Not provided | 35000 | City of Sebring | Not provided | N/A
SFWMD-01 | SFWMD | USACE | Taylor Creek | The Taylor Creek STA is a two-celled STA. | Stormwater Treatment Areas (STAs) | Completed | 2008 | N/A | 3389 | Taylor Creek/ Nubbin Slough | 118 | 26900000 | 141882 | USACE/ SFWMD | USACE - $26,900,000/ SFWMD - $141,882 | N/A
SFWMD-02 | SFWMD | USACE | Nubbin Slough | The Nubbin Slough STA is the larger of the two pilot STAs constructed north of the lake; 2-celled enclosure. | Stormwater Treatment Areas (STAs) | Completed | 2015 | N/A | 8878 | Taylor Creek/ Nubbin Slough | 773 | N/A | 196548 | USACE/ SFWMD | N/A | N/A
SFWMD-03 | SFWMD | USACE | Lakeside Ranch Phase I | Phase I included a northern STA and inflow pump station (S-650), which began operating in 2012. | Stormwater Treatment Areas (STAs) | Completed | 2012 | N/A | 15080 | Taylor Creek/ Nubbin Slough | 919 | 22800000 | 132704 | Florida Legislature | USACE - $22,800,000/ SFWMD - $132,704 | N/A
SFWMD-04 | SFWMD | N/A | Otter Slough Restoration | Completed project included 5 ditch plugs and removal of 2 berms to help attenuate regional stormwater runoff, as well as provide nutrient reductions due to plant uptake from overland flows. | Hydrologic Restoration | Completed | 2009 | N/A | 12 | Lower Kissimmee | 500 | N/A | 0 | N/A | N/A | N/A
SFWMD-05 | SFWMD | USACE | Kissimmee River Restoration | Acquiring more than 100,000 acres of land in the river's floodplain and headwaters, backfilling 22 miles of the C-38 Canal, reconnecting remnant sections of the original river channel, removing 2 water control structures, modifying portions of the river's headwaters, and implementing the Headwaters Regulation Schedule to meet the project hydrologic criteria needed to meet the KRRP ecological goals. When restoration is complete, more than 40 square miles of river-floodplain ecosystem will be restored, including over 12,000 acres of wetlands and 40 miles of historic river channel. | Hydrologic Restoration | Underway | 2020 | N/A | 39128 | Lower Kissimmee | 25000 | 780000000 | N/A | USACE | USACE - $780,000,000 | N/A
SFWMD-06 | SFWMD | DEP | Phase I Rolling Meadows | Restore historic Lake Hatchineha floodplain wetlands and habitat within the Rolling Meadows property, which was purchased jointly with DEP. | Wetland Restoration | Completed | 2016 | N/A | 144 | Upper Kissimmee | 1900 | 43200000 | 150000 | DEP | DEP - $150,000 | N/A
SFWMD-07 | SFWMD | N/A | Gardner-Cobb Marsh | Project includes various activities (ditch plugs, berm removal, exotic veg. treatment, and culvert replacement) to help attenuate regional stormwater runoff. May provide ancillary WQ benefits due to nutrient plant uptake from overland flows in marsh. | Hydrologic Restoration | Planned | TBD | N/A | 11 | Upper Kissimmee | 2000 | TBD | 0 | Florida Legislature | TBD | N/A
SFWMD-08 | SFWMD | N/A | Rough Island | Completed project included various activities (e.g., ditch plugs, ditch filling, exotic removal) to help attenuate regional stormwater runoff and provide incidental nutrient reductions due to plant uptake from overland flows. | Hydrologic Restoration | Completed | 2009 | N/A | 134 | Upper Kissimmee | 1000 | N/A | 0 | N/A | N/A | N/A
SFWMD-09 | SFWMD | N/A | Oasis Marsh Restoration | Completed project included filling 4 ditches, totaling 2.4 ac in size, with 3,144 cubic yds of sediments from an adjacent levee to restore floodplain function of 77 ac of wetlands and reconnect them to the littoral zone of Lake Kissimmee. | Wetland Restoration | Completed | 2010 | N/A | 431 | Upper Kissimmee | 77 | N/A | 0 | N/A | N/A | N/A
SFWMD-10 | SFWMD | N/A | Lykes West Waterhole Marsh | This project pumps excess water from the C-40 Canal for phosphorus removal via uptake within the wetlands and associated marshes before it enters Lake Okeechobee. | Dispersed Water Management (DWM) | Completed | 2006 | N/A | 9185 | Indian Prairie | 2370 | 50000 | 470238 | Florida Legislature | FRESP - $470,238 | N/A
SFWMD-11 | SFWMD | N/A | Rafter T Ranch | Storage of 1,298 ac-ft of water through above ground impoundment and pasture. | Dispersed Water Management (DWM) | Completed | 2014 | N/A | 198 | Lake Istokpoga | 2602 | 580741 | 162736 | Florida Legislature | Florida Legislature - $743,477 | N/A
SFWMD-12 | SFWMD | N/A | Buck Island Ranch (NEPES-1) | Storage of 1,573 ac-ft of water through pasture. | Dispersed Water Management (DWM) | Completed | 2012 | N/A | 2397 | Indian Prairie | 1048 | 1725 | 173600 | Florida Legislature | Florida Legislature - $173,600 | N/A
SFWMD-13 | SFWMD | N/A | Dixie West | Storage of 315 ac-ft of water through pasture. | Dispersed Water Management (DWM) | Completed | 2012 | N/A | 508 | Lower Kissimmee | 1295 | 33000 | 51500 | Florida Legislature | Florida Legislature - $51,500 | N/A
SFWMD-14 | SFWMD | N/A | Dixie Ranch | Storage of 856 ac-ft of water through pasture. | Dispersed Water Management (DWM) | Completed | 2012 | N/A | 454 | Lower Kissimmee | 3771 | 42500 | 146500 | Florida Legislature | Florida Legislature - $146,500 | N/A
SFWMD-15 | SFWMD | N/A | Dixie Ranch | See SFWMD-14. | Dispersed Water Management (DWM) | Completed | 2012 | N/A | See SFWMD-14. | Taylor Creek/ Nubbin Slough | See SFWMD-14. | See SFWMD-14. | See SFWMD-14. | See SFWMD-14. | Included in SFWMD-14. | N/A
SFWMD-16 | SFWMD | N/A | Lost Oak Ranch | Storage of 374 ac-ft of water through pasture. | Dispersed Water Management (DWM) | Completed | 2013 | N/A | 62 | Upper Kissimmee | 1832 | 79073 | 55000 | Florida Legislature | Florida Legislature - $55,000 | N/A
SFWMD-17 | SFWMD | N/A | Willaway Cattle and Sod | Storage of 229 ac-ft of water through above ground impoundment. | Dispersed Water Management (DWM) | Completed | 2013 | N/A | 252 | Lower Kissimmee | 69 | 302479 | 1878 | Florida Legislature | Florida Legislature - $1,878 | N/A
SFWMD-18 | SFWMD | N/A | XL Ranch (Lightsey) | Storage of 887 ac-ft of water through above ground impoundment and pasture. | Dispersed Water Management (DWM) | Completed | 2012 | N/A | 156 | Fisheating Creek | 3227 | 61396 | 137000 | Florida Legislature | Florida Legislature - $137,000 | N/A
SFWMD-19 | SFWMD | N/A | Triple A Ranch | Storage of 397 ac-ft of water through above ground impoundment. | Dispersed Water Management (DWM) | Completed | 2015 | N/A | 173 | Lower Kissimmee | 106 | 322186 | 30000 | Florida Legislature | Florida Legislature - $30,000 | N/A
SFWMD-20 | SFWMD | N/A | La Hamaca (Blue Head Ranch) | Storage of 3,462 ac-ft of water through pasture. | Dispersed Water Management (DWM) | Completed | 2017 | N/A | 1597 | Fisheating Creek | 5020 | 193750 | 361200 | Florida Legislature | Florida Legislature - $361,200 | N/A
SFWMD-21 | SFWMD | N/A | Nicodemus Slough | Storage of 33,860 ac-ft of water through above ground impoundment and pasture. | Dispersed Water Management (DWM) | Completed | 2015 | N/A | 7162 | Fisheating Creek | 15906 | 4900000 | 2500000 | Florida Legislature | Florida Legislature - $2,500,000 | N/A
SFWMD-22 | SFWMD | USACE | Kissimmee River Headwaters Revitalization | Increase regulatory stages and change the operating schedule on three major waterbodies in the Kissimmee Chain of Lakes. It is designed to increase storage in the headwater lakes to provide appropriate flow patterns to the restored Kissimmee River floodplain following completion of restoration construction and land acquisition. The increased storage is also expected to improve the quantity and quality of littoral habitat in the headwater lakes. | Hydrologic Restoration | Underway | 2020 | N/A | 1249 | Upper Kissimmee | 7200 | Included in SFWMD-05. | Included in SFWMD-05. | Included in SFWMD-05. | Included in SFWMD-05. | N/A
SFWMD-23 | SFWMD | N/A | Buck Island Ranch Wildlife Management Area (WMA) NE PES-2 | Storage of 620 ac-ft of water through pasture. | Dispersed Water Management (DWM) | Completed | 2015 | N/A | 1565 | Indian Prairie | 859 | 624600 | 163500 | Florida Legislature | Florida Legislature - $163,500 | N/A
SLID-01 | Spring Lake Improvement District | DEP | Spring Lake Improvement District (SLID) Improvements Phases 1-3 | Treatment of runoff through a STA. | Stormwater Treatment Areas (STAs) | Completed | 2016 | 196 | 154 | Lake Istokpoga | 3016 | 3671712 | 60000 | SLID/ DEP/ Florida Legislature | SLID - $69,267/ DEP - $3,186,445/ Legislature - $416,000 | G0377
SLID-02 | Spring Lake Improvement District | N/A | SLID Improvements Phase 4 | Modification of the existing STA (Project SLID-1) to include a bypass weir to direct more water to the STA. | Stormwater Treatment Areas (STAs) | Canceled | N/A | N/A | N/A | Lake Istokpoga | N/A | N/A | N/A | N/A | N/A | N/A
TW-01 | Town of Windermere | SFWMD | First Avenue and Forest Street Drainage Improvements | Construction of vegetated swales, exfiltration trench systems, and oil/grit separation units to treat stormwater runoff into Wauseon Bay which is directly connected to Lake Butler, which is an OFW. | BMP Treatment Train | Completed | 2018 | 66 | 9 | Upper Kissimmee | 23.5 | 566889 | Not provided | Windermere/ SFWMD | Windermere - $391,889/ SFWMD - $175,000 | N/A
VWCD-01 | Valencia WCD | N/A | Water Quality Awareness Program | Water quality education and awareness articles posted on the Orange County website. | Education Efforts | Completed | N/A | TBD | TBD | Upper Kissimmee | N/A | N/A | 1000 | Valencia Water Control District | $1,000 | N/A
VWCD-02 | Valencia WCD | N/A | C-4 Outfall | Replacement of existing outfall structure draining to C-4 canal. Reline existing storm pipes at outfall. Provide flow calming weir in C-4 Canal | Control Structure | Planned | 2020 | TBD | TBD | Upper Kissimmee | 107.1 | 62750 | 328214 | Valencia Water Control District | 62750 | N/A