## LOWCP_Projects
2011 LOWCP MM | Project | Subwatershed | Basin | Subwatershed/ Basin Issue | Project Type | Project Primary Objective | Status | Comments/Recommendations | Project Recommendation | Comments | Project Purpose
11 | Taylor Creek Stormwater Treatment Area (STA) | TC/NS | S-191 | Quality Quantity (maybe) | Regional | Quality | O&M |  | Keep. Current TP removal is 1.0 mt/yr (inflows < 6,000 ac-ft/yr) based on data collected for the period of 2008-2018. In order to achive performance goals, it is recommended to: 1. Add a flow equalization basin (FEB) to increase inflows needed to maintain wetland vegetation within the STA 2. Seek ways to improve/optimize TP performance (i.e., consider current operational measures and indentify possible needs for future operational measures) | 1. STA operation started in June 2008 2. Unable to maintain desirable vegetation for P updatake due to inconsistent availability of inflows to Cell 1. 3. Current subwatershed conditions differ from thosed used for design purposes. | Retain stormwater runoff and reduce phosphorus from the Taylor Creek Subwatershed. This STA is divided into two cells in series and is expected to treat about 10% of the water flow in Taylor Creek.
12 | Nubbins Slough Stormwater Treatment Area (STA) | TC/NS | S-191 | Quality Quantity (maybe) | Regional | Quality | O&M |  | Keep. Current average TP removal is 0.186 mt/yr (inflows < 702 ac-ft/yr) based on data collected for the period of 2008-2018. In order to achieve performance goals, it is recommended to: 1. Retrofit inflow pump station to operate within actual inflow and stage conditions 2. Complete levee repairs to remove stage restrictions. Funds are available in FY19 to cover these repairs. 3. Continue treating exotics and promoting wetland vegetation 4. Add a flow equalization basin (FEB) to increase inflows needed to maintain wetland vegetation within the STA 5. Public comment - Use the STA for water drainage from the Four Seasons subdivision from the north and the Berman Road subdivisions from the east. It is the current belief, the Okeechobee County Commission could assist in this effort. These suggestions would certainly make use of a STA which has not been functional since its inception and could certainly resolve a flood problem Okeechobee County has in both of these areas 6. Public Comment - Consider adding a pump station along the L-63N canal to pump additional water into the STA during dry times. During extreme wet periods add ASR wells along the perimeter of the STA and utlize those wells to store excess stormwater from the STA as well as water from the L-63N canal. | 1. STA operation started in September 2006 2. Low basin runoff has limited STA inflows which resulted in dry out and impeded establishment of wetland vegetation. 3. Inflow pump is oversized and cannot efficiently operate for current flow conditions. 4. Defects in levees required stage restrictions since start up. | The purpose of this STA is to divert and treat runoff from Nubbin Slough. This will be accomplished by pumping water from Nubbin Slough into the STA. Water will then discharge back to the slough through three outlet structures on the west side of Cell 2.
13 | Dispersed Water Management – Avon Park Air Force Range | LI | - | Quality Quantity (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized | Construction of this project was funded with a 90/10 cost share with the District and was completed in 2009. Data submittal was not required as part of cost share agreement. It is assumed that the benefits have been realized | Includes restoration of existing levee and water control structures. Will reduce flows and nutrient loading to Arbuckle Marsh.
16 | Dispersed Water Management – Lykes Basinger Grove | IP | C-41A | Quantity | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized | SFWMD provided $200,000 for construction of this project. Data submittal was not required as part of cost share agreement. It is assumed that the benefits have been realized | Includes construction of a 50,000 gpm pump station onsite and revamping the existing system of internal ditches.
17 | Dispersed Water Management – Sumica | UK | Tiger Lake, Lake Weohyakapka | Quality (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized | SFWMD agreed to provide $35,350 for construction of this project. Data submittal was not required as part of the agreement. It is assumed that the benefits have been realized | Restore the hydroperiod in the central marsh system by constructing a rock riprap berm in front of the outfall structure at SR60.
18 | Alternative Water Supply Projects – Joe Hall, Raulerson & Sons Ranch Stormwater Recycling Project | LK | S-65D | Quality (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized |  | Assess, plan, design, and construct water storage/disposal projects on public, private, and tribal lands
19 | Alternative Water Supply Projects – David H. Williams Sod & Cattle Stormwater Irrigation | LK | S-65D | Quality (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized |  | Assess, plan, design, and construct water storage/disposal projects on public, private, and tribal lands
20 | Alternative Water Supply Projects – Four K Ranch, Inc., Lippincott Farm Stormwater Recycling System | LK | S-65D | Quality (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized |  | Assess, plan, design, and construct water storage/disposal projects on public, private, and tribal lands
21 | Alternative Water Supply Projects - Haynes & Susan Williams, 101 Ranch 17.2 Acre Reservoir & 44 Acre Reservoir | LK | S-65D | Quality (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized |  | Assess, plan, design, and construct water storage/disposal projects on public, private, and tribal lands
23 | FRESP – Williamson Cattle Company Pilot Project | TC/NS | S-191 | Quality Quantity (maybe) | Source Control | Quantity | Completed |  | Closed. Implementation captured under MM 43 | See LOWCP MM 43. | Develop a payment program for working ranches that provide water management and/or water quality improvement services
24 | FRESP – Buck Island Ranch Pilot Project | IP | C-41 | Quality | Source Control | Quantity | Completed |  | Closed. Implementation captured under MM 43 | See LOWCP MM 43 | Develop a payment program for working ranches that provide water management and/or water quality improvement services
25 | Florida Ranchland Environmental Service Project (FRESP) - Lykes Bros. West Waterhole Pilot | IP | C-40 | Quality | Regional | Quality | O&M |  | Keep. Actual benefits are: water quality - 7.0 mt/yr and quantity - 13,400 ac-ft based on data collected during 2008-2018. Contract with service provider expires in September 2020. Provide funding to continue project implementation until construction of larger, long term capital projects is completed | Project operation started in November 2006 | Provide shallow storage, retention and detention to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities.
27 | FRESP – Lightsey XL Ranch Pilot Project | FEC | Fisheating Creek | Quality Quantity (maybe) | Source Control | Quantity | Completed |  | Closed. Implementation captured under MM 43 | See LOWCP MM 43 | Develop a payment program for working ranches that provide water management and/or water quality improvement services
29 | FRESP – Rafter T Ranch Pilot Project | LI | Arbuckle Creek | Quality Quantity (maybe) | Source Control | Quantity | Completed |  | Closed. Implementation captured under MM 43 | See LOWCP MM 43 | Develop a payment program for working ranches that provide water management and/or water quality improvement services
30 | Kissimmee River Restoration (KRR) – Lykes Basinger Grove and Boat ramp Nursery | LK | - | Quality (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized |  | Modify the existing surface water management system and to consruct protective levees around the existing nursery and the existing grove to provide additional flood protection for the Lykes Basinger Grove and Boatramp Nursery Food Protection project property and surrounding areas
33 | KRR – Lake Wales Ridge Wildlife and Environmental Area Restoration (Royce Unit) | LK | S-65BC, S-65D | Quality Quantity (maybe) | Source Control | Quantity | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized |  | Restore natural sheet flow within an area along the west side of Lake Istokpoga by filing four existing ditches at the north end of the property that currently flow freely into Josephine Creek and Lake Isokpoga
41 | Dispersed Water Management Lykes Nicodemus Slough | FEC | Nicodemus Slough North | None | Regional | Quantity | O&M |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | 1. Project operation started in 2015. 2. On average the project is storing approximately 43,600 ac-ft/yr based on data collected between 2015-2019 3. Current agreement expires in January 2023 | Capture/detain surface water from Lake Okeechobee when excess discharges from Lake Okeechobee flow to tide or may cause harm to the Caloosahatchee Estuary and/or Saint Lucie Estuary.
42 | Dispersed Water Management Istokpoga Marsh Watershed Improvement District (IMWID) | IP | C-41 | Quality | Source Control | Both | Construction |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | 1. Estimates ("most likely") are the result of implementing phase I and II. Benefits for each phase are unknown. 2. Operation of phase I should commence in 2019. | Reduce stormwater flows and total phosphorus load entering Lake Okeechobee coming off of the IMWID secondary conveyance system by storing water in above ground impoundments (AGI). Water collected in the impoundments would be made available to IMWID for normal water supply.
43 | Northern Everglades Payment for Environmental Service Program (NE-PES) Solicitation | FEC | Fisheating Creek | Quality Quantity (maybe) | Source Control | Quantity | O&M |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | Projects: XL Ranch (NEPES-1) and La Hamaca (NEPES-2). This project has an ancillary water quality benefit provided by never releasing the water it captures. This water is a nutrient reduction to the system. The quantification of this may be estimated by FDEP and added to the BMAP. However, this would be a temporary reduction should funds not continue to be made available to pay for these environmental services or should other more regional permanent projects come online thereby reducing the need for public private partnership environmental services. | Provide shallow storage, retention and detention to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities.
43 | Northern Everglades Payment for Environmental Service Program (NE-PES) Solicitation | IP | C-41 | Quality | Source Control | Quantity | O&M |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | Projects: Buck Island Ranch (NEPES-1) and Buck Island Ranch (NEPES-2). This project has an ancillary water quality benefit provided by never releasing the water it captures. This water is a nutrient reduction to the system. The quantification of this may be estimated by FDEP and added to the BMAP. However, this would be a temporary reduction should funds not continue to be made available to pay for these environmental services or should other more regional permanent projects come online thereby reducing the need for public private partnership environmental services. | Provide shallow storage, retention and detention to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities.
43 | Northern Everglades Payment for Environmental Service Program (NE-PES) Solicitation | LI | Lake Istokpoga | Quality Quantity (maybe) | Source Control | Quantity | O&M |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | Rafter T Ranch (NEPES-2). This project has an ancillary water quality benefit provided by never releasing the water it captures. This water is a nutrient reduction to the system. The quantification of this may be estimated by FDEP and added to the BMAP. However, this would be a temporary reduction should funds not continue to be made available to pay for these environmental services or should other more regional permanent projects come online thereby reducing the need for public private partnership environmental services. | Provide shallow storage, retention and detention to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities.
43 | Northern Everglades Payment for Environmental Service Program (NE-PES) Solicitation | LK | Lower Kissimmee | Quality (maybe) | Source Control | Quantity | O&M |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | Projects: Dixie West (NEPES-1), Triple A Ranch (NEPES-1), and Willaway Cattle & Sod (NEPES-1). This project has an ancillary water quality benefit provided by never releasing the water it captures. This water is a nutrient reduction to the system. The quantification of this may be estimated by FDEP and added to the BMAP. However, this would be a temporary reduction should funds not continue to be made available to pay for these environmental services or should other more regional permanent projects come online thereby reducing the need for public private partnership environmental services. | Provide shallow storage, retention and detention to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities.
43 | Northern Everglades Payment for Environmental Service Program (NE-PES) Solicitation | TC/NS | S-154 | Quality | Source Control | Quantity | O&M |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | Dixie Ranch (NEPES-1). This project has an ancillary water quality benefit provided by never releasing the water it captures. This water is a nutrient reduction to the system. The quantification of this may be estimated by FDEP and added to the BMAP. However, this would be a temporary reduction should funds not continue to be made available to pay for these environmental services or should other more regional permanent projects come online thereby reducing the need for public private partnership environmental services. | Provide shallow storage, retention and detention to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities.
43 | Northern Everglades Payment for Environmental Service Program (NE-PES) Solicitation | UK | Lake Kissimmee | Quality (maybe) | Source Control | Quantity | O&M |  | Keep. Continue project implementation until construction of larger, long term capital projects is completed | Lost Oak Ranch (NEPES-1).This project has an ancillary water quality benefit provided by never releasing the water it captures. This water is a nutrient reduction to the system. The quantification of this may be estimated by FDEP and added to the BMAP. However, this would be a temporary reduction should funds not continue to be made available to pay for these environmental services or should other more regional permanent projects come online thereby reducing the need for public private partnership environmental services. | Provide shallow storage, retention and detention to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities.
44 | Alternative Water Storage and Disposal Interim (AWSDI) Projects – Pearce/Hartman Property | IP | L-48, L-59E | Quality (maybe) Quantity (maybe) | Source Control | Quantity | Planning |  | Re-evaluate | The parcels are currently being leased. The lease agreement expires in 2022. However, the lease can be terminated with a 6-month notice. The parcels were initially removed from consideration due to the lessee's interest in pursuing additional compensation/improvements associated with USDA-NRCS assistance program | Utilize interim facilities for water storage by employing a range of site alternative measures at a number of project sites. Alternatives include construction of on-site measures such as temporary ditch blocks, minor berms, minimal earthwork, wetland restoration, and potential water diversions to the project site using temporary pump facilities.
46 | Old: Alternative Water Storage and Disposal Interim (AWSDI) Projects – Taylor Creek (Grass Island) Interim Project New: Grassy Island Flow Equalization Basin (FEB) | TC/NS | S-191 | Quality Quantity (maybe) | Regional | Quantity | Planning |  | Modify project scope. A flow equalization basin (FEB) is being proposed to provide the inflows needed to maintain the wetland vegetation at the the Taylor Creek STA | The property is currently leased for cattle grazing and the lease expires in September 2019. The project proposes installation of ditch plugs and control structures with flashboard risers to retain surface water and reduce flows to Taylor Creek. | Utilize interim facilities for water storage by employing a range of site alternative measures at a number of project sites. Alternatives include construction of on-site measures such as temporary ditch blocks, minor berms, minimal earthwork, wetland restoration, and potential water diversions to the project site using temporary pump facilities.
47 | Kissimmee River Restoration (KRR) – Three Lakes Wildlife management Area Hydrologic Restoration | UK | Lake Marian | Quality (maybe) | Source Control | Restoration | Completed |  | Closed. It is assumed that the benefits associated with this project have been realized |  | Restore hydrology to impacted wetlands associated with the Upper Kissimmee Chain of Lakes
48 | Kissimmee River Restoration (KRR) – Gardner-Cobb Marsh | UK | - | Quality (maybe) | Source Control | Restoration | Planning |  | Keep | The majority of Gardner Cobb Marsh remains under lease for light cattle grazing until 12/31/20 | Restore hydrology to impacted wetlands associated with the Upper Kissimmee Chain of Lakes
56 | Lemkin Creek Urban Stormwater Facility | TC/NS | S-133 | Quality (maybe) Quantity (maybe) | Regional | Both | Planning |  | Keep. An updated review of these alternatives would be necessary to assess which alternative provide the most cost effective solution based on basin needs. Also, since basin flow is flashy, additional water supply alternatives (e.g., reservoir, ASR, FEB) should be considered | In 2009 and 2010, the SFWMD in cooperation with Okeechobee County and the City of Okeechobee, conducted an analysis of 3 potential project alternatives for this area. The alternatives consisted of a shallow impoundment (alternatives 1 and 2) and a shallow wetland treatment system (alternative 3). TP removal estimates ranged from 13 to 62 lb/yr (alt. 1 and 2) and from 666 to 734 lb/yr for alternative 3. Cost estimates ranges from $3.7M (alt. 1) to $4.4 (alt. 3) | The impoundment/wetland treatment area will increase storage and treat water to remove phosphorus before it enters Lake Okeechobee
57 | Dispersed Water Management Potential Site - Fisheating Creek Marsh Watershed Project | FEC | Fisheating Creek | Quality Quantity (maybe) | Source Control | Quantity | Planning |  | Keep. More detailed planning and design will define the facility that is needed to meet phosphorus reductions as well as storage needs | No updates at this time | Evaluate, engineer, and rehabilitate the PL-566 water control structures in the Fisheating Creek Marsh Watershed project area to more effectively store and manage water and reduce phosphorus runoff from more than 50,000 acres in the headwaters of Fisheating Creek.
58 | Dispersed Water Management Potential Site - Okeechobee County East/West Stormwater Conveyance Project | TC/NS | - | Quality | Regional | Both | Planning |  | Keep. More detailed planning and design will define the facility that is needed to meet phosphorus reductions as well as storage needs | No updates at this time | Acquire 1,000 acres of land to implement a stormwater conveyance system with retention and treatment components from east to west through the City of Okeechobee and Okeechobee County. Following water quality treatment and storage, the water will be conveyed into SFWMD Lemkin Creek urban water storage and treatment facility before making its way into the Rim Canal and ultimately Lake O.
60 | Alternative Water Storage and Disposal Interim (AWSDI) Projects – Buckhead Ridge Property (TIIFF) | IP | - | Both | Source Control | Quantity | Planning |  | Keep. The proposed project land should be evaluated to determine the feasibility of constructing a AWSDI on TIIFF lands. ould be paired with a nutrient removal technology to address subwatershed issues | No updates at this time | Utilize interim facilities for water storage by employing a range of site alternative measures at a number of project sites. Alternatives include construction of on-site measures such as temporary ditch blocks, minor berms, minimal earthwork, wetland restoration, and potential water diversions to the project site using temporary pump facilities.
62 | Alternative Water Supply and Disposal Interim (AWSDI) Projects - Fisheating Creek (TIIFF) | FEC | Fisheating Creek | Quality Quantity (maybe) | Source Control | Quantity | Planning |  | Keep. The proposed project land should be evaluated to determine the feasibility of constructing a AWSDI on TIIFF lands. ould be paired with a nutrient removal technology to address subwatershed issues | No updates at this time | Utilize interim facilities for water storage by employing a range of site alternative measures at a number of project sites. Alternatives include construction of on-site measures such as temporary ditch blocks, minor berms, minimal earthwork, wetland restoration, and potential water diversions to the project site using temporary pump facilities.
63 | Alternative Water Storage and Disposal Interim (AWSDI) Projects – Harney Pond (TIIFF) | IP | - | Both | Source Control | Quantity | Planning |  | Keep. The proposed project land should be evaluated to determine the feasibility of constructing a AWSDI on TIIFF lands. ould be paired with a nutrient removal technology to address subwatershed issues | No updates at this time | Utilize interim facilities for water storage by employing a range of site alternative measures at a number of project sites. Alternatives include construction of on-site measures such as temporary ditch blocks, minor berms, minimal earthwork, wetland restoration, and potential water diversions to the project site using temporary pump facilities.
64 | Alternative Water Storage and Disposal Interim (AWSDI) Projects – Indian Prairie (TIIFF) | IP | - | Both | Source Control | Quantity | Planning |  | Keep. The proposed project land should be evaluated to determine the feasibility of constructing a AWSDI on TIIFF lands. Could be paired with a nutrient removal technology to address subwatershed issues | No updates at this time | Utilize interim facilities for water storage by employing a range of site alternative measures at a number of project sites. Alternatives include construction of on-site measures such as temporary ditch blocks, minor berms, minimal earthwork, wetland restoration, and potential water diversions to the project site using temporary pump facilities.
66 | Brady Ranch Stormwater Treatment Area (STA) | TC/NS | S-191 | Quality Quantity (maybe) | Regional | Quality | Planning |  | Keep. However, it is recommended to add a flow equalization basin (FEB) to the Brady Ranch STA to ensure inflows needed to ensure healthy wetland vegetation is maintained | No planning for the Brady Ranch site as a STA has been performed. Property is currenlty under lease agreement for cattle grazing with a hunting preserve. Lease agreement expires in May 2029. However, SFWMD may elect to terminate the lease by providing a 3-year notification to the lessee. | Treat water and remove phosphorus before it enters Lake Okeechobee. The 1,800-acre STA will receive flows from L-63 and will discharge to Lake Okeechobee.
68 | S-68 Stormwater Treatment Area (STA) | IP | - | Both | Regional | Quality | Planning |  | Keep. More detailed planning and design will define the facility that is needed to meet phosphorus reductions as well as storage needs for this subwatershed | No updates at this time | Provide additional water quality improvements in the Indian Prairie subwatershed.
75 | Istokpoga/Kissimmee Reservoir and Stormwater Treatment Area (RSTA) | IP | - | Both | Regional | Both | Planning |  | Keep. More detailed planning and design will define the facility that is needed to meet phosphorus reductions as well as storage needs for these subwatersheds (LI, IP, and LK) | No updates at this time | To enhance existing storage and capacity and provide additional water quality improvements in the Lake Okeechobee Watershed.
76 | Northern Everglades Chemical Treatment Pilot Project Parcel Level | - | - | - | Source Control | Quality | Planning |  | Keep. Conduct a feasibility analysis for a full-scale treatment system using most promising technologies | To date, SFWMD has evaluated 10 technologies. The data collected provides a simplified approach to cross-compare each technology's treatment performance, based on before/ versus after-application changes in constituent levels. Assessment was limited to the vendors who approached the SFWMD. Thus, the technologies evaluated represent only a small subsample of all available water treatment technologies An annual benefit is not assigned to this MM as it is programatic and the benefit is subject to site-specific conditions. Benefits can be applied on a small parcel level up to a large full scale regional level but may required proprietary/service contract level efforts. | Implement chemical treatment at the parcel level across the Lake Okeechobee Watershed
77 | Northern Everglades Chemical Treatment Regional - Reservoirs | - | - | - | Regional | Quality | Planning |  | Keep | No updates at this time | Addition of chemical treatment in CERP Lake Okeechobee reservoirs (Istokpoga Reservoir and Kissimmee Reservoir)
78 | Rolling Meadows/Catfish Creek Wetland Restoration (Phase 1) | UK | Catfish Creek | Quality (maybe) | Source Control | Restoration | O&M |  | Keep. Continue monitoring to document project benefits | Project operation started in April 2017. The extreme rainfall conditions in WY2018 and the first season of flow-through operation likely affected initial water quality benefits. Annual TP concentration went from 479 µg/L to 102 µg/L. | Restore a sod farm back to historic lake littoral wetlands connected to Lake Hatchineha.
10 & 39 | Hybrid Wetland Treatment Technology (HWTT) | TC/NS | S-191, S-133 | Quality Quantity (maybe) | Regional | Quality | O&M |  | Keep. However, when implementing this technology is important to note that: 1. This technology is well suited for the treatment of point sources where high nutrient concentrations and flows can be predicted to mitigate elevated concentrations prior to discharge to an off-site water body. 2. The cost effectiveness of this technology is variable and dependent on accurately determining the flow, nutrient concentrations and background water quality 3. Utilizing HWTT for large-scale application poses a more complicated process that requires a review of site-specific conditions, a comprehensive design, and an analysis of the potential cost per pound of nutrient removed | 1. Currently, there are 5 operational facilities: Nubbin Slough, Mosquito Creek, Lemkin Creek, Grassy Island and Wolf Ditch 2. These facilities have removed between 6.53 mt/yr (partial capacity) and 22.2 mt/yr (full capacity) 3. All HWTT systems continued to provide effective removal of TP. | Reduce phosphorus exports to Lake Okeechobee in the four priority basins (S-65D, S-65E, S-154, and S-191).
51, 55 | Lakeside Ranch Stormwater Treatment Area (STA) Phase I & II | TC/NS | S-135, S-191 | Quality Quantity (maybe) | Regional | Quality | O&M |  | Keep. It is expected that operation of the S-191A pump station will help to regulate water levels in the cells which should result in healthy vegetative communities. | 1. Phase I - Operational since 2013 2. Phase II - Start-up monitoring in preparation for operation 3. Phase III - Construction of S-191A pump station is currently scheduled to be completed in April 2021 4. Average annual TP load reduction for Phase I is 7 mt/yr (designed is 9 mt/yr) based on data collected for the period of 2013-2018 5. Reduced water levels, the increase in wildlife disturbances and the significant loss in vegetation have most likely contributed to the recent poor performance of Phase I | Capture and reduce the amount of total phosphorus from the S‑191 and S-135 basins prior to discharge back into the L-47 rim canal and eventually into Lake Okeechobee.
52-53, 69-74, 79-81 | Lake Okeechobee Watershed Restoration Project | - | - | - | Regional | Quantity | Planning |  | Keep. The LOWRP is a tentatively selected plan in conceptual design phase. Project features and/or configurations may be subject to change | 1. The LOWRP replaces the Kissimmee River Pilot ASR (MM 52), Taylor Creek ASR Reactivation (MM 53), Taylor Creek Reservoir (MM 69), Paradise Run Wetland Restoration (MM 70), Kissimmee Reservoir (MM 71), Istokpoga Reservoir (MM 72), Istokpoga STA (MM 73), Kissimmee Reservoir STA (MM 74), Port Mayaca ASR Pilot (MM 79), Ten-Well ASR System (Paradise Run) (MM 80), and Seminole Brighton Reservation ASR Pilot (MM 81). 2. The water quality and quantity benefits of these MM were estimated to be 68.62 mt/yr and 516,418 ac-ft/yr, respectively 3. The LOWRP study recommends 3 components of CERP: (1) Wetland Attenuation Feature (WAF) north of Lake Okeechobee; (2) ASR wells; and (3) Water Storage Reservoir. The estimated storage benefits include 5,200 acres of restored wetlands, 448,000 ac-ft/yr from the combination of ASR wells, and 200,000ac-ft/yr stored in the reservoir. | The major goals of the Lake Okeechobee Watershed Restoration Project (LOWRP) - part of the Comprehensive Everglades Restoration Plan - are to improve the quantity, timing, and distribution of water entering Lake Okeechobee. LOWRP will improve management of lake water levels, reduce excessive releases to the St. Lucie and Caloosahatchee estuaries, and increase operational flexibility. These goals will be achieved through storage of water in surface reservoirs and underground in aquifer storage and recovery wells. Additional wetland areas also will be restored to enhance habitat utilization in the subwatersheds that are the focus of this project.
New 1 | Septic - Sewage Conversion | TC/NS | - | Quality Quantity (maybe) | Source Control | Quality | Planning |  | Public comment - Treasure Island Septic to Sewer project. The Okeechobee Utility Authority (OUA) has completed a preliminary engineering study to provide a centralized wastewater collection system to serve up to 1,500 to 2,000 connections. It has been estimated that these connections will eliminate approximately 21.9 tons of nitrogen and 5.3 tons of phosphorus per year from the project area
New 10 | Long-term Water Quality Improvement Projects Solicitation | TBD | TBD | TBD | Regional | TBD | Planning |  | Provide shallow storage, retention/detention, or treatment to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities in BMAP priority subwatershed/basins
New 11 | Short-term Water Quality Improvement Projects Solicitation | TBD | TBD | TBD | Regional | TBD | Planning |  | Provide shallow storage, retention/detention, or treatment to enhance Lake Okeechobee and estuary health by reducing discharge volumes, reducing nutrient loading to downstream receiving waters, and expanding groundwater recharge opportunities in BMAP priority subwatersheds/basins
New 12 | C-38 Reservoir Assisted Stormwater Treatment Area | TC/NS | S-154C S-133 | Quality Quantity (maybe) | Regional | Quality | Planning |  | The project's goal is to treat water from three (3) priority basins (S-154, S-154C and S-133) in the Taylor Creek/Nubbin Slough Subwatershed and/or Lake Okeechobee
New 14 | West Water Hole Expansion | IP | C-40 | Quality | Regional | Quality | Planning |  | This public private partnership project will treat and remove phosphorus and nitrogen from the regional system by adding 500 acres to the existing Management Measure ID 25 - Florida Ranchland Environmental Service Project (FRESP) - Lykes Bros. West Waterhole Project for a total project area of 3,000 acres and estimated nutrient reductions of TP: 7.6 mt/yr and TN: 33.6 mt/yr
New 15 | Conservation Easement Program | TBD | TBD | TBD | TBD | TBD | Planning |  | Program for protection, restoration, and enhancement of lands in BMAP priority subwatersheds/basins through conservation easements
New 2 | Program for Edge-of-Field Treatment Projects | TBD | TBD | TBD | Source Control | Quantity | Planning |  | Program for construction of edge-of-field systems that improve water quality and/or conserve/recirculate water
New 3 | Floating Aquatic Vegetative Tiling (FAVT) (FDACS) | FEC | Fisheating Creek | Quality Quantity (maybe) | Source Control | Quality | Planning |  | 1. This technology uses the direct assimilation of nutrients from the water column using floating plant roots (as compared to plants rooted in the soil), and all the biomass is rapidly incorporated directly into the soil through tiling 2. FEC facility is comprised of 250 acres of FAV and submerged aquatic vegetation (FAV) communities with a treatment capacity of 100 cfs 3. Status: FEC facility became operational in 2016. The facility is currently in an optimization phase
New 4 | Brighton Valley NE PPP | IP | C-41 | Both | Regional | Quality | Planning |  | 1. This Northern Everglades Public Private Partnership (NEPPP) project will detain onsite rainfall and pump water from the C-41A Canal and will treat it on approximately 8,142 acres of private agricultural lands. The total cost of the project is $42M of which $11.5 were appropriated under State Appropriation 1590A and the reminder is subject to receiving funds from the Florida Legislature 2. Status: Construction is expected to be completed in September 2019
New 5 | El Maximo Ranch NE PPP | LK | S65A/Kissimmee River | Quality (maybe) | Regional | Quality | Planning |  | 1. This Northern Everglades Public Private Partnership (NEPPP) project will detain onsite rainfall and pump water from the C-38 Canal (aka Kissimmee River) and Blanket Bay Slough and will treat it on the 7,030-acre ranchland. The total cost of the project is $49.2M of which $10.6 were appropriated under State Appropriation 1590A and the reminder is subject to receiving funds from the Florida Legislature 2. Status: Permitting
New 7 | Grassy Island Interim Storage | TC/NS | S-191 | Quality Quantity (maybe) | Regional | Quantity | Planning |  | The project's objective is to increase regional surface water storage capacity and operational flexibility of the primary stormwater conveyance system Cost Estimate: $5.3K (design/engineering/construction)
New 8 | Brady Ranch Interim Storage | TC/NS | S-191 | Quality Quantity (maybe) | Regional | Quantity | Planning |  | The project's objective is to expand regional surface water storage and reduce the volume of flow that is lost to tide or otherwise results in harmful discharging to receiving waters. Cost Estimate: $12M
New 9 | L-59 Interim Storage | IP | L-59W | Quality (maybe) Quantity (maybe) | Regional | Quantity | Planning |  | The project's objective is to expand regional surface water storage and reduce the volume of flow that is lost to tide or otherwise results in harmful discharging to receiving waters. Cost Estimate: $9.9M (design/engineering/construction)
Source Control 1 | Agricultural BMPs – Owner- Implemented and Cost-Share Propose Changing to: FDACS Best Management Practices Program | All | All |  |  |  | Ongoing |  | Comments: 1. As indicated in LOWPP 2011 Update: Current - 51.8 mt/yr; Near-term - 16.8 mt/yr; Long-term - 18 mt/yr 2. Expected TP load reduction estimates are also being calculated as part of the Basin Management Action Plan (BMAP) 5-Year Review and Update in 2019 Recommendations: 1. Ensure BMPs are implemented as decsribed on the conservation plan and/or Notice of Intent (NOI) 2. Evaluate existing agricultural BMPs for improvement of current practices and development of new agricultural nonpoint source interim measures and BMPs