## Targets BMAP Table 75
Subwatershed | WY2014–WY2018 TP Load (mt/yr) | % Contribution of Load | TP Load Required Reduction (mt/yr) | TP Target (mt/yr)
Fisheating Creek | 72.4 | 12 | 59.7 | 12.7
Indian Prairie | 102.5 | 17 | 84.5 | 18
Lake Istokpoga | 47.7 | 8 | 39.3 | 8.4
Lower Kissimmee | 125.9 | 21 | 103.8 | 22.1
Taylor Creek/Nubbin Slough | 113.6 | 19 | 93.7 | 19.9
Upper Kissimmee | 90.5 | 15 | 74.6 | 15.9
East Lake Okeechobee | 16.8 | 3 | 13.9 | 2.9
South Lake Okeechobee | 29 | 5 | 23.9 | 5.1
West Lake Okeechobee | 0 | 0 | 0 | 0
Total | 598.4 | 100 | 493.4 | 105

## Progress BMAP Table 76
Subwatershed | TP Load Required Reduction (mt/yr) | TP Reduction Through June 30, 2019 (mt/yr) | TP Reductions Achieved Through June 30, 2019 (%)
Fisheating Creek | 59.7 | 14.4 | 24.1
Indian Prairie | 84.5 | 20.5 | 24.3
Lake Istokpoga | 39.3 | 2.5 | 6.4
Lower Kissimmee | 103.8 | 5.6 | 5.4
Taylor Creek/Nubbin Slough | 93.7 | 23.3 | 24.9
Upper Kissimmee | 74.6 | 16.4 | 22
East Lake Okeechobee | 13.9 | 4 | 28.8
South Lake Okeechobee | 23.9 | 8.3 | 34.7
West Lake Okeechobee | 0 | 0.5 | N/A
Total | 493.4 | 95.5 | 19.4

## Targets 3-1-20
Subwatershed | WY2015–WY2019 TP Load (mt/yr) | % Contribution of Load | TP Load Required Reduction (mt/yr) | TP Target (mt/yr) | Subwatershed | WY2015–WY2019 TP Load (mt/yr) | % Contribution of Load
Fisheating Creek | 63.6463 | 11.2669 | 51.816 | 11.8302 | Fisheating Creek Subwatershed | 63.6463 | 11.3
Indian Prairie | 87.2661 | 15.4482 | 71.0455 | 16.2206 | Indian Prairie Subwatershed | 87.2661 | 15.4
Lake Istokpoga | 47.6919 | 8.4426 | 38.8272 | 8.8647 | Lake Istokpoga Subwatershed (S-68) | 47.6919 | 8.4
Lower Kissimmee | 124.7234 | 22.079 | 101.5404 | 23.1829 | Lower Kissimmee Subwatershed [(S-65E) - (S-65)] | 124.7234 | 22.1
Taylor Creek/Nubbin Slough | 104.7177 | 18.5375 | 85.2533 | 19.4644 | Taylor Creek/Nubbin Slough Subwatershed | 104.7177 | 18.5
Upper Kissimmee | 93.3594 | 16.5268 | 76.0062 | 17.3532 | Upper Kissimmee Subwatershed (S-65) | 93.3594 | 16.5
East Lake Okeechobee | 16.7293 | 2.9615 | 13.6198 | 3.1096 | East Lake Okeechobee Subwatershed | 16.7293 | 3
South Lake Okeechobee | 26.7549 | 4.7362 | 21.7818 | 4.9731 | South Lake Okeechobee Subwatershed | 26.7549 | 4.7
West Lake Okeechobee | 0.007398 | 0.0013096 | 0.0060229 | 0.0013751 | West Lake Okeechobee Subwatershed | 0.007398 | 0
Total | 564.8963 | 100 | 459.8963 | 105 | Totals from Lake Okeechobee Watershed | 564.8963 | 100
|  |  | 459.8963 | 105

## Progress 3-1-20
Subwatershed | TP Load Required Reduction (mt/yr) | TP Reduction Through June 30, 2019 (mt/yr) | TP Reductions Achieved Through June 30, 2019 %)
Fisheating Creek | 51.816 | 14.4 | 27.79%
Indian Prairie | 71.0455 | 20.5 | 28.85%
Lake Istokpoga | 38.8272 | 2.5 | 6.439%
Lower Kissimmee | 101.5404 | 5.6 | 5.515%
Taylor Creek/Nubbin Slough | 85.2533 | 23.3 | 27.33%
Upper Kissimmee | 76.0062 | 16.4 | 21.58%
East Lake Okeechobee | 13.6198 | 4 | 29.37%
South Lake Okeechobee | 21.7818 | 8.3 | 38.11%
West Lake Okeechobee | 0.0060229 | 0.5 | 100%
Total | 459.8963 | 95.5 | 20.77%

## Targets 3-1-21
Subwatershed | WY2016–WY2020 TP Load (mt/yr) | % Contribution of Load | TP Load Required Reduction (mt/yr) | TP Target (mt/yr) | Subwatershed | WY2016–WY2020 TP Load (mt/yr) | % Contribution of Load
Fisheating Creek | 63.9 | 11.8268 | 51.4819 | 12.4181 | Fisheating Creek Subwatershed | 63.9 | 11.8268
Indian Prairie | 79.8 | 14.7696 | 64.2919 | 15.5081 | Indian Prairie Subwatershed | 79.8 | 14.7696
Lake Istokpoga | 44 | 8.1436 | 35.4492 | 8.5508 | Lake Istokpoga Subwatershed (S-68) | 44 | 8.1436
Lower Kissimmee | 122.8 | 22.7281 | 98.9355 | 23.8645 | Lower Kissimmee Subwatershed [(S-65E) - (S-65)] | 122.8 | 22.7281
Taylor Creek/Nubbin Slough | 95.1 | 17.6013 | 76.6186 | 18.4814 | Taylor Creek/Nubbin Slough Subwatershed | 95.1 | 17.6013
Upper Kissimmee | 90.1 | 16.6759 | 72.5903 | 17.5097 | Upper Kissimmee Subwatershed (S-65) | 90.1 | 16.6759
East Lake Okeechobee | 18.2 | 3.3685 | 14.6631 | 3.5369 | East Lake Okeechobee Subwatershed | 18.2 | 3.3685
South Lake Okeechobee | 26.4 | 4.8862 | 21.2695 | 5.1305 | South Lake Okeechobee Subwatershed | 26.4 | 4.8862
West Lake Okeechobee | 0 | 0 | 0 | 0 | West Lake Okeechobee Subwatershed | 0 | 0
Total | 540.3 | 100 | 435.3 | 105 | Totals from Lake Okeechobee Watershed | 540.3 | 100
| 1191145.38 |  | 435.3 | 105 | Table 8B-6 3/1/21 SFER
959662.38

## Progress 3-1-21
Subwatershed | TP Load Required Reduction (mt/ur) | TP Reduction Through December 31, 2020 (mt/yr) | TP Reductions Achieved Through December 31, 2020 (%)
Fisheating Creek | 51.4819 | 15.3247 | 29.77%
Indian Prairie | 64.2919 | 2.6771 | 4.164%
Lake Istokpoga | 35.4492 | 6.1679 | 17.4%
Lower Kissimmee | 98.9355 | 17.6502 | 17.84%
Taylor Creek/Nubbin Slough | 76.6186 | 24.6296 | 32.15%
Upper Kissimmee | 72.5903 | 22.3829 | 30.83%
East Lake Okeechobee | 14.6631 | 2.1567 | 14.71%
South Lake Okeechobee | 21.2695 | 2.9804 | 14.01%
West Lake Okeechobee | 0 | 0.58772 | 100%
Total | 459.8963 | 94.6 | 20.57%
| 1013896.6031 | lbs/yr

## Reductions2020
Row Labels | Sum of TP Reduction (kg/yr) | Sum of TP Reduction (mt/yr) | Sum of TNReduction (mt/yr)
Fisheating Creek | 15324.7089 | 15.3247 | 43.4306
Lake Istokpoga | 2677.1022 | 2.6771 | 43.2557
Lower Kissimmee | 6167.9037 | 6.1679 | 48.884
Upper Kissimmee | 17650.1545 | 17.6502 | 75.1133
Taylor Creek/ Nubbin Slough | 24629.5667 | 24.6296 | 51.0238
Indian Prairie | 22382.9237 | 22.3829 | 92.5681
East Lake Okeechobee | 2156.6956 | 2.1567 | 24.616
South Lake Okeechobee | 2980.374 | 2.9804 | 50.4616
West Lake Okeechobee | 587.7196 | 0.58772 | 8.2034
Grand Total | 94557.1491 | 94.5571 | 437.5566
Note: Completed and ongoing projects only

## Targets 3-3-22
Subwatershed | WY2017–WY2021 TP Load (mt/yr) | % Contribution of Load | TP Load Required Reduction (mt/yr) | TP Target (mt/yr) | Subwatershed | WY2017–WY2021 TP Load (mt/yr)
Fisheating Creek | 55.2 | 10.3081 | 44.3765 | 10.8235 | Fisheating Creek Subwatershed | 55.2
Indian Prairie | 76.2 | 14.2297 | 61.2588 | 14.9412 | Indian Prairie Subwatershed | 76.2
Lake Istokpoga | 41.1 | 7.6751 | 33.0412 | 8.0588 | Lake Istokpoga Subwatershed (S-68) | 41.1
Lower Kissimmee | 135 | 25.2101 | 108.5294 | 26.4706 | Lower Kissimmee Subwatershed [(S-65E) - (S-65)] | 135
Taylor Creek/Nubbin Slough | 101.3 | 18.9169 | 81.4373 | 19.8627 | Taylor Creek/Nubbin Slough Subwatershed | 101.3
Upper Kissimmee | 84 | 15.6863 | 67.5294 | 16.4706 | Upper Kissimmee Subwatershed (S-65) | 84
East Lake Okeechobee | 21.7 | 4.0523 | 17.4451 | 4.2549 | East Lake Okeechobee Subwatershed | 21.7
South Lake Okeechobee | 21 | 3.9216 | 16.8824 | 4.1176 | South Lake Okeechobee Subwatershed | 21
West Lake Okeechobee | 0 | 0 | 0 | 0 | West Lake Okeechobee Subwatershed | 0
Total | 535.5 | 100 | 430.5 | 105 | Totals from Lake Okeechobee Watershed | 535.5
| 1180563.3 |  | 949080.3 | 231483 | Table 8B-6 3/2/22 SFER

## Progress 3-30-22
Subwatershed | TP Load Required Reduction (mt/yr) | TP Reduction Through December 31, 2021 (mt/yr) | TP Reductions Achieved Through December 31, 2021 (%)
Fisheating Creek | 44.3765 | 15.3 | 34.48%
Indian Prairie | 61.2588 | 23 | 37.55%
Lake Istokpoga | 33.0412 | 2.7 | 8.172%
Lower Kissimmee | 108.5294 | 13.2 | 12.16%
Taylor Creek/Nubbin Slough | 81.4373 | 32.3 | 39.66%
Upper Kissimmee | 67.5294 | 17.9 | 26.51%
East Lake Okeechobee | 17.4451 | 2.3 | 13.18%
South Lake Okeechobee | 16.8824 | 3 | 17.77%
West Lake Okeechobee | 0 | 0.6 | 100%
Total | 430.5 | 110.3 | 25.62%

## Reductions2021
Row Labels | Total TP Reductions (lbs/yr) | Total TP Reductions (mt/yr)
Fisheating Creek | 33794 | 15.3
Indian Prairie | 50709 | 23
Lake Istokpoga | 5978 | 2.7
Lower Kissimmee | 29187 | 13.2
Taylor Creek/ Nubbin Slough | 71275 | 32.3
Upper Kissimmee | 39375 | 17.9
East Lake Okeechobee | 5160 | 2.3
South Lake Okeechobee | 6616 | 3
West Lake Okeechobee | 1249 | 0.6
Grand Total | 243343 | 110.3
Note: Completed and ongoing projects only