## Projects
PROJECTS PROVIDED BY SFWMD | Project Name | Project Description | Project Location | Status | Estimated Annual Load Reduction | Completion Date (Estimated or Actual | Next Steps | Estimated Total Costs | DEP Staff Comments
| Kissimmee River Restoration | Restore ecological integrity by restoring 40 miles of meandering river and more than 12,000 miles of wetlands through the design and construction of physical project features coupled with application of optimized hydrologic conditions (From TM's Nov 2013 ppt) | Lower Kissimmee Sub-Watershed | Under Construction: Acquired nearly all lands needed in the historical river floodplain ($250 million); Removed 2 large water control structures including S-65B; Backfilled 22 miles of canal (~ 65% complete, Phases I and IV); Recarved 9 miles of remnant river channel (~ 60% complete); Rehydrate 26,500 acres of river floodplain (~ 60% complete); Restoration Evaluation Program thru 2020. | 20.6 Metric Tons; It is estimated that the KRR will result in a TP reduction of 19% at structure S-65E. This percent redcution was applied to the S-65A-E and S-65 basins. Assumes 100% BMP implementation. | 2017-2020 | Major features still need to be completed:Phase 2/3 Backfilling & remove S-65C. S-69 Weir. | $780M estimated total cost: State/ SFWMD investment to date - $345M Federal investment to date - $315M Remaining Costs: 120M | Needs further evaluation. Need to determine what additional benefits could be achieved by expediting this project and account for work done on the project after 2009.
| Kissimee River Restoration Headwaters | This is part of the Kissimmee River Restoration involving modifying portions of the river’s headwaters to meet hydrologic criteria for river restoration. In the Upper Kissimmee Basin, as a result over 7,000 acres (ac) of littoral marsh are expected to develop on the periphery of the four lakes regulated by water control structure S-65. | Lower Kissimmee Sub-Watershed | Planning: Implementation of a new headwaters regulation schedule is proposed after construction is complete. Needs NEPA analysis | No load reduction estimate, but estimated to store up to 100,000 ac-ft of flow annually | Following completion of the KRR construction components | - | - | Would likely estimate load reduction using wet detention values. Will likely fall into 2nd phase.
| Lakeside Ranch STA Phase I | Lands for the Lakeside Ranch STA are in the Taylor Creek/Nubbin Slough Sub-watershed, which is identified in the Lake Okeechobee Protection Plan as a priority sub-watershed. The Lakeside Ranch STA Project is designed in two phases. Phase I included construction of a 1,200 acre STAorth, canal improvements, and the installation of the S-650 pump station. | Taylor Creek/Nubbin Slough Sub-Watershed | Constructed and Operational | 9 Metric Tons | 2012 | Continue to operate, evaluate effectiveness and if necessary optimize. | $22.8 M Phase I Construction; Operational cost estimate $XX | Included in current project list.
| Istokpoga Marsh Watershed Improvement District (IMWID) Phase I | This project is located in the Indian Prairie Sub-watershed which, based on a long term average (2001–2012), has the highest TP loading (103 mt, or 20 percent) of the nine sub-watersheds in the LOW. It is a phased project designed as a stormwater recycling system that will afford opportunities to capture and store excess stormwater during wet periods, reducing flows and nutrient loads to Lake Okeechobee, and then return the stored water to the canal system providing a supplemental source of surface water to augment farm irrigation during dry times. Phase I includes constriction of a 308 acre AGI. Phase 1: 308 acre AGI Land acquired, design under way and agreements in place for construction; Future Phases include additional AGIs (up to approximately 900 additional acres) and water quality features. | Indian Prairie Sub-Watershed | Phase 1: 308 acre AGI Land acquired, design under way and agreements in place for construction; | 1 Metric Ton | 2016-2017 | Complete design and construct Phase 1 AGI | SFWMD/State investment to date - $12.2M | According to Highlands County, Phase II will be completed by 2019. We are waiting for information from the County about the second phase of the project in order to calculate benefits. This reflects 25% of total project
| Phase I Rolling Meadows | The goal of this project is to restore historic Lake Hatchineha floodplain wetlands and habitat within the Rolling Meadows property which was purchased jointly with FDEP. Phase I, which is fully funded, seeks to restore approximately 1,900 acres of previously drained floodplain marsh with an anticipated construction start of late 2014. | Upper Kissimmee Sub-watershed (south of Lake Hatchineha) | Phase I: Parcel B is approximately 1,970 acres, Environmental contamination cleanup has been completed, Conceptual planning efforts have been completed, Detailed design is under way (60% completed); | Unknown | 2015-2016 | Complete design (FY14) and construct (FY15) Phase I | Estimated Total Cost: $43.2M, SFWMD/State Investment to date - $38M | Not included in current projects. Need more detail. Land SFWMD owns. Other entities are doing water supply impact mitigations. Required as mitigation. Restoration Project- ditch plugs, etc. Lesley talking to engineers to see
| C-44 RASTA | CERP water quality component (6,300 acre STA, 6 cells) combined with C-44 Reservoir (3,400 acres) project to construct storage and water quality improvement features to help reduce harmful freshwater discharges and reduce nutrient loading to the St. Lucie Estuary and Indian River Lagoon, and to increase wetland/upland habitat for threatened and endangered species | East Lake Okeechobee Sub-Watershed | SFWMD has acquired 100% of lands needed for C-44 reservoir and STA; Corps is the lead on construction of reservoir, construction has begun; SFWMD pursuing construction of STAs/ reservoir discharge canal and pump station (Anticipated construction start of June 2014) | Load reduction to the Lake not calculated at this time as FDEP staff indicated this may not be included in the first BMAP phase as it is in the C-44/East Lake Okeechobee Sub-watershed. | Estimated completion 2018 and fully operational in 2020 | SFWMD pursuing construction of STAs/ reservoir discharge canal and pump station (Anticipated construction start of June 2014) | Estimated Total Cost: $$566M; Estimated non-federal expenditures: $224.6M; Estimated federal expenditure: $46.4M Remaining costs: $295M | Need to determine if partial completion of the project will provide benefits that can be calculated in this first phase of the BMAP. Not in sub-watersheds.
| Nubbin Slough STA - Critical Project | The Nubbin Slough STA is the larger of the two pilot STAs constructed north of the lake. It is also a two-celled enclosure with an effective treatment area of 773 ac (313 ha). The projected long-term average TP reduction within the STA is approximately 5.0 mt/yr., or about 85 percent of the TP load of Nubbin Slough at the project location (Stanley Consultants, Inc., 2003). | Taylor Creek/Nubbin Slough Sub-Watershed | Constructed but needs repairs | 3 to 5 Metric Tons | USACE completed construction of this facility in June 2006 but it remains inoperable. | The USACE and SFWMD have agreed to a one-year time extension (until September 9, 2014) for completing repairs, commissioning the pump station, and transferring the facility to the SFWMD. | Combined Nubbin Slough and Taylor Creek STA Critical Project expenditures (land, design/engineering, and construction) as of August 2013: $26.97M Estimated repair costs: Unknown Estimated Annual Operational Cost: $XX | No credit being applied. Project began before 2009. Need to re-evaluate if credit can be applied once the STA becomes operational.
| Taylor Creek STA - Critical Project | The Taylor Creek STA is a two-celled STA which an effective treatment area of 118 acres (48 ha), which is fairly small compared to the Everglades STAs . It is designed to remove 2 mt/yr. TP from the Taylor Creek drainage basin. | Taylor Creek/Nubbin Slough Sub-Watershed | Constructed and Operational | 2 Metric Tons Flow-through operations at the TC-STA commenced on June 26, 2008. By the end of WY2013, the TC-STA had almost 37 months of flow-through; eight months in WY2009 (June 26, 2008–February 24, 2009), slightly less than eight months in WY2011 (September 8, 2010–April 30, 2011), a full twelve months in WY2012, and nine months in WY2013 (May 1, 2012–January 31, 2013), with TP load removals of 1.44, 0.91, 1.11, and 0.58 mt of TP respectively. TP load removal over the 37-month flow-through period was 4.04 mt. | USACE completed construction in 2006; Flow through operations commenced in mid-2008 suspended then re-commenced in 2009 | Continue to operate, evaluate effectiveness and if necessary optimize. | Combined Nubbin Slough and Taylor Creek STA Critical Project expenditures (land, design/engineering, and construction) as of August 2013: $26.97M Estimated Annual Operational Cost: $XX | No credit being applied. Project began before 2009. Need to re-evaluate if credit can be applied once the STA becomes operational.
| Gardner-Cobb Marsh | This restoration project, situated on 2,000 acres, is located south of Cypress Lake and includes 23 ditch plugs, berm removal, exotic treatment, and culvert replacement. It helps attenuate regional stormwater runoff and provide incidental nutrient reductions due to plant uptake from overland flows in the marsh. In 2011 LOPP, the acre-ft. of storage was still to be determined. | Upper Kissimmee Sub-Watershed | Initial hydrological restoration complete, additional habitat enhancements ongoing | LOPP 2011 estimated 0.024 mt/yr. | started in 2009, habitat improvements ongoing | Habitat enhancements ongoing; This a future component of Kissimmee River Headwaters Revitalization Project |  | Not included in current projects. Need more detail. Hydrologic Restoration. Estimated load reduction based on acre ft. of storage and 100% BMP implementation
| Otter Slough | This restoration project situated on 550 acres, located south/southwest of Lake Kissimmee, includes five ditch plugs and removal of two berms. It helps attenuate regional stormwater runoff, as well as providing incidental nutrient reductions due to plant uptake from overland flows. In 2011 LOPP, it was estimated to create 71 acre-ft of storage | Upper Kissimmee Sub-Watershed | Initial hydrological restoration complete, additional habitat enhancements ongoing | DEP has 8 kg/yr which is the value estimated in the LOPP2011 (0.008 mt/year). | started in 2009, habitat improvements ongoing | Habitat enhancements ongoing; This a future component of Kissimmee River Headwaters Revitalization Project | Unknown | Not included in current projects. Need more detail. Hydrologic Restoration. Estimated load reduction based on acre ft of storage and 100% BMP implementation
| Rough Island | This restoration project situated on 1,000 acres, is located southwest of Cypress Lake and west of the C-36 Canal. The project includes 31 ditch plugs and exotic removal. It helps attenuate regional stormwater runoff and provides incidental nutrient reductions due to plant uptake from overland flows. In 2011 LOPP, it was estimated to create 215 acre-ft of storage | Upper Kissimmee Sub-Watershed | Initial hydrological restoration complete, additional habitat enhancements ongoing | LOPP 2011 estimated 0.28 mt/yr | started in 2009, habitat improvements ongoing | Habitat enhancements ongoing; This a future component of Kissimmee River Headwaters Revitalization Project | Unknown | Not included in current projects. Need more detail. Hydrologic Restoration. Estimated load reduction based on acre ft of storage and 100% BMP implementation
| Oasis Marsh Restoration | The Oasis wetlands are located in floodplain of the southwest corner of Lake Kissimmee and the site is a mosaic of dewatered wetlands and uplands. The site was purchased by the SFWMD in 1998 as part of the Kissimmee Chain of Lakes Project to raise lake stages. To restore the floodplain function, four ditches totaling 2.4 acres in size were filled with 3,144 cubic yards of sediment material from a levee adjacent to the site in spring 2010. The restoration of the topography of Oasis Marsh will restore approximately 77 acres of wetlands and reconnect them to the littoral zone of Lake Kissimmee. | Upper Kissimmee Sub-Watershed | Initial hydrological restoration complete, additional habitat enhancements ongoing | Unknown | started in 2009, hydrological improvements complete 2010, habitat improvements ongoing | Habitat enhancements ongoing; This a future component of Kissimmee River Headwaters Revitalization Project | Unknown | Not included in current projects. Need more detail. Hydrologic Restoration. Estimated load reduction based on acre ft of storage and 100% BMP implementation
POTENTIAL PROJECTS | Shingle Creek | Hydrologic Restoration- Identified in 2014 SEFR as completed | [6 empty] | added from SEFR Appendix 8-3
| Three Lakes Wildlife Mgmt. Area | Hydrologic Restoration- Identified in 2014 SEFR as under construction | [6 empty] | added from SEFR Appendix 8-3
| In-Lake Strategies | Muck scraping and tilling- not identified for future, but had some success in 2007 and 2008 | [6 empty] | added from SEFR Appendix 8-3
| Lakeside Ranch Phase II | Designed but waiting to see about performance of Phase 1 of this STA |  |  | 10 metric tons per year. |  |  |  | added from SEFR Appendix 8-3
| Brady Ranch STA | CERP Project. Potential issue with consistent flows and need for diversions which may be inconsistent with water supply needs. |  |  | 5 metric tons per year. |  |  |  | added from SEFR Appendix 8-3
| Istokpoga Reservoir and Istokpoga STA | Would provide 29mt/yr of TP load reduction. Indefinitely on hold pending cost share issues. |  |  | 29 metric tons per year. |  |  |  | added from SEFR Appendix 8-3
| HWTTs | Not identified for future, but have had success in previous projects. FDACS is the lead agency. | [6 empty] | added from SEFR Appendix 8-3
| Treasure Island septic removal | DEP analysis showed this may not be cost effective based on typical TP reductions in septic systems, however, literature shows that improperly installed or functioning systems can contribute to TP loads. These are on canals, many 50+ yrs. old, or are thought to have direct discharge. | [6 empty] | added from SEFR Appendix 8-3
| Inactive Dairies- Lagoon Remediation | Develop program to remediate wastewater lagoons on inactive dairies. Within the northern 6 sub-watersheds, 516 inactive dairies are identified in the WAM model. This is identified as a potentially significant legacy load by both SFWMD and FDACS staff. | All 6 sub watersheds | none |  |  |  |  | Conversations held with Bonnie Wolf Pelaez and Lesley Bertolotti (3-14).

## DWM Projects
Operational Dispersed Water Management Projects in Lake Okeechobee Watershed
DWM Category | Project Name | Storage / Retention (ac-ft/yr) | Construction Costs | Annual O&M and Service Payments | County | Status | Retention in: Pasture Only or Above Ground Impoundment (AGI)
FRESP
FRESP | West Waterhole Marsh * (TP Reduction Project) | 5000 | 50000 | 493750 | Glades | Operational | AGI * | Note: For load reduction see measured information previously sent to Kim and Katie
FRESP | Rafter T Ranch | 1145 | 431524 | 92490 | Highlands | Operational | AGI & Pasture | Note: For load reduction see measured information previously sent to Kim and Katie
NE-PES 1
NE-PES 1 | Buck Island Ranch | 1573 | 1928 | 173600 | Highlands | Operational | Pasture Only
NE-PES 1 | Dixie West | 315 | 7228 | 51500 | Okeechobee | Operational | Pasture Only
NE-PES 1 | Dixie Ranch | 856 | 17015 | 146500 | Okeechobee | Operational | Pasture Only
NE-PES 1 | Lost Oak Ranch | 374 | 61030 | 55000 | Polk | Operational | Pasture Only
NE-PES 1 | Willaway Cattle & Sod | 229 | 325494 | 1879 | Okeechobee | Operational | AGI
NE-PES 1 | XL Ranch (Lightsey) | 887 | 52415 | 130150 | Highlands | Operational | AGI & Pasture
| Total | 10379
* For a summary of nutrient removal from this project, see the document "Nutrient Removal at Lykes Bros. Inc. West Waterhole Marsh Water Management Alternative 2008 - 2012." As of 3/14/14, the report for the 2013 nutrient removal data had not been produced.
Pending Dispersed Water Management Projects in Lake Okeechobee Watershed
DWM Category | Project Name | Storage / Retention (ac-ft/yr) | Construction Costs | Annual O&M and Service Payments | County | Status | Retention in: Pasture Only or Above Ground Impoundment (AGI)
NE-PES 1 | Triple A Ranch | 397 | 322186 | 28500 | Okeechobee | Construction | AGI
NE-PES 2 | Blue Head Ranch | 3462 | 193750 | 361200 | Highlands | Design/Permitting | Pasture Only
Private Lands | Nicodemus Slough | 34000 | 4900000 | 2968328 | Glades | Construction | AGI & Pasture
| Total | 37859