LSJR Main Stem BMAP Implementation Schedule

for the 2010 Annual Report

Project Milestones for November 1, 2009 through December 31, 2010

| Date | Entity | Project Number | Description |
| --- | --- | --- | --- |
| 11/01/09 | Orange Park | OP-2 | Final plans and specifications complete for Phase Two improvements at WWTF |
| 12/31/09 | Seminole Electric | SE-1 | SCR upgrade complete |
| 01/01/10 | St. Johns County | SJC-5, SJC-13, SJC-23 | Start development of slow release fertilizer ordinance |
| 01/30/10 | Orange Park | OP-1 | Complete construction of Phase One improvements at WWTF |
| 2/28/10 | Orange Park | OP-1 | Begin operation of Phase One improvements at WWTF |
| 04/01/10 | Atlantic Beach | AB-2 | Begin construction on reuse water line to Selva Marine Golf Course (pending agreement with county club) |
| 04/15/10 | Orange Park | OP-1 | Operational level attained for Phase One improvements at WWTF |
| 05/30/10 | Palatka | PAL-5 | Complete construction on zero discharge at WWTF |
| 08/31/10 | Putnam County | PUT-2 | Complete construction and trade with Hiawatha WWTF |
| 09/01/10 | Neptune Beach | NB-1 | Complete final plans and specifications for the WWTF upgrade |
| 09/30/10 | Green Cove Springs | GCS-1, GCS-2 | Preliminary plans complete for WWTFs upgrades |
| 10/01/10 | Atlantic Beach | AB-3 | Complete plans and specifications for WWTF upgrade to AWT |
| 10/01/10 | CCUA | CCUA-2 | Complete construction on reuse water upgrades |
| 10/01/10 | Putnam County | PUT-4 | Take over O&M at Edgefield RST |
| 10/01/10 | St. Johns County | SJC-6 | Take over O&M at Deep Creek RST |
| 10/31/10 | Putnam County | PUT-6 | Complete project assessment for Algal Initiative |
| 10/31/10 | St. Johns County | SJC-17, SJC-26 | Complete project assessment for Algal Initiative |
| 11/01/10 | Orange Park | OP-3 | Preliminary plans complete for Phase Three improvements at WWTF |
| 11/30/10 | Atlantic Beach | AB-2 | Complete construction on reuse water line to Selva Marine Golf Course (pending agreement with county club) |
| 12/01/10 | CCUA | CCUA-2 | Achieve operational level on reuse water upgrades |
| 12/15/10 | Atlantic Beach | AB-2 | Begin operation on reuse water line to Selva Marine Golf Course (pending agreement with county club) |
| 12/31/10 | Camp Blanding | CB-1 | Complete regrade/maintenance of next set of swales |
| 12/31/10 | FDOT | COJ-94 | Complete construction of Beach Blvd improvements from west of FCCJ to east of San Pablo |
| 12/31/10 | Jacksonville Beach | JB-2 | Complete FDOT Beach Blvd widening (Pond 2) |
| 12/31/10 | JEA | JEA-10 | Complete phase out of Beacon Hills |
| 12/31/10 | JEA | JEA-13 | Complete construction of Arlington East |
| 12/31/10 | Palatka | PAL-5 | Operational level attained for zero discharge at WWTF |
| 12/31/10 | St. Johns County | SJC-7 | Purchase TP credits from Hastings WWTF |

Ongoing Project Efforts

| Entity | Project Number | Description |
| --- | --- | --- |
| City of Jacksonville | COJ-51 | Education |
| Clay County | CC-1, CC-3, CC-12, CC-17 | Education |
| FDOT | COJ-117, COJ-118 | Education |
| St. Johns County | SJC-3, SJC-11, SJC-21 | Education |
| St. Johns County | SJC-4, SJC-12, SJC-22 | LID |
| St. Johns County | SJC-2, SJC-10, SJC-20 | Street sweeping |