## Project Credits
Project Number | Project Name | Project Description | Start Date | Completion Date | Cost | Cost Annual O&M | Acres Treated | Project Type | Status | TN Base Load (lbs/yr) | TN Efficiency (%) | TN Credit (lbs/yr) | TP Base Load (lbs/yr) | TP Efficiency (%) | TP Credit (lbs/yr)
M-02 | Lake Gem/Park Lake COOP BMP | Construct 2nd generation baffle box | 2010 |  | 30000 | 3000 | 3.4 | 2nd Generation Baffle Box | Delayed indefinitely |  | 19.05% |  |  | 15.5% |  | keep since delayed indefinitely? | If keep, need GIS file
M-03 | Lake Gem/Park Lake COOP BMP | Construct 2nd generation baffle box | 2010 |  | 30000 | 3000 | 20 | 2nd Generation Baffle Box | Delayed indefinitely |  | 19.05% |  |  | 15.5% |  | keep since delayed indefinitely? | If keep, need GIS file
M-04 | Lake Gem/Park Lake COOP BMP | Construct 2nd generation baffle box | 2010 |  | 60000 | 6000 | 3.1 | 2nd Generation Baffle Box | Delayed indefinitely |  | 19.05% |  |  | 15.5% |  | keep since delayed indefinitely? | If keep, need GIS file
M-05 | Lake Gem/Park Lake COOP BMP | Construct 2nd generation baffle box | 2010 |  | 60000 | 6000 | 178.9 | 2nd Generation Baffle Box | Delayed indefinitely |  | 19.05% |  |  | 15.5% |  | keep since delayed indefinitely? | If keep, need GIS file
M-06 | Lake Gem/Park Lake COOP BMP | Construct 2nd generation baffle box | 2010 |  | 60000 | 6000 | 58.1 | 2nd Generation Baffle Box | Delayed indefinitely |  | 19.05% |  |  | 15.5% |  | keep since delayed indefinitely? | If keep, need GIS file
M-14 | Horatio Avenue Infiltration Trench | Construct infiltration trenches | 2014 |  | 150000 | 5000 | 5 | Infiltration trenches | Planned | [6 empty] | Need GIS file and permit
M-16 | Street Sweeping | Street sweeping once every two weeks of 71 miles | N/A | N/A | N/A | 100000 | 2898 | Street Sweeping | Completed | [6 empty] | Need weight or volume of material
M-17 | Education Efforts | Landscaping ordinance, PSAs, presentations/ pamphlets, website, illicit discharge program | N/A | N/A | 0 | 0 | 0 | Education | Ongoing | 3200.3 | 1.5% | 48 | 247.1 | 1.5% | 3.7
M-20 | Park Lake Baffle Boxes | Construction 2nd generation baffle box | 2012 |  | 0 | 0 | 58 | 2nd Generation Baffle Box | Planned |  | 19.05% |  |  | 15.5% |  | Need GIS file
M-21 | Minnehaha Circle Baffle Box | Construction 2nd generation baffle box | 2012 |  | 0 | 0 | 7.7 | 2nd Generation Baffle Box | Completed |  | 19.05% |  |  | 15.5% |  | Need GIS file
[10 empty] | Total |  | 48 |  |  | 3.7
[10 empty] | Total Required Reductions |  | 646 |  |  | 137
[10 empty] | Remaining Reductions |  | 598 |  |  | 133.3