## Altamonte Springs
Project Number | Project Name | Lead Entity | Project Detail | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Status
A-1 | TMDL BMPs | Altamonte Springs | BMPs included in the TMDL |  |  | 32.9 | varies | Completed
A-2 | Street Sweeping | Altamonte Springs | Street sweeping two times per month |  |  | 0.5 | 4 | Ongoing
A-3 | Education Efforts | Altamonte Springs | FYN, PSAs, pamphlets, presentations, website, illicit discharge program |  |  | 4.6 | 4 | Ongoing
38

## Casselberry
Project Number | WBID | Subbasin | Project Location |  | Project Name | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Status | Comments
C-1 | 2994K | Gee Creek | 28.6708 | -81.3364 | Lake Concord Stormwater Park/Anniversary Park - Plumosa Baffle Box | Casselberry | Plumosa Baffle Box - Portion of Redevelopment and Retrofit of City-owned property into an educational stormwater Park including installation of 2 2nd generation baffle boxes and an exfiltration trench, and other BMPs | 10/2007 | 09/2009 | 43250 | Stormwater Utility (construction), Community Redevelopment Agency (design) | 0.5 | 25 | Reduce phosphorus, nitrogen, TSS (593.7 kg/yr), and gross pollutant inputs to Lake Concord | 4 | 10.83 | 1=Stormwater Retrofit (CDS or baffle box) | 2=Started | Re-vegetation includes swale and reverse berm construction to capture untreated runoff before it discharges directly to the lake
C-2 | 2994K | Gee Creek | 28.6708 | -81.3364 | Lake Concord Stormwater Park/Anniversary Park - Exfiltration Trench | Casselberry | Exfiltration System - Portion of Redevelopment and Retrofit of City-owned property into an educational stormwater Park including installation of 2 2nd generation baffle boxes and an exfiltration trench, and other BMPs (1) | 10/2007 | 09/2009 | 143200 | Stormwater Utility (construction), Community Redevelopment Agency (design) | 0 | 5 | Reduce phosphorus, nitrogen, TSS (593.7 kg/yr), and gross pollutant inputs to Lake Concord | 4 | 10.83 | 13=Other structural BMP | 2=Started | Re-vegetation includes swale and reverse berm construction to capture untreated runoff before it discharges directly to the lake
C-3 | 2994K | Gee Creek | 28.6708 | -81.3364 | Lake Concord Stormwater Park/Anniversary Park - Dry Detention | Casselberry | Dry Detention - Portion of Redevelopment and Retrofit of City-owned property into an educational stormwater Park including installation of 2 2nd generation baffle boxes and an exfiltration trench, and other BMPs (1) | 10/2007 | 09/2009 | 75000 | Stormwater Utility (construction), Community Redevelopment Agency (design) | 0 | 20 | Reduce phosphorus, nitrogen, TSS (593.7 kg/yr), and gross pollutant inputs to Lake Concord | 4 | 10.83 | 2=Dry detention pond | 2=Started | Re-vegetation includes swale and reverse berm construction to capture untreated runoff before it discharges directly to the lake
C-4 | 2994K | Gee Creek | 28.6708 | -81.3364 | Lake Concord Stormwater Park/Anniversary Park - Swale, Wetland Revegetation, & Boardwalk | Casselberry | Swale and Lakeshore Revegetation with Educational Boardwalk - Portion of Redevelopment and Retrofit of City-owned property into an educational stormwater Park including installation of 2 2nd generation baffle boxes and an exfiltration trench, and other BMPs (1) | 10/2007 | 09/2009 | 742000 | Stormwater Utility (construction), Community Redevelopment Agency (design/construction), FRDAP Grants, other City funds | 0 | 5 | Reduce phosphorus, nitrogen, TSS (593.7 kg/yr), and gross pollutant inputs to Lake Concord | 4 | 10.83 | 4=Swales | 2=Started | Re-vegetation includes swale and reverse berm construction to capture untreated runoff before it discharges directly to the lake
C-5 | 2994K | Gee Creek | 28.6708 | -81.3364 | Lake Concord Stormwater Park/Anniversary Park | Casselberry | Baffle Box, Pervious Pavement, and Bioretention/Parking Lot - Portion of Redevelopment and Retrofit of City-owned property into an educational stormwater Park including installation of 2 2nd generation baffle boxes and an exfiltration trench, and other BMPs (1) | 10/2007 | 09/2009 | 226500 | Stormwater Utility (construction), Community Redevelopment Agency (design/construction), FRDAP Grants, other City funds | 0.1 | 84 | Reduce phosphorus, nitrogen, TSS (593.7 kg/yr), and gross pollutant inputs to Lake Concord | 4 | 10.83 | 13=Other structural BMP | 2=Started | Re-vegetation includes swale and reverse berm construction to capture untreated runoff before it discharges directly to the lake
C-6 | N/A (Grassy Lake) | Gee Creek | 28.6643 | -81.3456 | Anchor Road Reconstruction | Casselberry | Reconstruction of Anchor Road with drainage improvements including upgraded detention/retention ponds | 2007-10-01 | 2009-10-01 | 2000000 | City of Casselberry, Seminole County, and Community Development Block Grant | 3.1 | 60 | Provides stormwater treatment prior to discharge to lake | 13 | 60.7 | 3=Wet detention pond | 2=Started | Structural & Nonstructural BMPS: pervious pavements, bioretention/ rain garden, exfiltration, 2 baffle boxes, dry detention, environmental swales, stormwater reuse; shoreline re-vegetation; educational signage and displays
C-7 | 2994B1 | Gee Creek | 28.6733 | -81.3259 | North Lake Triplet Shoreline Revegetation | Casselberry | Remove existing nuisance vegetation from the north and west shores of North Lake Triplet and replace with beneficial species; install reverse berm and swale (2) | 2007-12-01 | 2014-09-01 | 80000 | Stormwater Utility Fund | 0.1 | 5 | Provides stormwater treatment prior to discharge to lake | 2.6 | N/A | 4=Swales | 3=Planned & Funded | Re-vegetation includes swale and reverse berm construction to capture untreated runoff before it discharges directly to the lake
C-8 | 2994I | Gee Creek | 28.6729 | -81.3287 | Secret Lake Shoreline Revegetation | Casselberry | Remove existing nuisance vegetation from the east and southwest shores of Secret Lake and replace with beneficial species; install 2 reverse berms and swales | 2008-01-01 | 2008-05-01 | N/A | Stormwater Utility Fund | 0 | 5 | Provides stormwater treatment prior to discharge to lake | 0.6 | N/A | 4=Swales | 1=Completed | Re-vegetation includes swale and reverse berm construction to capture untreated runoff before it discharges directly to the lake
C-9 | N/A (Grassy Lake) | Gee Creek | 28.663 | -81.3435 | Fountain/Aeration and Revegetation for Grassy Lake | Casselberry | Installation of an aeration system to satisfy the high BOD loading to this waterbody but constructed as a decorative fountain. The project would also include shoreline revegetation for both aesthetics and nutrient removal with environmental swale construction as practicable. (17) | 2009-03-01 | 2009-07-01 | $150,000 | Stormwater Utility Fund | 0 | 5 | Installation of an aeration system to satisfy the high BOD loading to this waterbody but constructed as a decorative fountain because of its location as an entry point to the City. The project would also include shoreline revegetation for both aesthetics and nutrient removal; swales and reverse berms would be installed as feasible. | N/A | N/A | 13=Other structural BMP | 3=Planned & Funded
C-10 | 2997B | Howell Creek | 28.643 | -81.3165 | 672 & 676 San Pablo Avenue 2nd generation Baffle Boxes | Casselberry | Replace existing storm manholes with two 2nd generation Baffle Boxes for removal of pollutants (sediment and detritus) (4b) | 2009-03-01 | 2010-04-01 | 300000 | Stormwater Utility Fund; possible SJRWMD and EPA 319 funds | 1.3 | 25 | Remove sediment and detritus to pre-treat stormwater inputs to Lake Howell | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-11 | 2997B | Howell Creek | 28.6439 | -81.3195 | Madrid Drive at Desoto Drive 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with 2nd generation Baffle Boxes for removal of pollutants (sediment and detritus) (4d) | 2009-03-01 | 2010-04-01 | $150,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 0.4 | 25 | Remove sediment and detritus to pre-treat stormwater inputs to Lake Howell | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-12 | 2997B | Howell Creek | 28.6439 | -81.3182 | Sonora Drive at Desoto Drive 2nd generation Baffle box | Casselberry | Replace existing storm manholes with 2nd generation Baffle Boxes for removal of pollutants (sediment and detritus) (4a) | 2009-03-01 | 2010-04-01 | $170,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 2.4 | 25 | Remove sediment and detritus to pre-treat stormwater inputs to Lake Howell | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-13 | N/A (Grassy Lake) | Gee Creek | 28.6634 | -81.3426 | Live Oaks Center 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4m) | 2010-03-01 | 2011-04-01 | $100,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 1.9 | 25 | Remove sediment and detritus stormwater inputs to Middle Lake Triplet | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-14 | 2994B1 | Gee Creek | 28.6645 | -81.3293 | 360 South Lake Triplet Drive 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4e) | 2011-03-01 | 2012-04-01 | $140,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 1.7 | 25 | Remove sediment and detritus stormwater inputs to South Lake Triplet | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-15 | N/A (Lake Hodge) | Gee Creek | 28.6918 | -81.3202 | Lake Hodge Park 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4j) | 2011-03-01 | 2012-04-01 | $170,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 3.3 | 25 | Remove sediment and detritus stormwater inputs to Gee Creek | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-16 | 2994B1 | Gee Creek | 28.6679 | -81.3311 | 161 South Lake Triplet Drive 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4k) | 2011-03-01 | 2012-04-01 | $170,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 5.5 | 25 | Remove sediment and detritus stormwater inputs to Lake Hodge | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-17 | 2994B1 | Gee Creek | 28.6622 | -81.3268 | 530 South Lake Triplet Drive 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4f) | 2011-03-01 | 2012-04-01 | $140,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 1.3 | 25 | Remove sediment and detritus stormwater inputs to South Lake Triplet | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-18 | N/A (Queen's Mirror) | Gee Creek | 28.6575 | -81.3264 | Carriage Hill Unit 4 2nd generation Baffle Boxes at the three outfalls north of Violet Dell, Tulip Trail and Lowndes Square Queens Mirror. | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4n) | 2012-03-01 | 2013-04-01 | $400,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 3.3 | 25 | Remove sediment and detritus stormwater inputs to Queen's Mirror Lake | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-19 | 2994A | Gee Creek | 28.6858 | -81.3194 | 808 Osceola Trail 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4.i) | 2013-03-01 | 2014-04-01 | $140,000 | Stormwater Utility Fund; possible SJRWMD, TMDL, and EPA 319 funds | 1.2 | 25 | Remove sediment and detritus stormwater inputs to Secret Lake | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-20 | N/A | Gee Creek | 28.668 | -81.3138 | Park Drive Drainage/Wetland Improvements | Casselberry | Construction of stormwater retention area on Lots 10A & 11 on north side of Park Drive. (7) | 2013-03-01 | 2014-04-01 | $36,000 | Stormwater Utility Fund | 4.6 | 60 | Retention to provide treatment for surrounding area | N/A | N/A | Wet retention pond | 3=Planned & Funded
C-21 | N/A | Gee Creek | 28.6608 | -81.3296 | Alum Injection System for Carriage Hill Detention Pond | Casselberry | Construction of a feed system for the addition of aluminum sulfate salt (alum) to the influent to the new wet detention pond for removal of pollutants, especially phosphorus, from stormwater system influent to Queens Mirror and the Triplet Lake chain. (18) | 2013-03-01 | 2014-04-01 | $120,000 | Stormwater Utility Fund | 16.5 | 90 | Construction of a feed system for the addition of aluminum sulfate salt (alum) to the influent to the new wet detention pond for removal of pollutants, especially phosphorus, from stormwater system influent to Queens Mirror and the Triplet Lake chain. | N/A | N/A | 13=Other structural BMP | 3=Planned & Funded
C-22 | 2994B1 | Gee Creek | 28.6726 | -81.3264 | Middle Lake Triplet Shoreline Revegetation | Casselberry | Remove existing nuisance vegetation from the north shore of Middle Lake Triplet and replace with beneficial species; install reverse berm and swale (3) | 2013-12-01 | 2014-06-01 | $33,000 | Stormwater Utility Fund | 0.1 | 5 | Provides stormwater treatment prior to discharge to lake | 2 | N/A | 4=Swales | 3=Planned & Funded
C-23 | 2994I | Gee Creek | 28.6745 | -81.3302 | Secret Way at canal 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4h) | 2014-03-01 | 2014-12-01 | $170,000 | Stormwater Utility Fund; possible SJRWMD and EPA 319 funds | 0.7 | 25 | Remove sediment and detritus stormwater inputs to Secret Lake | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-24 | 2994B1 | Gee Creek | 28.671 | -81.3306 | 51 North Lake Triplet Drive 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4.l) | 2014-03-01 | 2014-12-01 | $140,000 | Stormwater Utility Fund; possible SJRWMD and EPA 319 funds | 1.3 | 25 | Remove sediment and detritus stormwater inputs to Middle Lake Triplet | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
C-25 | 2994B1 | Gee Creek | 28.6665 | 81.3272 | South Lake Triplet Swales | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4.l) | 2014-03-01 | 2014-12-01 | 80000 | Stormwater Utility Fund; possible SJRWMD and EPA 319 funds | 0.2 | 5 | Provide pre-treatment of golf course runoff prior to entering S Lake Triplet | 0.003 | N/A | 4=Swales | 4=Envisioned, but Not Funded
C-26 | 2994B1 | Gee Creek | 28.6656 | 81.3294 | South Lake Triplet 2nd generation Baffle Box | Casselberry | Replace existing storm manholes with Baffle Boxes for removal of pollutants (sediment and detritus) (4.l) | 2014-03-01 | 2014-12-01 | $140,000 | Stormwater Utility Fund; possible SJRWMD and EPA 319 funds | 0.8 | 25 | Remove sediment and detritus stormwater inputs to South Lake Triplet | 0.003 | N/A | 1=Stormwater Retrofit (CDS or baffle box) | 4=Envisioned, but Not Funded
C-27 | N/A | Entire city |  |  | Street Sweeping | Casselberry | Weekly street sweeping |  | Ongoing |  |  | 10.2 | 5 | Remove sediment and detritus stormwater inputs to basin |  |  |  | Ongoing
C-28 | N/A | Entire city |  |  | Education Efforts | Casselberry | FYN, landscape and irrigation ordinances, PSAS, pamphlets/presentations, website, illicit discharge program |  | Ongoing |  |  | 85.6 | 5.5 | Educate public about nutrient management |  |  |  | Ongoing
C-29 |  |  |  |  | Existing BMPs | Casselberry | BMPs that were in place at the time of the TMDL |  |  |  |  | 283.3 | varies |  |  |  |  | Completed
429.4

## Eatonville
Project Number | Project Name | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Project Footprint (Acres) | Treatment Acres | Project Type | Status
E-1 | Street Sweeping | Eatonville | Monthly street sweeping |  | Ongoing |  |  | 0.3 | 3 |  |  |  | Ongoing
E-2 | Existing BMPs |  | Eatonville | BMPs that were in place at the time of the TMDL |  |  |  | 9.6 | varies |  |  |  | Completed
9.9

## FDOT
Project Number | Project Name | ERP Permit Number | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Status
FDOT -1 | FM: 240167-1 SR434 |  | FDOT | DOT FM: 240167-1 SR434 | 2006 | 2007 |  |  | 4 | 20 |  |  |  |  | Completed
FDOT -2 | FM: 240196-1 SR17-92 Basin A&B |  | FDOT | DOT FM: 240196-1 SR17-92 Basin A&B |  |  |  |  | 24.6 | 64.5 |  |  |  |  | Design
FDOT -3 | FM: 240196-1 SR17-92 Basin C&D | 42-117-98715-1 42-117-99042-1 42-117-99042-2 | FDOT | DOT FM: 240196-1 SR17-92 Basin C&D |  |  |  |  | 4.2 | 84 |  |  |  |  | Design
FDOT -4 | FM: 240163-1 SR 46 |  | FDOT | SR 46 over Lake Jesup |  |  |  |  | 5.4 | [5 empty] | Construction
FDOT -5 | Street Sweeping |  | FDOT | Monthly street sweeping |  | Ongoing |  |  | 90.3 | 3 |  |  |  |  | Ongoing
FDOT -6 | Education Efforts |  | FDOT | Pamphlets/presentations, website, illicit discharge program |  | Ongoing |  |  | 6.5 | 1 |  |  |  |  | Ongoing
FDOT -7 | Existing BMPs |  | FDOT | BMPs that were in place at the time of the TMDL |  |  |  |  | 182 | varies |  |  |  |  | Completed
317

## Lake Mary
Project Number | WBID | Subbasin | Project Location |  | Project Name | ERP Permit Number | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Annual Project-Specific O&M Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Status
LM-1 | 2986 | Soldier's Creek | 28.7362 | -81.3093 | Lake Mary Woods |  | City of Lake Mary | Eliminating 106 septic tanks, 18 within 75 feet of surface water, some of them were failing. | 5/2005 | 4/2006 | $3,700,000 | $2056 | Lake Mary Water and Sewer Fund | 44.5 | N/A | Low Impact development in downtown development district and through out the city will reduce load on the Soldier's Creek as well as Crystal lake basins. | 6260 |  | 13=Ordinance/Rule change | Completed
LM-2 |  |  |  |  | Street Sweeping |  | City of Lake Mary | Quarterly street sweeping |  | Ongoing |  |  |  | 2.7 | 2 |  |  |  |  | Ongoing
LM-3 |  |  |  |  | Education Efforts |  | City of Lake Mary | FYN, ordinances, PSAs, pamphlets, presentations, website, illicit discharge program |  | Ongoing |  |  |  | 67.6 | 5.5 |  |  |  |  | Ongoing
LM-4 |  |  |  |  | Existing BMPs |  | City of Lake Mary | BMPs that were in place at the time of the TMDL | [5 empty] | 95.1 | [5 empty] | Completed
LM-5 |  |  |  |  | Regional Project |  | City of Lake Mary | Participate in a regional project | 2009 | 2014 |  |  |  | 16.7 |  |  |  |  | Regional project | Planned
226.6

## Longwood
Project Number | Project Name | ERP Permit Number | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (metric tons/yr) | % BMP Reduction | Project Type | Status
L-1 | South Grant Street Drainage Project | 42-117-1260ANM-ERP | City of Longwood | Drainage improvements on South Grant Street | 2008 | 2009 | 300000 | Stormwater Utility Fee | 0.1 | 5 | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
L-2 | North Grant Street Drainage Project |  | City of Longwood | Drainage improvements on North Grant Street | 2009 | 2010 | 300000 | Stormwater Utility Fee | 0.2 | 5 | 1=Stormwater Retrofit (CDS or baffle box) | 3=Planned & Funded
L-3 | Sewering projects to remove septic tanks |  | City of Longwood | Sewering projects to remove tanks within 75 ft of surface waters (remove 20 septic tanks) | 2009 | 2013 |  | Public Utilities Fund Revenues | 22.7 | N/A | 9=Wastewater plant improvements | 3=Planned & Funded
L-4 | Street Sweeping |  | City of Longwood | Quarterly street sweeping |  | Ongoing |  |  | 0.6 | 2 |  | Ongoing
L-5 | Education Efforts |  | City of Longwood | FYN, pamphlets, presentations, website, illicit discharge program |  | Ongoing |  |  | 44.9 | 4 |  | Ongoing
L-6 | Existing BMPs |  | City of Longwood | BMPs that were in place at the time of the TMDL |  |  |  |  | 67.1 | varies |  | Completed
135.6

## Maitland
Project Number | WBID | Subbasin | Project Location |  | Project Name | ERP Permit Number | Lead Entity | Project Partner(s) | Project Detail | Project Start Date | Project End Date | Project Cost | Project-Specific Annual O&M Costs | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Status | Comments
M-1 | 2997 | Downtown Pond/MI22 | 28ø37'49.46873"N | -81ø21'43.38208"W | Sybelia Parkway Regional Pond | 4-095-91505-3 | Maitland | None | Construct wet pond | 2005 | 2007 | 4400000 | 3000 | Ad valorum funding/user fees | 36.8 | 55 | Remove phosphorus from Howell Creek basin stormwater | 16.3 | 125.2 | 3=Wet detention pond | 1=Completed | Master Stormwater Pond for Downtown Area, pond is 3.5 acres, site is 16.3 acres,
M-2 | 2997 | GE2 | 28ø36'44.93940"N | -81ø22'06.67071"W | Lake Gem/Park Lake COOP BMP | 42-095-51727-1 | Maitland | DOT/ Winter Park | Construct second generation baffle box | 2010 | 2011 | 30000 | 3000 | Stormwater Utility | 0.27 | 25 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 3.3792 | 1=Stormwater Retrofit (CDS or baffle box) | 4=Envisioned, but Not Funded
M-3 | 2997 | GE3 | 28ø36'44.82838"N | -81ø21'54.38704"W | Lake Gem/Park Lake COOP BMP | 42-095-51727-1 | Maitland | DOT/ Winter Park | Construct second generation baffle box | 2010 | 2011 | 30000 | 3000 | Stormwater Utility | 3 | 225 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 19.9715 | 1=Stormwater Retrofit (CDS or baffle box) | 4=Envisioned, but Not Funded
M-4 | 2997 | GE4 | 28ø36'42.48685"N | -81ø22'07.74522"W | Lake Gem/Park Lake COOP BMP | 42-095-51727-1 | Maitland | None | Construct second generation baffle box | 2010 | 2011 | 60000 | 6000 | Stormwater Utility | 0.2 | 25 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 3.112 | 1=Stormwater Retrofit (CDS or baffle box) | 4=Envisioned, but Not Funded
M-5 | 2997 | GE91 | 28ø36'27.68085"N | -81ø22'01.16467"W | Lake Gem/Park Lake COOP BMP | 42-095-51727-1 | Maitland | None | Construct second generation baffle box | 2010 | 2011 | 60000 | 6000 | Stormwater Utility | 18.9 | 25 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 178.9056 | 1=Stormwater Retrofit (CDS or baffle box) | 4=Envisioned, but Not Funded
M-6 | 2997 | GE92 | 28ø36'30.70189"N | -81ø21'53.01516"W | Lake Gem/Park Lake COOP BMP | 42-095-51727-1 | Maitland | None | Construct second generation baffle box | 2010 | 2011 | 60000 | 6000 | Stormwater Utility | 9.1 | 25 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 58.0854 | 1=Stormwater Retrofit (CDS or baffle box) | 4=Envisioned, but Not Funded
M-7 | 2997 | MA10 | 28ø36'57.35495"N | -81ø21'48.05496"W | Lake Maitland Basin - Ridgewood Area Quality Neighborhood Program City Street Improvement Plan | 42-095-115834-3 | Maitland | None | Construct infiltration trenches | 2009 | 2010 | 60000 | 2500 | Stormwater Utility | 0.51 | 40 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 3.8746 | 13=Other structural BMP | 3=Planned & Funded | Infiltration trench use off-line retention pollutant removal numbers
M-8 | 2997 | MA12 | 28ø36'53.73735"N | -81ø21'51.09357"W | Lake Maitland Basin - Ridgewood Area Quality Neighborhood Program City Street Improvement Plan | 42-095-115834-3 | Maitland | None | Construct infiltration trenches | 2009 | 2010 | 170000 | 8500 | Stormwater Utility | 1.7 | 40 | Remove phosphorus from Howell Creek basin stormwater | 0.3 | 15.0291 | 13=Other structural BMP | 3=Planned & Funded | Infiltration trench use off-line retention pollutant removal numbers
M-9 | 2997 | MA17 | 28ø36'45.66276"N | -81ø21'44.71284"W | Lake Maitland Basin - Ridgewood Area Quality Neighborhood Program City Street Improvement Plan | 42-095-115834-3 | Maitland | None | Construct infiltration trenches | 2009 | 2010 | 100000 | 5000 | Stormwater Utility | 0.6 | 40 | Remove phosphorus from Howell Creek basin stormwater | 0.2 | 9.1603 | 13=Other structural BMP | 3=Planned & Funded | Infiltration trench use off-line retention pollutant removal numbers
M-10 | 2997 | MA4 | 28ø37'38.63"N | -81ø21'59.13.07"W | North Lake Maitland Leaf Trap Project |  | Maitland | None | Install curb inlet leaf trap | 2009 | 2010 | 3000 | 6000 | Stormwater Utility | 0.1 | 5 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 16.84 |  | 3=Planned & Funded | Leaf Trap
M-11 | 2997 | MA93 | 28ø36'48.82"N | -81ø21'59.09"W | Lake Maitland Basin - Ridgewood Area Quality Neighborhood Program City Street Improvement Plan | 42-095-115834-3 | Maitland | None | Construct infiltration trenches | 2009 | 2010 | 100000 | 8500 | Stormwater Utility | 0.9 | 40 | Remove phosphorus from Howell Creek basin stormwater | 0.3 | 14.8 | 13=Other structural BMP | 3=Planned & Funded | Infiltration trench use off-line retention pollutant removal numbers
M-12 | 2997 | MI10 | 28ø38'04.44728"N | -81ø20'52.43157"W | Dommerich Lot Baffle Box | 40-095-45392-3 | Maitland | None | Construct second generation baffle box | 2010 | 2011 | 60000 | 5000 | Ad valorum funding | 1.1 | 25 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 24.7358 | 1=Stormwater Retrofit (CDS or baffle box) | 4=Envisioned, but Not Funded | CDS Unit
M-13 | 2997 | MI12 | 28ø37'57.20325"N | -81ø20'54.62745"W | Chipewa Trail Baffle Box |  | Maitland | None | Construct second generation baffle box | 2007 | 2007 | 60000 | 5000 | Ad valorum funding | 1.1 | 25 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 25.2905 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed | CDS Unit
M-14 | 2997 | N12a | 28ø37'38.38420"N | -81ø21'38.72562"W | Horatio Avenue Infiltration Trench |  | Maitland | None | Construct infiltration trenches | 2012 | 2014 | 150000 | 5000 | Stormwater Utility | 0.9 | 40 | Remove phosphorus from Howell Creek basin stormwater | 0.1 | 5.04 | 13=Other structural BMP | 4=Envisioned, but Not Funded | Infiltration trench use off-line retention pollutant removal numbers
M-15 | 2997 | N12b | 28ø37'40.11746"N | -81ø21'28.27809"W | Minnehaha Park Stormwater Improvements Dry Stormwater Pond | 112586 | Maitland | None | Construct wet pond | 2007 | 2008 | 65000 | 2000 | Ad valorum funding | 1.38 | 35 | Remove phosphorus from Howell Creek basin stormwater | 0.4 | 9.9 | 2=Dry detention pond | 1=Completed | Dry Pond - retrofit for existing park - previously no treatment permit number 112586
M-16 | 2997 | Entire City of Maitland | 28ø37'38.38420"N | -81ø21'38.72562"W | Street Sweeping |  | Maitland | None | Street Sweeping - once every 2 weeks | 2005 | ongoing | NA | 100000 | Stormwater Utility/Ad valorum funding | 7.4 | 4 | Remove phosphorus from Howell Creek basin stormwater | 0 | 2898 | 14=Other non-structural project | 5=Ongoing | Street Sweeping once every 2 weeks
M-17 | 2997 | Entire City of Maitland | 28ø37'38.38420"N | -81ø21'38.72562"W | Education Efforts |  | Maitland | None | Landscaping ordinance, PSAs, presentations/ pamphlets, website, illicit discharge program |  | ongoing |  |  |  | 40.8 | 4.5 | Remove phosphorus from Howell Creek basin stormwater |  |  | 14=Other non-structural project | 5=Ongoing | Nutrient related education efforts
M-18 |  |  |  |  | Existing BMPs |  | Maitland |  | BMPs that were in place at the time of the TMDL | [5 empty] | 0.9 | [5 empty] | Completed
125.66

## OOCEA
Project Number | Project Name | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | Project Footprint (Acres) | Treatment Acres | Project Type | Status
OOCEA-1 | Existing BMPs | OOCEA | BMPs that were in place at the time of the TMDL |  |  |  |  | 13.9 |  |  |  | Completed

## Orange County
Project Number | Project Name | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Status
OC-1 | Hall Road Improvements | Orange County | OC CIP Hall Road Improvements |  |  |  | 0.1 | 10
OC-2 | OC CIP Lake Wauntta | Orange County | OC CIP Lake Wauntta |  |  |  | 3.5 | 5
OC-3 | Lake Sue Inlet Baskets | Orange County | Lake Sue inlet baskets |  |  |  | 0.7 | [5 empty] | Completed
OC-4 | Street Sweeping | Orange County | Weekly and monthly street sweeping |  |  | Ongoing | 27.4 | 3 and 5 |  |  |  |  | Ongoing
OC-5 | Education Efforts | Orange County | FYN, ordinances, PSAs, pamphlets, presentations, website, illicit discharge program |  |  | Ongoing | 151 | 5.5 |  |  |  |  | Ongoing
OC-6 | TMDL BMPs | Orange County | BMPs that were in place at the time of the TMDL |  |  |  | 45.5 | [5 empty] | Completed
228.2

## Orlando
Project Number | WBID | Subbasin | Project Location |  | Project Name | ERP Permit Numer | Lead Entity | Project Partner(s) | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Method Used to Calculate NPS Load Reduction | Status | Comments
ORL-1 | 2997Q | Howell Creek | -81.3867 | 28.5511 | Lake Dot Water Quality Restoration | 20376 | Orlando | n/a | Installation of Alum Treatment System, where aluminum sulfate (alum) is injected into stormline on a flow-proportioned basis | 1988 | 07/1990 | 569207 | City of Orlando Stormwater Utility Fee | 69.8 | 25, 64, and 84 | Remove nitrogen and phosphorus from Lake Dot basin and Howell Branch chain-of-lakes | 0.1 | 276 | 13=Other structural BMP | Runoff Volume x EMC's x assumed 50% reduc for TN and 90% reduc for TP --- Alum Treatment of Stormwater: The First Ten Years, Environmental Research and Design, 2002; Estimation of Stormwater Loading Rate Parameters for Central and South Florida, Environmental Research & Design, June 25, 2002 | 1=Completed
ORL-2 | 2997L | Howell Creek | -81.3706 | 28.5788 | Hazel Street Outfall Improvements | Exempt | Orlando | n/a | Installation of Continuous Deflective Separation (CDS) Unit at Lake Winyah from 96" pipe | 07/2000 | 07/2003 | 410992 | City of Orlando Stormwater Utility Fee | 8.3 | 5 and 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Winyah basin and Howell Branch chain-of-lakes | 0.1 | 505 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = 4 times/year
ORL-3 | 2997J | Howell Creek | -81.3553 | 28.568 | Lake Rowena Screening Facility & Alum Stormwater Treatment | 45968 | Orlando | n/a | Installation of an underground, flow-actuated rotating bar screen on 108" outfall pipe to capture debris with additional treatment via Alum Treatment System | 1994 | 1996 | 596512 | City of Orlando Stormwater Utility Fee | 55 | 90 and 96 | Remove nitrogen, phosphorus and gross pollutants from Lake Rowena basin and Howell Branch chain-of-lakes | 0.25 | 470 | 1=Stormwater Retrofit (CDS or baffle box); 13=Other structural BMP | Runoff Volume x EMC's x assumed 50% reduc for TN and 90% reduc for TP --- Alum Treatment of Stormwater: The First Ten Years, Environmental Research and Design, 2002; Lake Rowena Water Quality Report, [City of Orlando] Stormwater Utility Bureau, Nov 1992; Estimation of Stormwater Loading Rate Parameters for Central and South Florida, Environmental Research & Design, June 25, 2002 | 1=Completed | Groundwater seepage accounts for 17.8 kg/yr TP and 388.7 kg/yr TN Maintenance Frequency = 3 times/month
ORL-4 | 2997N | Howell Creek | -81.3671 | 28.5585 | Lake Highland CDS Unit | Exempt | Orlando | n/a | Installation of Continuous Deflective Separation (CDS) Unit at Lake Highland | 1998 | 1999 | 60000 | City of Orlando Stormwater Utility Fee | 1 | 5 and 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Highland basin and Howell Branch chain-of-lakes | 0.1 | 45 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = 2 times/month
ORL-5 | 2997J | Howell Creek | -81.3954 | 28.5586 | Mills Avenue Retrofit | 42-095-2147AN-ERP 42-095-94668-1 42-095-63458-1 42-095-89369-2 42-095-89369-1 42-095-94668-2 | Orlando | n/a | Construction of Storm Flo Litter Collection Screen on Mills Ave., adjacent to Lake Rowena to treat runoff from 36" and 24" stormlines | 01/2009 | 04/2009 | $250,000 | City of Orlando Stormwater Utility Fee | 8.4 | 18 and 69 | Remove nitrogen and phosphorus from Lake Rowena basin and Howell Branch chain-of-lakes | 0.1 | 88.6 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 3=Planned & Funded | (Assumed reduction efficiency to be between 1st Generation and 2nd Generation Baffle Boxes [(10% + 25%)/2=18%] ; Maintenance Frequency = 1 time/month
ORL-6 | 2997R | Howell Creek | -81.3645 | 28.5699 | Overbrook Stormwater Improvements | 113623 | Orlando | SJRWMD | Construct 2nd generation baffle box upstream of Lake Adair; Implement pollution prevention methods, including gravel bottom and check dams to settle out pollutants | 10/2007 | 07/2008 | $400,000 | City of Orlando Stormwater Utility Fee + Ad valorem funding | 1.8 | 64 and 84 | Remove nitrogen, phosphorus and sediments from Lake Adair basin and Howell Branch chain-of-lakes | 5.1 | 236 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = 1-2 times/month
ORL-7 | 2997R | Howell Creek | -81.398 | 28.5651 | Guernsey Park - Expansion of Wet Detention Pond |  | Orlando | n/a | Expansion of wet detention pond to treat 61% of sub-basin drainage | n/a | n/a | $425,000 | City of Orlando Stormwater Utility Fee | 0.04 | 50 | Remove nitrogen and phosphorus from Lake Adair basin and Howell Branch chain-of-lakes | 0.9 | 80 | 3=Wet detention pond | Howell Branch Chain of Lakes Diagnostic Study, Boyle Engineering Corp, July 2008: Nitrogen and Phosphorus Loads - US EPA's Simple Method + Pollutant Removal Efficiencies for Typical Stormwater Management Systems in Florida, Harper, 1995; EMC - FDEP Draft TMDL Report Nutrient and Unionized Ammonia TMDLs for Lake Jesup WBIDs 2981 and 2981A, Gao, 2005; Runoff - Evaluation of Current Stormwater Design Criteria within the State of Florida, Harper and Baker, 2007 | 4=Envisioned, but Not Funded | Grant applications submitted to: US EPA Section 319 Nonpoint Source Management Program + SJRWMD Cost-Share Program
ORL-8 | 2997R | Howell Creek | -81.3871 | 28.5646 | Ivanhoe Plaza Park Exfiltration | 42-095-1865AN-ERP 42-095-2233AN-ERP | Orlando | n/a | Installation of exfiltration galleries to treat 100% of sub-basin drainage | n/a | n/a | $1,100,000 | City of Orlando Stormwater Utility Fee | 1.3 | 50 | Remove nitrogen and phosphorus from Lake Adair basin and Howell Branch chain-of-lakes | 2.0 | 49 | 5=100% on-site retention | Howell Branch Chain of Lakes Diagnostic Study, Boyle Engineering, July 2008: Nitrogen and Phosphorus Loads - US EPA's Simple Method + Pollutant Removal Efficiencies for Typical Stormwater Management Systems in Florida, Harper, 1995; EMC - FDEP Draft TMDL Report Nutrient and Unionized Ammonia TMDLs for Lake Jesup WBIDs 2981 and 2981A, Gao, 2005; Runoff - Evaluation of Current Stormwater Design Criteria within the State of Florida, Harper and Baker, 2007 | 4=Envisioned, but Not Funded | Grant applications submitted to: US EPA Section 319 Nonpoint Source Management Program + SJRWMD Cost-Share Program
ORL-9 | 2997P | Howell Creek | -81.3879 | 28.5558 | Don Dudley Park 2nd Generation Baffle Boxes | 42-095-2042AMN-ERP | Orlando | n/a | Construct two 2nd Generation Baffle Boxes upstream of Lake Concord and reroute flow to treat 30" and 24" outfalls from nearly 100% of two sub-basins | n/a | n/a | $250,000 | City of Orlando Stormwater Utility Fee | 0.8 | 64 and 84 | Remove nitrogen, phosphorus and gross pollutants from Lake Concord basin and Howell Branch chain-of-lakes | 0.1 | 66 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 4=Envisioned, but Not Funded | Grant applications submitted to: US EPA Section 319 Nonpoint Source Management Program + SJRWMD Cost-Share Program; Maintenance Frequency = 1-2 times/month
ORL-10 | 2997L | Howell Creek | -81.3673 | 28.5798 | Winyah (Westchester Ave/Wilkinson St) 2nd Generation Baffle Box |  | Orlando | n/a | Construct 2nd Generation Baffle Box upstream of Lake Winyah to treat 71% of sub-basin | n/a | n/a | $72,000 | City of Orlando Stormwater Utility Fee | 1.6 | 25 | Remove nitrogen, phosphorus and gross pollutants from Lake Winyah basin and Howell Branch chain-of-lakes | 0.1 | 30 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 4=Envisioned, but Not Funded | Grant applications submitted to: US EPA Section 319 Nonpoint Source Management Program + SJRWMD Cost-Share Program; Maintenance Frequency = 1-2 times/month
ORL-11 | 2997R | Howell Creek | -81.3933 | 28.5593 | Westmoreland 2nd Generation Baffle Box | 42-095-2042AN-ERP | Orlando | n/a | Construct 2nd Generation Baffle Box upstream of Lake Adair | n/a | 2006 | $35,000 | City of Orlando Stormwater Utility Fee | 0.1 | 64 and 84 | Remove nitrogen, phosphorus and gross pollutants from Lake Adair basin and Howell Branch chain-of-lakes | 0.1 | 5.3 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Grant applications submitted to: US EPA Section 319 Nonpoint Source Management Program + SJRWMD Cost-Share Program; Maintenance Frequency = 1-2 times/month
ORL-12 | 2997R | Howell Creek |  |  | Stormwater Filtration Systems / Inlet Baskets |  | Orlando | n/a | Installation of 6 inlet baskets around perimeter of Lake Adair |  | 2007 | $5400 | City of Orlando Stormwater Utility Fee | 0.1 | 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Adair basin and Howell Branch chain-of-lakes |  | 25 | 13=Other structural BMP | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = After every rain event, which can be multiple times per week during rainy season; Approximate Average over course of year = 1 time/week/yr
ORL-13 | 2997S | Howell Creek |  |  | Stormwater Filtration Systems / Inlet Baskets | 42-095-2087AN-ERP | Orlando | n/a | Installation of 11 inlet baskets in Spring Lake basin |  | 2007 | $9900 | City of Orlando Stormwater Utility Fee | 0.03 | 64 | Remove nitrogen, phosphorus and gross pollutants from Spring Lake basin and Howell Branch chain-of-lakes |  | 25 | 13=Other structural BMP | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = After every rain event, which can be multiple times per week during rainy season; Approximate Average over course of year = 1 time/week/yr
ORL-14 | 2997M | Howell Creek |  |  | Stormwater Filtration Systems / Inlet Baskets |  | Orlando | n/a | Installation of 13 inlet baskets in Lake Formosa basin |  | 2007 | $11,700 | City of Orlando Stormwater Utility Fee | 0.1 | 5 and 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Formosa basin and Howell Branch chain-of-lakes |  | 14 | 13=Other structural BMP | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = After every rain event, which can be multiple times per week during rainy season; Approximate Average over course of year = 1 time/week/yr
ORL-15 | 2997N | Howell Creek |  |  | Stormwater Filtration Systems / Inlet Baskets |  | Orlando | n/a | Installation of 29 inlet baskets in Lake Highland basin | 42-117-98514-1 | 2007 | $26,100 | City of Orlando Stormwater Utility Fee | 3.6 | 5 and 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Highland basin and Howell Branch chain-of-lakes |  | 223 | 13=Other structural BMP | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = After every rain event, which can be multiple times per week during rainy season; Approximate Average over course of year = 1 time/week/yr
ORL-16 | 2997J | Howell Creek |  |  | Stormwater Filtration Systems / Inlet Baskets | 42-095-1824AN-ERP | Orlando | n/a | Installation of 2 inlet baskets in Lake Rowena basin |  | 2007 | $1800 | City of Orlando Stormwater Utility Fee | 0.5 | 5 and 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Rowena basin and Howell Branch chain-of-lakes |  | 39 | 13=Other structural BMP | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = After every rain event, which can be multiple times per week during rainy season; Approximate Average over course of year = 1 time/week/yr
ORL-17 | 2997F + 2997I | Howell Creek |  |  | Stormwater Filtration Systems / Inlet Baskets | 42-095-94487-1 42-095-1851ANY-ERP | Orlando | n/a | Installation of 49 inlet baskets in Lake Ivanhoe basin |  | 2008 | $44,100 | City of Orlando Stormwater Utility Fee | 0.6 | 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Ivanhoe basin and Howell Branch chain-of-lakes |  | 242 | 13=Other structural BMP | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = After every rain event, which can be multiple times per week during rainy season; Approximate Average over course of year = 1 time/week/yr
ORL-18 | 3168Z | Howell Creek |  |  | Stormwater Filtration Systems / Inlet Baskets |  | Orlando | n/a | Installation of 4 inlet baskets in Lake Druid basin |  | 2007 | $1800 | City of Orlando Stormwater Utility Fee | 0.4 | 5 and 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Druid basin and Howell Branch chain-of-lakes | 0.1 | 39 | 13=Other structural BMP | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = After every rain event, which can be multiple times per week during rainy season; Approximate Average over course of year = 1 time/week/yr
ORL-19 |  |  |  |  | Street Sweeping |  | Orlando | n/a | Street Sweeping throughout all public roads within City limits | approx. 01/1977 |  | $1,800,000/yr | City of Orlando Stormwater Utility Fee | 14.3 | 4, 5, and 7 | Remove all gross pollutants and sediment from MS4 throughout City |  |  | 6=Urban nonstructural BMPs (e.g. street sweeping) |  | 1=Completed | From Oct 2005-Sept 2006, approx. 26,324 cubic yards removed from streets. Additional benefit is the prevention of gross pollutants entering MS4 that could clog system and cause flooding
ORL-20 |  |  |  |  | Storm Sewer Inlet Marker Installation |  | Orlando | n/a | To increase awareness, install metal placards above curb inlets, giving instructions, "No Dumping! Drains to Lake" | 01/1998 |  | $500/yr | City of Orlando Stormwater Utility Fee | N/A | N/A - part of education credit | Reduce the number of illicit discharges(pollutants) from entering MS4 throughout City |  |  | 10=Education Project |  | 1=Completed | Additional benefit is the prevention of gross pollutants entering MS4 that could clog system and cause flooding
ORL-21 |  |  |  |  | Green Business |  | Orlando | UCF Stormwater Academy, FDEP, USEPA | Increase the implementation of BMP's in Landscaping, Vehicle Maintenance and Restaurant Industries | 8/10/05 |  |  | City of Orlando Stormwater Utility Fee + Section 319 Nonpoint Source Management Program - Grant from USEPA | N/A | N/A - part of education credit | Reduce pollutants entering MS4 throughout the City |  |  | 10=Education Project; 14=Other non-structural project |  | 2=Started | To be designated as "Green," business must schedule Employee Training with City, Post BMP's at worksite and be subject to Compliance Inspections by City staff
ORL-22 |  |  |  |  | Groundskeeping Maintenance Training |  | Orlando | n/a | Mandatory training on how to protect the City's stormwater system for all Contractors awarded City Groundskeeping contracts & applicable City personnel | 02/2005 |  |  | City of Orlando Stormwater Utility Fee | N/A | N/A - part of education credit | Reduce pollutants entering MS4 throughout the City |  |  | 10=Education Project |  | 1=Completed | Training required on an annual basis for term of contract. Offered in English and Spanish. As of 5/21/07, 7 contractors with 67 employees and 189 City employees have attended training.
ORL-23 | 2997R | Howell Creek | 28.5605 | 81.4104 | Reading Dr (24" line) - 2nd Generation Baffle Box at Lake Adair |  | Orlando | n/a | Construct 2nd Generation Baffle Box upstream of Lake Adair to treat approximately 13% of subbasin | n/a | n/a | n/a | City of Orlando Stormwater Utility Fee | 0.5 | 64 | Remove nitrogen, phosphorus and gross pollutants from Lake Adair basin and Howell Branch chain-of-lakes | 0.1 | 26 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 4=Envisioned, but Not Funded | Maintenance Frequency = 1-2 times/month
ORL-24 | 2997S | Howell Creek | 28.5546 | 81.4012 | Spring Lake -2nd Generation Baffle Box at Rio Grande | 42-095-10567-1 | Orlando | n/a | Construct 2nd Generation Baffle Box upstream of Spring Lake to treat 100% of subbasin | n/a | n/a | $128,000 | City of Orlando Stormwater Utility Fee | 0.6 | 64 and 84 | Remove nitrogen, phosphorus and gross pollutants from Spring Lake basin and Howell Branch chain-of-lakes | 0.1 | 39 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 4=Envisioned, but Not Funded | Grant applications submitted to: US EPA Section 319 Nonpoint Source Management Program + SJRWMD Cost-Share Program ; Maintenance Frequency = 1-2 times/month
ORL-25 | 2997S | Howell Creek | 28.5544 | 81.3981 | Spring Lake- 2nd Generation Baffle Box at Springdale Rd |  | Orlando | n/a | Construct 2nd Generation Baffle Box upstream of Spring Lake to treat 100% of subbasin | n/a | n/a | n/a | City of Orlando Stormwater Utility Fee | 0.1 | 64 and 84 | Remove nitrogen, phosphorus and gross pollutants from Spring Lake basin and Howell Branch chain-of-lakes | 0.1 | 21 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = 1-2 times/month ; Inlet basket downstream of weir, located downstream of baffle box
ORL-26 | 2997S | Howell Creek | 28.5575 | 81.4045 | DOT Pond Maintenance, west of Spring Lake | 42-095-2006AN-ERP | Orlando | n/a | Removal of muck/sediment and expansion of wet detention pond to treat 95% and 5% of two sub-basins, respectively. | n/a | n/a | n/a | City of Orlando Stormwater Utility Fee | 5.1 | 64 | Removal of muck/sediment will minimize resuspension of nutrient-laden sediments, increase pond volume and increase detention time from 9.2 days to 31.7 days | 3.3 | 141 | 3=Wet detention pond | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data + Spring Lake Hydrologic/Nutrient Budget and Management Plan, Harper and Baker, January 2008 | 4=Envisioned, but Not Funded | Reduction based on Harper 2008 report (interpolation based on 9.2 day retention time)
ORL-27 | 3168Z | Howell Creek | 28.5587 | 81.3502 | Weber Dr - 2nd Generation Baffle Box at Lake Druid |  | Orlando | n/a | Construct 2nd Generation Baffle Box upstream of Lake Druid to treat approximately 7% of subbasin | n/a | 2006 | n/a | City of Orlando Stormwater Utility Fee | 0.3 | 25 | Remove nitrogen, phosphorus and gross pollutants from Lake Druid basin and Howell Branch chain-of-lakes | 0.1 | 6 | 1=Stormwater Retrofit (CDS or baffle box) | BMP Efficiency Values for the Lake Jesup BMAP (7/22/08)/ E. Livingston - BPJ/data | 1=Completed | Maintenance Frequency = 1-2 times/month
ORL-28 |  |  |  |  | Educational Component |  | Orlando | [5 empty] | City of Orlando Stormwater Utility Fee | 94.2 | 5.5
ORL-29 | 2997P | Howell Creek | 28.5499 | 81.3866 | Hughey Avenue Retrofit |  | Orlando | USEPA | Divert stormwater from Lake Concord basin to Lake Dot Alum Treatment before discharging into chain of lakes | 10/2010 | 12/2010 | $500,000 | City of Orlando Stormwater Utility Fee + Section 319 Nonpoint Source Management Program - Grant from USEPA | 3.8 | 60 | Remove nitrogen and phosphorus from Lake Concord basin and Howell Branch chain-of-lakes | 0.75 | 90.8 | 1, 13 | BPJ from E. Livingston and H. Harper (Jan 2009); based off Runoff Volume x EMCs x assumed 50% reduc for TN and 90% reduc for TP --- Alum Treatment of Stormwater: The First Ten Years, Environmental Research and Design, 2002; Estimation of Stormwater Loading Rate Parameters for Central and South Florida, Environmental Research & Design, June 25, 2002 | 3 - Planned & Funded
ORL-30 |  |  |  |  | TMDL BMPs |  | Orlando |  | BMPs that were in place at the time of the TMDL |  |  |  |  | 684.5 | [6 empty] | Completed
956.87
Note on W13: CUR10391:
Note on W14: CUR10391:
Note on W15: CUR10391:
Note on W16: CUR10391:
Note on W17: CUR10391:
Note on W18: CUR10391:
Note on W19: CUR10391:

## Oviedo
Project Number | Project Name | ERP Permit Number | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Status
OV-1 | Aulin Regional Stormwater Pond | 42-117-1169AN-ERP 42-117-108216-1 42-117-1201AN-ERP | Oviedo | Aulin Regional Stormwater Pond |  |  |  | 14.8 | 60
OV-2 | Lightwood Knox Canal Project | 42-117-1183AN-ERP 42-117-0240AM-ERP 42-117-97565-1 42-117-101528-1 42-117-99429-1 42-117-1339AN-ERP | Oviedo | Lightwood Knox Canal Project |  |  |  | 82.3 | 20 |  |  |  |  | 4=Envisioned, but Not Funded
OV-3 | Sweetwater Creek Project | 42-117-0315AN 42-117-99267-1 42-117-1043ANG 42-117-1205AN-ERP | Oviedo | Sweetwater Creek Project |  |  |  | 30.4 | 20 |  |  |  |  | 4=Envisioned, but Not Funded
OV-4 | Solary Canal Stormwater Treatment Area |  | Winter Springs, Oviedo, Seminole County | Regional Stormwater Treatment Facility consisting of an 8.0-acre wet pond and 4.8-acre wetland | 7/2009 | 2/2010 | 2400000 | 230 |  | Regional Stormwater Facility to treat upstream basin | 12.7 | 1471 | 3=Wet detention pond, 15=Wetland treatment | 4=Envisioned, but Not Funded
OV-5 | Street Sweeping |  | Oviedo | Monthly street sweeping |  | Ongoing |  | 11.8 | 3 |  |  |  |  | Ongoing
OV-6 | Education Efforts |  | Oviedo | FYN, illicit discharge program |  | Ongoing |  | 46.2 | 4 |  |  |  |  | Ongoing
OV-7 | TMDL BMPs |  | Oviedo | BMPs that were in place at the time of the TMDL |  |  |  | 376.8 | [5 empty] | Completed
792.3

## Sanford
Project Number | Project Name | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Project-Specific Annual O&M Costs | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction
S-1 | BMPs not in TMDL | Sanford | BMPs not in TMDL | [5 empty] | 16.5 | varies
S-2 | Street Sweeping | Sanford | Street Sweeping | [5 empty] | 3.6 | 5
S-3 | Public Education | Sanford | Public Education | [5 empty] | 108.9 | 4
S-4 | Regional Project | Sanford | Participate in a regional project in Seminole County | [5 empty] | 11.8
S-5 | BMPs from the TMDL | Sanford | BMPs that were in place at the time of the TMDL | [5 empty] | 461.4
602.2

## Seminole County
Project Number | WBID | Subbasin | Project Location |  | Project Name | ERP Permit Number | Lead Entity | Project Partner(s) | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Method Used to Calculate NPS Load Reduction | Status | Comments
SC-1 | 2997A | Howell | 81.3298 | 28.6229 | Cassel Creek RSF |  | Seminole County | SJRWMD | Regional Stormwater Facility to treat water in the sub basin upstream | Est 1/2010 | Est 9/2010 | $ 1,700,000 | Seminole County | 153.5 | 54 | Regional Stormwater Facility to treat upstream basin | 10 | 830 | 3=Wet detention pond | Harper Method | 3=Planned & Funded, (Partially Funded 4/1/09 | Final Design Loading Calculations Pending 4/1/09 and Future Efficiency Monitoring
SC-2 | 2997 | Howell | 81.3136 | 28.6331 | Lake Ann Outfall | 4-117-62532-2 | Seminole County | SJRWMD | Baffle box and pipe replacement | 4/2001 | 10/2001 | $148,000 | Seminole County | 13 | 10 | Load reduction and flood control | 0.1 | 322 | 1=Stormwater Retrofit (CDS or baffle box) | Harper Method | 1=Completed
SC-3 | 2997 | Howell | 81.3119 | 28.6458 | Red Bug Lake Road RSF |  | Seminole County | SJRWMD | Regional Stormwater Facility to treat water in the sub basin upstream | Est 6/2009 | Est 3/2010 | $ 1,400,000 | Seminole County & SJRWMD | 88.9 | 51 | Regional Stormwater Facility to treat upstream basin | 9 | 1050 | 3=Wet detention pond | Harper Method | 3=Planned & Funded, (Partially Funded 4/1/09) | Final Design Loading Calculations Pending 4/1/09 and Future Efficiency Monitoring
SC-4 | 2982 | Jesup | 28.752 | 81.233 | Navy Canal RSF | 4-117-90051-1 | Seminole County | SJRWMD | Regional Stormwater Facility to treat water in the sub basin upstream | 3/1/2005 | 10/14/2006 | $ 2,112,336 (Design $275,305: R/W -N/A: Construction $ 1,832,531: Misc $4,500 Permit Fee | SJRWMD ($1,660,000) Seminole County ($452,336) | 309.3 | 67 | Regional Stormwater Facility to treat upstream basin | 7 | 889 | 3=Wet detention pond | Harper Method | 1=Completed | Efficiency monitoring underway 2008/2009
SC-5 | 2981B1 | Jesup | 28.759 | 81.213 | Cameron Ditch RSF | 59-0226748-001 (FDEP) | Seminole County | SJRWMD | Regional Stormwater Facility to treat water in the sub basin upstream | 4/17/2006 | 10/14/2006 | $ 3,735,374 (Design $277,684: R/W N/A: Construction $1,161,155: CEI $74,875: Misc $109,324) | SJRWMD ($2,923,424) Seminole County ($811,950) | 73.7 | 76 | Regional Stormwater Facility to treat upstream basin | 32 | 376 | 3=Wet detention pond, 15=Wetland treatment | Harper Method | 1=Completed | Efficiency monitoring underway 2008/2009
SC-6 |  | Howell Creek | 28.628 | 81.325 | Lake Howell Road Pond Retrofit | 42-117-22249-6 | Seminole County | N/A | Retrofit of an old FDOT pond now under county jurisdiction that drains Howell Branch Road | May 2007 | 2007-11-01 | N/A | Seminole County | 7 | 63 | Pond retrofit | 4.0 | 23 | 3=Wet detention pond | Harper Method | 1=Completed
SC-7 |  | Lake Jesup |  |  | Solary Canal Stormwater Treatment Area |  | Winter Springs, Oviedo, Seminole County |  | Regional Stormwater Treatment Facility consisting of an 8.0-acre wet pond and 4.8-acre wetland | 7/2009 | 2/2010 | 2400000 | SJRWMD, Winter Springs, Oviedo, Seminole County | 230 |  | Regional Stormwater Facility to treat upstream basin | 12.7 | 1471 | 3=Wet detention pond, 15=Wetland treatment | City of WSp Master Plan; CDM; 3/2009 | 3-Planned & Funded Advertise for Construction Bids 3/29/09
C-6 | N/A (Grassy Lake) | Gee Creek | 28.6643 | -81.3456 | Anchor Road Reconstruction |  | Seminole County |  | Reconstruction of Anchor Road with drainage improvements including upgraded detention/retention ponds | 2007-10-01 | 2009-10-01 | 2000000 | City of Casselberry, Seminole County, and Community Development Block Grant | 5.6 | 60 | Provides stormwater treatment prior to discharge to lake | 13 | 60.7 | 3=Wet detention pond |  | 2=Started
SC-8 |  |  |  |  | Street Sweeping |  | Seminole County/ Casselberry |  | Monthly and quarterly street sweeping |  | Ongoing |  |  | 13.1 | 2 and 3 | [5 empty] | Ongoing
SC-9 |  |  |  |  | Education Efforts |  | Seminole County |  | FYN, ordinances, PSAs, pamphlets, presentations, website, illicit discharge program |  | Ongoing |  |  | 558.3 | 5.5 | [5 empty] | Ongoing
SC-10 |  |  |  |  | TMDL BMPs |  | Seminole County |  | BMPs that were in place at the time of the TMDL |  |  |  |  | 1807.4 | [6 empty] | Completed
3259.8

## Turnpike
Project Number | Project Name | Lead Entity | Project Detail | Project Start Date | Project End Date | Project Cost | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Status
T-1 | TMDL BMPs | Turnpike | BMPs that were in place at the time of the TMDL |  |  |  |  | 261.3 | varies | Completed
T-2 | Street Sweeping | Turnpike | Monthly street sweeping |  | Ongoing |  |  | 3.2 | 3 | Ongoing
T-3 | Education Efforts | Turnpike | Presentations, illicit discharge program |  | Ongoing |  |  | 9 | 2 | Ongoing
273.5

## Winter Park
Project Number | Subbasin | Project Location |  | Project Name | ERP Permit Number | Lead Entity | Project Partner(s) | Project Detail | Project Start Date | Project End Date | Project Cost | Project-Specific Annual O&M Costs | Funding Source(s) | Estimated Load Reduction-TP (lbs/yr) | % BMP Reduction | Benefit | Project Footprint (Acres) | Treatment Acres | Project Type | Status
WP-1 | Howell Creek | 25.7815 | 77.8107 | Lake Island Interconnect | 4-095-20947-2 | City of Winter Park | N/A | First Flush bypass to Wet Retention Ponds | 2002-06-01 | 2003-09-01 | 408009 | 0 | Stormwater Utility | 9.4 | 20 or 64 | First flush capture and treatment for a previously untreated Commercial District | <1 | 74.5 | 3=Wet detention pond | 1=Completed
WP-2 | Howell Creek | 25.8037 | 77.7908 | Via Lugano Exfiltration |  | City of Winter Park | N/A | Off Line Exfiltration | 1996-10-01 | 1997-11-01 | 200000 | 0 | Stormwater Utility | 1.3 | 30 | Improved collection and treatment of a previously untreated Residential subbasin | <1 | 25.3 | 2=Dry detention pond | 1=Completed
WP-3 | Howell Creek | 25.7853 | 77.7956 | N. Park Ave. Exfiltration |  | City of Winter Park | N/A | Off Line Exfiltration | 2004-06-01 | 2004-10-01 | 250000 | 0 | Stormwater Utility | 6.6 | 30 | Improved collection and treatment of a previously untreated Residential subbasin | <1 | 21.4398 | 2=Dry detention pond | 1=Completed
WP-4 | Howell Creek | 25.7925 | 77.7983 | Fairway 3 Exfiltration |  | City of Winter Park | FDEP/ CWP | Off Line Exfiltration | 2006-11-01 | 2007-10-01 | 1000000 | 0 | Stormwater Utility and Florida Forever Grant | 5.5 | 30 | Improved collection and treatment of a previously untreated Residential and Commercial subbasin | <1 | 57.3947 | 2=Dry detention pond | 1=Completed
WP-5 | Howell Creek | 25.7987 | 77.7968 | McKean Road CDS |  | City of Winter Park | SJRWMD/CWP | CDS UNIT ON 24" OUTFALL | 2004-05-01 | 2005-06-01 |  | 0 | SJRWMD / CWP Stormwater Utility | 0.1 | 5 | Removal of Gross particles from outfall discharge | <0.1 | 5.5762 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-6 | Howell Creek | 25.8032 | 77.7881 | Pinetree Rd Outfall CDS |  | City of Winter Park | N/A | CDS UNIT ON 42" OUTFALL | 2004-05-01 | 2005-06-01 |  | 0 | Stormwater Utility | 0.6 | 5 | Removal of Gross particles from outfall discharge | <0.1 | 64.7804 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-7 | Howell Creek | 25.7937 | 77.7968 | 1190 Park Ave CDS |  | City of Winter Park | N/A | CDS UNIT ON 30" OUTFALL | 1998-08-01 | 1999-11-01 |  | 0 | Stormwater Utility | 0.2 | 5 | Removal of Gross particles from outfall discharge | <0.1 | 22.8245 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-8 | Howell Creek | 25.8008 | 77.7803 | Moss/ Venetian Dry Capture 1st Generation Baffle box |  | City of Winter Park | N/A | BAFFLE SCREEN ON 15" OUTFALL | 2000-02-01 | 2007-03-01 |  | 0 | Stormwater Utility | 0.1 | 10 | Capture of leaf material prior to Lake entry | <0.1 | 3.019 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-9 | Howell Creek | 25.7898 | 77.7937 | Green Cove Road 2 CDS Units |  | City of Winter Park | SJRWMD/CWP | 2 CDS UNITS ON TWO 24" OUTFALLS | 2004-05-01 | 2006-06-01 |  | 0 | SJRWMD / CWP Stormwater Utility | 0.1 | 5 | Removal of Gross particles from outfall discharge | <0.1 | 11.3507 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-10 | Howell Creek | 25.8056 | 77.8089 | Courtland Alum Injection treatment | 42-095-46263-1 | City of Winter Park | N/A | Alum injection at Lake Mizell outfall |  |  |  | 0 | Stormwater Utility | 21.2 | 90 | Reduction of Suspended Nitrates, Phosphates, and Metals from Stormwater Discharge | <1 | 88.0837 | 13=Other structural BMP | 1=Completed
WP-11 | Howell Creek | 25.8106 | 77.8143 | Partnership/ wet detention/ Windsong | 42-095-93549-1 | City of Winter Park | Windsong / CWP | Developer's agreement to treat Palmer ditch basin run off within site MSSW |  |  |  | 0 | Stormwater Utility | 4.1 | 20 | Previously untreated runoff being treated within a permitted Stormwater System | 2.75 | 84.5455 | 3=Wet detention pond | 1=Completed
WP-12 | Howell Creek | 25.7972 | 77.8089 | Lincoln Ave Alum Injection treatment | 42-095-45577-1 | City of Winter Park | N/A | Alum injection at Lake Osceola outfall |  |  |  | 0 | Stormwater Utility | 37.7 | 90 | Reduction of Suspended Nitrates, Phosphates, and Metals from Stormwater Discharge | <1 | 17.5873 | 13=Other structural BMP | 1=Completed
WP-13 | Howell Creek | 25.7972 | 77.8089 | Alexander Place Alum Injection treatment with baffle box | 42-095-98168-1 42-095-94484-1 42-095-2173AN-ERP | City of Winter Park | N/A | Alum injection at Lake Osceola outfall |  |  |  | 0 | Stormwater Utility | 35 | 90 | Reduction of Suspended Nitrates, Phosphates, and Metals from Stormwater Discharge | <1 | 24.6124 | 13=Other structural BMP | 1=Completed
WP-14 | Howell Creek | 25.7972 | 77.8089 | Morse /Alum Injection treatment |  | City of Winter Park | N/A | Alum injection at Lake Osceola outfall |  |  |  | 0 | Stormwater Utility | 6.9 | 90 | Reduction of Suspended Nitrates, Phosphates, and Metals from Stormwater Discharge | <1 | 57.127 | 13=Other structural BMP | 1=Completed
WP-15 | Howell Creek | 25.8028 | 77.8053 | Trismen and Lakewood Drive Exfiltration |  | City of Winter Park | N/A | Off Line Exfiltration |  |  |  | 0 | Stormwater Utility | 0.4 | 30 | Improved collection and treatment of a previously untreated Residential subbasin | <1 | 7.3525 | 2=Dry detention pond | 1=Completed
WP-16 | Howell Creek | 25.8017 | 77.8043 | Trismen CDS Unit |  | City of Winter Park | N/A | CDS Unit on 24" outfall |  |  |  | 0 | Stormwater Utility | 0 | 5 | Removal of Gross particles from outfall discharge | <0.1 | 0.39142 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-17 | Howell Creek | 25.8022 | 77.807 | Trismen Dry 1st Generation Baffle Box |  | City of Winter Park | N/A | Baffle screen on 15" outfall |  |  |  | 0 | Stormwater Utility | 0 | 10 | Capture of leaf material prior to Lake entry | <0.1 | 1.8425 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-18 | Howell Creek | 25.8084 | 77.7998 | Elizabeth CDS treating Inlet at Bonita and Dale |  | City of Winter Park | N/A | CDS on 15" Pipe | 2004-05-01 | 2006-06-01 |  | 0 | Stormwater Utility | 0.1 | 25 | Removal of Gross particles from inlet capture | <0.1 | 2.3512 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-19 | Howell Creek | 25.7962 | 77.8305 | Lake Chelton Outfall Improvement |  | City of Winter Park | N/A | 4 Dry Capture Baffle inlets and boxes | 2003-09-03 | 2004-01-09 |  | 0 | Stormwater Utility | 0 | 10 | Capture of leaf material prior to Lake entry | <0.1 | 28.6487 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-20 | Howell Creek | 25.7934 | 77.8175 | Lakeview Road Bricking |  | City of Winter Park | N/A | CDS Installation on 24" Outfall | 2006-03-01 |  |  | 0 | Stormwater Utility | 0.1 | 5 | Removal of Gross particles from outfall discharge | <0.1 | 9.5251 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-21 | Howell Creek | 25.7863 | 77.8231 | Mead Gardens Borrow Pit Pond Retrofit | 4-095-20716-4 | City of Winter Park | FDEP/CWP | Retrofit Screening devices (two baffle boxes) to existing MSSW | 2006-05-06 | 2006-09-01 |  | 560000 | Stormwater Utility and 319 Grant | 3.4 | 20 or 64 | Modification to existing Stormwater treatment system to improve performance and better serve Public Education | 1 | 62.0566 | 10=Education Project | 1=Completed
WP-22 | Howell Creek | 25.7951 | 77.824 | Glencoe Road Bricking |  | City of Winter Park | N/A | Stormwater capture and screening system (baffle box) | 2007-03-01 | 2007-06-01 |  | 0 | Stormwater Utility | 0.1 | 10 | Capture of leaf material prior to Lake entry | <0.1 | 3.3894 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-23 | Howell Creek | 25.7999 | 77.8242 | Laurel Road Dry Retention Pond |  | City of Winter Park | N/A | On Line Dry retention Pond | 1999-05-01 | 2001-03-01 |  | 0 | Stormwater Utility / 319 Grant | 1.2 | 20 | Improved collection and treatment of a previously untreated Residential subbasin | <1 | 17.1463 | 2=Dry detention pond | 1=Completed
WP-24 | Howell Creek | 25.798 | 77.8141 | Alum Injection Treatment/ Rollins | 42-095-46145-1 | City of Winter Park | N/A | Alum injection At Outfalls to Lake Virginia | 1995-01-01 |  |  | 0 | Stormwater Utility | 26.8 | 90 | Reduction of Suspended Nitrates, Phosphates, and Metals from Stormwater Discharge | <1 | 72.9892 | 13=Other structural BMP | 1=Completed
WP-25 | Howell Creek | 25.7918 | 77.8185 | 9th Grade Center Pond Wet Detention | 40-095-27358-1 | City of Winter Park | N/A | Wet Detention Pond Retrofit | Pre 1995 | Pre 1995 |  | 0 | Stormwater Utility | 10.1 | 20 | Retrofit treatment of a previously untreated Residential subbasin | 1 | 110.8023 | 3=Wet detention pond | 1=Completed
WP-26 | Howell Creek | 25.7939 | 77.817 | Lakeview Bricking |  | City of Winter Park | N/A | Stormwater capture and screening system (baffle box) | 2005-02-01 | 2006-11-01 |  | 0 | Stormwater Utility | 0.1 | 10 | Capture of leaf material prior to Lake entry | 0.2 | 6.9686 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-27 | Howell Creek | 25.7933 | 77.8201 | Oxford Road Bricking |  | City of Winter Park | N/A | Stormwater capture and screening system (baffle box) | 2006-08-01 | 2006-11-01 |  | 0 | Stormwater Utility | 0.1 | 10 | Capture of leaf material prior to Lake entry | <0.1 | 5.2764 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-28 | Howell Creek | 25.7939 | 77.8126 | Stormwater Ordinance #1832 6/25/89 Fully enforced 1/91 |  | City of Winter Park | N/A | City Ordinance requiring 1" Treatment for new Commercial and Residential development and redevelopment | 1991-01-01 | Ongoing |  | 0 | Private Development | Part of education credit | 4 | Developer required Stormwater Treatment per individual Site characteristics | N/A | 5.2764 | 12=Ordinance/Rule Change | 5=Ongoing
WP-29 | Howell Creek | 25.7838 | 77.811 | Lake Island Park | 4-095-46221-1 | City of Winter Park | N/A | Created treatment volume in Lake Mednsen, construct control structures for wet detention treatment | Pre 1995 | 1996-03-01 |  | 0 | City of Winter Park | 30.5 | 20 | Wasteland converted to Park and Open Space with Improved Stormwater Treatment of the contributing Basin runoff | 25 | 256 | 3=Wet detention pond | 1=Completed
WP-30 | Howell Creek | 25.803 | 77.7969 | 950 Palmer Ave Retrofit |  | City of Winter Park | N/A | Stormwater capture and screening system (baffle box) | 2007-07-01 |  |  | 0 | Stormwater Utility | 0.3 | 10 | Removal of Gross particles from outfall discharge | <0.1 | 18.33 | 1=Stormwater Retrofit (CDS or baffle box) | 1=Completed
WP-31 |  |  |  | Banchory Exfiltration |  | City of Winter Park |  | On-line Retention 0.25 treatment volume |  | 2008 |  |  |  | 0.4 | 30 |  |  |  |  | 1=Completed
WP-32 |  |  |  | Bryan CDS |  | City of Winter Park |  | CDS |  | 2008 |  |  |  | 0.2 | 5 |  |  |  |  | 1=Completed
WP-33 |  |  |  | E.Lake Sue CDS |  | City of Winter Park |  | CDS |  | 2008 |  |  |  | 0.1 | 5 |  |  |  |  | 1=Completed
WP-34 |  |  |  | Elizabeth Drive baffle box |  | City of Winter Park |  | Baffle box | [5 empty] | 1.1 | 10 |  |  |  |  | 1=Completed
WP-35 |  |  |  | Street Sweeping |  | City of Winter Park |  | Street sweeping two times per month |  | Ongoing |  |  |  | 13.6 | 4 |  |  |  |  | Ongoing
WP-36 |  |  |  | Education Efforts |  | City of Winter Park |  | FYN, landscape and fertilizer ordinances, pamphlets, presentations, website, illicit discharge program |  | Ongoing |  |  |  | 106.3 | 6 |  |  |  |  | Ongoing
WP-37 |  |  |  | TMDL BMPs |  | City of Winter Park |  | BMPs that were in place at the time of the TMDL | [5 empty] | 152.5 | [5 empty] | Completed
476.2

## Winter Springs
Project Number | Subbasin | Project Name | Lead Entity | Project Detail | Project Start | Project End | Project Cost | Funding Source(s) | Estimated TP Reduction (lb/yr) | % BMP Reduction | Status
WS-1 | Lake Jesup | Solary Canal Stormwater Treatment Area | Winter Springs, Oviedo, Seminole County | Regional Stormwater Treatment Facility consisting of an 8.0-acre wet pond and 4.8-acre wetland | 7/2009 | 2/2010 | 2400000 | SJRWMD, Winter Springs, Oviedo, Seminole County | 230 |  | 3-Planned & Funded Advertise for Construction Bids 3/29/09
WS-2 | Gee Creek | Winding Hollow Wetland Treatment Area | Winter Springs | Divert No Name Creek flow into wetland treatment system | 2020 | 2020 | 357000 | Stormwater Utility Fund | 210.1 | 35 | 4 - Envisioned but Not Funded
WS-3 | Howell Creek | Winter Springs and Wedgewood Filtration Devices | Winter Springs | Retrofit stormwater outfalls with flow-through filtration devices | 2020 | 2020 | 132000 | Stormwater Utility Fund | 24.7 | 30 | 4 - Envisioned but Not Funded
WS-4 | Gee Creek | North Orlando Townsite Filtration Devices | Winter Springs | Retrofit eastern and western outfalls with flow-through filtration devices | 2020 | 2020 | 80000 | Stormwater Utility Fund | 5.2 | 30 | 4 - Envisioned but Not Funded
WS-5 | Soldiers Creek | Highlands Regional Pond Enhancements | Winter Springs | Expansion of existing wet pond and redirection of untreated stormwater runoff to the pond | 2020 | 2020 | 1385000 | Stormwater Utility Fund (plus other sources) | 64.5 | 60 | 4 - Envisioned but Not Funded
WS-6 | Howell Creek, Gee Creek, Soldiers Creek | Education Efforts - Update Local Codes and Ordinances (Fertilizer Rule, etc.), FYN | Winter Springs | Maximize available public education credits through Code updates, fertilizer ordinance, FYN, etc. | Ongoing | TBD | $3,000/yr (FYN) | Stormwater Utility Fund | 92 | 4 | 5 - Ongoing
WS-7 | Howell Creek, Gee Creek, Soldiers Creek | Street Sweeping | Winter Springs | Continue current street sweeping program | Ongoing | N/A | N/A | N/A | 7.3 | 2 | 5 - Ongoing
WS-8 |  | TMDL BMPs | Winter Springs | BMPs that were in place at the time of the TMDL |  |  |  |  | 810.3 |  | Completed
1444.1

## Summary
Entity | 2009-2014 Required Reduction | Project Reductions | Credit/ (Deficit)
Altamonte Springs | 19 | 38 | 19
Casselberry | 342.7 | 429.4 | 86.7
DOT District 5 | 132.3 | 317 | 184.7
Eatonville | 23.4 | 9.9 | -13.5
Lake Mary | 264.3 | 226.6 | -37.7
Longwood | 205.5 | 135.6 | -69.9
Maitland | 124.8 | 125.66 | 0.86
OOCEA | 5.2 | 13.9 | 8.7
Orange County | 569.3 | 228.2 | -341.1
Orlando | 326.1 | 956.87 | 630.77
Oviedo | 258.7 | 792.3 | 533.6
Sanford | 602.2 | 602.2 | 0
Seminole County | 2137.3 | 3259.8 | 1122.5
Turnpike Authority | 101.1 | 273.5 | 172.4
Winter Park | 370.5 | 476.2 | 105.7
Winter Springs | 513 | 1444.1 | 931.1