## All
Entity | Credit Ranking | Subbasin | Project Name | Lead Entity | Project Partners | Project Type | Project Detail | ERP # | Project Start | Project End | Project Cost | Funding Source(s) | Estimated Nitrate Reduction (lbs/yr) | Nitrate Reduction Calculation Method | Status | Contact Name | Contact Phone | Contact Email | Comments
|  |  |  | CDS, Baffle Box (1st Gen.), Baffle Box (2nd Gen.), Dry detention, wet detention, swales, drainage wells, alum treatment, sewering, etc. | 2-3 sentences; include treatment volume, retention time, # homes sewered, etc. as applicable | "Exempt" if applicable; see guidelines for details re: exempt projects | Mo/Yr | Mo/Yr or "Ongoing" | Specify capital vs. O&M, as applicable | Stormwater utility, ad valorem, 319, etc. |  |  | Completed; Started; Planned & Funded; Envisioned (unfunded); or Ongoing |  |  |  | Optional
Apopka | Low Impact | springshed/ Rock Springs Run | Victoria Plaza, Forest Avenue, and 3rd St | City of Apopka/Public Services |  | Relined gravity sewer | Relined to correct leaking joints |  | June 2007 | June 2007 | 71667 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Low Impact | springshed/ Rock Springs Run | Park Ave | City of Apopka/Public Services |  | Relined gravity sewer | Relined to correct leaking joints and corroded cast iron pipe |  | 2/11/08 | 2/14/08 | 75943 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Low Impact | springshed/ Rock Springs Run | Park Ave Gravity | City of Apopka/Public Services |  | Relined gravity sewer | Relined with CIPP to prevent leaks at joint |  | March 2009 | March 2009 | 14041 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Low Impact | springshed/ Rock Springs Run | Park Ave Sewer Line Rehab and Lift Station 9 Wet Well | City of Apopka/Public Services |  | Reline sewer line | Relined to prevent leaking joints |  | FY2010 | FY2010 | 67910 | Water & Sewer Maintenance Fund 401 |  |  | Planned & Funded | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 12/01/2009 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | EXCESSIVE ACCUMULATION OF GREASE AND RAGS IN LIFT STATION #1 CAUSING ROTO BALLS TO RAISE UP AND NOT FUNCTION PROPERLY, LEADING TO SPILL 720,000 GALLONS. ALL SPILLAGE WAS CONTAINED IN RETENTION POND #5. CORRECTION: VAC TRUCK USED TO CLEAN OUT WET WELL AND AFFECTED AREA, AND LIME APPLICATION. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 11/16/2009 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | BYPASS PUMPING OF LIFT STATION #7; PUMP FILTER CLOGGED CAUSING OVERFLOW INTO ROADSIDE DITCH, LESS THEN 1000 GALLONS, NO WETLAND SYSTEMS AFFECTED. MAINTENANCE PERFORMED TO CLEAR CLOGGING. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 11/9/2008 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | LIFT STATION #7 FAILURE - APPEARS THAT A LOAD OF RAGS WHERE DUMPED INTO SEWER COLLECTION SYSTEM, DISABLING THE CONTROL FLOATS. APPROX. 44,000 GALLONS DAYLIGHTED THROUGH MANHOLE ON W. HYWY 50 INTO DITCH SYSTEM. WETWELL CLEARED AND THE DITCH WAS LIMED AND CLEANED. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 10/6/2008 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | 12" PVC SEWER LINE BREAK ON W. COLONIAL (HYWY 50). LESS THAN 1,000 GALLONS SPILLED OUT. REPAIRED BREAK AND CLEANED SPILL. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 9/2/2008 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | SEWER MAIN BREAK; REPAIRED 12" FORCE MAIN. APPROX. 1,076,000 GALLONS SPILLED. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 5/23/2008 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | 12" SEWER MAIN BREAK ON W. COLONIAL DRIVE (HYWY 50), DEFECTIVE PIPE, APPROX. 20,000 TO 40,000 GALLONS WERE SPILLED INTO LAKE BENNETT. BROWNIE'S ENVIRONMENTAL DISPATCHED TRUCKS TO SUPPORT CITY TO DRAIN LIFT STATION, SHUT OFF VALVE TO ISOLATE SPILL AND KEEP TO A MINIMUM. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 5/12/2008 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | 12" SEWER MAIN BREAK ON W. COLONIAL DRIVE (HYWY 50), APPROX. 10,000 SPILLED OUT INTO INTERSECTION, BROWNIE'S DISPATCHED TRUCKS TO SUPPORT CITY TO DRAIN LIFT STATION, SHUT OFF VALVE TO ISOLATE SPILL AND KEEP TO A MINIMUM. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | LIFT STATION/TRANSMISSION LINE MALFUNCTION AND REPAIR REPORT 6/20/2007 | CITY OF OCOEE | CITY OF OCOEE | DOMESTIC WASTE | RUPTURED 12" SEWER FM, FDOT QUARDRAIL DRIVEN INTO TOP OF PIPE CAUSING WEAK SPOT IN THE HAUNCH OF THE PIPE. PIPE FAILURE OVER TIME. FAILED PIPE WAS REMOVED AND REPLACED. | --- | AS NEEDED | AS NEEDED | UNKNOWN | UTILITY FUND |  |  | COMPLETED | CITY OF OCOEE - UTILITIES | (407) 905 - 3159
Ocoee | Low Impact | SPRINGSHED / WEKIVA RIVER | Lift Station #7 Rehab and Relocation | Utilities/Engineering | City of Ocoee | The rehabilitation by replacement of the existing Lift Station #7 | Existing lift station had reached the end of its life cycle and was experiencing operational issues. The replacement station was reclocated north 900', a new gen set was provided, bypass pumping was provided and an increase in pump's hp. | FDEP #0018234-010 | August 2008 | November 2010 | 1901067 | Bond Proceeds | n/a | n/a | Completed and in Operation | City of Ocoee Utilities Department | (407) 905-3159 |  | Project increased treatment conveyance capacity by approx. 750 ERU per day and took offline an over-capacity forcemain suffering from historical failures.
Orange County | Low Impact | Wekiva Springshed/Study Area | All American Boulevard Improvements | Orange County Public Works (OCPW) | OCU/OCPW | Forcemain | Install 1200 feet of 4-inch forcemain. New forcemain expected to prevent ww leakage. All American Blvd from Clarcona Ocoee to Kennedy | TBD | TBD | TBD | 450000 | OCUD Capital Improvements Program Budget | 5.7843 | See Notes Below | 90% design | Christina Crosby | 407-254-9706 | Christina.Crosby@ocfl.net |  | 1200 | 4 | 100 | NA | 2.7568 | 0.32432 | 0.015847 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County | Low Impact | Wekiva Springshed/Study Area | Clarcona Ocoee - Clarke to Hiawassee Improvements | Orange County Public Works (OCPW) | OCU/OCPW | Forcemain | Install 7800 feet of forcemain. New forcemain expected to prevent ww leakage. Clarcona Ocoee Road from Clarke to Hiawasee | TBD | TBD | TBD | 5510000 | OCUD Capital Improvements Program Budget | 225.5878 | See Notes Below | 20% design | Christina Crosby | 407-254-9706 | Christina.Crosby@ocfl.net |  | 7800 | 24 | 100 | NA | 107.5135 | 12.6486 | 0.61805 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County | Low Impact | Wekiva Springshed/Study Area | Clarcona Ocoee - Ingram to Clarke | Orange County Public Works (OCPW) | OCU/OCPW | Forcemain | Install 4500 feet of 12" forcemain. New forcemain expected to prevent ww leakage. Clacona Ocoee Road from Ingram to Clarke | TBD | TBD | TBD | 1565000 | OCUD Capital Improvements Program Budget | 65.0734 | See Notes Below | 90% design | Christina Crosby | 407-254-9706 | Christina.Crosby@ocfl.net |  | 4500 | 12 | 100 | NA | 31.0135 | 3.6486 | 0.17828 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County | Low Impact | Wekiva Springshed/Study Area | North Pine Hills Forcemain Reroute | Orange County Public Works (OCPW) | OCU/OCPW | Forcemain | Install 11,000 ft of forcemain from Indian Hill Rd to PS #3411. New forcemain will prevent ww leakage. North Pine Hills Road at Indian Hill Road and Clarcona0Ocoee Road | TBD | TBD | TBD | 2000000 | OCUD Capital Improvements Program Budget | 212.0911 | See Notes Below | 60% design | Pollen Jung | 407-254-9779 | pollen.jung@ocfl.net |  | 11000 | 16 | 100 | NA | 101.0811 | 11.8919 | 0.58107 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County | Low Impact | Wekiva Springshed/Study Area | Huggins PS #3006 Replacements | Orange County Utilities (OCU) | None | #REF! | Replace Pump Station #3006 Huggins and North Hastings | TBD | TBD | TBD | 6500000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Construction to begin Fall 2011 | Alan Gay | 407-254-9724 | allen.gay@ocfll.net |  | NA | NA | NA | 31673.9104 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Lake Lawne Gravity Sewer Rehabilitation | Orange County Utilities (OCU) | Possible partnership with City of Orlando - final decision pending | #REF! | Combination of CIPP and point repairs to restore approximately 10,000 LF of 8-inch gravity sanitary sewer including lining or coating 40 manholes. Near 20-22-29-4552-08-001 | exempt | 2006 | ready for bid pending inclusion on SRF list | 1700000 | SRF | 0 | N/A | ongoing | Elizabeth O'Reilly | 407-254-9734 | elizabeth.oreilly@ocfl.net |  | 10000 | 8 | N/A | NA | 0 | 0 | 0 | Gravity sewers generally do not leak, but instead permit I/I. Also gravity pipe repair can cause double-counting with pump station replacements.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Powers Drive/ Hudson Street Wastewater Improvements | Orange County Public Works (OCPW) | OCPW & OCU | #REF! | In addition to upsized storm pipes that go to Lake Robin, project includes replacing FM, gravity line, and manhole. Replacement of the forcemain will reduce leakage of sewage. Near 24-22-28-7573-15-250 | NA | 10/21/08 | On-going | 80000 | OCUD Capital Improvements Program Budget | 0.47721 | See Notes Below | Planned and funded. At 100% construction plans - to go to bid soon | Christina Crosby | 407-254-9706 | Christina.Crosby@ocfl.net |  | 66 | 6 | 100 |  | 0.22743 | 0.026757 | 0.0013074 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Clarcona-Ocoee Road East Utilities Improvements from Clarke Road to Hiawassee Road | Orange County Public Works (OCPW) | OCPW & OCU | #REF! | Forcemain from Avalon Road to Hiawassee Road. 7600 LF 36" FM; 760 LF 30" FM; and 1200 LF 12" FM Many parcels near 35-21-28-0000-00-150 | Unknown | Construction Summer 2009 to Summer 2011 | Summer 2011 | 2400000 | OCUD Capital Improvements Program Budget | 329.7053 | See Notes Below | Bids received; contractor selection by BCC soon; Construction will start Summer 2009 | Bhanu Engineer | 407-254-9716 | Bhanu.Engineer@ocfl.net |  | 7600 | 36 | 100 | NA | 157.1351 | 18.4865 | 0.9033 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Clarcona-Ocoee Road East Utilities Improvements from Clarke Road to Hiawassee Road | Orange County Public Works (OCPW) | OCPW & OCU | #REF! | Forcemain from Avalon Road to Hiawassee Road. 7600 LF 36" FM; 760 LF 30" FM; and 1200 LF 12" FM Many parcels near 35-21-28-0000-00-150 | Unknown | Construction Summer 2009 to Summer 2011 | Summer 2011 | 2400000 | OCUD Capital Improvements Program Budget | 27.4754 | See Notes Below | Bids received; contractor selection by BCC soon; Construction will start Summer 2009 | Bhanu Engineer | 407-254-9716 | Bhanu.Engineer@ocfl.net |  | 760 | 30 | 100 | NA | 13.0946 | 1.5405 | 0.075275 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Clarcona-Ocoee Road East Utilities Improvements from Clarke Road to Hiawassee Road | Orange County Public Works (OCPW) | OCPW & OCU | #REF! | Forcemain from Avalon Road to Hiawassee Road. 7600 LF 36" FM; 760 LF 30" FM; and 1200 LF 12" FM Many parcels near 35-21-28-0000-00-150 | Unknown | Construction Summer 2009 to Summer 2011 | Summer 2011 | 2400000 | OCUD Capital Improvements Program Budget | 17.3529 | See Notes Below | Bids received; contractor selection by BCC soon; Construction will start Summer 2009 | Bhanu Engineer | 407-254-9716 | Bhanu.Engineer@ocfl.net |  | 1200 | 12 | 100 | NA | 8.2703 | 0.97297 | 0.047542 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Clarcona-Ocoee Road West Utilities Improvements from Ingram Road to Clarke Road | OCU project as a part of OCPW Roadway Improvements Project | OCU/OCPW | #REF! | Extend 4500 of 12" Force main from Hobson Road to Ingram Road Many parcels near 33-21-28-0000-00-023 | Unknown | Anticipated start of construction Fall 2009 | Fall 2011 | 665000 | OCUD Capital Improvements Program Budget | 65.0734 | See Notes Below | 90% design | Bhanu Engineer | 407-254-9716 | Bhanu.Engineer@ocfl.net |  | 4500 | 12 | 100 | NA | 31.0135 | 3.6486 | 0.17828 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Maitland Boulevard Extension East form Rose Avenue to Hiawassee Road | Orlando Orange County Expressway Authority (OOCEA) | OOCEA & OCU | #REF! | Relocate 710 LF 4" FM; 1280 LF 16" FM; and 710LF 8" gravity main Many parcels near 30-21-29-0521-00-010 | Unknown | Jan 2007 | May 2008 construction complete | 969000 | OCUD Capital Improvements Program Budget | 3.4224 | See Notes Below | In-service | Bhanu Engineer | 407-254-9716 | Bhanu.Engineer@ocfl.net |  | 710 | 4 | 100 | NA | 1.6311 | 0.19189 | 0.0093764 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Maitland Boulevard Extension East form Rose Avenue to Hiawassee Road | Orlando Orange County Expressway Authority (OOCEA) | OOCEA & OCU | #REF! | Relocate 710 LF 4" FM; 1280 LF 16" FM; and 710LF 8" gravity main Many parcels near 30-21-29-0521-00-010 | Unknown | Jan 2007 | May 2008 construction complete | 969000 | OCUD Capital Improvements Program Budget | 24.6797 | See Notes Below | In-service | Bhanu Engineer | 407-254-9716 | Bhanu.Engineer@ocfl.net |  | 1280 | 16 | 100 | NA | 11.7622 | 1.3838 | 0.067616 | Nutrients Reduced = (gph*24hrs)*(3.785 L/gal)*(32.6mg/L)*(0.0000022 lb/mg) in Lbs/day
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Lakewood Forest and Tealwood Cove Wastewater Improvements | Orange County Utilities (OCU) | None | #REF! | Pump Station #3045 will be removed and relocated plus removal of existing force main and installation of 800 feet of gravity sewer. 29-21-29-4940-00-230 | None | Design started Feb 2009 | Design is Ongoing | CIP Project | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Design started Feb 2009 and is ongoing. Project will bid in Spring 2010 | Steve Beasley | 407-25449729 | Stephen.Beasley@ocfl.net |  | NA |  |  | 1696.3 | 0.14167 | 0 | 0.00092296 | Assume 11% of flow is leaked for 1.5 hours.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | NWSA Huggins PS | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3006 Near 13-22-28-7575-03-010 | None | Fall 2009 | Fall 2010 | 814000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | In-service | Alan Gay | 407-254-9724 | Alan.Gay@ocfl.net |  | NA | NA | NA | 31673.9104 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year. | 1387317.2763 | 0.14167
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Hiawassee Rd. | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3038 26-22-28-0000-00-003 | None | Pre-2007 | Spring 2007 | 2000000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | In-service | Alan Gay | 407-254-9724 | Alan.Gay@ocfl.net |  | NA | NA | NA | 73862.7708 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | NWSA PS "B" | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3411 06-22-29-5844-00-110 | None | Pre-2007 | Spring 2007 | 2000000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | In-service | Alan Gay | 407-254-9724 | Alan.Gay@ocfl.net |  | NA | NA | NA | 50734.74 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Laurel Park | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3099 20-23-29-5360-00-170 | None | 2006 | April 2008 | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | 0.33688 | Complete | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | Unknown | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Chateau Orleans | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3133 21-23-29-5361-00-211 | None | 2006 | April 2008 | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | 0.33688 | Complete | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | Unknown | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Sherry Drive | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3225 12-23-30-1280-00-001 | None | 2007 | January 2008 | 229050 | OCUD Capital Improvements Program Budget | 0.33688 | 0.33688 | Complete | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | Unknown | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Citrus Cove | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3251 33-21-29-1341-00-002 | None | 2007 | January 2008 | 244320 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Complete | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | 2201.8683 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Magnolia Bay | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3302 32-21-29-7134-03-301 | None | 2007 | January 2008 | 290130 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Complete | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | 3286.9737 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Sun Bank PS # F3169 (fka 3001) | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #F3169 19-22-29-6954-08-051 | None | Fall 2009 | Summer 2010 | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | 0.33688 | Planned | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | Unknown | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Lake Sherwood Hills | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3230 23-22-28-0000-00-053 | None | Fall 2009 | Summer 2010 | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Planned | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | 310.7563 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Lonesome Pines PS # F3195 (fka 3012) | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #F3195 Near 13-22-28-5175-04-040 | None | Fall 2009 | Summer 2010 | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | 0.33688 | Planned | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | Unknown | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Breezewood Sub | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3014 12-22-28-0885-00-000 | None | TBD | TBD | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Planned | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | 4593.5204 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Lake Sparling 1 | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3028 01-22-28-0000-00-005 | None | TBD | TBD | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Planned | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | 529.1225 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Lake Sparling 2 | Orange County Utilities (OCU) | None | #REF! | R/R of wastewater pump station #3202 01-22-28-4743-00-040 | None | TBD | TBD | 250000 | OCUD Capital Improvements Program Budget | 0.33688 | See Notes Below | Planned | Herb Collado | 407-254-9725 | Heriberto.Collado@ocfl.net |  | NA | NA | NA | 2575.6129 | 0.14167 | 0 | 0.00092296 | Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Toilet VIP | OCU | None | #REF! | Water conservation voucher program: OCU provides up to 2 vouchers for households replacing a 3.5 gal/flush toilet in homes built prior to 1992. County-wide. During 2006-2008 program, notification letters went to 687 addresses in 32703 zip code and 1205 addresses in 32712. In 2009, notification letters went to 259 addresses in 32703 and 150 addresses in 32712. | None | April 2006 | June 2009 | 445382 | OCUD & SFWMD | Unknown | Unknown | Ongoing. 78 vouchers issued to date. 11 vouchers in 32703 zip and 36 in 32712 zip (remaining unknown). | Jackie Torbert | 407-254-9830 | jacqueline.torbert@ocfl.net |  | NA | NA | NA | NA | NA
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Pre-rinse spray valve retrofit program | OCU | None | #REF! | Water conservation valve replacement program: OCU replaced valves on existing pre-rinse spray valves that used more than 1.6 gal/minute. 7 program respondents were in 32703 zip and 1 was in 32712 zip. | None | July 2007 | July 2009 | 29503.5 | OCUD & SFWMD | Unknown | Unknown | Completed | Jackie Torbert | 407-254-9830 | jacqueline.torbert@ocfl.net |  | NA | NA | NA | NA | NA
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Water Watch | OCU | None | #REF! | Water conservation patrol program. : OCU staff patrols commercial and residential properties for water ordinance violators. 242 water violations in zip codes 32713-32703 | None | April 2001 | Ongoing | $1138699 to date | OCUD | Unknown | Unknown | Ongoing | Jackie Torbert | 407-254-9830 | jacqueline.torbert@ocfl.net |  | NA | NA | NA | NA | NA
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | Mobile Irrigation lab audit | OCU | None | #REF! | Water conservation audit program: OCU staff provides free high water user audits and points out system deficiencies. 28 audits in zips 32712-32703 | None | 2000 | Unknown | 75000 | OCUD | Unknown | Unknown | Ongoing | Jackie Torbert | 407-254-9830 | jacqueline.torbert@ocfl.net |  | NA | NA | NA | NA | NA
Orlando | Low Impact | Little Wekiva River | Fairview Shores - North Service Area | City of Orlando |  | New Sanitary Service + 2 Stormceptor Units | Improvements of the sanitary sewer, drainage and roadway. Installed new sanitary force main, lift station(#65) and gravity pipes in area with septic tanks to reduce nutrient seepage into groundwater table. Installed 2 Stormceptors to capture gross pollutants before reach lake. | 40-095-97536-1 | 2006 | 2008 | 4522401 | Multiple Sources including Stormwater Utility & Wastewater General Construction Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | Rio Grande Sanitary Sewer | City of Orlando |  | New Sanitary Service | Installation of gravity lines in area with septic tanks to reduce nutrient seepage into groundwater table |  | 1999 | 2000 | 1622124 | Wastewater General Construction Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | West Lake Fairview Sanitary Sewer | City of Orlando |  | New Sanitary Service | Installation of sanitary sewer in area with septic tanks to reduce nutrient seepage into groundwater table |  |  |  | 6000000 | Wastewater General Construction Fund |  |  | Envisioned | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River, Little Wekiva Canal | Mercy Dr Sewer Rehab | City of Orlando |  | Sanitary Force Main and Pipe Replacement | Replaced Force Main on Mercy Dr from S of Princeton to LS #45. Connected or replaced new sanitary pipe to existing pipes. |  | 2000 | 2002 | 878400 | Wastewater Renewal and Replacement Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net | Prior to replacement, Force Main failure had caused 2 major overflows into Lake Lawne
Orlando | Low Impact | Little Wekiva River, Little Wekiva Canal | Regent Ave Force Main 2613 | City of Orlando |  | New Sanitary Force Main | Construction of force main along Silver Star Rd connecting Lift Station #37 to existing 24" Force Main and 24" gravity sewer on Mercy Dr |  |  |  | 2000000 | Wastewater Collection System Construction Fund |  |  | Envisioned | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net | Design Complete; Waiting for additional $1 Million in funding
Orlando | Low Impact | Little Wekiva River | Lift Station #37 Improvements | City of Orlando |  | Sanitary Lift Station Replacement | Lift station is one of oldest in City. The wet well is made of brick and starting to fail. Lift station will be replaced with pre-cast concrete with a liner and bigger capacity. A new pumping station and associated components will be installed, along with a standby generator. Gravity pipes in area will also be replaced. |  | 6/2009 | Ongoing | 1400000 | Wastewater Collection System Construction Fund |  |  | Ongoing | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | Lift Station #93 Improvements | City of Orlando |  | Sanitary Lift Station Replacement | Lift Station was relocated and completely rebuilt with new, upgraded equipment, including a generator not present at previous location |  | 1999 | 2001 | 767632.31 | Wastewater General Construction Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | Lynx Facility | City of Orlando |  | New Sanitary Service + Lift Station | Installation of sanitary sewer in area with septic tanks to reduce nutrient seepage into groundwater table |  | 2006 | 2007 |  |  |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | West Lake Silver Phase 1 & 2 | City of Orlando |  | New Sanitary Lift Station | Installation of Lift Station in new commercial area |  | 1999 | 2000 |  |  |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Springshed | Master Pump/Equilization at Water Conserv II | City of Orlando |  | Sewage Treatment Upgrades | Installation of Equalization Basin will regulate flows to allow for enhancement of treatment and overall reduction of TN & TP in effluent. (Average Flow = 14 MGD (Daily ranges: 7-25 MGD)) |  | 1/09 | Ongoing | 13009575 | Wastewater General Construction Fund | See Comments |  | Ongoing | Paul Deuel | (407) 246-3510 | Paul.Deuel@cityoforlando.net | Estimated 15-20% TN & TP Reduction in effluent; Expected Completion Date = June 2011
Orlando | Low Impact | Springshed | Phase One Treatment Plant Improvements at Water Conserv II | City of Orlando |  | Sewage Treatment Upgrades | Installation of Internal Recycle Pump + Improvements to Aeration and Secondary Clarifier |  | 2011 | 2014 | 12000000 | State Revolving Fund | See Comments | Under Design | Planned & Funded | Paul Deuel | (407) 246-3510 | Paul.Deuel@cityoforlando.net | Estimated 20% NOx Reduction in effluent
Orlando | Low Impact | Little Wekiva River | Lift Station #85 VFD's | City of Orlando |  | Sanitary Lift Station Improvements | Installation of Variable Frequency Drives that will extend life of pump motors, which prevents possibility of overflows. In addition, will be more energy efficient at a future cost savings to City. |  |  |  | 2830 | Wastewater General Construction Fund |  |  | Envisioned | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | Line Sanitary Sewers | City of Orlando |  | Line Sanitary Sewers | Line sewers to prevent untreated sewage from escaping through cracks and joints. Project will reduce nutrient seepage into groundwater table. |  |  |  | 2500 | Wastewater Collection System Construction Fund |  |  | Planned & Funded | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net | 0.5 miles of pipe are expected to be lined within basin
Orlando | Low Impact | Little Wekiva River | Sanitary System Inspections | City of Orlando |  | Sanitary System Inspections | Conduct proactive inspections and perform routine maintenance on lift stations and sanitary lines. Identify problem areas and increase maintenance frequency or perform repairs to prevent overflows from occurring. In addition, assist with Sunshine State One-call of Florida ("Call Before You Dig" / Line Locates). |  |  | Ongoing |  | Wastewater Collection System Construction Fund |  |  | Ongoing | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Apopka |  |  | Manholes on Alabama & 8th Street | City of Apopka/Public Services |  | Spraycoat Brick Manholes | Relined manholes with supercoat spray to prevent leaking between bricks |  | December 2008 | December 2008 | 2325 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka |  |  | Manholes on Little St & 9th St | City of Apopka/Public Services |  | Spraycoat Brick Manholes | Relined manholes with supercoat spray to prevent leaking between bricks |  | December 2008 | December 2008 | 2325 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka |  |  | Manholes on Park Ave | City of Apopka/Public Services |  | Spraycoat | Spraycoat manholes with supercoat, rehabbed manhole |  | January 2009 | January 2009 | 2450 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka |  |  | Manholes in Charleston Park subdivision | City of Apopka/Public Services |  | Spraycoat | Spraycoat due to H2S dissolving precast manhole. Prevent H2S from weakening structure. 8 manholes |  | January 2009 | January 2009 | 21320 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka |  |  | Lift Station 10 Wet Well | City of Apopka/Public Services |  | Spraycoat | Rehab Lift Station wet well due to H2S dissolving concrete walls |  | February 2009 | February 2009 | 12975 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
FLDOH |  | parcel | pretreatment for OSTDS | county health departments | applicant, if applicable local jurisdiction and CHD | wastewater management | include higher pretreatment in an OSTDS (new or old) |  | various | various | variable | applicant | either less increase or some decrease; depending on site conditions and if this is a new establishment or a better system replacing an old OSTDS | site-specific | ongoing |  |  |  | Currently, lot-specific requirements (e.g. authorized sewage flow) would prompt such treatment. Future implementation or expansion depends on local and state regulations. To quantify this, a review of permits issued since 1/2007 would be necessary.
FLDOH |  | BMAP-Area | sanitary survey | local jurisdiction | CHD | wastewater management | such surveys can ID and eventually remedy sanitary nuisances due to, e.g. surface discharge of sewage | n/a | depends on jurisdiction |  |  | needs dedicated funding for sustained effort |  | depends on conditions | occasionally occurring |  |  |  | A mandate and funding by local or state entities appears to be a key issue that needs to be in place to allow a sustained effort. Some counties (outside the Wekiva BMAP) have established such projects or programs. Need clear goals and directives from jurisdictions. Need clarification on authority and roles of participants in the survey (e.g. to enter parcels)
FLDOH |  | parcel | (new onsite sewage system construction permits) (not a nitrogen reduction project but relevant) | county health departments | applicant | wastewater management | new onsite system construction | n/a | various | various | variable | applicant | negative (additional nitrogen input and load) | 29 lbs TN input; 17.4 lbs TN load (Roeder 2008); 16.3 lbs NO3-N (Mactec 2010) | ongoing |  |  |  | to quantify this, a review of permits issued since 1/2007 would be necessary
FLDOH |  | parcel | (repair and modification permits for onsite sewage systems) (not a nitrogen reduction project but relevant) | county health departments | applicant | wastewater management | repairs and modifications to existing onsite sewage systems | n/a | various | various | variable | applicant | depending on site conditions, some reduction in high water table areas | up to ~12 lbs reduction in GW load when system is currently underneath the water table and is lifted 24" above it (most will be less). This is based on:29 lbs TN input; 17.4 lbs TN load (Roeder 2008); 16.3 lbs NO3-N (Mactec 2010) | ongoing |  |  |  | to quantify this, a review of permits issued since 1/2007 would be necessary
FLDOH |  | Wekiva Study Area | DOH 2006/2007 Wekiva Study task 1 | DOH | Ellis&Associates | Research and Study | measured septic tank effluent and shallow groundwater concentrations underneath the drainfield | n/a | 1/2007 | 6/2007 | ~200,000 | legislative appropriation | (results indicated an increase compared to the earlier MACTEC assessment) | provided data to refine nitrogen input and load assessment | completed | Elke Ursin | 850-245-4070 | elke_ursin@doh.state.fl.us | http://www.doh.state.fl.us/environment/ostds/wekiva/task1/FinalReport.zip
FLDOH |  | Wekiva Study Area | DOH 2006/2007 Wekiva Study task 2 | DOH | Otis Environmental Consultants | Research and Study | estimated nitrogen removal in soil underneath drainfields as a function of pretreatment, texture and water table conditions | n/a | 1/2007 | 6/2007 | 25000 | legislative appropriation | n/a | provide tool to estimate nitrogen reduction in soil under drainfields | completed | Elke Ursin | 850-245-4070 | elke_ursin@doh.state.fl.us | http://www.doh.state.fl.us/environment/ostds/wekiva/task2/FinalReport_06-07.pdf
FLDOH |  | Wekiva Study Area | DOH 2006/2007 Wekiva Study task 3 | DOH | Dr. L. Young, U of Florida | Research and Study | estimate nitrogen inputs for the Wekiva Study Area | n/a | 1/2007 | 6/2007 | 25000 | legislative appropriation | n/a | estimate of nitrogen input for Wekiva Study Area | completed | Elke Ursin | 850-245-4070 | elke_ursin@doh.state.fl.us | http://www.doh.state.fl.us/environment/ostds/wekiva/task3/FinalReport06-07.pdf
FLDOH |  | Wekiva Study Area | DOH 2006/2007 Wekiva Study task 4 | DOH | n/a | Research and Study | review a range of possible nitrogen management strategies for onsite systems in the Wekiva Study Area | n/a | 1/2007 | 6/2007 | staff report |  | n/a | provides some estimates for nitrogen reduction options | completed | Eberhard Roeder | 850-245-4070 | eberhard_roeder@doh.state.fl.us | http://www.doh.state.fl.us/environment/ostds/wekiva/task4/FinalReport.pdf
FLDOH |  | Wekiva Study Area | DOH 2006/2007 Wekiva Study final report | DOH | see above | Research and Study | summarizes task 1-4 | n/a | 1/2007 | 6/2007 | ~250,000 (see above) | legislative appropriation | n/a |  | completed | Elke Ursin | 850-245-4070 | elke_ursin@doh.state.fl.us | http://www.doh.state.fl.us/environment/ostds/wekiva/TaskFinal/2006WekivaFinal.pdf
FLDOH |  | Wekiva Study Area | revised Wekiva Study Area input and loading estimates | DOH | n/a | Research and Study | estimate contributions to input and loading of nitrogen by various sources, building on MACTEC2007 report, DOH 2006/2007 study results and other information | n/a | 7/2007 | 5/2008 | staff report |  | n/a | estimate of nitrogen input and loading for Wekiva Study Area | completed | Eberhard Roeder | 850-245-4070 | eberhard_roeder@doh.state.fl.us | http://www.doh.state.fl.us/environment/ostds/wekiva/WekivaEstimateFinal.pdf
FLDOH |  | statewide | inventory of OSTDS | DOH | EarthSteps and GlobalMind | wastewater management | created parcel attribute of wastewater disposal method for each improved parcel based on known OSTDS permits, known sewer service areas, and estimates for unknown parcels | n/a | 10/2008 | 6/2009 | 150000 | legislative appropriation | n/a | provides locational information for OSTDS and allows revised estimates of number of OSTDS | completed | Elke Ursin | 850-245-4070 | elke_ursin@doh.state.fl.us | final report is at http://www.doh.state.fl.us/environment/ostds/research/07-01-09Materials/Statewide_Inventory_OSTDS.pdf; comparison with 2004/2005 assessment for the Wekiva Study Area would be of interest; some checking will be useful if local utilities provided data in any particular watershed; data have been provided to Catherine Murray in the Watershed Evaluation and TMDL Development section;
FLDOH |  | Wekiva Basin | MACTEC 2010 report | DEP/SJRWMD
Oakland | [5 empty] | Septic Tank CPP policies | Investigate feasibility of community septic system |  |  |  |  | Town |  |  | Spring, 2011 | Roland Magyar | 407-656-1117 ext 12 | planning@oaktownusa.com
Assumptions and Calculations (see Equations and References worksheet for more detail): | [7 empty] | Total: | [12 empty] | Total Lb/day | 1.2965
1. Gravity Sewers: Assumed no contribution to springshed; gravity sewers generally do not leak, but instead permit I/I. Also gravity pipe repair can cause double-counting of leakage with pump station replacements. | [20 empty] | Total Lb/year | 473.2396
2. Forcemains: Used OCU Standard specifications (L = S*D*P^0.5/148,000) for calculating max leakage after replacement. From Culver, et.al. assumed that newer pipes leaked 2% and older pipes leaked 17%. In other words L (calculated using OCU Standard Specs) = 2%. Prior to replacement, multiplied by 17/2.
32.64 | Typical Nitrate for domestic ww, per 2005 Marion County Planning Dept. Report
3. Pump Stations: Used pump station design flow spreadsheet for flows. Used actual OCU SSO reports to assume 1241 gallons of overflow per event and assumed replacement of a PS would prevent 1 SSO per year.
4. Facility improvements: Used pre-post design nutrient estimates to calculate nutrient reduction.
5. Storage & Repump: Assumed no contribution or reduction from basin.
6. Public Outreach: unknown
Notes:
(1) Pipe Lengths approximated
Note on D33: changed to Tier 10 on 5/20/04 at request of Bill Scott
Note on D34: changed to Tier 10 on 5/20/04 at request of Bill Scott
Note on D37: email dated 1/12/04 states no problem at this time. new panel, new well, valve box. Property and no access avail. Swapped from Tier 10 to Tier 11 on 5/20/04 on large crane truck list, Larry Mansfield the operator for this tier
Note on D38: old ps # = 305-23
Note on H38: NEW PS # WILL BE:F3169
Note on D40: original ps # 306-63 THIS STATION NEEDS REAL ESTATE TO BE REBUILT
Note on D41: approved for construction in 1970 GIS file number is 392
Note on D42: approved for construction in 1970
Note on D43: as built in 1976