## Combined
Entity | Credit Ranking | FDEP Comments | Subbasin | Project Name | Lead Entity | Project Partners | Project Type | Project Detail | ERP # | Project Start | Project End | Project Cost | Funding Source(s) | Estimated Nitrate Reduction (lbs/yr) | Nitrate Reduction Calculation Method | Status | Contact Name | Contact Phone | Contact Email | Comments
|  |  | Springshed, Blackwater Creek, Rock Springs Run, Wekiva River, Little Wekiva River, or Little Wekiva Canal |  |  |  | CDS, Baffle Box (1st Gen.), Baffle Box (2nd Gen.), Dry detention, wet detention, swales, drainage wells, alum treatment, sewering, etc. | 2-3 sentences; include treatment volume, retention time, # homes sewered, etc. as applicable | "Exempt" if applicable; see guidelines for details re: exempt projects | Mo/Yr | Mo/Yr or "Ongoing" | Specify capital vs. O&M, as applicable | Stormwater utility, ad valorem, 319, etc. |  |  | Completed; Started; Planned & Funded; Envisioned (unfunded); or Ongoing |  |  |  | Optional
Altamonte | High Impact |  | Little Wekiva | Keller Rd WWTF Reclaimed water storage pond | City of Altamonte Springs | N/A | Reclaimed water storage pond | Provide 7.8 MG of reclaimed water storage | N/A | 04/2009 | ongoing |  |  |  |  | Started | Jay Diceglie | 407-571-8338 | jvdiceglie@altamonte.org
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | MAC Professional Center | Montgomery Executive Center Associates LLC | Private | Stormwater system | Construct an underdrain type stormwater retention system for a new Professional Office Bldg. | SJRWMD ERP Permit 40-117-96445-2 | 01/03/2007 | 3/2009 |  | Private |  |  | complete
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Brantley Terrace Condo | Pulte Home Corporation | Private | Stormwater system | PHASE THREE OF LAKE LOTUS CLUB, A MULTI-FAMILY CONDOMINIUM DEVELOPMENT | SJRWMD ERP Permit 40-117-76048-2 | 040/7/2000 | 05/2007 |  | Private
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Bank Atlantic at Altamonte Mall | BankAtlantic Bancorp Inc | Private | Stormwater system | Demo existing site & construct a 4,500 sf bldg with associated parking, drive isles, etc. & a water management system with on site retention to retain the PAV with a connection to a FDOT drainage culvert on site located in an existing drainage easement. | SJRWMD ERP Permit 42-117-10938-1 | 07/19/2007 | 3/2008 |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Essian | Essian Construction LLC | Private | Stormwater system | Construct stormwater management system to serve a 6,400 sf retail building with associated parking and impervious totaling 0.30ac | SJRWMD ERP Permit 42-117-110916-1 | 9/7/2007 | 12/2009 |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | West Altamonte Operations & Admin Center | City of Altamonte Springs | N/A | Stormwater system | Reconstruction of an existing city facility to accommodate a new 23,000 +/- square foot office building, new covered equipment/vehicle storage areas and reconfiguration of existing drive and parking areas. | SJRWMD ERP Permit #40-117-108457-1 | 4/6/2007 | 3/2009 |  |  |  |  | complete
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Seminole Community College - Altammonte Springs | Seminole Community College - Altamonte Springs | Private | Stormwater system | Construction of a stormwater drainage system to route drainage from a 100,000 sf bldg, paved parking, sidewalks, & future phases. | SJRWMD ERP Permit #40-117-29137-3 | 3/3/2006 | 12/2007 |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Centex Homes | Sutton Place Townhomes | Private | Stormwater system | Construction of roads, bldgs, & parks for a 62-unit townhome project. Mod of 2 existing controls in that the weirs are to be modified. | SJRWMD ERP Permit #40-117-22012-10 | 5/29/2007 | 10/2008 |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Spring Centre III | Keyes Assett Management inc. | Private | Stormwater system | Modify an existing stormwater management system to serve Spring Centre South Commercial Center. The existing system was permitted by Florida Department of Environmental Regulation. | SJRWMD ERP Permit #40-117-63585-1 | 4/26/2000 | 10/2007 |  | Private development | [6 empty] | Parcel # 02-21-29-517-0000-0030
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Medallion Convenience Store @ Douglas | MDC 2 LLC (Medallion Conv Store) | Private | Stormwater system | To demolish existing gas station, convenience store & carwash & rebuild a gas station, convenience store & car wash. | SJRWMD ERP Permit #40-117-107214-1 | 1/15/2008 | under construction |  | Private development | [6 empty] | Parcel #01-21-29-5CK-290A-0050, 1110 Douglas Ave
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Mind Comet Office Bldg | Mind Comet Corp. | Private | Stormwater system | Construction of an office bldg with associated asphalt drives, concrete walks & stormwater treatment facility. | SJRWMD ERP Permit #42-117-102382-3 | 5/10/2006 | 11/2007 |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Gateway Clinic | FF South & Company, Inc. | Private | Stormwater system | Construction of Gateway Crossings commercial development. This development consists of retail/commercial/shopping buildings with associated parking, landscaping, utility and stormwater infrastructure. Stormwater runoff is managed in a 5 acre dry online retention/detention pond. the project also includes paving of a portion (1,000 LF +/-) of Arletta Street tha twill provide access to the site. Stormwater runoff from Arletta Street will be managed onsite. | SJRWMD Permit #40-117-64342-8 | 3/28/2008 | under construction |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | TriCity Electric | TricCity Electric | Private | Stormwater system | Construction of 4,000 s.f. warehouse w/parking and future retention. | SJRWMD Permit #40-117-116413-1 | No permit req'd | 5/2009 |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Altamonte Town Center Amenities & Cranes Roost Lakeshore Grading | City of Altamonte Springs | N/A |  | Amphitheater improvements; Faux Bridges; Overlook; Promenade "A" (including the public plaza & park); and Promenade "B." Installation of a sheet pile wall and associated lakeshore grading along Promenades "A" & "B" (Old Shorecrest Drive). | SJRWMD Permit #4-117-28902-7 | 5/24/2005 | **
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Altamonte Town Center, Phase 5 | Unicorp National Developments Inc | N/A | Stormwater system | Secondary drainage system for the 5.45 ac Phase 5 development of Altamonte Springs Town Center & contains approximately 60LF of 15" RCP, 240 LF of 24" RCP, 375 LF of 14" x 23" ERCP, and 12 drainage structures. | SJRWMD Permit #40-117-28902-6 | 2/15/2005 | ** |  | Private Development | [6 empty] | See related SJRWMD Permits 40-117-91528 (1 - 5) Altamonte Town Center Developments
Altamonte | TBD | Explain WQ benefits | Little Wekiva | Cranes Roost Blvd Roadway Improvements & Altamonte Town Center (West Side) | City of Altamonte Springs | N/A | Stormwater system | Revised configuration of the previously permitted exfiltration system south of Shorecrest Dr and construction of a public plaza and park over the underground exfiltration system south of Shorecrest Dr. | SJRWMD MSSW Permit #40-117-28902-5 | 10/9/2003 | ** | [8 empty] | See related SJRWMD Permits 40-117-91528 (1 - 5) Altamonte Town Center Developments
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Altamonte Town Center Phase I | Altamonte Springs Investments LLC | N/A | Stormwater system | Approval from the St. Johns River Water Management District (SJRWMD) is requested to construct the proposed improvements, which include the following: Re-development of the existing developed site, including demolition of existing buildings and parking lots, followed by construction of new buildings and parking deck structures; and Construction of pollutant removal structures to improve the quality of stormwater runoff discharged to Cranes Roost Lake. | SJRWMD Permit #40-117-51695-2 | 6/7/2004 | ** |  | Private development | [6 empty] | See related SJRWMD Permits 40-117-91528 (1 - 5) Altamonte Town Center Developments
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Altamonte Mall Theater & Restaurant Addition | General Growth Properties, Inc. | Private | Stormwater system | The project consists of alterations to the existing Altamonte Mall to develop a project to be known as the Altamonte Mall Theater and Restaurant Addition, a 14.4 acre project. The project includes a 75,000 sf theater building, two parking decks, two restaurants, stormsewer system alterations and two baffle boxes.The baffle boxes will provide a level of treatment for surface water runoff. | SJRWMD Permit # 40-117-85489-1 | 8/29/2002 |  |  | Private development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Crossroads |  | Private | Stormwater system
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | Bruster's Ice Cream | G&G Family Enterprises | Private | Stormwater system | Construct an underground storage/exfiltration system that will then be tied into the storm inlet located at the corner of Richbee Dr & SR 434. | SJRWMD Permit #42-117-103061-1 | 2006-03-10 | 01/2007 |  | Private Development
Altamonte | TBD | Need to demonstrate that project goes beyond that required to mitigate new development or construction | Little Wekiva | People's First Community Bank - Lake Brantley | People's First Community Bank | Private | Stormwater system | Construction of a new 1-story drive-in bank with associated asphalt paving & concrete walks. | SJRWMD Permit #42-117-112889-1 | 9/13/2007 | 9/2008 |  | Private Development
Altamonte | Study |  | Little Wekiva | Lake Orienta, Adelaide and Florida Hydrologic/Nutrient Budgets and Management Plans | City of Altamonte Springs | N/A | Hydraulic and Nutrient loading study | City contracted with consultants, PEC and ERD, to determine the phosphorous and nitrogen loadings on Lakes Orienta, Florida and Adelaide. Treatment options were recommended based on the study results. | N/A | 2006 | 07/2009 |  |  |  |  | Completed | Danielle Marshall | 407-571-8331 | dmarshall@altamonte.org
FDOT D5 | 4 Medium Impact |  | Springshed | FM: 410983-1 | FDOT D5 | NA | 4 Wet Detention | SR 50: from Avalon Road to SR 429/Western Beltway | 40-095-94790-3 | Scheduled Start: 2013 | Anticipate Completion: 2015 | N/A | Legislative | TBD | TBD | Design 100% | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | Design build project. Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | 2 Medium Impact |  | Springshed | FM: 409870-1 | FDOT D5 | NA | Dry Retention and Wet Detention | Old CR44B: Add lanes US441 to SR44. | Pending | Pending Final Design and Funding | Pending | N/A | Legislative | TBD | TBD | Design 30% | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | Treatment of existing imperv. w/ new impervious. Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | 2 Medium Impact |  | Little Wekiva River | FM: 240231-3 | FDOT D5 | NA | 2 Dry Retention | Add lanes SR 434: from SR 414 (Maitland Blvd.) to Lotus Landing Blvd. | 40-117-94187-1 | Pending Final Design and Funding | Pending | N/A | Legislative | TBD | TBD | Design | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | Permitted with FM: 240231-2. Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | 2 Medium Impact |  | Little Wekiva River | FM: 240231-2 | FDOT D5 | NA | 2 Exfiltration | Add lanes SR 434: from Lotus Landing Blvd. to SR 436 | 40-117-94187-1 | Construction Started 2007 | Construction Completed 2008 | N/A | Legislative |  |  | Completed | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | treatment of existing imperv. w/ new impervious. Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | 2 Medium Impact |  | Springshed | FM: 239535-2 | FDOT D5 | NA | 2 Wet Detention | SR 50: Add lanes from E ramps of Turnpike to Avalon Rd. | 40-095-108657-1 | Design Complete. Awaiting funding for construction | Pending | N/A | Legislative | TBD | TBD | Design 100% / Pending Funding | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | Goes with FM: 410983-1. Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | 2 Med Impact |  | Little Wekiva River | FM: 239496-2 | FDOT D5 | NA | 2 Wet Detention | SR 423: Add lanes from Shader Rd. to SR424 (Edgewater Dr.) | 40-095-64860-5 | Design Complete. Awaiting funding for construction | Pending | N/A | Legislative | TBD | TBD | Design 100% / Pending Funding | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | SW treatment designed to "Apopka" criteria. Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | 7 Medium Impact |  | Springshed & Harris Chain Surface runoff | FM: 238314-1 | FDOT D5 | NA | 3 Wet Detention and 3 Dry Retention, 1 Exfiltration | SR 500 | 4-069-87720-1 | 2004 | 2007 | N/A | Legislative | TBD | TBD | Complete | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | This project has multiple wet detention and dry retention systems which discharge to either the Harris Chain or Wekiva Springshed. Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | 2 Medium Impact |  | Wekiva River | FM: 239289 | FDOT D5 | NA | Wet Detention and Dry Retention | SR 438 | 40-095-51769-1 |  |  | N/A | Legislative | TBD | TBD | Complete | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | Project Treatment Summary Report on file regarding treatment above and beyond.
FDOT D5 | Low Impact |  | Wekiva River | FM: 238406 | FDOT D5 | NA | Ditch Block System | SR 44 | 40-069-26637-1 | 1999 | 2002 | N/A | Legislative | TBD | TBD | Complete | Primary: Patrick Muench, P.E. Secondary: Robert J. Potts | (386)-943-5000 | Patrick.Muench@dot.state.fl.us | Project Treatment Summary Report on file regarding treatment above and beyond.
Mt. Dora | Low Impact |  | Springshed | Gilbert Park NSBB | City of Mount Dora | NA | 2nd Generation Baffle Box Eliminate Retention Pond / Alternative Treatment | Installed Suntree 6-12-94 NSBB at Tremain St & Liberty St. Filled in open pit retention pond to create usable park space on lakefront. | NA | 2008-10-16 | 2008-10-30 | 54000 | City of Mount Dora / Lake County Water Authority |  |  | Completed | Paul Ritter | 352-735-7150 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | Gilbert Park Pipe Relining | City of Mount Dora | NA | Pipe repair | Existing CMP pipe rusted and collapsing. 150 LF of pipe relinged with fused HDPE. | NA | 2009-01-05 | 2009-01-15 | 3500 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7152 | ritterp@cityofmountdora.com
Mt. Dora | Medium Impact |  | Springshed | 4th Ave. & McDonald St. Retention Pond Restoration | City of Mount Dora | NA | Retention Pond Restoration | Removed accumulated sediment and debris from retention pond. Installed new inlet pipe to prevent eosion. Replaced erosion protection around inlet pipes. | NA | 2009-03-01 | 2009-03-30 | 3000 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | Lakeside Inn Pipe Rapair | City of Mount Dora | NA | Pipe repair | Existing 32" dia VCP had cracked and was failing. 100 LF of fused HDPE was slip-lined into the pipe and upstream under the rail road tracks. | NA | 2009-08-01 | 2009-08-30 | 25000 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7144 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | Grandview St. Pipe Sealing | City of Mount Dora | NA | Pipe repair | Joints in 42" dia RCP pipes under Rail Raod and park were leaking or failing. All points of seapage were sealed. | NA | 2009-09-10 | 2009-09-20 | 14000 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7151 | ritterp@cityofmountdora.com
Mt. Dora | Medium Impact |  | Springshed | Lake John Rehabilitation | City of Mount Dora | FDEP, LCWA | Wetland Rehabilitation | Lake Johns is part of the greater Lake Gertrude Basin project. The wetland was excavated to remove excess sediment and exotic vegetation. Step-wise drainage was re-established between the three onds and new vegetation was planted. | NA | 2009-01-10 | 2009-12-30 | 1200000 | FDEP, City of Mount Dora | Unknown |  | Completed | Mark Rudowske | 352-735-7151
Mt. Dora | Low Impact |  | Springshed | Pine & Jackson Pipe Repair | City of Mount Dora | NA | Pipe Repair | Replaced crushed section of 36x54 CMP to allow proper drainage of NE area of city. | NA | 2010-02-04 | 2010-02-10 | 3000 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | 1552 Hilltop Dr Pipe Relining | City of Mount Dora | NA | Pipe repair | Reline existing CMP pipe with HDPE to eliminate sink hole formation and erosion into Lake Nettie. |  | 2010-06-10 | 2010-07-01 | 13000 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | 4th Ave. Stormwater Project | City of Mount Dora | Lake County Water Authority | Stormwater System Upgrade | Increased pipe size under Rail Road tracks to increase discharge. Installed additinoal inlet structures. Installed Suntree 5-10-102 NSBB under Donnelly St. to create treatment train with unit at 4th Ave & lakefront. | NA | 2010-09-01 | 2010-11-20 | 325000 | City on Mount Dora/ Lake County Water Authority | est. 200 lbs/yr | EMC(Loading/yr) X BMP efficiency | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Medium Impact |  | Springshed | Hwy 441 & Hwy 46 StormTech Installation | Lake County | Lake County | Exfiltration System | Installed StormTech System: 100 LF in-line arrangement with "Isolator Rows" at each end for maintenance. | NA | 2010-12-05 | 2010-12-15 | Included in overall road project | Lake County |  |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | Sylvan Dr Pipe Re-Lining | City of Mount Dora | NA | Pipe Repair | Re-lined failing CMP pipe into Lake Gertrude. | NA | 2011-03-15 | 2011-03-25 | 3500 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Medium Impact |  | Springshed | S. Johns St StormTech Installation | City of Mount Dora | NA | Exfiltration System | Installed StormTech System: two 50 LF rows with "Isolator Row" for maintenance. Re-graded and paved road to improve drainage. | NA | 2011-06-01 | 2011-08-30 | 18000 | City of Mount Dora |  |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | Lake John Inflow Pipes Reconstruction | City of Mount Dora | NA | Pipe repair | Three inflow pipe bubble up strucutres were failing. Pipes were extended futrther into lake during low water. Mitered end section re-set with erosion mat. Over-flow grate replaced to allow increased discharge. | NA | 2011-10-01 | 2011-11-20 | 1000 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | Donnelly St & Lincoln Ave Pipe Repair | City of Mount Dora | NA | Pipe repair | Headwall broke away from pipe, water undermining Donnelly St. Installed dropo structure and extended pipeline 140 LF. | NA | 2011-12-05 | 2011-12-29 | 35000 | City of Mount Dora | NA |  | Completed | Paul Ritter | 352-735-7155 | ritterp@cityofmountdora.com
Mt. Dora | Low Impact |  | Springshed | Lake Gertrude Outfall Replacement | City of Mount Dora | Lake County, Lake County Water Authority | Pipe Replacement | Installed new 24" storm water discharge pipe from Lake Gertrude to Lake Dora. Also installed two nutruient reduction treatment boxes. | NA | 2007-06-01 | 2008-02-01 | 590835 | Lake County, Lake County Water Authority |  |  | Completed | Paul Ritter | 352-735-7145 | ritterp@cityofmountdora.com
Mt. Dora | Medium Impact |  | Springshed | 5th & McDonald Parking Lot | City of Mount Dora | NA | Exfiltration System | Installed three 36" Diameter exfiltration pipes under new parking lot | NA |  |  |  | City of Mount Dora |  |  | Completed | Paul Ritter | 352-735-7149 | ritterp@cityofmountdora.com
Lake County | Medium Impact |  | Springshed | Wolfbranch Drainage Retrofit | Lake County Stormwater | n/a | dry retention | This project was implemented to minimize water quality impact to the Wolf Branch Sink Watershed.The project is outside of the Wekiva River Hydrologic Basin but within the Wekiva Recharge Basin. We are currently in acquisition for the pond sites. The project involves removing the concrete flumes in the Wolf Branch right of way and piping that area to two new dry retention ponds (A&B) with percolation through soils as the recovery method. Not all of the basin runoff can be treated in the ponds due to topography. What area cannot be treated in the ponds will be caught in a CDS unit within Wolf Branch right of way and compensating treatment for this area will be provided in pond B. | 42-069-125066-1 | 11/07 | ongoing | $67,766.65 capital | stormwater mstu | n/a | n/a | ongoing | Mary Hamilton | 352-483-9080 | mhamilton@lakecountyfl.gov
Lake County | Study |  | Blackwater Creek | Royal Trails Drainage and Water Quality Improvements | Lake County Stormwater | n/a | study | The flood analysis, pollutant loading model and conceptual project priorities are completed. This year we will be doing field verification to prioritize projects for design. | n/a | 09/07 | 12/09 | $394,100.57 capital | stormwater mstu | n/a | n/a | ongoing | Mary Hamilton | 352-483-9080 | mhamilton@lakecountyfl.gov
Oakland | Medium Impact |  | Springshed | SFR Infill depressions | Oakland | n/a | SFR Infill depressions | Install depressional retention on all new infill single family residences in old part of town to increase recharge and decrease surface flow |  | Post-2000 | ongoing |  | Owner |  |  | Ongoing | Roland Magyar | 407-656-1117 ext 12 | planning@oaktownusa.com
Ocoee | Low Impact |  | Springshed / Wekiva River | Sabinal Ct and Geneva St Drainage Improvements - Prima Vista Subd. | City of Ocoee | None | BAFFLE BOX | The City of Ocoee is applying for a Government Modification in accordance with rule 40C-42.024(2)(c). The City of Ocoee is requesting permission to perform construction activities within an existing channel system that connects to Lake Lotta within the Wekiva Recharge Protection Basin, but does not lie within the Lake Apopka Basin. The construction activities include removing and replacing a concrete stormwater junction box; remove a segment of 30-inch RCP; Install 18" RCP, install 42" RCP to replace the 30" RCP; install a second generation baffle box; pipe end treatments; repair and regrade channel side slopes and install stabilization matting. The proposed improvements are to alleviate flooding, improve safety, and improve safety, and improve water quality of a subdivision that has no permitted stormwater management treatment system. (Refer to construction drawings) | 40-095-124661-1 | February 2011 | May 2011 | $200,00 | Stormwater Utility | Unknown at this time | Monitoring Program |  | City of Ocoee - Richard Campanale | 407-905-3170 | rcampanale@ci.ocoee.fl.us | Providing WQT to the most practicable limits per a second generation baffle box system. Lake Lotta Watershed - Closed Basin
Ocoee | Medium Impact |  | Springshed / Wekiva River | Villages of West Oak Subdivision | Private | Private | DRY RETENTION | CONSTRUCTION OF TWO DRY RETENTION POND TO SERVE A 33 LOT SINGLE FAMILY 5.5 AC. SUBDIVISION | 42-095-76674-1 |  | Completed 6/20/2000 | Private | Private | 0.16 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Village Construction Ltd. | Unknown | Unknown | WQ per SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Lotta Watershed - Closed Basin. 100 year attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Remington Oaks Phase I and II Subdivision | Private | Private | DRY RETENTION | 140 LOT SINGLE FAMILY 49.5 AC. SUBDIVISION WITH 2 DRY RETENTION PONDS | 40-095-27996-1 |  | Completed 7/30/2000 and 5/22/2001 | Private | Private | 1.43 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Imperial Partnership | Unknown | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Prairie Lake Watershed - Closed Basin; 25 year 96 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Olympia, PUD | Private | Private | WET DETENTION / DRY RETENTION | 21.2 AC. COMMERCIAL AND PUBLIC DEVELOPMENT INCLUDING A WALGREENS STORE, AND ONE PUBLIC LIBRARY; ONE WET DETENTION SYSTEM AND ONE DRY RETENTION SYSTEM CONSTRUCTED | 40-095-56711-1 |  | Completed 5/24/2001 | PRIVATE | PRIVATE | 5.16 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Olympia Development Group | Unknown | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Olympia Watershed - Closed Basin; 25 year 96 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Orchard Park Phase III Subdivision | Private | Private | DRY RETENTION | The Orchard Park Phase III 30.7 ac. Subdivision is located west of Lake Addah, on the south side of Clarcona-Ocoee Road, in west Orange County. The site is located within the Wekiva River Hydrologic Basin, south of State Road 436, within the Most Effective Recharge Area, but does not contain any portions of the Riparian Habitat Protection Zone (RHPZ). The project consists of construction of a 65-lot single-family residential subdivision and a dry retention pond. The applicant does not propose any deve | 40-095-71161-1 |  | 5/31/2001 | Private | Private | 0.89 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Cambridge Development | 407-865-9600 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Meadow Watershed - Closed Basin; 100 year 24 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Willows on the Lake | Private | Private | DRY RETENTION/WET DETENTION | Construction of a surface water management system to serve an 86-unit single family 15.18 acre subdivision and a 9.99 acre Publix shopping center. | 40-095-64191-1 |  | Completed 1/31/2002 | Private | Private | 6.29 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Unknow | Unknown | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Johio Watershed - Closed Basin; 25 year 96 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Cambridge Village Subdivision | Private | Private | DRY RETENTION | Cambridge Village is a proposed 8.97-acre single-family residential subdivision located southeast of the intersection of White Road and Clarke Road in the City of Ocoee. The surface water management system includes 30-lots, associated road, and one dry retention system. | 42-095-68471-1 |  | Completed 5/13/2002 | Private | Private | 0.46 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Village Construction Ltd. | 407-880-6789 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Lotta Watershed - Closed Basin; 100 year 24 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Wellington Place Subdivision | Private | Private | DRY RETENTION | Construct surface water management system to serve a 14 acre residential subdivision. | 40-095-81989-1 |  | Completed 8/12/2003 | Private | Private | 0.28 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE |  |  |  |  | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Stanley Watershed ; 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Low Impact |  | Springshed / Wekiva River | Lake Bennett Commercial Subdivision | Private | Private | DRY DETENTION W/ UNDERDRAIN | CONST OF COMMERCIAL SUBDIVISION - OFFICE, RETAIL, BANK COORDINATED CARE UNIT | 40-095-27660-1 |  | Completed 9/23/2003 | Private | Private | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | James Slater | Unknown | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Lotta Watershed - Closed Basin; 100 year 24 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Wentworth Apartments | Private | Private | WET DETENTION | CONSTRUCTION OF 264 APARTMENTS AND 2 PONDS OF A 14.81 ACRE SITE; TWO WET DETENTION PONDS | 40-095-27287-2 |  | Completed 12/10/2003 | Private | Private | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Victoria Equities, Inc. | Unknown | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; Wet Detention Treatment Criteria. Prairie Lake Watershed - Closed Basin; 25 year 96 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Forest Trails Subdivision | Private | Private | DRY RETENTION | Three dry-retention ponds to serve 51.8 acre single-family residential development. | 40-095-90157-1 |  | Completed 6/28/2005 | Private | Private | 1.5 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | E H Development | 407-571-4336 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Prairie Lake Reserve | Private | Private | DRY RETENTION | Construct surface water management system to serve 42 ac residential subdivision (townhomes). Three retention ponds permitted. | 40-095-96398-1 |  | Completed 4/9/2008 | Private | Private | 1.2 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | Park Square Enterprise, Inc. | 407-529-3068 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; Wet Detention Treatment Criteria. Prairie Lake Watershed - Closed Basin; 25 year 96 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Shoppes of West Oaks | Private | Private | DRY RETENTION | Construction of a 8.45 ac. shopping plaza with associated site improvements including parking, sidewalks, & utility extensions to serve development with a dry retention pond to treat stormwater runoff. | 42-095-111192-1 |  | Completed 10/12/2010 | Private | Private | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | Completed | SHOPPES OF WEST OAKS, LLC - ALAN CHARRON | 407-291-9000 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. Lake Lotta Watershed - Closed Basin; 100 year 24 hour attenuation required. 3" TV Retention assumed for Closed Basin Criteria.
Ocoee | Medium Impact |  | Springshed / Wekiva River | ABC Fine Wine & Spirits Store # 52 | Private | Private | DRY RETENTION | 2.96-ACRE PROJECT;PROPOSED SURFACE WATER MANAGEMENT SYSTEM WILL RETAIN AND RECOVER 3-INCHES OF RUNOFF FROM THE INCREASE IN IMPERVIOUS AREA. SEWERED AREA | 42-095-108387-1 (WEKIVA RECHARGE PROTECTION BASIN) | 1/2007 | 1/2008 | PRIVATE | PRIVATE | 1.95 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | COMPLETED | ABC LIQOURS, INC. | (407) 851 - 0000 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Arden Park South | Private | Private | DRY RETENTION | 98.52-ACRE PROJECT;CONSTRUCT A 157-SINGLE FAMILY RESIDENTIAL SUBD. WITH FOUR DRY RETENTION PONDS.SWMS TO STORE AND RECOVER PRE-VERSE POST DEV RUNOFF VOLUME FROM THE 25YR/96HR EVENT. SEWERED AREA | 40-095-106746-2 (WEKIVA RECHARGE PROTECTION BASIN) | CITY APPROVED - ON-HOLD | UNKNOWN | PRIVATE | PRIVATE | 2.85 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ON-HOLD | ARDEN PARK VENTURES LLC | (407) 339 - 4114 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Central Sweeping | Private | Private | DRY RETENTION | 3.73-ACRE PROJECT TO BE SERVED BY A DRY RETENTION SYSTEM TO MEET THE WEKIVA BASIN CRITERIA. SEWERED AREA | 42-095-122821-1 (WEKIVA RECHARGE PROTECTION BASIN) | UNDER CITY REVIEW | UNDER CITY REVIEW | PRIVATE | PRIVATE | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | CENTRAL SWEEPING SERVICES, INC | 771 BUSINESS PARK BLVD, WINTER GARDEN, FL 34787 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Crystal Investment Business Plaza | Private | Private | DRY RETENTION - STORMTECH EXFILTRATION SYSTEM | 1.73-ACRE PROJECT; CONSTRUCT OFFICE OFFICE PROJECT SERVED BY SUBSURFACE RETENTION SYSTEM. SYSTEM TO RETAIN AND RECOVER 3-INCHES OF RUNOFF FROM IMPERVIOUS AREA. SEWERED AREA | 42-095-118725-1 (WEKIVA RECHARGE PROTECTION BASIN) | UNDER CITY REVIEW | UNDER CITY REVIEW | PRIVATE | PRIVATE | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | CRYSTAL INVESTMENTS GROUP, LLC - LAYKRAM MOHAN | (407) 812 - 5480 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Freeman Commerce Park | Private | Private | RETENTION - EXFILTRATION TRENCH | 10.64-ACRE FREEMAN COMMERCE PARK SERVED BY STORMWATER MANAGEMENT SYSTEM USING EXFILTRATION. SEWERED AREA | 42-095-108542-1 | ON-HOLD | ON-HOLD | PRIVATE | PRIVATE | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONHOLD | FREEMAN DEVELOPMENT CO. LLC | 250 INTERNATIONAL PARKWAY, SUITE 260, LAKE MARY, FL 32746 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Hackney Prairie Park | Private | Private | DRY RETENTION | 4.26-ACRE PROJECT SERVED BY A STORMWATER TREATMENT RETENTION SYSTEM. SEWERED AREA | 42-095-121774-1 | IN CONSTRUCTION | UNKNOWN | PRIVATE | PRIVATE | 0.24 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | CITY OF OCOEE PARKS & RECREATION - JEFF HAYES | (407) 383 - 3575 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Ingram Estates Subdivision | Private | Private | DRY RETENTION | 11.47-ACRE RESIDENTIAL SITE SINGLE-LOTS, WITH STORMWATER SYSTEM - TWO DRY RETENTION SYSTEMS. RECHARGE VOLUME TO BE RECOVERED WITHIN 72-HOURS. SEWERED AREA. | 42-095-97164-2 (WEKIVA RECHARGE PROTECTION BASIN) | CITY APPROVED - ON-HOLD | UNKNOWN | PRIVATE | PRIVATE | 1.95 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | LAKE TRACY - GREGORY D. LEE | (407) 699 - 1118 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Oak Trail Reserve | Private | Private | DRY RETENTION | CONSTRUCTION AND OPERATION OF A SURFACE WATER MANAGEMENT SYSTEM SERVING A 61 SINGLE FAMILY LOTS ON A 34.57-ACRE RESIDENTIAL DEV. LOCATED WITHIN WEKIVA RIVER PROTECTION BASIN. SEWERED AREA. | 40-095-109837-1 (WEKIVA RECHARGE PROTECTION BASIN) | ON-HOLD | ON-HOLD | PRIVATE | PRIVATE | 5.86 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | CENTER LAKE PROPERTIES LTD - RICHARD GONZALEZ | (407) 859 - 3550 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Ocoee Carwash | Private | Private | RETENTION - OFF-LINE EXFILTRATION TRENCH | 1.79-ACRE CAR WASH FACILITY , LAKE LOTTA WATERSHED BASIN. SEWERED AREA | 42-095-114314-1 (WEKIVA RIVER HYDROLOGIC BASIN) | COMPLETED | COMPLETED | PRIVATE | PRIVATE | 8.59 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | COMPLETED | ACJE HOLDINGS LLC - ALAN SCHNEIDER | (917) 747 - 4100 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Shoppes at the Village | Private | Private | RETENTION - EXFILTRATION TRENCH | CONSTRUCTION OF A STORMWATER MANAGEMENT SYSTEM W/ STORMWATER TREATMENT BY EXFILTRATION FOR 0.91-ACRE RETAIL CENTER. SEWERED AREA | 42-095-122630-1 (WEKIVA RECHARGE PROTECTION BASIN) | UNDER CITY REVIEW | UNKNOWN | PRIVATE | PRIVATE | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | ROMERCA INTERNATIONAL INC. - GUSTAVO ROMER | (407) 451 - 9779 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Shoppes at West Oaks | Private | Private | DRY RETENTION | CONSTRUCT AN 8.46-ACRE RETAIL SHOPPING FACILITY. RETENTION SYSTEM TO RUNOFF. SEWERED AREA | 42-095-111192-1 (WEKIVA RIVER HYDROLOGIC BASIN) | IN CONSTRUCTION | UNKNOWN | PRIVATE | PRIVATE | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | SHOPPES OF WEST OAKS, LLC - ALAN CHARRON | (407) 291 - 9000 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Silver Ridge Crossing | Private | Private | RETENTION - EXFILTRATION TRENCH | 1.53-ACRE PROJECT; CONSTRUCT COMMERCIAL BUILDIN WITH PARKING STORMTECH EXFILTRATION SYSTEM TO TREAT RUNOFF, SEWERED AREA. | 42-095-97872-3 (WEKIVA RECHARGE PROTECTION BASIN) | ON-HOLD | ON-HOLD | PRIVATE | PRIVATE | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | DAKHIL DEVELOPMENT LLC | (407) 851 - 2292 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Villa Roma | Private | Private | WET DETENTION | 8.92-ACRE PROJECT; CONSTRUCT A 52 TOWN HOME SUBD. TO BE SERVED BY A WET DETENTION SYSTEM. THE PROJECT WILL PROVIDE 100-YEAR COMPENSATING STORAGE. SEWERED AREA. | 40-095-95767-2 (WEKIVA RECHARGE PROTECTION BASIN) | ON-HOLD | ON-HOLD | PRIVATE | PRIVATE | 5.16 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | PRJJ LLC - PETER PALERMO | (407) 654 - 0999 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | West Colonial Property | Private | Private | WET DETENTION | CONSTRUCT A 6.95-ACRE COMMERCIAL DEVELOPMENT. SEWERED AREA | 40-095-115245-1 | UNDER CITY REVIEW | UNKNOWN | PRIVATE | PRIVATE | 4.98 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | JASPER AND KIRAN WALIA | 5329 TIDENS GROVE BLVD. WINDERMERE, FL 34786 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Ocoee | Medium Impact |  | Springshed / Wekiva River | Whispering Pines Subdivision | Private | Private | DRY RETENTION | DRY RETENTION TO SERVE 105.78 -ACRE RESIDENTION SUBD. INCLUDING 109 RESIDENTIAL LOTS, 154 TOWNHOMES, ROAD STORMSEWER AND (8) DRY RETENTION PONDS. SEWERED AREA | 4-095-107071-1 (WEKIVA RECHARGE PROTECTION BASIN) | ON-HOLD | ON-HOLD | PRIVATE | PRIVATE | 0 | PRE-/POST POLLUTANT LOAD ANALYSIS SPREADSHEET MODIFIED FOR TN; RESULTS OF TN MULTI. BY 30% TO OBTAIN NITRATE REDUCTION VALUE | ONGOING | OCOEE GOLF, LLC - DEBORAH HAGEN | (407) 699 - 0894 | Unknown | SJRWMD Req.: Per 40C-42.026 Design Standards; On-Line Treatment: 1" Runoff or 1.75" Runoff from Impervious Area, Whichever is greater. WRPB Req's 3", New Development System Treats 2" Runoff or 1.25" Runoff from Imprevious Area Above and Beyond Required. In addition, Ocoee Watersheds are Landlocked and require Developments to provide storage for 100 Year Events.
Orlando | High Impact |  | Little Wekiva River | Little Lake Fairview Restoration and Dubsdread Golf Course Renovation Project | City of Orlando | FDEP, SJRWMD, FDOT, Diocese of Orlando | Wet Detention Ponds | Expansion of 5 wet detention ponds and creation of 10 additional wet detention ponds within golf course. The 15 ponds were constructed in series of 3 interconnected systems. All systems eventually discharge to adjacent wetland, except in high flows, where runoff discharges to drainwell or ditch routed to Little Lake Fairview. Project also restored hydroperiod of said wetland and improved the quality of the wetland. Also,drainwell elevation raised to allow for more treatment before discharged. | 4-095-27936-2 |  | 2008 | 9000000 | City of Orlando Stormwater Utility, City Real Estate, City Parks and Recreation, FDOT, Grants from SJRWMD & State of Florida | See Comments | Evaluation of Current Stormwater Design Criteria within State of Florida (Harper & Baker 2007) | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Treatment Acres = 422 Acres; TN Reduction = 265lb/5 months in rainy season (June-Oct) which equates to 66% removal efficiency [All values from Camp, Dresser, McKee report]
Orlando | Low Impact |  | Little Wekiva River | Lake Silver Treatment Structure (Westmoreland Dr CDS Unit) | City of Orlando |  | CDS | Installation of CDS unit to capture gross pollutants from entering Lake Silver |  | 2000 | 2000 | 565702 | Lake Silver Outfall |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Maintenance Frequency = 1/month; Average volume removed = 2 cubic yds
Orlando | High Impact |  | Little Wekiva River, Little Wekiva Canal | Center of Commerce | City of Orlando | Orange County Environmental Protection Division | Wet detention ponds | Construction of detention ponds to provide treatment and attenuation for Little Wekiva Canal |  |  |  | 16866000 | City of Orlando Stormwater Utility + Orange County Environmental Protection Divison (CBIR Grant) | See Comments | Evaluation of Current Stormwater Design Criteria within State of Florida (Harper & Baker 2007) | Envisioned | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Treatment Acres = 4,710 Acres ; Nitrogen Reduction = 11,060 lb/yr (25% of nitrogen from system) & Phosphorus Reduction = 2,551 lb/yr (52% of phosphorus from system))
Orlando | Low Impact |  | Little Wekiva River | 4 Baffle Boxes on Ardsley | City of Orlando |  | Baffle Box with Screen | Capture gross pollutants and reduce levels of nitrogen entering basin by removing leaves and clippings before enters Lake Silver |  | 2006 | 2006 | 7800 | City of Orlando Stormwater Utility |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Treatment Acres = 26.2 acres; Maintenance frequency = averages 2/month
Orlando | Low Impact |  | Little Wekiva River | 22 Inlet Baskets around Lake Orlando | City of Orlando |  | Inlet Baskets | Installation of 22 Inlet Baskets in Lake Orlando Basin |  | 2008 | 2008 | 7700 | City of Orlando Stormwater Utility |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Treatment Acres = 21.8 acres; Maintenance frequency = averages 2/month
Orlando | Low Impact |  | Little Wekiva River | 2 Inlet Baskets around Lake Sarah | City of Orlando |  | Inlet Baskets | Installation of 3 Inlet Baskets in Lake Sarah Basin |  | 2006 | 2006 | 2250 | City of Orlando Stormwater Utility |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Treatment Acres = 3.7 acres; Maintenance frequency = averages 2/month
Orlando | Low Impact |  | Little Wekiva River | 2 Inlet Baskets around Lake Daniel | City of Orlando |  | Inlet Baskets | Installation of 2 Inlet Baskets in Lake Daniel Basin |  | 2006 | 2006 | 1500 | City of Orlando Stormwater Utility |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Treatment Acres = 3.7 acres; Maintenance frequency = averages 2/month
Orlando | Low Impact |  | Little Wekiva River | 4 Inlet Baskets around Lake Silver | City of Orlando |  | Inlet Baskets | Installation of 4 Inlet Baskets in Lake Silver Basin |  | 2004 | 2004 | 3000 | City of Orlando Stormwater Utility |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Treatment Acres = 15.1 acres; Maintenance frequency = averages 2/month
Orlando | Medium Impact |  | Little Wekiva River | Palomar Exfiltration | City of Orlando |  | Exfiltration | Installation of 20' pipe to capture debris in separate chamber before percolating into ground |  | 2006 | 2006 | 30000 | City of Orlando Stormwater Utility |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net
Orlando | Low Impact |  | Little Wekiva River | Sandbar Removal on Lake Sarah | City of Orlando |  | Sandbar Removal | Removal of 300 cubic yards of sediment from Lake Sarah |  | 2006 | 2006 | 20000 | City of Orlando Stormwater Utility | See Comments |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Typically, the removal of sediments from a stormwater system is removing the potential for phosphorus, bound to the sediment, being released into the water column under certain conditions. In addition, these sediments may also contain heavy metals and specific volatiles associated with stormwater runoff from vehicles and the asphalt surface.
Orlando | Study |  | Little Wekiva River, Little Wekiva Canal | Little Wekiva River-Preliminary Engineering Evaluation Lake Lawne, Center of Commerce, and Lake Orlando Sites | City of Orlando | St Johns River Water Management District | Study | Recommend nutrient-reduction projects within Little Wekiva River watershed, using suggested drainage improvements from CDM report |  |  | 8/2008 | 49900 | SJRWMD + City of Orlando Stormwater Utility |  |  | Completed | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net
Orlando | Medium Impact |  | Little Wekiva River, Little Wekiva Canal | Stormwater System Inspections | City of Orlando |  | Public Stormwater System Inspections | Conduct proactive inspections and perform routine maintenance on 13 ponds and 31 ditches within basin to ensure systems are being maintained at optimal pollutant removal efficiency (and flood prevention) |  | 1970 | Ongoing |  | City of Orlando Stormwater Utility |  |  | Ongoing | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net
Orlando | Medium Impact |  | Little Wekiva River, Little Wekiva Canal | Compliance Inspections of Private Stormwater Systems | City of Orlando |  | Stormwater System Inspections | Inspect 233 of all commercial, single- and multi-family systems in basin for functionality on annual basis. Systems include, but is not limited to: retention and detention ponds, underdrains, exfiltration, and underground vaults. By ensuring ponds are maintained at design criteria, City is ensuring level of pollutant removal efficiency is being achieved. |  | 1989 | Ongoing | $166,000/yr | City of Orlando Stormwater Utility |  |  | Ongoing | Jim Hunt | (407) 246-3646 | Jim.Hunt@cityoforlando.net | Inspection accounts for 79% of all parcels in basin with stormwater systems. Inspectors have enforcement capabilities, which include writing violation letters and issuing fines.
Orlando | Medium Impact |  | Little Wekiva River | Rio Grande Pond | City of Orlando |  | Wet Detention Pond | Increase area of existing pond system to increase storage volume and provide some treatment for runoff for the updated Rio Grande Avenue storm sewer system. (3.6-ac pond treating 27.1-ac drainage basin) |  | 2002 | 2003 | 240000 | City of Orlando Stormwater Utility |  |  | Completed |  |  |  | No calculations available at time of project submission, but could be calculated upon request.
Orange County | High Impact |  | Little Wekiva Canal (Lake Lawne) | C-7 Canal Project | Orange County EPD | FDEP (Funding) | Wet detention | 160 acre drainage basin, residence time 36 days, .81 acre-ft/day | SJRWMD Permit # 4-095-120144-1 | 10/2009 | 2/2010 | $1,000,000 capital | ad valorem, CBIR grant | 206.8 lbs/yr | EMC(Loading/yr) X BMP efficiency | Construction contract out to bid 7/20/09 | Rick Baird | 407-836-1483 | rick.baird@ocfl.net | EMC loading based on unincorporated area of Little Wekiva Canal in TMDL report.
Orange County | Low Impact |  | Little Wekiva Canal (Lake Lawne) | North Lake Lawne Stormwater Treatment Project | Orange County EPD | Pine Hills Safe Neighborhood Partnership FDEP (319 Funding) | Curb inlet baskets | Install 120 curb/grate inlet baskets on stormdrains and apply stormdrain markers | none | Proposed start 12/2009 | 2/2010 | $100,000 capital $1900 O&M/yr | ad valorem, 319 grant(?) | 157.52 lbs/yr | EMC(Loading/yr) X BMP efficiency | Planned and funded | Rick Baird | 407-836-1483 | rick.baird@ocfl.net | this project will move forward by end of year with or without 319 grant funds.
Orange County | Med Impact |  | Little Wekiva Canal (Bay Lake) | Bay Lake Stormwater Improvement Project | Orange County EPD | UCF Stormwater academy | Second Generation Baffle Box | Will treat ~70 acres with 2nd generation baffle box and utilize Bold and Gold™ to increase nitrogen removal rates | none | Proposed start 12/2009 | 2/2010 | 211000 | ad valorem, TMDL WQ Grant | 251.6 lbs/yr | EMC(Loading/yr) X BMP efficiency | Envisioned | Rick Baird | 407-386-1483 | rick.baird@ocfl.net | EMC loading based on unincorporated area of Little Wekiva Canal in TMDL report.
Orange County | Medium Impact |  | Little Wekiva Canal (Lake Lawne) | C-5 Canal - Solar Reuse | Orange County EPD | CIBR and 319 Grants | Wet Detention | Online wet detention with solar powered irrigation system for reuse on adjacent sports fields. | TBD | Proposed start 2013 | 2013 | TBD | CIP Budget, CIBR and 319 grant match | TBD | TBD | Planned and funded | Ron Novy | 407-836-1409 | ronald.novy@ocfl.net | Design and engineering has begun. Construction date TBD
Orange County | High Impact |  | Little Wekiva Canal (Bay Lake) | Bay Lake Stormwater Retrofit | Orange County EPD | FDEP Funding | Modular Wetlands with Bold and Gold™ media | Providing treatment for two drainage basins totaling 91.7 acres | TBD | 2012-2013 | TBD | 260000 | advalorem and grant match | 13.79 | Bay Lake Study | Planned and funded | Ron Novy | 407-836-1409 | ronald.novy@ocfl.net | Engineering to start in 2012
Orange County | Low Impact |  | Little Wekiva Canal | Elba Way | Orange County EPD | none | revegetation of shoreline | Project will reduce temperature of water and impvrove SCI | none | completed |  | 40000 | ad valoreum | 0 | NA | completed | Dan Homblette | 407-836-1490 | dan.homblette@ocfl.net | This project was added to restorartion of LW canal done by OC Stormwater
Orange County | Medium Impact |  | Little Wekiva Canal (Lake Westin) | Lake Westin Curb Inlet Baskets | Orange County EPD | none | Curb Inlet Baskets | Install 160 curb/grate inlet baskets on stormdrains and apply stormdrain markers | none | 2012 | 2012 | 160000 | ad valorem | 61.67 lbs/yr | In-House Study | Planned and funded | Ron Novy | 407-836-1409 | ronald.novy@ocfl.net | 14.6g (avg) TN removed per basket per month
Orange County | Medium Impact |  | Little Wekiva Canal | Riverside Pond | Orange County EPD | FDEP (Funding) | Wet detention | The project will expand the size of the 0.8 acre existing treatment pond to 1.6 acre and add aeration to address the D.O. impairment | SJRWMD Permit # 4-095-20838-2 | 1/2012 | 6/2012 | 766918 | ad valorem, CBIR grant | TBD |  | Construction started 1/2012 | Brian Catanzaro | 407-836-1428 | brian.catanzaro@ocfl.net | Partial treatment of 11,800 acres of drainage to the Little Wekiva Canal. Increasing existing pond storage from 8.95 acre feet to 15.06 acre feet
Orange County | Low Impact |  | L. Wekiva | Riverside Park Road | Orange County Stormwater Mgmt. | SJRWMD | Erosion Protection | Structural stabilization of the channel bed and banks in the main stem of the river and into the Lake Lovely Outfall Canal and included a grade control structure.The project included gabions, Reno mattress, and riprap channel bottom and side bank protection. |  | 1998-06-01 | 2001-01-22 | 600000 | FDEP Agreement No. ADM 515 - Amendment #3 SJRWMD Contract 97W253 | unknown |  | Constructed | Mike Drozeck | 407-836-7990 | Mike.Drozeck@ocfl.net
Orange County | Low Impact |  | L. Wekiva | Riverside Acres Arch Pipe | Orange County Stormwater Mgmt. | SJRWMD | Erosion Protection | Replace the existing 1,750 feet of pipearch pipe within Riverside Acres subdivision with an open channel section and restore to reflect the original river configuration |  | 1998-11-06 | 2004-12-06 | 5000000 | Interlocal Agreement Orange County & SJRWMD | unknown |  | Constructed | Mike Drozeck | 407-836-7990 | Mike.Drozeck@ocfl.net
Orange County | Low Impact |  | L. Wekiva | NRCS Riverside Park Avenue | Orange County Stormwater Mgmt. | NRCS (USDA) | Erosion Protection | Erosion protection of Little Wekiva River bank. Installation of rip rap. Project length of 150 ft. | 40-095-27756-4 | 2005-03-01 | 2005-09-27 | 350000 | NRCS Grant (75%) & General Revenue (25%) | unknown |  | Constructed | Daniel Negron Vega | 407-836-7743 | daniel.negron@ocfl.net
Orange County | Low Impact |  | L. Wekiva | NRCS Riverside Acres | Orange County Stormwater Mgmt. | NRCS (USDA) | Erosion Protection | Erosion protection of Little Wekiva River bank. Installation of rip rap. Project length of 287 ft. | 40-095-56491-3 | 2005-03-01 | 2005-12-27 | 650000 | NRCS Grant (75%) & General Revenue (25%) | unknown |  | Constructed | Daniel Negron Vega | 407-836-7743 | daniel.negron@ocfl.net
Orange County | Low Impact |  | L. Wekiva | Elba Way | Orange County Stormwater Mgmt. | SJRWMD | Erosion Protection | Erosion protection of Little Wekiva River. Installation of gaibions,grade control structures, river reshaping. | 4-095-56459-7 | 2008-11-01 | 2009-07-01 | 1000000 | SJRWMD Grant | unknown |  | Constructed | Matt Hassan | 407-836-7990 | Medhat.Hassan@ocfl.net
Orange County | Low Impact |  | L. Wekiva | Gusty Lane | Orange County Stormwater Mgmt. | SJRWMD | Erosion Protection | Removal of existing triple aluminum pipes along the Little Wekiva River at Gusty Lane Drive, and replacing it with a control structure using riprap, and gabion materials. A pipe & an inlet was installed for an existing ditch adjacent to the canal. | 40-095-56459-6 | 2003-10-30 | 2005-06-21 | 132000 | SJRWMD Grant (75%) & General Revenue (25%) | unknown |  | Constructed | Mike Drozeck | 407-836-7990 | Mike.Drozeck@ocfl.net
Orange County | Low Impact |  | L. Wekiva | Sherry Drive | Orange County Stormwater Mgmt. | SJRWMD | Erosion Protection | Erosion protection of Little Wekiva River bank. Installation of gabion block and reno mattress. Project length of 400 ft. | 40-095-56459-5 | 2006-01-15 | 2006-06-29 | 600000 | SJRWMD Grant (75%) & General Revenue (25%) | unknown |  | Constructed | Daniel Negron Vega | 407-836-7743 | daniel.negron@ocfl.net
Orange County | Medium Impact |  | L. Wekiva | Stormwater Pond Inspection | Orange county EPD |  | Education/enforcement | Inspection of private/public stormwater ponds for compliance of performance and permit conditions. |  |  |  |  | General Fund | unknown | unknown | ongoing | Dan Homblette | 407-836-1490 | dan.homblette@ocfl.net
Orange County | Low Impact |  | Little Wekiva | Little Wekiva Slope Stabilization West/East Banks | Orange County Roads & Drainage Division | USDA NRCS | Erosion and flood control | project will eliminate erosion of banks due to construction of steel sheet pile | Area 1-east-40-095-56459-8; Area 2-west-40-095-56459-9 | Area 1-east 1/2009; Area 2-west 2/2010 | Area 1-east 9/2009; Area 2-west9/2010 | Area 1-east ;Area 2-west $700,000 | Federal funds and general funds | unknown |  | completed | Penny Post | 407-836-7858 | penny.post@ocfl.net
Seminole County | High Impact |  | Sweetwater Creek | Sweetwater Cove Dredging and Drainage Improvements and Sweetwater Tributary Erosion Project | Seminole County | SJRWMD | Retention Pond | Increase water quality treatment resonance time through water quality treatment pond expansion, plus construction of an online sedimentation basin; plus erosion control measures along Sweetwater Creek; area served = 2,181 acres | 4-117-97866-2 | 4/2009 | EST COMPLETE 3/2012 | 2700000 | SJRWMD AND COUNTY FUNDS | TN = 2609 TP = 68 TSS = 151,296 | EMC modeling-based approach | ACTIVE | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Bear Lake | Bear Lake Road Reconstruction | Seminole County | N/A | Retention Pond | Provide water quality treatment to an existing roadway and subdivision through increased wet retention and utilization of an existing dry retention pond; area served = 32 acres | 40-117-63245-1 | 2006 | 2008 | 2200000 | SEMINOLE COUNTY | TN = 91.4 TP = 32.3 | EMC modeling-based approach | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Lake Lotus | Bunell Road Widening | Seminole County | N/A | Retention Pond, Exfiltration | Provide treatment to an untreated roadway through construction of a new wet retention basin and exfiltration trench. Designed to hold treatment volume plus 50%; area served = 7.5 acres | 40-117-29231-1 | 2009 | 2010 | 3200000 | SEMINOLE COUNTY | TN = 35.9 TP = 9.1 | EMC modeling-based approach | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Lake Lotus | Eden Park Road | Seminole County | N/A | Retention Pond, Exfiltration, Baffle Box | Provide treatment to an untreated roadway through exfiltration, installation of CDS units and new wet retention basin; area served = 10.6 acres | 40-117-29231-1 | 2008 | 2010 | 3500000 | SEMINOLE COUNTY | TN = 58.6 TP = 14.1 | EMC modeling-based approach | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Low Impact |  | Lake Brantley | Palm Springs Road Paving and Drainage | Seminole County | N/A | 2nd Generation Baffle Box | Paving a dirt road and installing a 2nd generation baffle box to provide water quality treatment; area served = 0.4 acres | 42-117-86265-1 | 2001 | 2003 | 255000 | SEMINOLE COUNTY | TN = 1.3 TP = 0.2 | 2ND GENERATION BAFFLE BOX | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Little Wekiva River | Markham Woods Road - 3 Lane SR 434 to Springs Landing Blvd | Seminole County | N/A | Exfiltration Trench | Provide water quality treatment for the additional traffic lane through construction of new exfiltration trench; area served = 12.4 acres | 40-117-29357-1 | 2001 | 2003 | 1400000 | SEMINOLE COUNTY | TN = 45.9 TP = 7.7 | ON-LINE 0.25 INCH RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Little Wekiva River | Markham Woods Road –3 Lane Springs Landing Blvd to EE Williamson Rd | Seminole County | N/A | Exfiltration Trench | Provide water quality treatment to an existing roadway through exfiltration trench; area served = 9.2 acres | 40-117-29197-1 | 2004 | 2006 | 2300000 | SEMINOLE COUNTY | TN = 32.4 TP = 4.4 | ON-LINE 0.75 INCH RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Wekiva River | Wekiva Springs Road – SR 434 to Sabal Point | SEMINOLE COUNTY | N/A | Exfiltration Trench | Provide water quality treatment for new impervious portions of roadway improvements through construction of an on-line exfiltration trench; area served = 3.4 acres | 40-117-21780-1 | 2006 | 2008 | 6900000 | SEMINOLE COUNTY | TN = 15.5 TP = 2.5 | ON-LINE RETENTION 0.25 INCH | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Sweetwater Creek | Wekiva Springs Road Hunt Club to Fox Valley | Seminole County | N/A | Swale | Provide water quality treatment to an existing roadway through swales; area served = 7 acres | 40-117-21780-6 | 2007 | 2008 | 1800000 | SEMINOLE COUNTY | TN= 53.3 TP = 9.3 | ON-LINE 0.75 INCH RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Wekiva River | Wekiva Springs Road at Wekiva Springs State Park | Seminole County | N/A | Wet Retention | Construction of two interconnected sedimentation ponds to provide additional water quality treatment for 2 sq miles of residential development. Area served = 2 sq miles |  | 2001 | 2005 | 220000 | SEMINOLE COUNTY | TN = 166.7 TP = 50.42 | HARPER WET POND METHODOLOGY | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Little Wekiva River | Little Wekiva Grade Control – Montgomery Rd to SR 434 | Seminole County | SJRWMD & SEMINOLE COUNTY | Grade Control | Reduce sediment loads through bank stabilization and construction of 2 river grade control structures in the Little Wekiva River; area served = >5,000 acres | 4-117-121590-1 | 12/2011 | 2012 | 850000 | SJRWMD & SEMINOLE COUNTY | TN = 298.3 TP = 31.4 TSS = 9818 | EROSION RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Little Wekiva River | North Western Erosion control Project | Seminole County | SJRWMD & SEMINOLE COUNTY | Stream Stabilization | Reduce sediment loads through bank stabilization along the Little Wekiva River; area served > 5,000 acres | 40-117-56459-1 | 2004 | 2004 | 950000 | SJRWMD & SEMINOLE COUNTY | TN = 32.0 TP = 3.4 TSS = 1053 | EROSION RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Little Wekiva River | Weathersfield Erosion Control Project | Seminole County | SJRWMD & SEMINOLE COUNTY | Stream Stabilization | Reduce sediment loads through bank stabilization along the Little Wekiva River; measures included gabion lining, reno mattresses, gabion baskets to serve as grade control structures; area served = >5,000 acres | 4-095-56459-1 | 2000 | 2001 | 750000 | SJRWMD & SEMINOLE COUNTY | TN = 27.9 TP = 2.9 TSS = 919 | EROSION RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Little Wekiva River | Grade Control Structures 6 & 7 | Seminole County | SJRWMD & SEMINOLE COUNTY | Grade Control | Reduce sediment loads through bank stabilization and river grade control structures in the Little Wekiva River; area served = >5,000 acres | 4-117-22522-3 | 2001 | 2001 | 300000 | SJRWMD & SEMINOLE COUNTY | TN = 174.3 TP = 18.4 TSS = 5736 | EROSION RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Little Wekiva River | Horse Lovers Lane Erosion Control Project | Seminole County | SJRWMD & SEMINOLE COUNTY | Stream Stabilization | Reduce sediment loads through bank stabilization along the Spring Lake outfall, a tributary to the Little Wekiva River; used gabions and grade control structures plus replacement of culverts; area served = >1,000 acres | 40-117-56459-1 | 2003 | 2004 | 700000 | SJRWMD & SEMINOLE COUNTY | TN = 112.9 TP = 11.9 TSS = 3715 | EROSION RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Medium Impact |  | Wekiva River | Wekiva Park Drive Erosion Control Project | SEMINOLE COUNTY | SEMINOLE COUNTY | Grade Control | Reduce sediment loads through grade control structures; area served = 400 acres | 40-117-81782-1 | 2008 | 2010 | 350000 | SEMINOLE COUNTY | TN = 35.6 TP = 3.8 TSS = 1172 | EROSION RETENTION | complete | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | High Impact |  | Wekiva River | Triangle Drive Treatment Pond | Seminole County | SEMINOLE COUNTY | Wet Retention | Construct wet detention pond and provide ecological restoration on a drainage parcel near Triangle Drive prior to draining into Lake Brantley; area served = 372 acres | N/A | PLANNED | PLANNED | 800000 | SEMINOLE COUNTY | TN = 221.5 TP = 146.4 | HARPER WET POND METHODOLOGY ON-LINE | PLANNED - NOT FUNDED | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | High Impact |  | Wekiva River | West Wekiva Trail Treatment Pond | Seminole County | SEMINOLE COUNTY | Wet Retention | Construct wet detention pond and provide ecological restoration on a drainage parcel North of West Wekiva Tr. Prior to discharge into Wekiva River; area served = 220 acres | N/A | PLANNED | PLANNED | 900000 | SEMINOLE COUNTY | TN = 112.5 TP = 73.8 | HARPER WET POND METHODOLOGY ON-LINE | PLANNED -NOT FUNDED | Mark Flomerfelt | 407-665-5709 | mflomerfelt@seminolecountyfl.gov
Seminole County | Low Impact |  | SPRING LAKE (WBID 2987A) | SPRING LAKE | SEMINOLE COUNTY | HOA/VOLUNTEERS | EXOTICS REMOVAL/REVEGETATION W/ NATIVE SPECIES | ACCOMPLISHED USING IN-HOUSE STAFF, RESIDENTS, AND VOLUNTEERS | N/A | 2008 | 2009 | 75000 | SEMINOLE COUNTY |  |  | COMPLETE | KIM ORNBERG | 407-665-2417 | kornberg@seminolecountyfl.gov
Seminole County | Low Impact |  | MIRROR LAKE (WBID 3000C) | MIRROR LAKE | SEMINOLE COUNTY | HOA/VOLUNTEERS | EXOTICS REMOVAL/REVEGETATION W/ NATIVE SPECIES | ACCOMPLISHED USING IN-HOUSE STAFF, RESIDENTS, AND VOLUNTEERS | N/A | 2008 | 2010 | 75000 | SEMINOLE COUNTY |  |  | COMPLETE | KIM ORNBERG | 407-665-2417 | kornberg@seminolecountyfl.gov
Seminole County | Low Impact |  | LAKE MOBILE (WBID 2998B) | LAKE MOBILE | SEMINOLE COUNTY | SEMINOLE COUNTY SCHOOL BOARD & VOLUNTEERS | EXOTICS REMOVAL/REVEGETATION W/ NATIVE SPECIES | ACCOMPLISHED USING IN-HOUSE STAFF, RESIDENTS, AND VOLUNTEERS | N/A | 2009 | 2009 | 25000 | SEMINOLE COUNTY |  |  | COMPLETE | KIM ORNBERG | 407-665-2417 | Kornberg@seminolecountyfl.gov
Seminole County | Low Impact |  | LITTLE WEKIVA RIVER(WBID 2987) | LWR @ SPRINGS LANDING BRIDGE | SEMINOLE COUNTY | HOA/VOLUNTEERS | EXOTICS REMOVAL/REVEGETATION W/ NATIVE SPECIES | ACCOMPLISHED USING IN-HOUSE STAFF, RESIDENTS, AND VOLUNTEERS | N/A | 2010 | 2010 | 10000 | SEMINOLE COUNTY |  |  | COMPLETE | KIM ORNBERG | 407-665-2417 | kornberg@seminolecountyfl.gov
Turnpike | Medium Impact |  | Springshed | Widen Turnpike, Gotha to Beulah | Florida's Turnpike | N/A | dry retention | Roadway, 1.25 inches treated in dry retention, recovered in 72 hours |  | 1/15/2008 | 12/31/2010 | Construction $62 million | Toll Revenue | 86% removal | Harper | under construction | Terry Miller | 407-264-3626
Turnpike | Medium Impact |  | Springshed | Widen Turnpike, Beulah to SR 50 | Florida's Turnpike | N/A | dry retention | Roadway, 3 inches treated in dry retention, recovered in 72 hours. |  | 12/11/2008 | 09/30/2011 | PE Consultant $6.8 million, ROW $3.5 million, Construction $108 million, Environmental Agencies $1.6 million | Toll Revenue | 95% removal | Harper | under construction | Craig Bostic | 407-264-3480
Winter Garden | Medium Impact |  | Springshed | Dillard Street Pond Expansion | City of Winter Garden | N/A | Wet Detention | This project was part of the permitting process for the New City Hall in Winter Garden. The stormsewer system adjacent to the pond was modified to treat previously untreated runoff. | 40-095-85722-5 | Feb 09 | Sept 09 | Capital | Stormwater | 272.03 | Assumed at 50% removal | Completed | Michael Kelley | 407 656 4111 | mkelley@cwgdn.com | This project was designed to meet the Lake Apopka Rule. The nitrate reduction in this stormwater pond is assumed to be 50 %.
Winter Garden | Medium Impact |  | Springshed | Plant Street Segment 1 | City of Winter Garden | N/A | Road Widening with Wet Detention | This project involves widening Plant Street including blowing out the intersecion of West Crown Point Road in Winter Garden. There was no stormwater treatment for this section of raod prior to the widening. | 40-095-82584-2 | June 09 | Ongoing | Capital | Stormwater, Utlities | 250.05 | Assumed at 50% removal | Ongoing | Michael Kelley | 407 656 4111 | mkelley@cwgdn.com | This project was designed to meet the Lake Apopka Rule. The nitrate reduction in this stormwater pond is assumed to be 50 %. This project is on schedule and is to be completed by 5/20/10.