## All
Entity | Credit Ranking | Subbasin | Subbasin Code | Project Name | Lead Entity | Project Partners | Project Type | Project Detail | ERP # | Project Start | Project End | Project Cost | Funding Source(s) | Estimated Nitrate Reduction (lbs/yr) | Nitrate Reduction Calculation Method | Status | Contact Name | Contact Phone | Contact Email | Comments
Apopka | Low Impact | Springshed/ Rock Springs Run | C1AP1 | Victoria Plaza, Forest Avenue, 3rd Street, Park Ave | City of Apopka/Public Services |  | Relined gravity sewer | Relined to correct leaking joints |  | June 2007/2008 | June 2007/2008 | 200591 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Low Impact | Springshed/ Rock Springs Run | C1AP1 | Manholes (Alabama & 8th St; Little St. & 9th St; Park Ave; Charleston Park Subdivision) | City of Apopka/Public Services |  | Spraycoat Brick Manholes | Relined manholes with supercoat spray to prevent leaking between bricks |  | December 2008/2009 | December 2008/2009 | 28420 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Low Impact | Springshed/ Rock Springs Run | C1AP1 | Lift Station 9 & 10 Wet Wells | City of Apopka/Public Services |  | Reline/Spraycoat | Rehab Lift Station wet well due to H2S dissolving concrete walls |  | February 2009/2010 | February 2009/2010 | 41945 | Water & Sewer Maintenance Fund 401 |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | High Impact | Little Wekiva | C1AP2 | Altamonte Springs Reuse to the City | City of Apopka/Public Services | City of Altamonte Springs | Reclaimed Water Collection | The City is in planning stage of receiving the City of Altamonte's reclaim water that is currently being discharged into the Little Wekiva - wet weather discharge. This will also reduce groundwater withdrawal from the City | [7 empty] | Planning | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | High Impact | Little Wekiva | C1AP2 | Utilities Inc Reuse to the City | City of Apopka/Public Services | Utilities Inc | Reclaimed Water Collection | The City is in design stage of receiving Utilities Inc's reclaim water that is currently being discharged into the Little Wekiva - starting at 1MG/day. This will also reduce groundwater withdrawal from the City |  | 2012 | [5 empty] | Design | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | High Impact | Springshed/ Rock Springs Run | C1AP1 | Orange County Reuse to the City | City of Apopka/Public Services | Orange County | Reclaimed Water Collection | The City is in the design stage of receiving 3 MGD of reclaimed water that is currently going to Orange County RIBs. This will also reduce groundwater withdrawal from the City |  | Late 2012 | 2013 |  |  |  |  | Design | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Explain how this increases nutrient removal | Springshed/ Rock Springs Run | C1AP1 | Downtown Regional Stormwater Storage Pond | City of Apopka/Public Services |  | Reclaim/Stormwater Storage Pond | Improvement of an existing drainage system and lined storage pond that will increase pollutant removal. Water will be reused in the reclaimed collection system. | [7 empty] | Proposed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | High Impact | Springshed/ Rock Springs Run | C1AP1 | Northwest Reclaim and Stormwater Storage Pond | City of Apopka/Public Services |  | Reclaim/Stormwater Storage Pond | The City constructed a 120 MG lined Reclaim storage pond. The pond also collects stormwater from the 300 acre NW recreation facility that is filtered and distibuted for irrigation. This will also reduce groundwater withdrawal |  | 2007 | 2008 | 750000 |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Cannot list as BMAP project. However, an ordinance that requires sewer for new development can be listed. Does the city have this? | Springshed/ Rock Springs Run | C1AP1 | Ustler Road and Sir Arthur Ct Forcemain Extension | City of Apopka/Public Services |  | Collection System Expansion | The City installed 1,000 feet of 4 inch forcemain to enable new homes being constructed to connect to the City's collection system |  |  | 2009-08-03 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Please confirm the # of septic tanks taken offline Low Impact | Springshed/ Rock Springs Run | C1AP1 | US 441 Forcemain Extention | City of Apopka/Public Services |  | Collection System Expansion/Septic to Sewer system | The City extended it WW collection system by installing 12,236 ft of 12 in forcemain to Jones Ave, making connections to Zellwin Farms and Zellwood Elementary School) and providing availability for future connections in the area. |  |  | 2006-12-19 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | How many septic tanks does this project take offline | Springshed/ Rock Springs Run | C1AP1 | East 13th St Force Main Extension | City of Apopka/Public Services |  | Collection System Expansion/Septic to Sewer system | The City installed 1,450 feet of 4 inch force main to make sewer collection system available to new construction and for connections for current septic in the area |  |  | 2007-08-21 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Cannot list as BMAP project. However, an ordinance that requires sewer for new development can be listed. Does the city have this? | Springshed/ Rock Springs Run | C1AP1 | Trailer Haven Lane 4 inch Forcemain | City of Apopka/Public Services |  | Collection System Expansion | City installed 1,210 feet of 4 inch force main to accommodate new home construction in the area. Trailer Haven Ln abutts the west boundary of the Wekiva Springs State Park; therefore, preventing new septic from being installed near the State Park |  |  | 2010-06-01 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Medium Impact | Springshed/ Rock Springs Run | C1AP1 | Kelly Park at Rock Springs (Orange County Park) | City of Apopka/Public Services |  | Collection System Expansion/Septic to Sewer system | The Rock Springs Road & Kelly Park Rd collection system expansion allowed the City to connect the Orange County Kelly Park recreation area to the City's collection system and abandon their septic |  |  | 2009-12-11 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Please confirm the # of septic tanks taken offline; also see Line #3 Comment. Low Impact | Springshed/ Rock Springs Run | C1AP1 | Kelly Park Road 8 inch Forcemain | City of Apopka/Public Services |  | Collection System Expansion/Septic to Sewer system | The City installed 1,250 ft of 8 in Forcemain along the east end of Kelly Park Rd. This allowed Orange County's Kelly Park to connect to the City's collection system and abandon their septic. It also allows for future septic connections near the Wekiva and Rock Springs area |  |  | 2006-01-10 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Cannot list as BMAP project. However, an ordinance that requires sewer for new development can be listed. Does the city have this? | Springshed/ Rock Springs Run | C1AP1 | Rock Springs Rd (RSR) 8 inch Forcemain | City of Apopka/Public Services |  | Collection System Expansion/Septic to Sewer system | The City extended 10,400 ft of FM to its collection system on RSR N from Ponkan Rd. to Kelly Park Rd. This will provide collection for areas close to the Wekiva Springs State Park. Thereby preventing the expansion of septic tank use in the area. | [7 empty] | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Please provide more information on size of the plant. Low Impact | Springshed/ Rock Springs Run | C1AP1 | Yothers Rd and Zellwood Station | City of Apopka/Public Services |  | Collection System Expansion | The City installed 5,375 ft of 10 inch FM and a lift station which allowed the Zellwood Mobile Home Park to decommission their package WWF and effluent percolation pond, reducing effluent load to the basin |  |  | 2005-09-07 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | Please provide more information on size of the plant. Low Impact | Springshed/ Rock Springs Run | C1AP1 | Chalet North Mobile Home Park |  |  | Collection System Expansion | The City worked in cooperation with Orange County EPD and the park to decommission the package wastewater treatment facility and effluent percolation pond and connect to the City's collection system |  |  | 2003-02-10 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | How many septic tanks does this project take offline | Springshed/ Rock Springs Run | C1AP1 | Jones Avenue 12 inch Forcemain Extension | City of Apopka/Public Services |  | Collection System Expansion/Septic to Sewer system | City installed 1,250 feet of 12 inch force main in anticipation of connecting future commercial development to the City's collection system and off of existing septic |  |  | 2010-10-26 | 65000 |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | How many septic tanks does this project take offline | Springshed/ Rock Springs Run | C1AP1 | Zellwin Farms Sewer Connection and Holly Creek Phase IIA Subdivision |  |  | Septic to Sewer system | Jones Ave forcemain installation allowed City to connect Zellwin Farms to the City's wastewater collection system and off septic |  |  | 2011-06-23 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Apopka | low Impact | Springshed/ Rock Springs Run | C1AP1 | Individual Septic to Sewer Projects |  |  | Septic to Sewer system | Dr. Philip Trinh Dental Office (Existing septic was placed on City's wastewater collection system); Honey Transport Inc. (Existing septic was abandoned and the business was placed on City collection system); United Pentocostal Church (The City worked with the church to abandon their existing septic system during their expansion and connect to the collection system); Robinsons Restaurant (The City worked with the restaurant to transfer their wastwater effluent treatment from their septic system to the City's collection system) |  |  | 2011-09-07 |  |  |  |  | Completed | Jessica Schilling | 407-703-1731 | Jschilling@apopka.net
Eustis | n/a permit required collection system upgrade | Wekiva Springshed | B1EU | Bates Ave WWTP Nitrogen Reduction | City of Eustis | FDEP | Nitrification | Install new treatment train to meet Wekiva Parkway & Protection Act standard of 10 mg/l |  |  | expected April 2012 | 5100000 | State Revolving Fund |  |  |  | Rick Gierok | 352-483-5480 | gierokr@ci.eustis.fl.us
Mt. Dora | Low Impact | Wekiva Springshed | B2MD | Lift Station #1, 2, 3, 7, 9, 10, 11, 12, 13, 14, 15, 16, 17, 20, 22, 25, 27, 28, 30, 31, & 34 Piping | Mt. Dora | None | Sanitary System Inspections | #1-Cleaned & Camera Inspected 8" & 10" Pipe totaling 11,981 ft (Alex&er St, Donnelly St, Baker St, Lake Dora Rd, Tremain St) #2-Cleaned & Camera Inspected 8" pipe totaling 15,275 ft (Gr&view, Clayton, Liberty, Simpson, Rhodes, Rossiter, Stowe, Plymouth, First Ave) #3 - Cleaned & Camera Inspected 8" pipe totaling 2,223 ft (S& Lake Ct, High Pt) # 7- Cleaned & Camera Inspected 8" pipe totalling 1,975 ft & upsized 360 ft of force main (Chetanham Ct, Coventry Ct, Cantebury Ct, Dorsett Ct, & Liberty Ave) #9 -Cleaned & Camera Inspected 12,281 ft of 8" pipe (2nd ave, 3rd ave, 4th ave, 5th ave, Simpson, Rhodes, Rossiter, Lake Franklin Dr, Summit Ave, Grovel&, Pinecrest & Stanley Bell Dr) #10 - Cleaned 22.558 ft of 8" pipe, Camera inspected 2,500 ft of 8" pipe (Unser, Orange, Simpson, Rhodes, Wardell, Limit Ave, Jefferson Dr, Jackson Ave, Grant Ave, Florida Ave, Pine Ave, Highl& Ave & FearonAve) # 11 -Smoke Testing of 10,228 ft of 8", 10" & 12" Pipe (Stacey Dr, Sunrise Blvd, Karen Dr, Stacey Cir, Brookside Cir, Brookside Dr, Elizabeth Ln, Eric Ln, Oak Cir, Briarcliff Ln & Cottonwood Ln) #12- Smoke Testing of 3,214 ft of 8" pipe (St. & rews Wy & Heathl & Ct) #13 - Smoke Testing of 10,811 ft of 8" Pipe (Laurel Ridge Dr, St. James Way, Pine Hollow Dr, Arcadian Ct, Covey Cir & Friars Ct) #14 - Smoke Testing of 1,524 ft of 8" pipe on Greenbriar Trl. #15 - Smoke Testing of 11,674 ft of 8" pipe (Hunter Green, Country Club Blvd, Oakcrest Cir, Laurel Dr, Shadowood Cir, Falcon Brindge Pl & Spring Creek Ct) #16 - Smoke testing of 5,399 ft of 8" pipe (Park Forest Blvd, Chase Ct, Stafford Springs Blvd, Citrus Cir, Edgewater Dr, Wyngate Ct & Country Club Blvd) #17 - Smoke Testing of 3,885 ft of 8" pipe (Loch Leven Ln, Juliette Blvd, Augustus Ln, & Caesars Ct) #20 - Cleaned & Camera Inspected 8" Pipe totaling 5,688 ft (Waterman Ave, Oakhill Ln, Mapleton Ln, Rockport Ln, Elmwood Ln, York Ln, Warfield Way, Salem Ave, Waterford Ave, Essex Ave, Beacon Ln) #22- Cleaned & Camera Inspected 3,666 ft of 8" & 21" pipe on Limit Ave. #23 - Cleaned & Camera Inspected 745 ft of 8" pipe on Magnolia Ending. #25- Cleaned & Camera Inspected 6,741 ft of 8" pipe (Village Ln, Stratford Ln, Foxboro Ct, Amherst Ln, Clagary Ln, Mary Ln, Ken Ct, David Ct & Durham Ct) #27 -Cleaned & Camera Inspected 2,628 ft of 8" pipe on Spring Harbor Cir. #28 -Cleaned & Camera Inspected 1,163 ft of 8" pipe. #30 -Cleaned & Camera Inspected 2,509 ft of 8" pipe (Ole&er, Camellia, Azalea & Laurel Dr) #31 -Cleaned & Camera Inspected 512 ft of 8" pipe on Arbor Way. #34 - Cleaned, Camera Inspected & Smoke Tested 10,168 ft of 8" pipe (Castelli Blvd, Capri Ln, Palermo Ct, Isola Bella Blvd, Stefano Ct & Murano Ct) | None | Jan 2006 thru Jun 2011 | December 2006 thru October 2011 | 21000 | Sewer Maintenance Fund |  |  | Completed | Patti Olney | 352-551-9263 | olneyp@ci.mount-dora.fl.us
Mt. Dora | Low Impact | Wekiva Springshed | B2MD | Lift Station #10 Piping Replacement (Pine Avenue) | Mt. Dora | DCA | Gravity Sewer Pipe Replacement | Replace 602 feet of 8" Pipe and two manholes. | None | October 2011 | December 2011 | 160000 | CDBG Grant |  |  | Completed | Patti Olney | 352-551-9263 | olneyp@ci.mount-dora.fl.us
Mt. Dora | Low Impact | Wekiva Springshed | B2MD | Pipe Lining 2007, 2008, 2009, and 2010 | Mt. Dora | None | Line Sanitary Sewers | 2007- Lined 7,094 ft of 8" sewer main on Clayton & Liberty St. 2008- Lined 8,040 ft of 8" & 10" sewer main (Gr&view, Alex&er, Tremain, Baker, Lake Dora Rd, Pine Ave & Donnelly St). 2009 -Lined 3,746 ft of 8" pipe on Old Eustis Rd & Donnelly St. 2010 -Lined 1,500 ft of 21" pipe along Lake John. | None | Jan 2007 - Jan 2011 | Dec 2007 - Dec 2011 | 705917 | Sewer Maintenance Fund |  |  | Completed | Patti Olney | 352-551-9263 | olneyp@ci.mount-dora.fl.us
Mt. Dora | Medium Impact | Wekiva Springshed | B2MD | CDBG Grant | Mt. Dora | DCA | Septic Tank Converted to Gravity Sewer | Extended 8" sewer main and installed 4 laterals to connect 4 duplexes to City Sewer on 11th Avenue. The existing septic systems were abandoned. | None | May 2011 | Dec 2011 | 63000 | CDBG Grant |  |  | Completed | Patti Olney | 352-551-9263 | olneyp@ci.mount-dora.fl.us
Ocoee | Low Impact | Springshed / Wekiva River | S3OCE1 | Lift Station #7 Rehab and Relocation | Utilities/Engineering | City of Ocoee | The rehabilitation by replacement of the existing Lift Station #7 | Existing lift station had reached the end of its life cycle and was experiencing operational issues. The replacement station was reclocated north 900', a new gen set was provided, bypass pumping was provided and an increase in pump's hp. | FDEP #0018234-010 | August 2008 | November 2010 | 1901067 | Bond Proceeds | n/a | n/a | Completed and in Operation | City of Ocoee Utilities Department | (407) 905-3159 |  | Project increased treatment conveyance capacity by approx. 750 ERU per day and took offline an over-capacity forcemain suffering from historical failures.
Orlando | Low Impact | Little Wekiva River | S4ORL | Fairview Shores - North Service Area | City of Orlando |  | New Sanitary Service + 2 Stormceptor Units | Improvements of the sanitary sewer, drainage and roadway. Installed new sanitary force main, lift station(#65) and gravity pipes in area with septic tanks to reduce nutrient seepage into groundwater table. Installed 2 Stormceptors to capture gross pollutants before reach lake. | 40-095-97536-1 | 2006 | 2008 | 4522401 | Multiple Sources including Stormwater Utility & Wastewater General Construction Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Medium Impact | Little Wekiva River | S4ORL | Rio Grande Sanitary Sewer | City of Orlando |  | New Sanitary Service | Installation of gravity lines in area with septic tanks to reduce nutrient seepage into groundwater table |  | 1999 | 2000 | 1622124 | Wastewater General Construction Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Medium Impact | Little Wekiva River | S4ORL | West Lake Fairview Sanitary Sewer | City of Orlando |  | New Sanitary Service | Installation of sanitary sewer in area with septic tanks to reduce nutrient seepage into groundwater table |  |  |  | 6000000 | Wastewater General Construction Fund |  |  | Envisioned | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River, Little Wekiva Canal | S4ORL | Mercy Dr Sewer Rehab | City of Orlando |  | Sanitary Force Main and Pipe Replacement | Replaced Force Main on Mercy Dr from S of Princeton to LS #45. Connected or replaced new sanitary pipe to existing pipes. |  | 2000 | 2002 | 878400 | Wastewater Renewal and Replacement Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net | Prior to replacement, Force Main failure had caused 2 major overflows into Lake Lawne
Orlando | Low Impact | Little Wekiva River, Little Wekiva Canal | S4ORL | Regent Ave Force Main 2613 | City of Orlando |  | New Sanitary Force Main | Construction of force main along Silver Star Rd connecting Lift Station #37 to existing 24" Force Main and 24" gravity sewer on Mercy Dr |  |  |  | 2000000 | Wastewater Collection System Construction Fund |  |  | Envisioned | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net | Design Complete; Waiting for additional $1 Million in funding
Orlando | Low Impact | Little Wekiva River | S4ORL | Lift Station #37 Improvements | City of Orlando |  | Sanitary Lift Station Replacement | Lift station is one of oldest in City. The wet well is made of brick and starting to fail. Lift station will be replaced with pre-cast concrete with a liner and bigger capacity. A new pumping station and associated components will be installed, along with a standby generator. Gravity pipes in area will also be replaced. |  | 6/2009 | Ongoing | 1400000 | Wastewater Collection System Construction Fund |  |  | Ongoing | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | S4ORL | Lift Station #93 Improvements | City of Orlando |  | Sanitary Lift Station Replacement | Lift Station was relocated and completely rebuilt with new, upgraded equipment, including a generator not present at previous location |  | 1999 | 2001 | 767632.31 | Wastewater General Construction Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Medium Impact | Little Wekiva River | S4ORL | Lynx Facility | City of Orlando |  | New Sanitary Service + Lift Station | Installation of sanitary sewer in area with septic tanks to reduce nutrient seepage into groundwater table |  | 2006 | 2007 |  |  |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | S4ORL | West Lake Silver Phase 1 & 2 | City of Orlando |  | New Sanitary Lift Station | Installation of Lift Station in new commercial area |  | 1999 | 2000 |  |  |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Springshed | S4ORL | Master Pump/Equilization at Water Conserv II | City of Orlando |  | Sewage Treatment Upgrades | Installation of Equalization Basin will regulate flows to allow for enhancement of treatment and overall reduction of TN & TP in effluent. (Average Flow = 14 MGD (Daily ranges: 7-25 MGD)) |  | 1/09 | Ongoing | 13009575 | Wastewater General Construction Fund | See Comments |  | Completed | Paul Deuel | (407) 246-3510 | Paul.Deuel@cityoforlando.net | Estimated 15-20% TN & TP Reduction in effluent; Expected Completion Date = June 2011
Orlando | Low Impact | Springshed | S4ORL | Phase One Treatment Plant Improvements at Water Conserv II | City of Orlando |  | Sewage Treatment Upgrades | Installation of Internal Recycle Pump + Improvements to Aeration and Secondary Clarifier |  | 2011 | 2014 | 12000000 | State Revolving Fund | See Comments | Under Design | Ongoing | Paul Deuel | (407) 246-3510 | Paul.Deuel@cityoforlando.net | Estimated 20% NOx Reduction in effluent
Orlando | Low Impact | Little Wekiva River | S4ORL | Lift Station #85 VFD's | City of Orlando |  | Sanitary Lift Station Improvements | Installation of Variable Frequency Drives that will extend life of pump motors, which prevents possibility of overflows. In addition, will be more energy efficient at a future cost savings to City. |  |  |  | 2830 | Wastewater General Construction Fund |  |  | Envisioned | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Low Impact | Little Wekiva River | S4ORL | Line Sanitary Sewers | City of Orlando |  | Line Sanitary Sewers | Line sewers to prevent untreated sewage from escaping through cracks and joints. Project will reduce nutrient seepage into groundwater table. |  |  |  | 2500 | Wastewater Collection System Construction Fund |  |  | Planned & Funded | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net | 0.5 miles of pipe are expected to be lined within basin
Orlando | Low Impact | Little Wekiva River | S4ORL | Sanitary System Inspections | City of Orlando |  | Sanitary System Inspections | Conduct proactive inspections and perform routine maintenance on lift stations and sanitary lines. Identify problem areas and increase maintenance frequency or perform repairs to prevent overflows from occurring. In addition, assist with Sunshine State One-call of Florida ("Call Before You Dig" / Line Locates). |  |  | Ongoing |  | Wastewater Collection System Construction Fund |  |  | Ongoing | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orlando | Medium Impact | Little Wekiva River | S4ORL | Arthur Ave Sewer Line | City of Orlando |  | New Sanitary Service | Installation of approximately 1200' of gravity lines in area with septic tanks to reduce nutrient seepage into groundwater table. |  | 1998 | 1998 | 53977 | Wastewater General Construction Fund |  |  | Completed | Chuck Shultz | (407) 246-2658 | Charles.Schultz@cityoforlando.net
Orange County | Low Impact | Wekiva Springshed/Study Area | S7OC1? | Forcemain/Gravity Replacement (All American Boulevard Improvements; Clarcona Ocoee - Clarke to Hiawassee Improvements; Clarcona Ocoee - Ingram to Clarke; North Pine Hills Forcemain Reroute; Maitland Boulevard Extension East form Rose Avenue to Hiawassee Road) | Orange County Public Works (OCPW) | OCU/OCPW | Forcemain/Gravity | Install 1200 feet of 4-inch forcemain. New forcemain expected to prevent ww leakage. All American Blvd from Clarcona Ocoee to Kennedy; Forcemain from Avalon Road to Hiawassee Road. 7600 LF 36" FM; 760 LF 30" FM; and 1200 LF 12" FM Many parcels near 35-21-28-0000-00-150; Install 4500 feet of 12" forcemain. New forcemain expected to prevent ww leakage. Clacona Ocoee Road from Ingram to Clarke; Install 11,000 ft of forcemain from Indian Hill Rd to PS #3411. New forcemain will prevent ww leakage. North Pine Hills Road at Indian Hill Road and Clarcona0Ocoee Road; Relocate 710 LF 4" FM; 1280 LF 16" FM; and 710LF 8" gravity main Many parcels near 30-21-29-0521-00-010 | TBD | TBD | TBD | 10494000 | OCUD Capital Improvements Program Budget | 685.57 | Notes | 90% design | Christina Crosby | 407-254-9706 | Christina.Crosby@ocfl.net | ROW purchase underway
Orange County (Utilities) | Low Impact | Wekiva Springshed/surface watershed | S7OC1? | Gravity Sewer Rehab (Lake Lawne Rehabilitation; Powers Drive/ Hudson Street Wastewater Improvements; Lakewood Forest and Tealwood Cove Wastewater Improvements) | Orange County Utilities (OCU) | Possible partnership with City of Orlando - final decision pending | Gravity Sewer Replace/Repairs | Combination of CIPP and point repairs to restore approximately 10,000 LF of 8-inch gravity sanitary sewer including lining or coating 40 manholes. Near 20-22-29-4552-08-001; In addition to upsized storm pipes that go to Lake Robin, project includes replacing FM, gravity line, and manhole. Replacement of the forcemain will reduce leakage of sewage. Near 24-22-28-7573-15-250; Pump Station #3045 will be removed and relocated plus removal of existing force main and installation of 800 feet of gravity sewer. 29-21-29-4940-00-230 | exempt | 2006 & 2008 | On-going | 1780000 | SRF & OCUD Capital Improvements Program Budget | 605.55 | N/A | Construction 75% complete | Elizabeth O'Reilly | 407-254-9734 | elizabeth.oreilly@ocfl.net
Orange County | Low Impact | Wekiva Springshed/Study Area | S7OC1? | Pump Station Replacements/Repairs (Huggins PS #3006 Replacements; Hiawassee Rd.; NWSA PS "B"; Laurel Park; Chateau Orleans; Sherry Drive; Citrus Cove; Magnolia Bay; Sun Bank PS # F3169 (fka 3001); Lake Sherwood Hills; Lonesome Pines PS # F3195 (fka 3012); Breezewood Sub; Lake Sparling 1; Lake Sparling 2) | Orange County Utilities (OCU) | None | Pump station | Replace Pump Station #3006 Huggins and North Hastings; R/R of wastewater pump station #3038 26-22-28-0000-00-003; R/R of wastewater pump station #3411 06-22-29-5844-00-110; R/R of wastewater pump station #3099 20-23-29-5360-00-170; R/R of wastewater pump station #3133 21-23-29-5361-00-211; R/R of wastewater pump station #3225 12-23-30-1280-00-001; R/R of wastewater pump station #3251 33-21-29-1341-00-002; R/R of wastewater pump station #3302 32-21-29-7134-03-301; R/R of wastewater pump station #F3169 19-22-29-6954-08-051; R/R of wastewater pump station #3230 23-22-28-0000-00-053; R/R of wastewater pump station #F3195 Near 13-22-28-5175-04-040; R/R of wastewater pump station #3014 12-22-28-0885-00-000; R/R of wastewater pump station #3028 01-22-28-0000-00-005; R/R of wastewater pump station #3202 01-22-28-4743-00-040 | TBD | 2006 - present | 2007-ongoing | 13263500 | OCUD Capital Improvements Program Budget | unknown | Notes | ongoing | Alan Gay | 407-254-9724 | allen.gay@ocfll.net
Seminole County | Low Impact | Wekiva Basin | S8SC1? | Lift Station Rehab | Seminole County Environmental Services | N/A | lift station rehabilitation | Wet well sealing and rehab of lines (Wilson School LS, Breckenridge LS, Stockbridge LS, Lake Forest #5 LS, Buckingham LS, Retreat at Wekiva LS, Aster Farms LS, Bel-Aire #3 LS, Bel-Aire #1 LS, Heathrow Master LS) | n/a | 7/2004 | 4/2006 | 324353 | Water & Sewer Maintenance Fund 401 |  |  | completed | Ruth Hazard | 407-665-2115 | rhazard@seminolecountyfl.gov
Seminole County | Low Impact | Wekiva Basin | S8SC1? | Gravity Main Testing & Repairs | Seminole County Environmental Services | n/a | lateral repair | lateral repair- 1512 Cherry Rdg, 2067 Northumbria, 169 Killarney Ct, Shadowmoss Dr gravity main repair- 844 Preserve Terr, International Dr. & CR46A, Lake Rena Dr. smoke testing and sealing laterals- Alaqua Lakes, Heathrow Woods # 1 & 2 LS, Lake Forest 1 & 2, Lake Forest 1 & 2 additional work, Lake Forest 3 & 4, Aster Farms | n/a | 2/2005 | 12/2011 | 401878 | Water & Sewer Maintenance Fund 401 |  |  | completed | Ruth Hazard | 407-665-2115 | rhazard@seminolecountyfl.gov
Seminole County | Low Impact | Wekiva Basin | S8SC1? | Apple Valley LS | Seminole County Environmental Services | n/a | Lift station replacement | relocated and built brand new lift station | n/a | 5/2010 | 8/2010 | 351975 | Seminole County Capitol Improvement Projects |  |  | completed | Ruth Hazard | 407-665-2115 | rhazard@seminolecountyfl.gov
Seminole County | Low Impact | Wekiva Basin | S8SC1? | Bridgewater Drive | Seminole County Environmental Services | n/a | manhole sealing | manhole sealing | n/a | 7/2010 | 7/2010 | 16179 | Water & Sewer Maintenance Fund 401 |  |  | completed | Ruth Hazard | 407-665-2115 | rhazard@seminolecountyfl.gov
Winter Garden | Low Impact | Springshed | S2WG | State Road 50 Utility Relocation | City of Winter Garden | N/A | Sewering | Replacement of City utilities due to the widening of SR 50. This project includes the replacement of 5,210 LF of 24 inch clay pipe and 2,650 Lf of 18 inch clay pipe. | N/A | Jan 10 | 12/2011 | Capital | Utilities |  |  | Ongoing | Michael Kelley | 407 656 4111 | mkelley@cwgdn.com | The existing clay pipe is being replaced with SDR 26 PVC pipe. This project also includes the installation of fiberglass sanitary sewer manholes.
Note on B10: sandra doty: Replacing with city ordinance
Note on B13: sandra doty: Replacing with city ordinance
Note on B16: sandra doty: Replacing with city ordinance