## Contact Information
First Name | Last Name | Agency Name | Street Address | Street Address 2 | City | State | Zipcode | Phone # | Cell # | Email
Mary | Brabham | SJRWMD | 601 South Lake Destiny Rd. | Suite 200 | Maitland | FL | 32751 | 407-659-4829 |  | mbrabham@sjrwmd.com
Robert | Mattson | SJRWMD | 4049 Reid Street |  | Palatka | FL | 32177 | 386-329-4582 |  | rmattson@sjrwmd.com
Casey | Fitzgerald | SJRWMD | 4049 Reid Street |  | Palatka | FL | 32177 | 386-329-4554 |  | cfitzgerald@sjrwmd.com
Jim | Troiano | SJRWMD | 4049 Reid Street |  | Palatka | FL | 32177 | 386-643-1960 |  | jtroiano@sjrwmd.com

## Project Data Collection
Year Added | Spring | Project Number | Project, Phase or Milestone | Agency | Contact | Project Type | Project Description | Start Date | Status | Completion Date | Associated Permit #, if applicable | Treated Acres | Estimated TN Load Reduction (lbs/yr) | Estimated NOx Load Reduction (lbs/yr) | Estimated TP Load Reduction (lbs/yr) | Back UP Calculations Available (Yes/No) | Construction Cost | Annual Operation and Maintenance Cost | Funding Source(s) | Project Partner(s) | Project Area Map | Name of Project Map File (if providing electronically)
Adoption | Silver | S013 | LochLoosa Wildlife Conservation Area | SJRWMD | n/a | Conservation Land Acquisition | Acquisition of land around Lochloosa Lake and around north side of Orange Lake for Lochloosa Wildlife Conservation Area. Benefits: No increase in surface runoff of pollutants due to land-use change. | 2003 | Completed Project | 2003 | n/a | 28337 | n/a | n/a | n/a | No | 16058211 | n/a | SJRWMD ad valorem; Preservation 2000; Alachua County cost-share | n/a | No
Adoption | Silver | S067 | SJRWMD Springs Protection Initiative Science (SPIS) | SJRWMD | Robert Mattson/Casey Fitzgerald | Studies | In 2013, the SJRWMD initiated a Springs Protection Initiative and the District recognizes this effort as a strategic priority for the agency. The initiative includes three major components: projects, science and regulation. The science component (SPIS) acknowledged that effective management of springs required advanced understanding of the relative influences and manageabilities of the numerous natural and anthropogenic forcings that affect spring's ecological health and that substantial interdisciplinary research was needed to achieve this goal (FDEP, 2007). The District contracted with the UF Water Institute to partner and work collaboratively on this integrated work. Technical workgroups were organized as follows: Springshed Supergroup (Surface Water, Ground Water, and Nitrogenbiogeochemistry) and the Springs Ecosystem Supergroup (Hydrology and Hydrodynamics, Biology, and Physicochemistry). The effort focused on the Silver Springs system and its' springshed with a goal to provide a much more robust scientific foundation for determining the most cost-effective approaches to protect and restore Silver Springs and River. The findings and results of this investigation will support future BMAP activities. The three-year effort was finalized in December 2017 and will be featured at the February 2018 UF Water Institute Symposium. The final report can be downloaded from this webpage: https://www.sjrwmd.com/waterways/springs/springs-science-investigation/. | 2013 | Completed Project | 2017 | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | SJRWMD | University of Florida | No | https://www.sjrwmd.com/waterways/springs/springs-science-investigation/
Adoption | Silver | S068 | SJRWMD Water Resource Information and Data Collection | SJRWMD | David Hornsby/ Rob Mattson | Data Collection | The SJRWMD has core monitoring in/on Silver Springs, Silver River and contributing area to Silver Springs. The core monitoring consist of discharge monitoring, surface and ground water levels, surface and ground water quality, and biological monioring. As part of the SJRWMD Springs Protection Initiative, the SJRWMD has added an additional discharge monitoring site, increased the number and sampling frequency of surface and ground water quality sites, increased biological monioring and added continuous water quality monitoring at five sites in the Silver River. Upon conclusion of the SPIS, some of the monitoring sites have been eliminated. A current list is attached as a separate worksheet: SJRWMD Monitoring. | 2000 | Ongoing Project | ongoing | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | SJRWMD | USGS | No
| Silver | new | SJRWMD Submerged aquatic vegetation (SAV) and algae monitoring | SJRWMD | Robert Mattson | Data Collection | The SJRWMD monitors SAV and algae annually on the Silver River between April and June. District staff estimate SAV cover by species and algal cover collectively, using 0.25 m2 quadrats and the Braun-Blanquet cover scale. A separate worksheet has been added to this file for a map and more detail. | 2012 | Ongoing Project | ongoing | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | SJRWMD | n/a | Yes, see added worksheet
Adoption | Silver | S114 | Silver Springs Forest | SJRWMD | Mary Brabham | Conservation Land Acquisition | This project involves acquisition of 4,900 acres of managed forest land, owned by Rayonier, east of Indian Lake State Forest and west of C.R. 315. The acquired land will be restored to an appropriate ecosystem and opened for recreational use. This tract is identified in the Heather Island Florida Forever Project and as a US Forest Service Forest Legacy Project: Silver Springs Watershed (Phase 1). | 2016 | Completed Project | 2016 | n/a | 4900 | n/a | n/a | n/a | No | 11617000 | n/a | FDEP ($2,000,000); FSJRWMD ($8,700,000); Marion County ($917,000) | FDEP, Marion County | Yes | FLSilverSpringsWatershedFY2015.pdf
2016 | Silver | S134 | Silver Springs Forest | SJRWMD | Mary Brabham | Restoration Project | The project will address water resources at the site and in the receiving system with hydrology, attenuation, and sediment transport improvements. The project will provide reduction of turbid water discharges to the Silver River, the project will reduce nutrient loading by up to 13,000 pounds per year. Evaluation of the final project elements is still underway. | 2017 | Ongoing Project | 2018-09-01 | n/a | 4900 | 2300-11,500 | n/a | 300-1500 | No | 2370000 | n/a | SJRWMD ($1,895,000); FDEP ($475,00) | FDEP, Marion County | n/a | n/a

## Sheet1
Agriculture BMP | Completed Project | Silver | Wastewater System Upgrade | Adoption
Planning | In Progress | Rainbow | Wastewater Service Area Expansion (OSTDS) | 2016
Conservation Land Acquisition | Ongoing Project | Both | Wastewater Service Area Expansion (Package Plant) | 2017
Data Collection | Funded Planned Project |  | Wastewater Collection System Maintenance
Studies | Unfunded Planned Project |  | Reuse Project
Regulation or Ordinance | Conceptual Project |  | Wastewater Level of Service Planning
Urban Structural BMP | Cancelled Project
Street Sweeping
Education and Outreach
Stormwater Operation and Maintenance

## SJRWMD Monit sites update
SJRWMD - Silver Springs/River active surface water monitoring stations
Station | Frequency | Latitude | Longitude | Coordinate System | Parameters
SSR | Bimonthly | 291240.768 | 815922.194 | DMS | Springs Initiative
SSG-Mammoth | Bimonthly | 291258.45 | 820309.7 | DMS | Springs Initiative
SILBIRD | Monthly/Continuous | 291255.514 | 820227.396 | DMS | CM**/Continuous
Half Mile Creek | Bimonthly | 291258.9824 | 820226.16 | DMS | Springs Initiative
Springs Initiative |  |  | CM** |  |  | Continuous
Alkalinity |  |  | Alkalinity |  |  | Depth of Collection
Conductivity |  |  | Conductivity |  |  | DO
Chloride |  |  | Chloride |  |  | % DO
Sulfate |  |  | Sulfate |  |  | fDOM
BOD |  |  | Chlorophyll |  |  | Nitrate + Nitrite
Dissolved Nitrate + Nitrite |  |  | Dissolved Nitrate + Nitrite |  |  | pH
Dissolved Orthphosphate |  |  | Dissolved Orthphosphate |  |  | Phosphate
Total Major Metals |  |  | Total Metals |  |  | Relative Chlorophyll
Total and Dissolved Total Kjeldahl Nitrogen |  |  | Total and Dissolved Total Kjeldahl Nitrogen |  |  | Salinity
Total and Dissolved Total Phosphorus |  |  | Total and Dissolved Total Phosphorus |  |  | Specific Conductance
Fluoride |  |  | Color |  |  | Turbidity
Color |  |  | Total and dissolved Organic Carbon |  |  | Water Temperature
Total and dissolved Organic Carbon |  |  | Dissolved Ammonia
Dissolved Ammonia |  |  | Total and dissolved silica
Total and dissolved silica |  |  | Total suspended solids |  | ** - NOTE THAT THESE ARE GRAB SAMPLES
Total suspended solids |  |  | Turbidity |  | ANALYSED IN THE LAB; THEY ARE TAKEN
Turbidity |  |  | Volatile suspended solids |  | WHEN THE CONTINUOUS SENSORS ARE
Volatile suspended solids |  |  | Water temperature |  | SERVICED
Water temperature |  |  | Air temperature
Air temperature |  |  | Depth of collection
Depth of collection |  |  | Depth of stream
Depth of stream |  |  | Weather
Weather |  |  | pH
pH |  |  | Conductivity
Conductivity |  |  | DO
DO |  |  | % DO
% DO |  |  | Secchi
Secchi |  |  | Cloud cover
Cloud cover |  |  | Wind direction
Wind direction |  |  | Wind speed
Wind speed

## Annual SAV&Algae Monitoring
SJRWMD Annual submerged aquatic vegetation (SAV) and algae annually on Silver River (2012 to Present)
Comment | X | Y | OBJECTID | Datum | WGS_84 | SiteID | N | W
SLVR01 | 82° 3' 9.86" W | 29° 12' 57.42" N | 1 | WP | D | slvr1 | 29.2159 | -82.0527
SLVR02 | 82° 3' 8.24" W | 29° 12' 55.84" N | 2 | WP | D | slvr2 | 29.2155 | -82.0523
SLVR03 | 82° 3' 5.29" W | 29° 12' 54.83" N | 3 | WP | D | slvr3 | 29.2152 | -82.0515
SLVR04 | 82° 2' 58.31" W | 29° 12' 56.88" N | 4 | WP | D | slvr4 | 29.2158 | -82.0495
SLVR05 | 82° 2' 49.67" W | 29° 12' 56.92" N | 5 | WP | D | slvr5 | 29.2158 | -82.0471
SLVR06 | 82° 2' 40.42" W | 29° 12' 55.15" N | 6 | WP | D | slvr6 | 29.2153 | -82.0446
SLVR07 | 82° 2' 21.01" W | 29° 12' 53.93" N | 7 | WP | D | slvr7 | 29.215 | -82.0392
SLVR08 | 82° 2' 4.31" W | 29° 12' 33.26" N | 8 | WP | D | slvr8 | 29.2092 | -82.0345
SLVR09 | 82° 1' 50.02" W | 29° 12' 23.47" N | 9 | WP | D | slvr9 | 29.2065 | -82.0306
SLVR10 | 82° 1' 0.41" W | 29° 12' 8.78" N | 10 | WP | D | slvr10 | 29.2024 | -82.0168
SLVR11 | 82° 0' 11.37" W | 29° 12' 18.19" N | 0 |  |  | slvr11 | 0 | 0
SLVR12 | 81° 59' 38.58" W | 29° 12' 35.14" N | 12 | WP | D | slvr12 | 29.2098 | -81.9941
SLVR13 | 81° 59' 36.10" W | 29° 12' 35.28" N | 0 |  |  | slvr13 | 0 | 0
SLVR14 | 81° 59' 18.45" W | 29° 12' 43.38" N | 0 |  |  | slvr14 | 0 | 0
The SJRWMD monitors SAV and algae annually on the Silver River between April and June. District staff estimate SAV cover by species and algal cover collectively, using 0.25 m2 quadrats and the Braun-Blanquet cover scale:
1 = < 5% cover (trace of vegetation)
2 = 5-25% cover
3 = 25-50% cover
4 = 50-75% cover
5 = 75-100% cover
0 = Bare bottom (no vegetation at all)