## Contact Information
First Name | Last Name | Agency Name | Street Address | Street Address 2 | City | State | Zipcode | Phone # | Cell # | Email
Dawn | Bowne | City of Dunnellon | 20750 River Drive |  | Dunnellon | FL | 34431 | 352-465-8500 ext 1002 |  | dbowne@dunnellon.org
Will | Fontaine | FGUA | 280 Wekiva Springs Road |  | Longwood | FL | 32779 | 352-409-6520 |  | wfontaine@govmserv.com

## Project Data Collection
Year Added | Spring | Project Number | Project, Phase or Milestone | Agency | Contact | Project Type | Project Description | Start Date | Status | Completion Date | Associated Permit #, if applicable | Treated Acres | Estimated TN Load Reduction (lbs/yr) | Estimated NOx Load Reduction (lbs/yr) | Estimated TP Load Reduction (lbs/yr) | Back UP Calculations Available (Yes/No) | Construction Cost | Annual Operation and Maintenance Cost | Funding Source(s) | Project Partner(s) | Project Area Map | Name of Project Map File (if providing electronically)
Adoption | Rainbow | R001 | River Protection Corridors | City of Dunnellon | Dawn Bowne | Regulation or Ordinance | The City of Dunnellon River Protection Corridor Areas for both the Rainbow and Withlacoochee River. The corridor extends 150 feet from the ordinary high water line and implements specific development standards for new development and for construction on existing lots with vested development rights after 2008. | 2008 | Ongoing Project | Ongoing | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | n/a | n/a | No
Adoption | Rainbow | R003 | Blue Cove Emergency Overflow Project | City of Dunnellon | Dawn Bowne | Urban Structural BMP | Project to construct a retention pond, with a control structure and pipe conveyance system to treat and convey flood overflows from Blue Cove to the Rainbow River. Prior to construction overflows sheet flowed through residential neighborhood to the River. | 2000 | Completed Project | 2011 | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | City of Dunnellon | SWFWMD | No
Adoption | Rainbow | R004 | Datesman Park Overflow Parking Lot Improvement | City of Dunnellon | Dawn Bowne | Urban Structural BMP | Project retrofitted a car and boat trailier overflow parking lot with pervious pavers and a stormwater retrntion pond. | 2000 | Completed Project | 2010 | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | City of Dunnellon | n/a | No
Adoption | Rainbow | R022 | Dunnellon Watershed Management Plan | City of Dunnellon | Dawn Bowne | Studies | The Dunnellon Watershed Management Plan developed a hydrologic and hydraulic model and water quality treatment recommendations for 9 stormwater discharge outfalls to the Rainbow and Withlacoochee Rivers. | 2004 | Completed Project | 2004 | n/a | n/a | n/a | n/a | n/a | No | 50000 | n/a | City of Dunnellon | Marion County, SWFWMD | No
Adoption | Rainbow | R050 | Rainbow River Acres Stormwater Retrofit | City of Dunnellon | Dawn Bowne | Urban Structural BMP | Proposed project in the vicinity of Oak St and Palmetto Way in the Rainbow River Acres subdivision. The Project would construct a stormwater pond to address flooding and to provide water quality for untreated stormwater runoff the currently sheetflows into the Rainbow River. | 2020 | Conceptual Project | TBD | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | City of Dunnellon | n/a | No

## Utility Project Data Collection
Year Added | Spring | Project Number | Agency | Contact | Project, Phase or Milestone | Project Type | Project Description | Start Date | Status | Completion Date | Associated Permit #, if applicable | Permited Effluent Nitrate Concentration (mg/L) | Permit Reporting Requirement for TN | Reported Effluent Nitrate Concentration (mg/L) | Reported Effluent TN Concentration (mg/L) | Permitted Capacity (MGD) | Operating Capacity (MGD) | For System Upgrades, Reduction in Effluent TN Concentration (mg/L) | For Service Area Expansions, Number of On-Site Treatment and Package Plants Closed | For Collection System Maintenance, Number of Leaks Detected and Repaired | For Reuse Projects, Elluent Used for Reuse (MGD) | Area Treated by Reuse | Project Cost | Annual Operation and Maintenance Cost | Funding Source(s) | Project Partner(s) | Description of Additional Treatment Provided Beyond Permit Requirements, If Applicable | Estimated Load Reduction (lbs/yr) (TN) - Land Surface
Adoption | Rainbow | R019 | City of Dunnellon | Dawn Bowne | Sewer Conversion Project, Phases 1-4 | Wastewater Service Area Expansion (OSTDS) | Project constructed new sewer system within the City limits allowing properties previously on septic systems (140 in Ph 2) hooked up to central sewer. | 2000 | Completed Project | 2012 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | 140 | n/a | n/a | n/a | n/a | n/a | City of Dunnellon | n/a | n/a | 3347.008
Adoption | Rainbow | R057 | City of Dunnellon | Dawn Bowne | Rio Vista WWTP Decommissioning | Wastewater System Upgrade | Project will decommisioned the Rio Vista WWTP and convert an existing lift station to pump waste water to the Rainbow Springs Plant. | 2015 | Completed Project | 2015 | FLA012674 | 12 | No | 2.33 | 6.05 | 0.025 | 0.006 | 3.05 | n/a | n/a | n/a | n/a | n/a | n/a | City of Dunnellon | n/a | n/a | 55.7431
Adoption | Rainbow | R058 | City of Dunnellon | Dawn Bowne | Rio Vista Collection System Maintenance | Wastewater Collection System Maintenance | Companion project to the Rio Vista WWTP decommisioning. The collection system is subject to high infiltration into the system after storm events resulting in overflows from the plant holding pond. | 2014 | Completed Project | 2015 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | City of Dunnellon | n/a | n/a | n/a
Adoption | Rainbow | R059 | City of Dunnellon | Dawn Bowne | SCADA Installation | Wastewater Collection System Maintenance | Planned phased project for installation of SCADA at City WWTPs followed by installation at lift stations. | 2020 | Conceptual Project | TBD | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | City of Dunnellon | n/a | n/a | n/a
Adoption | Rainbow | R054 | City of Dunnellon | Dawn Bowne | Wastewater Level of Service Coordination - Package Plant Abatement P113 Rainbow Springs Infrastructure Development | Wastewater Service Area Expansion (Package Plant) | Effort by the City of Dunnellon utility to improve the level of treatment of wastewater in the Rainbow Springs area. It is also anticipated that the project would initially allow 5 package plants to hook up to central sewer, with the potential for additional connections in the future. Design, permitting and construction of a wastewater force main from the Juliette Subdivision to the City of Dunnellon Wastewater Treatment Plant (WWTP) and upgrade of the Juliette Falls lift station with larger pumps. Once the force main is constructed, upgraded lift stations and connection force mains will be constructed at up to four sites. Project description also identified in the SWWMD Grant Funding project lis as “180th Street Corridor Wastewater Improvement Project” | 2019 | Funded Planned Project | 2020 | various | n/a | No | n/a | 6.4091 | 0.071 | 0.022 | 3.41 | 5 | n/a | n/a | n/a |  | n/a | SWFWMD; City of Dunnellon | SWFWMD | n/a | 228.5162
| Rainbow |  | City of Dunnellon | Dawn Bowne | Rainbow Springs WRF Decommissioning | Rerate the City of Dunnellon WRF to 0.50 MGD and construct a FM from Rainbow Springs WRF to the City's WRF and Decommission Rainbow Springs WRF. | Rerate the City of Dunnellon WRF to 0.50 MGD and construct a FM from Rainbow Springs WRF to the City's WRF and Decommission Rainbow Springs WRF. The City of Dunnellon recognizes the vital ecological and economic importance that Rainbow Springs and the Rainbow River has in the community. These bodies of water are listed as Outstanding Florida Waters and are classified as high priorities in the Surface Water Improvement and Management Plan (SWIM). These bodies of water are impaired under FAC 62-303(d) by total nitrogen (TN) as identified in the adopted Total Maximum Daily Load (TMDL). With this in mind, The primary objective of the PROJECT is to design and construct a sanitary sewer system which will remove from service the Rainbow Springs WRF (highlighted in on the location map) which treats approximately 0.15 MGD. The WRF contributes to the total nitrogen(TN) impairment of Rainbow Springs and the Rainbow River. The removal of the WRF will result in a substantial and measurable reduction in the identified pollutant sources. This is quantified in the Total Nutrient Removal section. This project is dependent on the rerating of the City of Dunnellon's WRF to 0.50 MGD. | 2020 | Unfunded Planned Project | N/A | various | N/A | YES | N/A | 25 | 0.23 | 0.15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | SWFWMD | N/A | 8943
Note on D6: Williams, Evan: Lead entity updated per conversation with City of Dunnellon Staff.

## Sheet1
Agriculture BMP | Completed Project | Silver | Wastewater System Upgrade | Adoption
Planning | In Progress | Rainbow | Wastewater Service Area Expansion (OSTDS) | 2016
Conservation Land Acquisition | Ongoing Project | Both | Wastewater Service Area Expansion (Package Plant) | 2017
Data Collection | Funded Planned Project |  | Wastewater Collection System Maintenance
Studies | Unfunded Planned Project |  | Reuse Project
Regulation or Ordinance | Conceptual Project |  | Wastewater Level of Service Planning
Urban Structural BMP | Cancelled Project
Street Sweeping
Education and Outreach
Stormwater Operation and Maintenance