## Contact Information
First Name | Last Name | Agency Name | Street Address | Street Address 2 | City | State | Zipcode | Phone # | Cell # | Email
Jim | Couillard | Marion County - Parks and Recreation | 111 SE 25th Ave |  | Ocala | FL | 34471 | 352-671-8559 |  | James.Coulliard@marioncountyfl.org
Greg | Wiley | Marion County - Parks and Recreation | [7 empty] | Greg.Wiley@marioncountyfl.org

## Project Data Collection
Year Added | Spring | Project Number | Project, Phase or Milestone | Agency | Contact | Project Type | Project Description | Start Date | Status | Completion Date | Associated Permit #, if applicable | Treated Acres | Estimated TN Load Reduction (lbs/yr) | Estimated NOx Load Reduction (lbs/yr) | Estimated TP Load Reduction (lbs/yr) | Back UP Calculations Available (Yes/No) | Construction Cost | Annual Operation and Maintenance Cost | Funding Source(s) | Project Partner(s) | Project Area Map | Name of Project Map File (if providing electronically)
Adoption | Silver | S094 | Sports Field Maintenance Equipment Wash Down Area | Marion County Parks | Jim Couillard | Urban Structural BMP | The FDEP has developed Best Management Practices (BMP) for the Enhancement of Environmental Quality on Florida Golf Courses manual which highlights a series of BMPs that can be implemented to offset the impacts that golf courses have on our environment. Active sports complexes can have the same impacts. One commonly used BMP is the construction of a “closed system equipment wash down area.” Similar facilities would allow Parks staff to wash down mowers and other equipment which have been used while maintaining the sports fields. Four sites (Brick City Adventure Park, Rotary Sportsplex, Shocker Park and Ralph Russell Memorial Park) are all within 10 miles of Silver Springs and therefore should receive a higher priority of scheduling the construction of the wash down facilities. | TBD | Conceptual Project | TBD | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | Marion County General Fund | n/a | No
Adoption | Silver | S095 | Parks Retention Pond Retrofits | Marion County Parks | Jim Couillard | Urban Structural BMP | This project is an inventory of stormwater facilities in Marion County Parks to identify and prioritize them for potential retrofits to enhance nitrogen removal. The retrofits would involve the removal of a layer of soil from the bottom of the basins and then the constructing an engineered soil matrix. The goal of this project is to retrofit specific stormwater basins to reduce groundwater pollution. The inventory be conducted using GIS asset management tools. | TBD | Conceptual Project | TBD | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | Marion County General Fund | n/a | No
Adoption | Silver | S099 | Marion/Aquifer-Friendly Fertilization Program for Sports Facilities | Marion County Parks | Jim Couillard | Studies | The goal of this project would be to develop a method of maintaining 67.77 acres (Wrigley Fields, Brick City Adventure Park, Shocker Park, Rotary Sportsplex, Ralph Russell Memorial Park and Belleview Sportsplex) of sports fields in a manner that reduces, if not eliminates, pollutant loading while keeping the fields healthy and safe. This program includes the creation and use of specific fertilizer formulas on the playing fields at the various sports complexes that the Department manages. | TBD | Conceptual Project | TBD | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | Marion County General Fund | n/a | No
Adoption | Silver | S113 | Silver Springs Sandhill Acquisition | Marion County Parks | Jim Couillard | Conservation Land Acquisition | Marion County has applied to have the The Silver Springs Sandhill acquisition project added to the Florida Forever list. This project would preserve 470 acres of high recharge sandhills that are within a mile of Silver Springs. The project is located just south of Indian Lake State Forest and east of the Cohadjoe Park (County). The majority of the acerage is zoned for medium and high density residential use but 221 acreas are currently used for improved cattle with the balance being pasture unmanaged hardwoods. Acquistion has been assigned to a third-party non-profit organization to close the sale of this site. Site has been acquired and is under management by Marion County Parks and Recreation. Consultants are being solicited to write state-required Unit Management Plan. | 2016 | Completed Project | 2017-09-01 | n/a | 470 | n/a | n/a | n/a | No | 4432979 | n/a | Florida Forever; Marion County | n/a | Yes | Silver Springs Sanhill Florida Forever Application 1-16-15.pdf
Adoption | Silver | S117 | Heather Island Conservation Easement | Marion County Parks | Jim Couillard | Conservation Land Acquisition | This project would establish a conservation easement on 5,223 acres of privately owned forest land east of C.R. 315 along the Oklawaha River. This tract is identified as part of the Heather Island Florida Forever project and is identified as Phase 2 of the Silver Springs Watershed Forest Legacy project. Land has been aquired by SJRWMD with plans for surface water improvements underway. | TBD 2015 | Completed Project | TBD 2016 | n/a | 5223 | n/a | n/a | n/a | No | n/a | n/a | n/a | n/a | Yes | FLSilverSpringsWatershedFY2015.pdf
Adoption | Silver | S006 | Silver Springs Conservation Area | FDEP - Division of State Lands/Marion County Parks | Greg Wiley | Conservation Land Acquisition | Acquisition of 346 acres of undeveloped land directly across SR 35 from Silver Springs State Park. The land was acquired under the Florida's First Magnitude Springs project by the Division of State Lands. By preserving land around springs, this project will aid in the protection of springs, karst windows, and the Floridan Aquifer from the effects of commercial, residential, and agricultural runoff; clearcutting and mining; and unsupervised recreation. | 2005 | Completed Project | 2005 | n/a | 346 | n/a | n/a | n/a | Yes | 7847000 | 7847000 | Florida Communities Trust | Marion County | Yes | Seldin Aerial Map.pdf

## Utility Project Data Collection
Year Added | Spring | Project Number | Agency | Contact | Project, Phase or Milestone | Project Type | Project Description | Start Date | Status | Completion Date | Associated Permit #, if applicable | Permited Effluent Nitrate Concentration (mg/L) | Permit Reporting Requirement for TN | Reported Effluent Nitrate Concentration (mg/L) | Reported Effluent TN Concentration (mg/L) | Permitted Capacity (MGD) | Operating Capacity (MGD) | For System Upgrades, Reduction in Effluent TN Concentration (mg/L) | For Service Area Expansions, Number of On-Site Treatment and Package Plants Closed | For Collection System Maintenance, Number of Leaks Detected and Repaired | For Reuse Projects, Elluent Used for Reuse (MGD) | Area Treated by Reuse | Project Cost | Annual Operation and Maintenance Cost | Funding Source(s) | Project Partner(s) | Description of Additional Treatment Provided Beyond Permit Requirements, If Applicable | Estimated Load Reduction (lbs/yr) (TN) - Land Surface
Adoption | Silver | S096 | Marion County Parks | Jim Couillard | Septic System Connection Removal in County Parks | Wastewater Service Area Expansion (OSTDS) | This project focuses on the removal of on‐site sewage treatment and disposal (septic) systems and connection to centralized wastewater facilities. There are a few parks within this BMAP area which are in close proximity to existing or planned wastewater facilities (Brick City Adventure Park, Rotary Sportsplex, and Baseline Road Trailhead). The goal of this project would be to remove as many septic systems within this area as possible. | TBD | Conceptual Project | TBD | various | n/a | No | n/a | n/a | n/a | n/a | n/a | 3 | n/a | n/a | n/a | n/a | n/a | Marion County General Fund | n/a | n/a | 71.7216
Adoption | Silver | S097 | Marion County Parks | Jim Couillard | Gore's Landing Package Plant Upgrade | Wastewater System Upgrade | The Department has one package plant wastewater facility located at Gore’s Landing, which is a flood prone area located along the Ocklawaha River. The current system is antiquated and may not meet current sewage disposal standards and should be upgraded. The goal of this project is to bring an existing sewage treatment system into compliance with current standards and regulations while being mindful of potential expansion of the park. Exact dollar figures for this project are currently unknown. | TBD | Conceptual Project | TBD | n/a | n/a | No | n/a | 8.97 | 0.005 | n/a | 2.97 | 1 | n/a | n/a | n/a | n/a | n/a | Marion County General Fund | n/a | n/a | 45.2342

## Sheet1
Agriculture BMP | Completed Project | Silver | Wastewater System Upgrade | Adoption
Planning | In Progress | Rainbow | Wastewater Service Area Expansion (OSTDS) | 2016
Conservation Land Acquisition | Ongoing Project | Both | Wastewater Service Area Expansion (Package Plant) | 2017
Data Collection | Funded Planned Project |  | Wastewater Collection System Maintenance
Studies | Unfunded Planned Project |  | Reuse Project
Regulation or Ordinance | Conceptual Project |  | Wastewater Level of Service Planning
Urban Structural BMP | Cancelled Project
Street Sweeping
Education and Outreach
Stormwater Operation and Maintenance