## Contact Information
First Name | Last Name | Agency Name | Street Address | Street Address 2 | City | State | Zipcode | Phone # | Cell # | Email
Rusella | Bowes-Johnson | City of Ocala | 1805 NE 30th Ave | Bldg#600 | Ocala | FL | 34470 | 352-351-6772 |  | rjohnson@ocalafl.org
Scott | Hersey | City of Ocala | 1808 NE 36th Ave |  | Ocala | FL | 34470 | 352-401-6941 |  | shersey@ocalafl.org

## Utility Project Data Collection
Year Added | Spring | Project Number | Agency | Contact | Project, Phase or Milestone | Project Type | Project Description | Start Date | Status | Completion Date | Associated Permit #, if applicable | Permited Effluent Nitrate Concentration (mg/L) | Permit Reporting Requirement for TN | Reported Effluent Nitrate Concentration (mg/L) | Reported Effluent TN Concentration (mg/L) | Permitted Capacity (MGD) | Operating Capacity (MGD) | For System Upgrades, Reduction in Effluent TN Concentration (mg/L) | For Service Area Expansions, Number of On-Site Treatment and Package Plants Closed | For Collection System Maintenance, Number of Leaks Detected and Repaired | For Reuse Projects, Elluent Used for Reuse (MGD) | Area Treated by Reuse | Project Cost | Annual Operation and Maintenance Cost | Funding Source(s) | Project Partner(s) | Description of Additional Treatment Provided Beyond Permit Requirements, If Applicable | Estimated Load Reduction (lbs/yr) (TN) - Land Surface
Adoption | Silver | S035 | City of Ocala | Jeff Halcomb/Darryl Muse/Renee O'Donnell Darryl Muse/Rusella Bowes-Johnson | Citywide Septic Tank and Well Elimination Program | Wastewater Service Area Expansion (OSTDS) | This project includes the connection of the remaining septic tanks within the City of Ocala at no cost to the homeowners. It is estimated that septic tanks provide between 26 and 40 percent of the pollutant load to the groundwater in the springshed. Elimination of the septic tanks in this project is estimated to provide a reduction in nitrogen loading to Silver Springs by approximately 20,321 pounds of nitrogen per year. | 2015 | In Progress | 2017 2018 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | 850 | n/a | n/a | n/a | 10500000 | n/a | City of Ocala; FDEP ($5,000,000), SJRWMD ($5,000,000), Legislative ($500,000) | n/a | n/a | 20321.12
Adoption | Silver | S036 | City of Ocala | Jeff Halcomb/Darryl Muse/Renee O'Donnell Darryl Muse/Rusella Bowes-Johnson | Package Plant Abatement | Wastewater Service Area Expansion (Package Plant) | Connection of White Oak MHP, Magnolia Gardens, and 301 Plaza to central sewer. | 2015 | Completed Project | 2015 2016 | FLA012677; FLA012668; FLA10683 | n/a | No | n/a | 8.97 | 0.0445 | 0.03 | 5.97 | 3 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 545.5513
Adoption | Silver | S042 | City of Ocala | Jeff Halcomb/Darryl Muse/Renee O'Donnell Darryl Muse/Rusella Bowes-Johnson | Reuse Projects | Reuse Project | Reuse projects to three golf courses and City parks and recreation sites. Courses may be served by any of the sewer facilities due to infrastructure configuration. | 2014 | Completed Project | 2015 2016 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Adoption | Silver | S055 | City of Ocala | Darryl Muse/Rusella Bowes-Johnson | Collection System Maintenance Program | Wastewater Collection System Maintenance | Maintenance program has used TV inspection on entire collection system. Slip lining of 175,000 feet of clay pipe is complete and 40,000 feet per year scheduled through 2020. Lift stations are upgraded at about 3 per year. System and plants are SCADA controlled and flows can be rerouted. | 2000 | Ongoing Project | 2020 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
Adoption | Silver | S091 | City of Ocala | Darryl Muse/Rusella Bowes-Johnson | City of Ocala Nitrogen Reduction Project | Wastewater System Upgrade | Upgrade of WRF #2 to AWT treatment standard for TN and decommissioning of WRF #1. WRF #1 was constructed in 1949, is a trickling filter facility and is not designed for the removal of nitrate. WRF #2 and #3 have sufficient capacity to handle the flows from WRF #1 and all of the plants will be interconnected to allow for routing of flows as needed. WRF #1 will remain operational as a relay and to process stormwater for reuse. | 2017 2016 | Completed Project | 2019 2016 | FLA010677 | 12 | Yes | 5.68 | 20.9 | 2.46 | 0.776 | 17.9 | n/a | n/a | n/a | n/a | 16000000 | n/a | City of Ocala ($9,600,000) | FDEP (potentially) | n/a | 42311.1446
Adoption | Silver | S092 | City of Ocala | Darryl Muse/Rusella Bowes-Johnson | City of Ocala Water Reclamation Facility 2 Nutrient Reduction Plan | Wastewater System Upgrade | Upgrade an existing wastewater plant to allow for advanced treatment and expand the availability of reclaimed water for irrigation use. The project consists of construction of two (2) 3.25 mgd Carrousels equipped with three (3), 100-HP mechanical surface aerators with variable-frequency drives (VFDs) and lower impeller and anaerobic and anoxic zone submersible mixers. This will allow the City of Ocala to reduce effluent TN to 3 mg/L or less. An estimated 500,000 gallons of day of public access reclaimed water is expected to be made available from this project, reducing draws on the aquifer and increasing flows to the springs. | 2014 | Completed Project | 2016 | FLA010680 | n/a | Yes | 2.88 | 6.93 | 6.5 | 2.305 | 3.93 | n/a | n/a | 0.5 | n/a | 12144000 | n/a | City of Ocala ($8,304,000); SJRWMD ($1,920,000); Legislative Funding ($1,275,620) | Legislature; SJRWMD | n/a | 27593.2911
Adoption | Silver | S115 | City of Ocala | Darryl Muse/Rusella Bowes-Johnson | Miscellaneous Water and Sewer | Wastewater Service Area Expansion (OSTDS) | Miscellaneous extension of exisitng water, sewer, and reuse facilities to provide services. | 2015 | In Progress | 2020 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 500000 | n/a | City of Ocala | n/a | n/a | n/a
Adoption | Silver | S116 | City of Ocala | Darryl Muse/Rusella Bowes-Johnson | Sanitary sewer smoke testing, tving, and lining program | Wastewater Collection System Maintenance | Smoke testing and inspection of existing sanitary sewer system | 2015 | In Progress | 2020 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | 3000000 | n/a | City of Ocala | n/a | n/a | n/a
2016 | Silver | S135 | City of Ocala | Darryl Muse, Barry Ginn, Rusella Bowes-Johnson, Oscar Tovar | Wetland Recharge Park | Reuse Project | The creation of a wetland park which will primarliy utilize treated wastewater, along with some stormwater. The wetland area will be over 30 acres in size, and will receive 3-5 million gallons of treated waste/storm water a day. This water will then recharge the Upper Floridan Aquifer. The plants in the wetland area will naturally uptake a large portion of the excess nutrients. This will potentially reduce nitrogen levels to near zero, along with a notable reduction of all TN as well. | 2016 | In Progress | 2019 | pending 0358251-001 | n/a | n/a | 2 | 3 | Between the two WRF's 10 MGD | 5.1 MGD | n/a | n/a | n/a | up to 5 mgd | 34 AC | 10000000 | TBD | currently sourcing SJWRMD Cost Share, FDEP Springs Funding, City of Ocala | n/a | See Project Description | 29000
2017 | Both | B049 | City of Ocala | Rusella Bowes-Johnson | Fox Meadow Sewer Expansion Project | Wastewater Service Area Expansion (OSTDS) | The objective of the project s to design and construct a sanitary sewer system which will remove from service approximately 275 septic tanks from the associated single family residential lots. The septic tanks contribute to the total nitrogen (TN) and total phosphorus (TP) impairment of Rainbow Springs and the Rainbow River. | 2018 | Unfunded Planned Project | 2020 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | 275 | n/a | n/a | n/a | 3500000 4705000 | n/a | currently sourcing | n/a | n/a | 6800 2918
2017 | Both | B050 | City of Ocala | Rusella Bowes-Johnson | Fairfield Village Sewer Expansion Project | Wastewater Service Area Expansion (Package Plant) | The objective of this project is to design and construct a sanitary sewer system which will remove from service a package plant which serves approximately 350 mixed use residential lots and 1 community center. The package plant contributes to the total nitrogen (TN) and total phosphorus (TP) impairment of Rainbow Springs and the Rainbow River. | 2018 | Unfunded Planned Project | 2020 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | 1 | n/a | n/a | n/a | 950000 875000 | n/a | currently sourcing | n/a | n/a | 900 600
2017 | Both | B051 | City of Ocala | Rusella Bowes-Johnson | Timberwood Sewer Expansion Project | Wastewater Service Area Expansion (OSTDS) | The objective of this project is to design and construct a sanitary sewer system which will remove from service approximately 180 septic tanks from the associated single family residential lots. The septic tanks contribute to the total nitrogen (TN) and total phosphorus (TP) impairment of Rainbow Springs and the Rainbow River. | 2018 | Unfunded Planned Project | 2020 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | 180 | n/a | n/a | n/a | 3000000 3316000 | n/a | currently sourcing | n/a | n/a | 4462 1910
2017 | Silver | S136 | City of Ocala | Rusella Bowes-Johnson | Southwood Villas and Lake Weir Sewer Expansion Project | Wastewater Service Area Expansion (OSTDS) | The objective of this project is to design and consturct a sanitary sewer system which will remove from service approximately 100 septic tanks from the associated single family residential lots. | 2019 | Unfunded Planned Project | 2021 | n/a | n/a | No | n/a | n/a | n/a | n/a | n/a | 100 | n/a | n/a | n/a | 1500000 | n/a | currently sourcing | n/a | n/a | 1434

## Sheet1
Agriculture BMP | Completed Project | Silver | Wastewater System Upgrade | Adoption
Planning | In Progress | Rainbow | Wastewater Service Area Expansion (OSTDS) | 2016
Conservation Land Acquisition | Ongoing Project | Both | Wastewater Service Area Expansion (Package Plant) | 2017
Data Collection | Funded Planned Project |  | Wastewater Collection System Maintenance
Studies | Unfunded Planned Project |  | Reuse Project
Regulation or Ordinance | Conceptual Project |  | Wastewater Level of Service Planning
Urban Structural BMP | Cancelled Project
Street Sweeping
Education and Outreach
Stormwater Operation and Maintenance