## Contact Information
First Name | Last Name | Agency Name | Street Address | Street Address 2 | City | State | Zipcode | Phone # | Cell # | Email
Robin | Hallbourg | Alachua County EPD | [7 empty] | Robin@alachuacounty.us
Sandra | Vardaman | Alachua County EPD | [7 empty] | SMVardaman@alachuacounty.us
Gus | Olmos | Alachua County EPD | [7 empty] | gus@alachuacounty.us

## Project Data Collection
Year Added | Spring | Project Number | Project, Phase or Milestone | Agency | Contact | Project Type | Project Description | Start Date | Status | Completion Date | Associated Permit #, if applicable | Treated Acres | Estimated TN Load Reduction (lbs/yr) | Estimated NOx Load Reduction (lbs/yr) | Estimated TP Load Reduction (lbs/yr) | Back UP Calculations Available (Yes/No) | Construction Cost | Annual Operation and Maintenance Cost | Funding Source(s) | Project Partner(s) | Project Area Map | Name of Project Map File (if providing electronically)
Adoption | Silver | S001 | Fertilizer and Landscape Irrigation Codes | Alachua County EPD | Robin Hallbourg Stacie Greco | Regulation or Ordinance | Alachua County/ Adopt and enforce Fertilizer Management and Landscape Irrigation Ordinances./ Benefits: Reduce volume of runoff from over irrigation and reduce nutrient loading from the use of fertilizers. Implements Alachua County Comp Plan Conservation and Open Space Element - Surface Water Systems Objective 4.6 | 2009 | Ongoing Project | Ongoing | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | Alachua County General Fund | n/a | No
Adoption | Silver | S007 | Little Orange Creek Land Acquisition | Alachua County EPD | Ramesh Buch Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2012 | Completed Project | 2012 | n/a | 699.04 | n/a | n/a | n/a | No | 795437.55 | n/a | Alachua County Fee Simple / Wild Spaces and Public Places sales tax / Noth American Wetland Act Grant / Alachua Conservation Trust | n/a | No
Adoption | Silver | S008 | Phifer Flatwoods Land Acquisition #1 - Lochloosa Creek | Alachua County EPD | Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2006 | Completed Project | 2006 | n/a | 600 | n/a | n/a | n/a | No | 2882239 | n/a | Alachua County Forever Bond proceeds | Alachua Conservation Trust; Florida Conservation Trust | No
Adoption | Silver | S009 | Phifer Flatwoods Land Acquisition #2 - Lochloosa Creek; Little Lochloosa Creek | Alachua County EPD | Ramesh Buch Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2009 | Completed Project | 2009 | n/a | 380 | n/a | n/a | n/a | No | 1170864 | n/a | Alachua County Forever Bond proceeds | n/a | No
Adoption | Silver | S010 | Longleaf Flatwoods Preserve Land Acquisition | Alachua County EPD | Ramesh Buch Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2003 | Completed Project | 2003 | n/a | 1388.5 | n/a | n/a | n/a | No | 2259654 | n/a | Alachua County Forever Bond proceeds | SJRWMD | No
Adoption | Silver | S011 | Rayonier Tract Acquisition (River Styx) | Alachua County EPD | Ramesh Buch Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2008 | Completed Project | 2008 | n/a | 1450 | n/a | n/a | n/a | No | 4855506 | n/a | Alachua County Forever Bond proceeds, SJRWMD, FFLP | SJRWMD | No
Adoption | Silver | S012 | Freddy Wood Land Tract Acquisition | Alachua County EPD | Ramesh Buch Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2008 | Completed Project | 2008 | n/a | 600 | n/a | n/a | n/a | No | 1136000 | n/a | Alachua County Forever Bond proceeds, FFLP | Natural Resources Conservation Service | No
Adoption | Silver | S069 | Water Quality Protection BMP Training | Alachua County EPD | Gus Olmos Stacie Greco | Education and Outreach | Alachua County / Training and education for contractors, government, and citizens in sedimentation and erosion control to improve stormwater quality. | 2007 | Ongoing Project | Ongoing | FLR04E005, FLR04E006 | n/a | n/a | n/a | n/a | No | n/a | 2000 | Gainesville Cleanwater Partnership Cost Share | City of Gainesville, FDOT District 2 | No
Adoption | Silver | S070 | Pet Waste Outreach | Alachua County EPD | Gus Olmos Stacie Greco | Education and Outreach | Alachua County/ Implement social marketing campaign to motivate citizens to scoop, bag, and trash dog wastes at home and in the community. / Benefits: Reduces bacteria and nutrient sources in all watersheds. Implements Alachua County Comp Plan Conservation and Open Space Element - Surface Water Systems Objective 4.6. | 2009 | Ongoing Project | Ongoing | n/a | n/a | n/a | n/a | n/a | No | 40655 | n/a | Gainesville Cleanwater Partnership Cost Share | City of Gainesville, FDOT District 2 | No
Adoption | Silver | S071 | Landscape Debris Social Marketing | Alachua County EPD | Gus Olmos Stacie Greco | Education and Outreach | Alachua County/ Implement social marketing campaign designed to get citizens to keep landscaping debris out of the roads and stormwater collection systems. / Benefits: Reduces bacteria and nutrient sources in all watersheds. Implements Alachua County Comp Plan Conservation and Open Space Element - Surface Water Systems Objective 4.6. | 2009 | Completed Project | 2010 | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | Gainesville Cleanwater Partnership Cost Share | City of Gainesville, FDOT District 2 | No
Adoption | Silver | S072 | Water Conservation and LID | Alachua County EPD | Gus Olmos Stacie Greco | Education and Outreach | Alachua County/ Conduct targeted public outreach to encourage water conservation and rain harvesting. Includes rain barrel sales and LID promotion. / Benefits: By harvesting rainwater and keeping stormwater on site, stormwater and the pollutants it transports is decreased. | 2009 | Ongoing Project | Ongoing | n/a | n/a | n/a | n/a | n/a | No | n/a | n/a | Gainesville Cleanwater Partnership Cost Share | City of Gainesville, FDOT District 2 | No
Adoption | Silver | S073 | Quantifying Nutrient Improvement in Street Sweeping | Alachua County EPD | Gus Olmos Stacie Greco | Education and Outreach | Gainesville urban area and Alachua County/Monitor and assess street sweepings to quantify nutrient reductions and subsequent potential water quality improvements. Benefits: Provide data to quantify nutreints in street sweepings and assess the potential for water quality improvement. Implements Alachua County Comp Plan Conservation and Open Space Element - Surface Water Systems Objective 4.6 and policies. | 2013 | Completed Project | 2016 | FLR04E005, FLR04E006 | n/a | n/a | n/a | n/a | No | 38940 | n/a | Gainesville Cleanwater Partnership Cost Share | City of Gainesville, FDOT District 2 | No
Adoption | Silver | S074 | Landscaping Behavior Change Social Marketing | Alachua County EPD | Gus Olmos Stacie Greco | Education and Outreach | Gainesville urban area and Alachua County/Alachua County/ Implement social marketing campaign designed to get citizens to make landscaping behavior changes that reduce nutrients in stormwater. / Benefits: Reduces nutrients sources in all watersheds. Implements Alachua County Comp Plan Conservation and Open Space Element - Surface Water Systems Objective 4.6. Benefits: Behavior changes to reduce nutrient inputs to stormwater; implement Alachua County Comp Plan Conservation and Open Space Element - Education and Outreach Objective 2.2; Surface Water Systems Objective 4.6; Alachua County Unified Land Development Code (ULDC), Chapter 407 Article 4 Landscaping - 406.43 Water Resources Buffers; ULDC Article 9 Stormwater Management. | 2013 | In Progress | 2017 | FLR04E005, FLR04E006 | n/a | n/a | n/a | n/a | No | n/a | 25000 | Gainesville Cleanwater Partnership Cost Share | City of Gainesville, FDOT District 2 | No
Adoption | Silver | S110 | Cypress Point Creamery Land Acquisition | Alachua County EPD | Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2014 | Completed Project | 2014 | n/a | 600 | n/a | n/a | n/a | No | 461000 | n/a | Wild Spaces and Public Places surtax; FRPP cost share | USDA Farm & Ranch Land Protection Program (FRPP) | No
Adoption | Silver | S111 | Higginbotham Ranch Acquisition | Alachua County EPD | Sandra Vardaman | Conservation Land Acquisition | No increase in surface runoff of pollutants due to land use change, continued aquifer recharge and ecosystem/habitat preservation; implement Alachua County Comp Plan Conservation and Open Space Element - Alachua County Forever Policy 6.2.1. | 2014 | Completed Project | 2014 | n/a | 600 | n/a | n/a | n/a | No | 756000 | n/a | Wild Spaces and Public Places surtax; FRPP cost share | USDA Farm & Ranch Land Protection Program (FRPP) | No
Note on A13: Robin Hallbourg: This is not an education project and should be removed.

## Sheet1
Agriculture BMP | Completed Project | Silver | Wastewater System Upgrade | Adoption
Planning | In Progress | Rainbow | Wastewater Service Area Expansion (OSTDS) | 2016
Conservation Land Acquisition | Ongoing Project | Both | Wastewater Service Area Expansion (Package Plant) | 2017
Data Collection | Funded Planned Project |  | Wastewater Collection System Maintenance
Studies | Unfunded Planned Project |  | Reuse Project
Regulation or Ordinance | Conceptual Project |  | Wastewater Level of Service Planning
Urban Structural BMP | Cancelled Project
Street Sweeping
Education and Outreach
Stormwater Operation and Maintenance