## St. Lucie All Projects
LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Basin(s) | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber
FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 3513 | 800 | North Fork | 1928 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-02 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 8397 | 1436 | Ten Mile Creek | 11877 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-03 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 50877 | 8218 | C-24 | 42785 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-04 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 68159 | 12479 | C-23 | 60127 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-05 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 60076 | 11994 | C-44/S-153 | 48803 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-06 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 159 | 40 | Basin 4/5 | 78 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-07 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 10 | 3 | Basin 6 | 19 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-08 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on WaSh model. Acres treated based on FDACS OAWP June 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 10839 | 2057 | South Fork | 8550 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-09 | Cost-share Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions based on WaSh model. | Agricultural BMPs | Completed | N/A | 52 | 19 | North Fork | 45 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-10 | Cost-share Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions based on WaSh model. | Agricultural BMPs | Completed | N/A | 525 | 146 | Ten Mile Creek | 955 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-11 | Cost-share Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions based on WaSh model. | Agricultural BMPs | Completed | N/A | 89627 | 26668 | C-24 | 3062 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-12 | Cost-share Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions based on WaSh model. | Agricultural BMPs | Completed | N/A | 65137 | 29777 | C-23 | 17563 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-13 | Cost-share Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions based on WaSh model. | Agricultural BMPs | Completed | N/A | 47585 | 9641 | C-44/S-153 | 9017 | TBD | TBD | FDACS | TBD | N/A
FDACS | Agricultural Producers | FDACS-14 | Cost-share Projects | Cost-share projects paid for by FDACS. Acres treated based on FDACS OAWP June 2019 Enrollment. Reductions based on WaSh model. | Agricultural BMPs | Completed | N/A | 11934 | 2678 | South Fork | 1947 | TBD | TBD | FDACS | TBD | N/A
FDACS | N/A | FDACS-15 | Credit for Changes in Land Use | Acreages and reductions based on a portion of differences between modeled agricultural land use coverage identified in Table B-13. DEP will estimate final numbers by next BMAP update. | Land Use Change | Completed | N/A | 439 | 88 | North Fork | 58 | N/A | N/A | N/A | N/A | N/A
FDACS | N/A | FDACS-16 | Credit for Changes in Land Use | Acreages and reductions based on a portion of differences between modeled agricultural land use coverage identified in Table B-13. DEP will estimate final numbers by next BMAP update. | Land Use Change | Completed | N/A | 501 | 101 | Ten Mile Creek | 74 | N/A | N/A | N/A | N/A | N/A
FDACS | N/A | FDACS-17 | Credit for Changes in Land Use | Acreages and reductions based on a portion of differences between modeled agricultural land use coverage identified in Table B-13. DEP will estimate final numbers by next BMAP update. | Land Use Change | Completed | N/A | TBD | TBD | C-24 | TBD | N/A | N/A | N/A | N/A | N/A
FDACS | N/A | FDACS-18 | Credit for Changes in Land Use | Acreages and reductions based on a portion of differences between modeled agricultural land use coverage identified in Table B-13. DEP will estimate final numbers by next BMAP update. | Land Use Change | Completed | N/A | 2428 | 521 | C-23 | 475 | N/A | N/A | N/A | N/A | N/A
FDACS | N/A | FDACS-19 | Credit for Changes in Land Use | Acreages and reductions based on a portion of differences between modeled agricultural land use coverage identified in Table B-13. DEP will estimate final numbers by next BMAP update. | Land Use Change | Completed | N/A | 1106 | 188 | C-44/S-153 | 138 | N/A | N/A | N/A | N/A | N/A
FDACS | N/A | FDACS-20 | Credit for Changes in Land Use | Acreages and reductions based on a portion of differences between modeled agricultural land use coverage identified in Table B-13. DEP will estimate final numbers by next BMAP update. | Land Use Change | Completed | N/A | 1827 | 346 | South Fork | 294 | N/A | N/A | N/A | N/A | N/A
FDOT District 4 | N/A | FDOT-01 | FM# 230108-1 (Ponds 2 & 3) | Widening and new late construction on State Road (SR) 68 from SR 9 to east of County Road (CR)-607A (40% credit, remaining 60% to Central Indian River Lagoon (CIRL). | Wet Detention Pond | Completed | 2013 | 0 | 0.03 | North Fork | 17.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-02 | FM# 230108-1 | Combined with FDOT-01. | Wet Detention Pond | Completed | 2013 | N/A | N/A | North Fork | 17.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-03 | FM# 230262-4 | Road widening of SR 70 from west of Rim Ditch Canal to west of Header Canal. | Dry Detention Pond | Completed | 2008 | 76.8 | 15.1 | Ten Mile Creek, C-24 | 102 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-04 | FM# 230262-5 | Road widening of SR 70 from Turnpike to Berman Rd. | Dry Detention Pond | Completed | 2010 | 92.4 | 18.4 | Ten Mile Creek | 123.7 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-05 | FM# 230262-3 | Road widening of SR 70 from Okeechobee County line, east 10.2 miles. | Dry Detention Pond | Completed | 2012 | 160.3 | 35.5 | C-24 | 195.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-06 | FM# 230262-2 | Road widening of SR 70 from Okeechobee County line, east 10.2 miles. | Dry Detention Pond | Completed | 2015 | 316.6 | 91 | C-24, C-23 | 238.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-07 | FM# 230295-1 | Road widening of SR 716 from Westmore-land Bridge to SR 5. | Dry Detention Pond | Completed | 2003 | 16.6 | 2.7 | North Fork | 17.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-08 | SPN 99004-1585 | Road widening of SR 5 from Jensen Beach Blvd to Port St. Lucie Blvd. | Dry Detention Pond | Completed | 2003 | 29.8 | 4.9 | North Fork | 30.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-09 | SPN 99004-1585 (Lake 3) | Road widening of SR A1A from Sewalls Point Rd. to west of MacArthur Blvd. | Wet Detention Pond | Completed | 2003 | 33.9 | 9.7 | North Fork | 13.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-10 | FM# 228819-1 (Basin A and B) | SR A1A Ernest Lyons Bridge replacement. | Wet Detention Pond | Completed | 2007 | 0.4 | 0.1 | North Mid-Estuary | 0 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-11 | FM# 228821-1 (West 1 A) | SR A1A Evans Crary Senior Bridge replacement. | Exfiltration Trench | Completed | 2001 | 10.9 | 2 | South Mid-Estuary | 2.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-12 | FM# 228821-1 (East) | SR A1A Evans Crary Senior Bridge replacement. | Exfiltration Trench | Completed | 2001 | 5.3 | 0.8 | North Mid-Estuary | 1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-13 | FM# 228831-1 | Bridge replacement at SR 714 crossing over Florida's Turnpike. | Dry Detention Pond | Completed | 2000 | 7.4 | 1.1 | Basin 4/5, Basin 6 | 9.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-14 | FM# 228801-1 | Road widening of SR 5 from Seabranch Blvd to north of Salerno Rd. | Dry Detention Pond | Completed | 2003 | 2.3 | 0.4 | South Coastal | 2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-15 | FM# 405504-1 | SR 9 rest area improvements. | Dry Detention Pond | Completed | 2005 | 39.8 | 6.1 | Basin 6, South Fork | 53.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-16 | FM# 230288-2 | Road widening of SR 5 from Rio Mar Dr. to Midway Rd. | Wet Detention Pond | Completed | 2009 | 122.7 | 37.7 | North Fork | 44.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | City of Port St. Lucie | FDOT-17 | FM# 419890-1 | Construction of interchange at SR 9 and Becker Rd. | BMP Treatment Train | Completed | 2010 | 3.2 | 1.6 | North Fork, C-23 | 42 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-18 | Street Sweeping | Not provided. | Street Sweeping | Completed | N/A | 1419 | 910 | North Fork, Ten Mile Creek, C-24, C-23, C-44/S-153, Basin 4/5, Basin 6, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-19 | Public Education | Pamphlets. | Education Efforts | Completed | N/A | 109.4 | 20 | North Fork, Ten Mile Creek, C-24, C-23, C-44/S-153, Basin 4/5, Basin 6, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | Martin County | FDOT-20 | FM# 230978-1 Indian St. Bridge (Pond East) | New bridge crossing on CR 714 from west of Mapp Rd. to east of SR 76 on Indian St. | Dry Detention Pond | Completed | 2014 | 3.9 | 0.7 | South Fork | 20.7 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-21 | FM# 230978-1 Indian St. Bridge (Pond West) | New bridge crossing on CR 714 from west of Mapp Rd. to east of SR 76 on Indian St. | Wet Detention Pond | Completed | 2014 | 0.2 | 0 | Basin 6, South Fork | 33.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-22 | State Road 615 Midway Rd. to Edwards Rd. (Basin B-1) | Not provided. | Wet Detention Pond | Completed | 2009 | 14.8 | 4.3 | North Fork | 7.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-23 | State Road 615 Midway Rd. to Edwards Rd. (Basin E) | Not provided. | Wet Detention Pond | Completed | 2009 | 20.3 | 6.2 | North Fork | 9.3 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-24 | FM# 410717-1 SR 70 Widening Kings Highway (Hwy.) to Jenkins Rd. (West Basin) | Road widening on SR 70 from Kings Hwy. to Jenkins Rd. | Dry Detention Pond | Completed | 2012 | 6 | 1 | North Fork | 6.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-25 | SR 713 (King's Hwy.) Turn Lanes | Not provided. | Grass swales without swale blocks or raised culverts | Completed | 2013 | 0 | 0 | North Fork | 0.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-26 | Johnson Honda of Stuart Turn Lane (Basin A and B) | Not provided. | Exfiltration Trench | Completed | 2010 | 0.2 | 0 | South Fork | 0.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-27 | FM# 228852-1 SR 76 Drainage Improvements at Cabana Point (Pond 9A) | SR 76 drainage improvements at Cabana Point. | Wet Detention Pond | Completed | 2006 | 14.1 | 4.1 | South Fork | 4.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-28 | FM# 228852-1 Osprey Ridge Planned Unit Development (PUD) - SR 76 Improvements | SR 76 Osprey Ridge PUD drainage improvements. | Exfiltration Trench | Completed | 2007 | 0.1 | 0 | South Fork | 0.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-29 | FM# 228852-1 SR 76 Improvements – Kanner Professional Center. | SR 76 improvements – Kanner Professional Center. | Exfiltration Trench | Completed | 2009 | 0.5 | 0.1 | South Fork | 0.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-30 | FM# 228851-1 (Basin A) | Resurfacing of SR 5 from just north of Bridge Rd. to just north of SE Dharyls St. | Dry Detention Pond | Completed | 2004 | N/A | N/A | Outside BMAP Area | 14.12 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-31 | FM# 228851-1 | Resurfacing of SR 5 from just north of Bridge Rd. to just north of SE Dharyls St. | Dry Detention Pond | Completed | 2004 | N/A | N/A | Outside BMAP Area | 25.72 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-32 | FM# 230132-1 (System No. 1) | Road widening of SR 615 between Ave. Q and Industrial Ave. | Dry Detention Pond | Completed | 2001 | N/A | N/A | Outside BMAP Area | 2.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-33 | FM# 228758-1 | SR 732 bridge replacement over Intracoastal Waterway. | Dry Detention Pond | Completed | 2006 | N/A | N/A | Outside BMAP Area | 18.55 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-34 | FM# 228819-1 (Basin C) | Road reconstruction and construction of 2 new bridges on SR A1A from Sewall's Point Rd. to west of MacArthur Blvd. | Dry Detention Pond | Completed | 2007 | N/A | N/A | Outside BMAP Area | 16.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-35 | FM# 228819-1 (Basin D) | Road reconstruction and construction of 2 new bridges on SR A1A from Sewall's Point Rd. to west of MacArthur Blvd. | Exfiltration Trench | Completed | 2007 | N/A | N/A | Outside BMAP Area | 4.41 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-36 | FM# 228819-1 (Basin E) | Road reconstruction and construction of 2 new bridges on SR A1A from Sewall's Point Rd. to west of MacArthur Blvd. | Exfiltration Trench | Completed | 2007 | N/A | N/A | Outside BMAP Area | 4.79 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-37 | FM# 405167-1 | Resurfacing of SR A1A from Hutchinson House West North to Martin County. | On-line Retention BMPs | Completed | 2005 | N/A | N/A | Outside BMAP Area | 30.07 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-38 | FM# 230296-1 | Shoulder widening and drainage improvements on SR A1A from C-1 Intake Canal to Fort Pierce city limits. | Grass swales without swale blocks or raised culverts | Completed | 2009 | N/A | N/A | Outside BMAP Area | 88.91 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-39 | FM# 230297-1 SR A1A Roadway Improvements Phase 3 | Roadway improvements on SR A1A from Blue Heron Blvd to Gulfstream Ave. | Exfiltration Trench | Completed | 2010 | N/A | N/A | Outside BMAP Area | 6.38 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-40 | FM# 228758-1 SR 702 Jensen Beach Causeway | New roadway construction on SR 702 from Indian River Dr. to SR A1A. | Dry Detention Pond | Completed | 2008 | N/A | N/A | Outside BMAP Area | 33.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-41 | FM# 419250-2 SR 710 Bridge Replacement – 100A, 100B, and 200 | Big John Monahon Bridge replacement on SR 710 from SW Trail Dr. to east of SR 76 connector ramps. | Dry Detention Pond | Completed | 2015 | 8.2 | 1.4 | C-44/S-153 | 17.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-42 | FM# 419250-2 SR 710 Bridge Replacement – 300 and 500 | Big John Monahon Bridge replacement on SR 710 from SW Trail Dr. to east of SR 76 connector ramps. | Dry Detention Pond | Completed | 2015 | 16.4 | 3.1 | C-44/S-154 | 28.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-43 | FM# 413046-1 SR 9 Widening | Road widening on SR 9 from Okeechobee Rd. to south of Indrio Rd. | On-line Retention BMPs | Completed | 2015 | 145 | 23.9 | North Fork | 152 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-44 | FM# 423022-1 CR 68 Orange Ave. | County to provide geographic information system (GIS) data for county road; proposed split of 25 % to FDOT and 75 % to St. Lucie County. | Dry Detention Pond | Completed | 2015 | TBD | TBD | North Fork | 5.62 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-45 | FM# 230108-1 SR 68 Orange Ave. (40% credit) | Combined with FDOT-1. | Wet Detention Pond | Completed | 2005 | N/A | N/A | North Fork | 17.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | St. Lucie County | FDOT-46 | 231440-2 Midway Rd. Widening, 25th St. to US 1 (Pond 1 and 2) | Road widening on Midway Rd. from SR 68 to SR 5. | Wet Detention Pond | Underway | 2020 | 1.3 | 1.3 | North Fork | 17.08 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | St. Lucie County | FDOT-47 | 231440-2 Midway Rd. Widening, 25th St. to US 1 (Pond 3 and 4) | Road widening on Midway Rd. from SR 68 to SR 5. | Wet Detention Pond | Underway | 2020 | 1.1 | 5.1 | North Fork | 14.19 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | St. Lucie County | FDOT-48 | 231440-2 Midway Rd. Widening, 25th St. to US 1 (Pond 5) | Road widening on Midway Rd. from SR 68 to SR 5. | Wet Detention Pond | Underway | 2020 | 0.8 | 2.5 | North Fork | 11.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-49 | 230978-2 CR 714 Martin Highway Widening – Danforth Basin | Road widening on CR 714 (Martin Hwy.) from east of Turnpike to just west of Mapp Rd. | Wet Detention Pond | Completed | 2016 | 14.9 | 4.6 | Basin 4/5, Basin 6 | 16.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-50 | 230978-2 CR 714 Martin Hwy. Widening – Wetlands Basin | Road widening on CR 714 (Martin Hwy.) from east of Turnpike to just west of Mapp Rd. | Wet Detention Pond | Completed | 2016 | 9.2 | 2.6 | Basin 6, South Fork | 12.11 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-51 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 1 | Road widening on SR 76 from I-95 to Monterey Rd. | Dry Detention Pond | Underway | 2019 | 3.9 | 0.6 | South Fork | 4.65 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-52 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 2A | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 4.5 | 1 | South Fork | 7.22 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-53 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 2B | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 9 | 1.8 | South Fork | 14.58 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-54 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 3 | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 16 | 3.8 | South Fork | 24.75 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-55 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 4 | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 8.1 | 2 | South Fork | 11.98 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-56 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 8 | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 7.9 | 2.2 | South Fork | 10.58 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-57 | Fertilizer Application Cessation | No longer applying routine fertilizer. | Fertilizer Cessation | Completed | 2016 | 23881 | 5970 | North Fork, Ten Mile Creek, C-24, C-23, C-44/S-153, Basin 4/5, Basin 6, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-58 | FM# 432705-1 | Road widening of SR 710 from north of Indiantown Rd to just south of bridge over C-44 Canal. | Grass swales without swale blocks or raised culverts | Underway | 2020 | 8.3 | 0.3 | C-44/S-153 | 121.39 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-59 | FM# 432705-1 | Road widening of SR 710 from north of Indiantown Rd to just south C-44 Canal bridge. | Grass swales without swale blocks or raised culverts | Underway | 2020 | 3 | 0.6 | C-44/S-153 | 37.66 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-60 | FM# 422641-2 | Road widening on SR 76 from I-95 to Monterey Rd. | BMP Treatment Train | Underway | 2019 | 0.8 | 0.4 | South Fork | 39.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-61 | FM# 230256-6 | Road widening of King's Highway; Phase I South | Wet Detention Pond | Underway | 2021 | 0.3 | 0.1 | North Fork | 38.95 | Not provided | Not provided | Florida Legislature | Not provided | N/A
FDOT District 4 | N/A | FDOT-62 | FM# 230256-7 | Road widening of King's Highway; Phase II | Wet Detention Pond | Underway | 2022 | 0.3 | 0.1 | North Fork | 24.87 | Not provided | Not provided | Florida Legislature | Not provided | N/A
City of Fort Pierce | DEP | FP-01 | Indian Hills Recreation Area (Phase I) Stormwater Improvements | Treatment train of 6 different BMPs are joined to improve water quality of stormwater runoff discharging into IRL. Also known as Heathcote Botanical Gardens Treatment Train. | BMP Treatment Train | Completed | 2015 | N/A | N/A | Outside BMAP Area | 1242 | 3000000 | 113000 | DEP | 1410000 | SO579
City of Fort Pierce | N/A | FP-02 | Moore's Creek Retrofit –Phases 3 and 4 | Channelized stormwater conveyance system reconfigured to provide increased detention areas, littoral shelves and meandering creek characteristics. | Wet Detention Pond | Completed | 2010 | N/A | N/A | Outside BMAP Area | 1887 | 7946935 | 92500 | Not provided | Not provided | N/A
City of Fort Pierce | N/A | FP-03 | Street Sweeping | City removes cubic yards of debris by street sweeping activities. | Street Sweeping | Completed | N/A | 2020 | 1295 | North Fork | N/A | Not provided | 89617 | City's stormwater utility | Not provided | N/A
City of Fort Pierce | N/A | FP-04 | Inlet Cleaning | City cleans storm inlets citywide and disposes of waste. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 65 | 40 | North Fork | N/A | Not provided | Not provided | Not provided | Not provided | N/A
City of Fort Pierce | N/A | FP-05 | Education Program | City delivers educational programs to public through trade associations, HOAs, or other means. Educates on hazards associated with illicit discharge, fertilizer use, the importance of water quality, and stormwater pollution protection. | Education Efforts | Completed | N/A | 1803.8 | 304.3 | North Fork | N/A | Not provided | Not provided | Not provided | Not provided | N/A
City of Fort Pierce | N/A | FP-06 | Virginia Ave. Outfall Canal | Stabilization of eroded canal banks as result of 2008 Tropical Storm Fay using rock rip-rap and gabion basket wall construction. | Shoreline Stabilization | Completed | 2008 | N/A | N/A | Outside BMAP Area | 161.4 | 3462572 | 1500 | Not provided | Not provided | N/A
City of Fort Pierce | N/A | FP-07 | Moore's Creek Retrofit Phase 2 | Not provided. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2008 | N/A | N/A | Outside BMAP Area | 1680 | 1480437 | Not provided | Not provided | Not provided | N/A
City of Fort Pierce | N/A | FP-08 | South Beach Baffle Boxes | Not provided. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2005 | N/A | N/A | Outside BMAP Area | 128 | 557003 | Not provided | Not provided | Not provided | N/A
City of Fort Pierce | DEP | FP-09 | Veterans Park Stormwater Improvements | Improvements to existing stormwater facility to incorporate BMPs along with pervious parking, lake construction, and bio swales. | BMP Treatment Train | Completed | 2016 | N/A | N/A | Outside BMAP Area | 44.1 | 2367000 | Not provided | DEP | 807500 | SO696/ G0417
City of Fort Pierce | N/A | FP-10 | North 2nd St. (Seaway Dr. Jorth to Taylor Creek Marina) | Project entails complete reconstruction of 2nd Street including drainage conveyance/storage, utility upgrades and replacement, roadway widening and reconstruction, sidewalk on west side, and landscaping and lighting improvements. | Wet Detention Pond | Completed | 2017 | N/A | N/A | Outside BMAP Area | Not provided | 1909176 | Not provided | Not provided | Not provided | N/A
City of Fort Pierce | DEP | FP-11 | Indian Hills Recreation Area (Phase II) Stormwater Improvements | Reestablishment of wetlands and pervious paver parking areas. | Wetland Restoration | Completed | 2016 | TBD | TBD | North Fork | 61 | 2337485 | Not provided | DEP | 1410000 | S0579
City of Fort Pierce | N/A | FP-12 | Ave. F (US Hwy. 1 to 6th Street) | Drainage improvements along Avenue F will include curb inlets, 100 linear feet (LF) of exfiltration trench, complete curb replacement, and roadway resurfacing. | Exfiltration Trench | Completed | 2017 | N/A | N/A | Outside BMAP Area | Not provided | 186327.373 | Not provided | Not provided | Not provided | N/A
City of Fort Pierce | N/A | FP-13 | Mechanical Removal of Water Lettuce at Moore's Creek Between N 10th St. and N 13th St. | "One time" mechanical removal of water lettuce at Moore's Creek between N 10th Street and N 13th Street. | Aquatic Vegetation Harvesting | Completed | Not provided | N/A | N/A | Outside BMAP Area | 0.035262 | 10740 | N/A | Not provided | Not provided | N/A
Hobe St. Lucie Conservancy District | Not provided | HSL-01 | Hobe Sound Polo Club | Not provided. | BMP Treatment Train | Completed | 2013 | 2914.9495 | 717.8364 | South Fork | 1736.3 | Not provided | Not provided | Not provided | Not provided | N/A
Hobe St. Lucie Conservancy District | Not provided | HSL-02 | Changes in Agricultural Land Uses | All landuses updated with new model | Land Use Change | Canceled | 2013 | N/A | N/A | C-44/S-153, South Fork | N/A | N/A | N/A | N/A | N/A | N/A
Hobe St. Lucie Conservancy District | Not provided | HSL-03 | 90% Implementation Agricultural BMPs | All Ag BMP enrollment now included in FDACS-01 | Agricultural BMPs | Canceled | 2013 | N/A | N/A | C-44/S-153, South Fork | N/A | N/A | N/A | N/A | N/A | N/A
Martin County | SFWMD/ DEP | MC-01 | Cedar Point Water Quality Retrofit | 1.7 ac-ft of water quality treatment (0.36 inches). | BMP Treatment Train | Completed | 2004 | 105.6 | 39 | South Mid-Estuary | 31.4 | 398027 | Not provided | DEP | 127000 | SO101
Martin County | SFWMD/ DEP | MC-02 | Indian River Drive Baffle Boxes | Six second generation baffle boxes | Baffle Boxes- Second Generation | Completed | 2010 | 77.3 | 11.1 | North Mid-Estuary | 39.1 | 741827 | Not provided | DEP/ SFWMD | SFWMD - $187,000/ DEP - $208,137 | SO363
Martin County | SFWMD/ DEP | MC-03 | Warner Creek/Leilani Heights Water Quality Retrofit Phase I | 8.0 ac-ft of water quality treatment (0.14 inches). | BMP Treatment Train | Completed | 2011 | 539.1 | 89.7 | North Mid-Estuary | 69.8 | 541854 | Not provided | DEP/ SFWMD | DEP - $558,625/ SFWMD - $825,000/ SFWMD - $704,375 | G0264
Martin County | SFWMD/ DEP | MC-04 | Warner Creek Phase II | 0.36 acre dry detention area with control structure | Dry Detention Pond | Completed | 2012 | 16.1 | 2.7 | North Mid-Estuary | 15.1 | 1750338 | Not provided | DEP/ SFWMD | N/A | G0265
Martin County | SFWMD/ DEP | MC-05 | Warner Creek Phase III –Beacon 21 | 2.96 acre wet detention area with control structure weir | Wet Detention Pond | Completed | 2012 | 3102.8 | 1218.3 | North Mid-Estuary | 1353.8 | 2122935 | Not provided | DEP/ SFWMD | N/A | G0266
Martin County | SFWMD/ DEP | MC-06 | Manatee Creek Water Quality Retrofit Phases I, II, and III | 30.4 ac-ft of water quality treatment (0.44 inches). | BMP Treatment Train | Completed | 2012 | 54.1 | 20.9 | South Fork, South Coastal | 16 | 7026439 | Not provided | DEP/ SFWMD | DEP - $1,833,992/ SFWMD - $2,591,205 | OT040740/ SO0257
Martin County | SFWMD/ DEP | MC-07 | Rio/St. Lucie- Water Quality Retrofit -Phase 1 | 3.0 ac-ft of water quality treatment (0.35 inches). | BMP Treatment Train | Completed | 2006 | 71 | 11.8 | North Mid-Estuary | 8.1 | 354161 | Not provided | DEP | 300179 | SO100
Martin County | SFWMD/ DEP | MC-08 | Rio/St. Lucie- Water Quality Retrofit -Phase 2 | 5.1 ac-ft of additional water quality treatment and control structures on existing lakes (0.7 inches). | Wet Detention Pond | Completed | 2008 | 427.9 | 123.9 | North Mid-Estuary | 119.8 | 998170 | Not provided | DEP | 776170 | OT050685
Martin County | SFWMD/ DEP | MC-09 | Salerno Creek Water Quality Retrofit | 54.5 ac-ft of water qualtiy treatment (1.03 inches). | BMP Treatment Train | Completed | 2003 | 1110 | 338 | South Fork, South Coastal | 207.9 | 4715074 | Not provided | DEP | 1541568 | OT060149/ WAP068/ WM800/ SP379
Martin County | SFWMD/ DEP | MC-10 | Coral Gardens Water Quality Retrofit | 8.5 ac-ft of water quality treatment (0.05 inches). | BMP Treatment Train | Completed | 2005 | 2511.7 | 1725.4 | South Fork, South Coastal | 2008 | 2321860 | Not provided | DEP | 2009741 | OT040741/ SO116
Martin County | SFWMD/ DEP | MC-11 | Fern Creek Water Quality Retrofit | 29.8 ac-ft of water quality treatment (0.81 inches). | BMP Treatment Train | Completed | 2005 | 1828.1 | 589.9 | South Fork | 607.1 | 2660200 | Not provided | DEP | 761141 | SO078/ WAP027
Martin County | SFWMD/ DEP/ FEMA | MC-12 | Old Palm City Water Quality Retrofit Phases I, II, and III | 8.1 ac-ft of water quality treatment (0.51 inches). | BMP Treatment Train | Completed | 2004 | 597 | 177.3 | Basin 6, South Fork | 141.4 | 4576473 | Not provided | DEP/ SFWMD/ FEMA | DEP - $851,156/ SFWMD - $1,200,000/ FEMA - $593,553 | G0034/ OT060148
Martin County | SFWMD/ DEP | MC-13 | North River Shores Baffle Boxes | Installation of +20 Baffle Boxes | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 10.9 | 8.7 | North Fork | 187.3 | 1310000 | Not provided | DEP | 500000 | SP557
Martin County | SFWMD/ DEP | MC-14 | Palm Lake Park Water Quality Retrofit | 7.7 ac-ft of water quality treatment (1.16 inches). | BMP Treatment Train | Completed | 2003 | 386.9 | 117.1 | North Fork | 80.1 | 1741098 | Not provided | DEP | 1480936 | WAP026
Martin County | SFWMD/ DEP | MC-15 | Tropical Farms Water Quality Retrofit | 43.2 ac-ft of water quality treatment (1.11 inches). | BMP Treatment Train | Completed | 2010 | 2844.9 | 825.6 | South Fork | 469.8 | 4047219 | Not provided | DEP/ SFWMD | SFWMD - $1,412,000/ DEP - $1,180,589 | OT060152/ SO361
Martin County | N/A | MC-16 | Septic to Central Sewer Conversions | 1,121 single-family and multifamily residential and commercial units in five neighborhoods. | OSTDS Phase Out | Completed | 2014 | 15385.5708 | N/A | North Fork, Basin 4/5, North Mid-Estuary | N/A | 28678946 | Not provided | NEEPP - North River Shores neighborhood | Not provided | N/A
Martin County | SFWMD | MC-17 | Danforth Creek – Phase 1 | 8.1 acre wet detention pond with littoral plantings and control structure | Regional Stormwater Treatment | Completed | 2014 | 6132.3 | 2266 | C-44/S-153, Basin 4/5, Basin 6, South Fork | 2459.3 | 1869255 | Not provided | SFWMD | 1035515 | N/A
Martin County | N/A | MC-18 | Street Sweeping | Not provided. | Street Sweeping | Completed | N/A | 108 | 69 | North Fork, C-23, C-44/S-153, Basin 4/5, Basin 6, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | Not provided | Not provided | Not provided | Not provided | N/A
Martin County | N/A | MC-19 | Baffle Box and Structure Cleanout | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 397 | 161 | Basin 4/5, Basin 6, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | Not provided | Not provided | Not provided | Not provided | N/A
Martin County | N/A | MC-20 | Education Program | FYN; landscaping, irrigation, fertilizer, and pet waste ordinances; PSAs, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 16643.6 | 2831.2 | North Fork, C-23, C-44/S-153, Basin 4/5, Basin 6, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | Not provided | Not provided | County | 60000 | N/A
Martin County | FDOT | MC-21 | FM# 230978-1 Indian St. Bridge (Pond East) | Not provided. | Dry Detention Pond | Completed | 2014 | 11.7 | 2 | South Fork | 20.7 | Not provided | Not provided | Not provided | Not provided | N/A
Martin County | FDOT | MC-22 | FM# 230978-1 Indian St. Bridge (Pond West) | Not provided. | Wet Detention Pond | Completed | 2014 | 108.5 | 32.8 | Basin 6, South Fork | 33.6 | Not provided | Not provided | Not provided | Not provided | N/A
Martin County | DEP | MC-23 | Golden Gate Water Quality Retrofit Phases I, II | Treatment train system, baffle boxes, dry detention & 5.61 ac-ft of wet detention | BMP Treatment Train | Completed | 2003 | 1149.9 | 279.5 | South Coastal | 201.8 | 2046145 | Not provided | DEP | 1322772 | WAP030/ G0012
Martin County | DEP | MC-24 | Golden Gate Water Quality Retrofit Phase III | Treatment train system, baffle boxes, & 2.26 ac-ft of wet detention | BMP Treatment Train | Completed | 2004 | 122.6 | 37 | South Coastal | 27.2 | 584371 | Not provided | DEP | 313060 | SO105
Martin County | DEP | MC-25 | Hibiscus Park Water Quality Retrofit Phases I and II | 1.24 ac-ft of Wet Detention volume | Wet Detention Pond | Completed | 2007 | 23.8 | 7.1 | South Coastal | 4.5 | 1390574 | Not provided | DEP | 687715 | OT050696
Martin County | DEP | MC-26 | Poinciana Gardens Water Quality Retrofit Phases I and II | Treatment Train system, 87.36 ac-ft of wet detention and baffle box | BMP Treatment Train | Completed | 2003 | 983.8 | 284.4 | South Fork, South Coastal | 188.3 | 2960547 | Not provided | DEP | 2235091 | WAP025
Martin County | N/A | MC-27 | Willoughby Creek Muck Dredging | Not provided. | Muck Removal/Restoration Dredging | Completed | 2012 | TBD | TBD | South Coastal | N/A | 13200000 | Not provided | Not provided | Not provided | N/A
Martin County | N/A | MC-28 | Manatee Pocket Dredging | Not provided. | Muck Removal/Restoration Dredging | Completed | 2012 | TBD | TBD | South Coastal | N/A | 1000000 | Not provided | Not provided | Not provided | N/A
Martin County | SFWMD/ DEP | MC-29 | Rio Water Quality Retrofit | Exfiltration Trenches & Baffle Boxes | BMP Treatment Train | Completed | 2014 | 419.5 | 69.3 | North Mid-Estuary | 50.2 | 696800 | Not provided | DEP/ SFWMD | DEP - $240,000/ SFWMD - $310,000 | SO642
Martin County | N/A | MC-30 | Old Palm City Beemats | Not provided. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Completed | 2013 | TBD | TBD | Basin 4/5, Basin 6, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | 21996 | Not provided | Not provided | Not provided | N/A
Martin County | FDACS | MC-31 | Bessey Creek Hybrid Wetland Treatment Technology (HWTT) | Not provided. | Hybrid wetland treatment technology (HWTT) | Completed | 2015 | 6081.3 | 1473.2 | C-23, Basin 4/5 | 2675 | 3000000 | Not provided | FDACS | 3000000 | N/A
Martin County | FDACS | MC-32 | Danforth Creek HWTT | Not provided. | Hybrid wetland treatment technology (HWTT) | Completed | 2016 | 5311.5 | 1286.7 | C-44/S-153, Basin 4/5, Basin 6, South Fork | 2419 | 3000000 | Not provided | FDACS | 3000000 | N/A
Martin County | N/A | MC-33 | Hoke Library Rain Garden | Not provided. | LID- Rain Gardens | Completed | 2015 | Not provided | Not provided | North Fork | Not provided | 4372 | Not provided | Not provided | Not provided | N/A
Martin County | N/A | MC-34 | Halpatiokee Park Rain Garden | Not provided. | LID- Rain Gardens | Completed | 2015 | Not provided | Not provided | South Fork | Not provided | 1500 | Not provided | Not provided | Not provided | N/A
Martin County | DEP | MC-35 | Manatee Pocket SW Prong Baffle Box | Not provided. | Baffle Boxes- Second Generation | Completed | 2016 | 477.4 | 67.7 | South Coastal | 236.2 | 232505 | Not provided | DEP | 100000 | S0759
Martin County | DEP | MC-36 | Martin County Golf Course WQ | Not provided. | Wet Detention Pond | Completed | 2016 | 872.6 | 252.9 | South Coastal, South Mid-Estuary | 206.7 | 156255 | Not provided | DEP | 50000 | S0765
Martin County | DEP | MC-37 | All American Ditch | Not provided. | Regional Stormwater Treatment | Completed | 2016 | 979.7 | 297.6 | Basin 6, South Fork | 267.7 | 5165376 | Not provided | DEP | 3000000 | S0758/ G0414
Martin County | SFWMD | MC-38 | Hilltop Street Exfiltration Trench | Not provided. | Exfiltration Trench | Completed | 2016 | 123.1 | 20.4 | North Mid-Estuary | 15.4 | 264774 | Not provided | SFWMD | 100000 | N/A
Martin County | N/A | MC-39 | Willoughby Creek STA | Not provided. | BMP Treatment Train | Underway | 2019 | 1553.6418 | 411.3448 | South Coastal | TBD | Not provided | Not provided | Not provided | Not provided | N/A
Martin County | N/A | MC-40 | Savannah Road Exfiltration Trench | N/A | BMP Treatment Train | Canceled | N/A | N/A | N/A | North Mid-Estuary | N/A | N/A | N/A | N/A | N/A | N/A
Martin County | N/A | MC-41 | Old Palm City Phase IV | Not provided. | BMP Treatment Train | Planned | 2021 | 80 | 29 | South Fork | TBD | TBD | TBD | N/A | N/A | N/A
Martin County | N/A | MC-42 | South Savannas Weir | Not provided. | Control Structure | Planned | 2020 | TBD | TBD | North Fork | TBD | TBD | TBD | TBD | TBD | N/A
Martin County | DEP | MC-43 | East Fork Creek STA | 700-foot long Stormwater Treatment Area (STA) and a 1500-foot long lake within an unopened right-of-way and FDOT Lateral Ditch to provide stormwater treatment. | Regional Stormwater Treatment | Planned | 2021 | TBD | TBD | South Fork, South Coastal | TBD | TBD | TBD | DEP | 1200000 | LPQ0004
North St. Lucie River WCD | St. Lucie River Issues Team (SLRIT) | NSLRWCD-01 | SLRIT Grant 2000–2001: Vegetation Control & Bank Restoration | Installation of C-25 diversion structure which regulates flow from the North St. Lucie River Water Control District (NSLRWCD) C-44/ North Emergency Relief Canal to SFWMD C-25. In addition, installation of 3 risers with adjustable gates. | Control Structure | Completed | 2003 | 1547.8 | 0 | North Fork, Ten Mile Creek | 4173 | 929000 | Not provided | NSLRWCD/ SLRIT 50/50 contribution match | Not provided | N/A
North St. Lucie River WCD | St. Lucie River Issues Team (SLRIT) | NSLRWCD-02 | SLRIT Grant 2007–2008: WCS Retrofits | Installation of adjustable gates on WCS to improve efficiency of water levels and better manage sediment transport downstream. | Control Structure | Completed | 2010 | 1558.3 | 0 | Ten Mile Creek, C-24 | 4701 | 77000 | Not provided | NSLRWCD/ SLRIT 50/50 contribution match | Not provided | N/A
North St. Lucie River WCD | St. Lucie County/ FDOT | NSLRWCD-03 | Canals 23 and 28 Retrofit for Stormwater Treatment and Attenuation | Construction of ponds and installation of WCS for area retrofit. Inclusion of WMD canals into pond footprints. | Control Structure | Completed | 2009 | 21.6 | 0 | North Fork | 44 | Not provided | Not provided | FDOT/ St. Lucie County/ NSLRWCD | Not provided | N/A
North St. Lucie River WCD | N/A | NSLRWCD-04 | Canal Maintenance Program | Maintenance program on over 200 miles of canal, now included in NSLRWCD water quality activities. | Aquatic Vegetation Harvesting | Canceled | 2013 | N/A | N/A | North Fork, Ten Mile Creek | 66225 | 4200000 | Not provided | NSLRWCD | Not provided | N/A
North St. Lucie River WCD | N/A | NSLRWCD-05 | Changes in Agricultural Land Uses | All landuses updated with new model | Land Use Change | Canceled | 2013 | N/A | N/A | North Fork, Ten Mile Creek | 1055 | N/A | N/A | N/A | N/A | N/A
North St. Lucie River WCD | N/A | NSLRWCD-06 | 90% Implementation Agricultural BMPs | All Ag BMP enrollment now included in FDACS-01 | Agricultural BMPs | Canceled | N/A | N/A | N/A | North Fork, Ten Mile Creek | N/A | N/A | N/A | N/A | N/A | N/A
North St. Lucie River WCD | N/A | NSLRWCD-07 | Change from Agricultural to Urban | All landuses updated with new model | Land Use Change | Canceled | N/A | N/A | N/A | North Fork, Ten Mile Creek | N/A | N/A | N/A | N/A | N/A | N/A
North St. Lucie River WCD | N/A | NSLRWCD-08 | Ideal Grove Hybrid Wetland Treatment Technology | Not provided. | Hybrid wetland treatment technology (HWTT) | Completed | 2013 | 433.1 | 132.2 | Ten Mile Creek, C-24 | 238 | 217929 | Not provided | Not provided | Not provided | N/A
North St. Lucie River WCD | Not provided | NSLRWCD-09 | Structure 81-1-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 124 | 124 | Ten Mile Creek | 2582.4253 | Not provided | Not provided | Not provided | Not provided | N/A
North St. Lucie River WCD | Not provided | NSLRWCD-10 | Structure 82-2-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 23 | 23 | Ten Mile Creek | 674.2808 | Not provided | Not provided | Not provided | Not provided | N/A
North St. Lucie River WCD | Not provided | NSLRWCD-11 | Structure 83-2-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 27 | 27 | Ten Mile Creek | 484.1701 | Not provided | Not provided | Not provided | Not provided | N/A
North St. Lucie River WCD | Not provided | NSLRWCD-12 | Structure 85-1-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 64 | 64 | Ten Mile Creek | 961.0664 | Not provided | Not provided | Not provided | Not provided | N/A
Pal Mar WCD | Not provided | PM-01 | 90% Implementation Agricultural BMPs | All Ag BMP enrollment now included in FDACS-01 | Agricultural BMPs | Canceled | N/A | N/A | N/A | C-44/S-153 | N/A | N/A | N/A | N/A | N/A | N/A
City of Port St. Lucie | DEP/ SFWMD/ SLC/ American Greenways/ Tax-Increment Financing (TIF) | PSL-01 | Woodstork Trail Design Districts 7, 8, and 9 | 4.6 acres of new filter marsh, 7.21 acres of new uplands, and installation of baffle box. | BMP Treatment Train | Completed | 2007 | 12 | 9.5 | North Fork | 228.8 | 3300000 | 1122000 | DEP/ SFWMD/ SLC/ American Greenways/ TIF | Not provided | G0140
City of Port St. Lucie | DEP/ City Center Special Assessments | PSL-02 | Wood Stork Trail Design District 6 | 7.74-acre wet detention area, .62-acre STA, and 3 baffle boxes. | BMP Treatment Train | Completed | 2008 | 4.3 | 3.2 | North Fork | 81 | 825500 | N/A | DEP/ City Center Special Assessments | Not provided | G0178
City of Port St. Lucie | DEP/ SFWMD | PSL-03 | Howard Creek STA | Construction of weir, 45-acre STA, littoral shelves, and new plantings. | BMP Treatment Train | Completed | 2010 | 1265.6 | 439 | North Fork | 435.8 | N/A | N/A | DEP/ SFWMD | Not provided | S0507
City of Port St. Lucie | N/A | PSL-04 | Eastern Watershed Improvement Project | Flood control, water quality, environmental restoration project consisting of 27 acres of wet detention ponds, littoral shelves, and created wetlands. | BMP Treatment Train | Completed | 2011 | 1378.4 | 795.3 | North Fork | 849.5 | 36000000 | N/A | City | Not provided | N/A
City of Port St. Lucie | NRCS/ SFWMD | PSL-05 | B-1 and B-2 WCS | WCS B-1 and B-2 protected North Fork of St. Lucie River (NFSLR) from receiving uncontrolled E-8 Canal discharges. System will stage appropriate discharge levels based on volume, retaining maximum flows. | Control Structure | Completed | 2007 | 6736.8 | 2087.9 | North Fork, C-24, C-23 | 1747.5 | 1800000 | 621000 | City/ NRCS/ SFWMD | Not provided | N/A
City of Port St. Lucie | NRCS/ SFWMD | PSL-06 | B-3 WCS | B-3 protected NFSLR from receiving uncontrolled E-8 Canal discharges. System will stage appropriate discharge levels based on volume, retaining maximum flows. | Control Structure | Completed | 2007 | 7026.7 | 2176.8 | North Fork | 1640.6 | N/A | N/A | City/ NRCS/ SFWMD | Not provided | N/A
City of Port St. Lucie | DEP | PSL-07 | E-8 Waterway Phase 1 Water Quality Retrofit | Control structure improvements, weirs, sediment removal, and construction of 2 STAs totaling 24.36 acres. Improvements will enhance stormwater drainage and flood protection capacity, improve water quality and restore native vegetation and habitat. | BMP Treatment Train | Completed | 2010 | 1532.4 | 1513.3 | North Fork | 1610.2 | 400000 | N/A | DEP | Not provided | S0239
City of Port St. Lucie | SFWMD | PSL-08 | E-17 Canal WCS | New WCS added to retain maximum flows in emergencies only. | Control Structure | Completed | 2008 | N/A | N/A | North Fork | 983.6 | 437000 | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-09 | Water and Wastewater Expansion | Multiple phase-outs of septic tanks from 2013 to 2019. | OSTDS Phase Out | Completed | 2019 | 44921.3644 | N/A | North Fork, C-24, C-23 | N/A | 91075666 | 3700000 | City | N/A | N/A
City of Port St. Lucie | N/A | PSL-10 | Street Sweeping | Materials are collected from roadways and the gutters using street sweeper truck. | Street Sweeping | Completed | N/A | 676 | 434 | North Fork | N/A | Not provided | 448000 | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-11 | Swale Maintenance | Removal and proper disposal of sediment captured in swale liner. | BMP Cleanout | Completed | N/A | 7649 | 3097 | North Fork | N/A | Not provided | 780000 | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-12 | Catch Basin Cleaning | Removal and proper disposal of sediment captured by catch basins. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 21 | 13 | North Fork | N/A | Not provided | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-13 | Education Program | Florida Yards and Neighborhoods (FYN) Program; fertilizer, landscape, irrigation, and pet waste ordinances; PSAs; stormwater educational shows; website; outreach programs; Stencil Program; and stormwater pollution hotline. | Education Efforts | Completed | N/A | 21978.3 | 3721.7 | North Fork, C-24, C-23 | N/A | Not provided | Not provided | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-14 | Tiffany Channel | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 56 | 9.6 | North Fork | N/A | N/A | 1900000 | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-15 | Patio STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 19.4 | 3.3 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-16 | Mary STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 13.4 | 2.3 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-17 | Leithgow STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 12.6 | 2.1 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-18 | Cane Slough 1/ Elks STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 61 | 10.5 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-19 | Cane Slough 2/ Azzi STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 44.5 | 7.6 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-20 | Loutus STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 41.2 | 6.8 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-21 | Howard Creek STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 65.4 | 10.9 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-22 | Bur St. STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 0 | 0 | North Fork | N/A | N/A | N/A | City | Not provided | N/A
St. Lucie West Services District | N/A | PSL-23 | St. Lucie West Services District (SLWSD) Aquatic Harvesting | Project moved to new entity (SLWSD) | Aquatic Vegetation Harvesting | Canceled | N/A | N/A | N/A | North Fork | N/A | N/A | N/A | N/A | N/A | N/A
St. Lucie West Services District | SLWSD | PSL-24 | SLWSD Catch Basin Cleaning | Project moved to new entity (SLWSD) | Catch Basin Inserts/Inlet Filter Cleanout | Canceled | N/A | N/A | N/A | North Fork | N/A | N/A | N/A | N/A | N/A | N/A
City of Port St. Lucie | N/A | PSL-25 | Atlantis Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 258.8 | 35.6 | North Fork | 115.8 | 628000 | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-26 | Evergreen Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 538.8 | 74.1 | North Fork | 241.4 | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-27 | Lansdown Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 253.9 | 35 | North Fork | 189 | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-28 | Streamlet/Manth Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 93.8 | 12.9 | North Fork | 89 | N/A | N/A | City | Not provided | N/A
City of Port St. Lucie | N/A | PSL-29 | Walters Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 403.6 | 55.6 | North Fork | 32 | N/A | N/A | City | Not provided | N/A
St. Lucie West Services District | DEP/ SLWSD | PSL-30 | SLWSD Water Management Improvement Project | Project moved to new entity (SLWSD) | Wet Detention Pond | Canceled | 2016 | N/A | N/A | North Fork | N/A | N/A | N/A | N/A | N/A | N/A
City of Port St. Lucie | DEP/ SFWMD | PSL-31 | St. Lucie River/C-23 Water Quality Project Phases I – VI | Water Farming Project – Pumps water from SFWMD C-23 Canal onto property for storage and retains rainfall on multiple phases of project. | Dispersed Water Management (DWM) | Underway | 2023 | TBD | TBD | C-23 | TBD | 3663383 | 180640 | City/ DEP/ SFWMD | Not provided | NF028
City of Port St. Lucie | N/A | PSL-32 | Veterans Memorial Water Quality Retrofit. Project 1 and 2 out of 6. | Installing control structures, digging ponds, and increasing storage. | BMP Treatment Train | Underway | 2025 | 5087.4 | 1555.7 | North Fork | 1065 | 3834193 | N/A | City/ SFWMD | SFWMD - $125,000 | N/A
St. Lucie West Services District | SLWSD | PSL-33 | Lake Harvey | Project moved to new entity (SLWSD) | Hydrologic Restoration | Canceled | 2017 | N/A | N/A | North Fork | N/A | N/A | N/A | N/A | N/A | N/A
City of Stuart | DEP/ SFWMD/ Healthy Rivers/ Florida Communities Trust (FCT) | S-01 | Poppleton Creek – Phase II and III | Muck sediment removal, creation of 6.5-acre retention pond, and 160-foot weir. Habitat reconstruction; passive recreational improvements. 4 continuous deflective seperation (CDS) baffle box units and street sweeping in basin. | BMP Treatment Train | Completed | 2008 | 2184.1 | 747.6 | South Fork, South Coastal, South Mid-Estuary | 629.1 | 4371250 | Not provided | DEP/ SFWMD/ Healthy Rivers/ FCT | Not provided | S0278/ G0083
City of Stuart | SFWMD/ Federal Emergency Management Agency (FEMA)/Martin County | S-02 | Airport Ditch Project | Conversion of 2 uncontrolled drainage ditches to tide into retention/detention facilities controlled by "v" notch weirs. | On-line Retention BMPs | Completed | 2003 | 815.1 | 421.4 | South Fork, South Mid-Estuary | 893.7 | 766756 | Not provided | SFWMD/ FEMA/ Martin County | Not provided | N/A
City of Stuart | SFWMD | S-03 | Crescent Basin Project | Stormwater retention through three first generation baffle boxes. | On-line Retention BMPs | Completed | 2003 | 501.8 | 83.1 | South Fork | 58.5 | 180000 | Not provided | City/ SFWMD | Not provided | N/A
City of Stuart | DEP/ SFWMD | S-04 | Krueger Creek Project | Removal of "ooze" sediments and installation of 4 baffle boxes plus 2 CDS units in 2010. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2001 | 17.6 | 13.6 | South Fork, South Mid-Estuary | 309.6 | 432000 | Not provided | City/ SFWMD/ DEP | Not provided | WAP015/ G0083
City of Stuart | N/A | S-05 | Street Sweeping | Pavement cleaning by sweeping, vacuum, or washing. | Street Sweeping | Completed | N/A | 275 | 176 | North Fork, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | 33000 | Not provided | City | Not provided | N/A
City of Stuart | N/A | S-06 | Sediment Removal from Storm Systems | Removal and proper disposal of sediment captured by catch basin inserts. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 54 | 33 | North Fork, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | N/A | 75000 | City | Not provided | N/A
City of Stuart | N/A | S-07 | Education Program | FYN Program. City ordinances for landscaping, irrigation, fertilizer, and pet waste management. City stormwater website. Stormwater calendars. Pollution prevention information posted on electronic billboards 365 days/year from 12 PM to 1 PM. | Education Efforts | Completed | N/A | 2202.4 | 370.5 | North Fork, South Fork, South Coastal, South Mid-Estuary, North Mid-Estuary | N/A | 30150 | Not provided | City | Not provided | N/A
City of Stuart | SFWMD/ Healthy Rivers | S-08 | North Point CRA Drainage Basin | There is 1 existing 1st-generation baffle box and street sweeping in basin, existing FDOT swale along basin's east boundary, and 2 FDOT retention/detention ponds near the Roosevelt Bridge. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 4 | 3 | North Fork, North Mid-Estuary | 1083.8 | 1339000 | Not provided | City/ SFWMD/ Healthy Rivers | Not provided | N/A
City of Stuart | DEP/ Florida Inland Navigation District (FIND)/ Healthy Rivers | S-09 | Anchorage Drainage Basin | There is 1 existing 1st-generation baffle box and 3 FDOT dry detention ponds in basin. Ponds receive runoff from roadways and portion of Roosevelt Bridge. Street swept in basin. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 0.9 | 0.7 | South Fork, South Mid-Estuary | 21.3 | 766500 | Not provided | City/ DEP/ FIND/ Healthy Rivers | Not provided | Not provided
City of Stuart | DEP | S-10 | Downtown Drainage Basin | Drainage basin contains 4 1st-generation baffle boxes and 4 CDS units installed between 2000 and 2012; 3 catch basin filter baskets installed in 2010-11. Streets swept 12 times per month. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 7 | 5 | South Fork, South Mid-Estuary | 116.6 | 275000 | Not provided | City/ DEP | Not provided | G0083
City of Stuart | DEP | S-11 | Hildebrad Basin | 1 CDS unit and 7 catch basin filter baskets installed in 2010-11; includes street sweeping in basin. | Hydrodynamic Separators | Completed | 2009 | 0 | 12.6 | South Mid-Estuary | 66.9 | 388480 | Not provided | City/ DEP | Not provided | G0083
City of Stuart | N/A | S-12 | Landfill Basin | Landfill closed; ongoing groundwater monitoring, zero discharge. Closed basin with no outfall. | 100% On-site Retention | Completed | 2013 | 539.2 | 95.4 | South Fork | 71 | 29144 | Not provided | City | Not provided | N/A
City of Stuart | N/A | S-13 | South Fork Drainage Basin | There are 2 1st-generation baffle boxes in northwest portion of basin and 1 unimproved ditch along south side of SE Ruhnkee St. that flows to wooded area on west side of basin boundary within city jurisdiction. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 14.7 | 12.1 | South Fork | 662.8 | Not provided | Not provided | City | Not provided | N/A
City of Stuart | DEP | S-14 | Neighborhood Initiated Sewer Expansion Program | Sewer expansion program to phase out septic tanks by expanding sewer service into areas of city using low pressure sewer system piping along road rights-of-way and individual residential grinder pump station at each home. | OSTDS Phase Out | Completed | 2013 | 1340.7 | N/A | South Fork, South Mid-Estuary | N/A | 3200000 | Not provided | City/ DEP | Not provided | S0793/ S0821
City of Stuart | N/A | S-15 | Eldorado Heights | Area of land within the south-central area of Stuart city limits that does not discharge to surface waterbody or adjacent basin. | Closed Basin | Completed | 2012 | 342 | 58.5 | South Fork | 29.8 | 779000 | Not provided | City | Not provided | N/A
City of Stuart | Martin Memorial Health Systems/ SFWMD | S-16 | Amerigo Avenue Drainage Improvements | Construction of dry retention areas to eliminate street flooding, provide water quality treatment, and TMDL reductions. | Dry Detention Pond | Completed | 2014 | 70 | 11.3 | South Mid-Estuary | 9.9 | 679557 | Not provided | City/ Martin Memorial Health Systems/ SFWMD | Not provided | N/A
City of Stuart | Martin County/ Healthy Rivers/ FCT/ DEP | S-17 | Haney Creek Project – Phase I - IV | Creation of flow-through marsh and multiple wetlands and control structures to address stormwater quality, environmental restoration and preservation, greenways, passive recreation, and environmental education. | Filter Marsh | Completed | 2016 | 736.9 | 223.7 | North Mid-Estuary | 626.4 | 4831411 | 9600 | Martin County/ Healthy Rivers/ FCT/ DEP | Not provided | WAP031
City of Stuart | N/A | S-18 | Nondischarge Areas | Area within eastern city limits with no stormwater infrastructure and no outfalls discharging to adjacent basin. | Non-contributing Basin | Completed | 2014 | 2385.6 | 412.1 | South Fork, South Mid-Estuary | 217.6 | N/A | N/A | City | Not provided | N/A
City of Stuart | DEP | S-19 | Baffle Boxes (22) Throughout City | Concrete structures containing a series of sediment settling chambers separated by baffles. Boxes are vacuum cleaned base on sediment depth inspection by city stormwater staff. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2014 | 27.3 | 20.9 | North Fork, South Fork, South Mid-Estuary, North Mid-Estuary | 474.9 | N/A | Not provided | City/ DEP | Not provided | G0083
City of Stuart | DEP | S-20 | CDS Units Throughout City | Hydrodynamic separators that capture, sediment, trap debris, and separate floating oils from runoff. CDS units are vacuum cleaned based on sediment depth inspections by city stormwater staff. | Hydrodynamic Separators | Completed | 2014 | 0 | 12.7 | South Fork, South Mid-Estuary | 65.9 | N/A | Not provided | City/ DEP | Not provided | G0083
City of Stuart | N/A | S-21 | SW South Carolina Dr. Drainage Project | Installation of a stormwater conveyance system and 1st-generation baffle box in a residential area to eliminate unrestricted sheet flow to St. Lucie River. | Stormwater System Rehabilitation | Completed | 2016 | 0.2 | 0.1 | South Fork | 2.83 | 100936 | Not provided | City | Not provided | N/A
City of Stuart | DEP | S-22 | Poppleton Creek Tidal Wetlands Creation and Restoration | Construct tidal red mangrove wetlands on 4.3 acres of city-owned property south of and adjacent to Poppleton Creek east of Palm City Rd. Project will clear exotic vegetation and create tidal wetlands. | Wetland Restoration | Completed | 2018 | 152.3766 | 0 | South Fork | 500 | 270200 | TBD | City/ DEP | Not provided | G0363
City of Stuart | DEP | S-23 | East Heart of Haney Creek Wetlands Restoration | Restore eastern third of Heart of Haney Creek to wetlands by creating system of berms and weirs within 6 acres of exotic cleared area. | Wetland Restoration | Underway | 2019 | TBD | TBD | North Mid-Estuary | 395 | 220000 | TBD | City/ DEP | DEP - $90,000/ City - $110,000 | S0891
City of Stuart | DEP/ Healthy Rivers | S-24 | Frazier Creek Pond | Construction of wet detention pond to eliminate unrestricted flow from ditch to tide. | Wet Detention Pond | Completed | 2002 | 898.4 | 376.9 | South Fork, South Mid-Estuary | 379 | 1702000 | Not provided | City/ DEP/ Healthy Rivers | Not provided | WAP016
St. Lucie County | N/A | SLC-001a | Platt’s Creek Stormwater Treatment Facility | Wet detention with alum injection. | Wet Detention Pond | Completed | 2008 | 1655.4 | 537.1 | North Fork | 311 | 3539475 | Not provided | County | Not provided | N/A
St. Lucie County | N/A | SLC-001b | Platt’s Creek Stormwater Treatment Facility | Not provided. | Wet Detention Pond | Completed | 2008 | 2807.9 | 875.2 | North Fork | 563.5 | N/A | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-002 | Indian River Estates Stormwater Improvements (Phases I and II) | Wet detention with alum injection. | Wet Detention Pond | Completed | 2009 | 5584.5 | 1688.8 | North Fork | 1004.4 | 4471114 | Not provided | County | Not provided | N/A
St. Lucie County | N/A | SLC-003 | Prima Vista | Not provided. | Baffle Boxes- Second Generation | Completed | 2006 | 217.8 | 30 | North Fork | 96.8 | 323483 | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-004 | Bay Street | Not provided. | Baffle Boxes- Second Generation | Completed | 2006 | 99.6 | 13.7 | North Fork | 44.3 | N/A | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-005 | Education Program | FYN; pet waste, landscape, irrigation, and fertilizer ordinances; PSAs; website; Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program. St.Lucie Water Champions. | Education Efforts | Completed | N/A | 2596.6 | 454.1 | North Fork, C-24, C-23 | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-006 | Street Sweeping | Materials are collected from road ways and the gutters using a street sweeper truck. | Street Sweeping | Completed | N/A | 210.6 | 135.2 | North Fork, Ten Mile Creek, C-24, C-23 | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-007 | Catch Basin Cleanout | Catch basins are cleaned out on a rotational basis using a vactruck. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 170.3 | 104.6 | North Fork, Ten Mile Creek, C-23 | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-008 | Platt's Creek Sump Cleanout | Not provided. | BMP Cleanout | Completed | N/A | 1181.6 | 511.5 | North Fork | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | DEP | SLC-009 | White City – Citrus/Seager Stormwater Improvement | Wet detention with polyacrylamide logs. | Wet Detention Pond | Completed | 2016 | 180.4 | 55.5 | North Fork | 38.9 | 1862859 | Not provided | DEP/ County | Not provided | G0382
St. Lucie County | N/A | SLC-010 | Education Program | FYN; pet waste, landscape, irrigation, and fertilizer ordinances; PSAs; website; Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program, St.Lucie Water Champions. | Education Efforts | Completed | N/A | 8821 | 1594 | North Fork, Ten Mile Creek, C-24, C-23 | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-011 | Street Sweeping | Materials are collected from road ways and the gutters using a street sweeper truck. | Street Sweeping | Completed | N/A | 113.4 | 72.8 | North Fork, Ten Mile Creek, C-24, C-24 | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-012 | Catch Basin Cleanout | Catch basins are cleaned out on a rotational basis using a vactruck. | BMP Cleanout | Completed | N/A | 91.7 | 56.4 | North Fork, Ten Mile Creek, C-24 | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-013 | Platt's Creek Sump Cleanout | Not provided. | BMP Cleanout | Completed | N/A | 1566.4 | 600.5 | North Fork | N/A | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | City of Port St. Lucie | SLC-014 | Platt’s Creek Compensatory Mitigation Project | Not provided. | Floodplain Restoration | Completed | 2015 | Not provided | Not provided | North Fork | 311 | 2600000 | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-015 | IRL South C23/C24 Comprehensive Everglades Restoration Program (CERP) Buffer – Teague Preserve Re-watering Project | Not provided. | Hydrologic Restoration | Underway | Not provided | TBD | TBD | North Fork, C-24, C-23 | TBD | 400000 | TBD | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-016 | Melville Rd. Master Drainage Plan | Not provided. | Stormwater System Rehabilitation | Underway | 2024 | TBD | TBD | North Fork | 175 | 5000000 | TBD | County | Not provided | N/A
St. Lucie County | N/A | SLC-017 | Swales Material Collection | Road side swale cleanout and retrofitting in MS4 area and non-MS4 area. | BMP Cleanout | Completed | N/A | TBD | TBD | North Fork, Ten Mile Creek, C-23 | Not provided | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-018 | Swales Material Collection | Road side swale cleanout and retrofitting. Project rolled into SLC-017. | BMP Cleanout | Canceled | N/A | TBD | TBD | North Fork, Ten Mile Creek, C-24 | Not provided | Not provided | Not provided | Not provided | Not provided | N/A
St. Lucie County | N/A | SLC-019 | Becker Preserve Ten-Mile Creek Oxbow Reconnection | Oxbow reconnection with muck dredging. | Floodplain Restoration | Underway | Not provided | TBD | TBD | North Fork | TBD | Not provided | Not provided | DEP | 700000 | LPQ0009
Town of Sewall's Point | SFWMD | SP-01 | Ridgeland Court Retrofit | Installation of exfiltration/baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 0.2 | 0.1 | North Mid-Estuary | 5.9 | Not provided | 300000 | Town/SFWMD | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-02 | Palm Court/Knowles | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | 0 | 0 | North Mid-Estuary | 12.9 | Not provided | N/A | Town/SFWMD | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-03 | Captain Cove | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | N/A | N/A | Outside BMAP Area | 4.9 | Not provided | N/A | Town/SFWMD | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-04 | Quail Run Park | Installation of direct link to a detention area prior to discharge to Indian River. | Dry Detention Pond | Completed | 2000 | N/A | N/A | Outside BMAP Area | 0.4 | Not provided | N/A | Town/SFWMD | Not provided | N/A
Town of Sewall's Point | N/A | SP-05 | Heritage Park | Installation of stormwater retrofit area in developed subdivision. | Stormwater System Rehabilitation | Completed | 2000 | 0 | 0 | North Mid-Estuary | 5.2 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-06 | Via Lucindia | Installation of exfiltration pipe. | Exfiltration Trench | Completed | 2000 | N/A | N/A | Outside BMAP Area | 2.7 | Not provided | N/A | Town/SFWMD | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-07 | Rio Vista Park | Installation of baffle boxes/ erosion control for outfall to Indian River. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 0 | 0 | North Mid-Estuary | 24.2 | Not provided | N/A | Town/SFWMD | Not provided | N/A
Town of Sewall's Point | N/A | SP-08 | India Lucie | Installation of retrofit of weir/ retention area with 2 baffle boxes in old subdivision without retention to directly discharge to Indian River. | Stormwater System Rehabilitation | Completed | 2003 | 4.5 | 1.5 | North Mid-Estuary | 31.1 | Not provided | N/A | Martin County | Not provided | N/A
Town of Sewall's Point | FEMA | SP-09 | India Lucie | Installation of retrofit of weir/ retention area with 2 baffle boxes in old subdivision without retention to directly discharge to Indian River. | Stormwater System Rehabilitation | Completed | 2006 | 0.2 | 0.1 | North Mid-Estuary | 5.6 | Not provided | N/A | Town/ FEMA | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-10 | Periwinkle | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | 0 | 0 | North Mid-Estuary | 15.7 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | N/A | SP-11 | Palm Road | Installation of grass swales. | Grass swales without swale blocks or raised culverts | Completed | 2008 | N/A | N/A | Outside BMAP Area | 0.8 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-12 | Riverview | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 0.5 | 0.4 | North Mid-Estuary | 9.6 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | N/A | SP-13 | Pineapple Lane | Installation of outfall exfiltration. | Exfiltration Trench | Completed | 2002 | 0 | 0 | North Mid-Estuary | 5.5 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | TOSP | SP-14 | Copaire | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | N/A | N/A | Outside BMAP Area | 1.8 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | TOSP | SP-15 | Homewood Park/South Sewall's Point Road | Installation of retention area with pervious Flexi-Pave and exfiltration pipe. | On-line Retention BMPs | Completed | 2009 | N/A | N/A | Outside BMAP Area | 13.9 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | DEP/ SFWMD | SP-16 | Pedway/ Greenway | Installation of exfiltration/ pervious paver sidewalk. | BMP Treatment Train | Completed | 2014 | N/A | N/A | Outside BMAP Area | 1.6 | Not provided | N/A | Town/ DEP/ SFWMD | Not provided | G0333
Town of Sewall's Point | FDOT | SP-17 | State Road A1A | Installation of outfall exfiltration. | Exfiltration Trench | Completed | 2012 | 101.9 | 15.1 | North Mid-Estuary | 12.1 | Not provided | N/A | FDOT | Not provided | N/A
Town of Sewall's Point | N/A | SP-18 | Education Program | Fertilizer ordinance. | Education Efforts | Completed | N/A | 24.1 | 4 | North Mid-Estuary | N/A | N/A | N/A | Town | N/A | N/A
Town of Sewall's Point | N/A | SP-19 | Street Sweeping | 19 cubic yards of debris collected through street sweeping. | Street Sweeping | Completed | N/A | 25 | 16 | North Mid-Estuary | N/A | Not provided | N/A | Town | N/A | N/A
Town of Sewall's Point | N/A | SP-20 | Delano Lane | Installation of exfiltration system. | Exfiltration Trench | Completed | 2000 | N/A | N/A | Outside BMAP Area | 1.2 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | N/A | SP-21 | Town Commons Park | Installation of water quality treatment/dry detention. | Dry Detention Pond | Completed | 2002 | N/A | N/A | Outside BMAP Area | 1 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | N/A | SP-22 | Island Road | Installation of exfiltration pipe with baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | N/A | N/A | Outside BMAP Area | 4.9 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-23 | Highpoint West | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | N/A | N/A | Outside BMAP Area | 7.9 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-24 | Mandalay (Marguerita) | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | N/A | N/A | Outside BMAP Area | 15.4 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-25 | Highpoint East | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | N/A | N/A | Outside BMAP Area | 15.6 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | SFWMD | SP-26 | High Point Exfiltration | Installation of exfiltration/swales. | BMP Treatment Train | Completed | 2014 | N/A | N/A | Outside BMAP Area | 6.4 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
Town of Sewall's Point | N/A | SP-27 | Extend Pedway/Greenway | Extension of existing pervious pedway by 9,000 LF to include pervious pavers and exfiltration. | BMP Treatment Train | Completed | 2016 | N/A | N/A | Outside BMAP Area | 28.2 | 201482.83 | N/A | Town | Not provided | N/A
Town of Sewall's Point | DEP/ SFWMD | SP-28 | South Sewell's Point Road - Phase 1 Mandalay (Marguerita) | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Underway | TBD | N/A | N/A | Outside BMAP Area | 21 | 2000000 | N/A | Town/ DEP/ SFWMD | Town - $1,400,000/ DEP - $600,000 | NS029
Town of Sewall's Point | N/A | SP-29 | Baffle Boxes | Installation of baffle boxes in various locations. | Baffle Boxes- First Generation (hydrodynamic separator) | Underway | TBD | N/A | N/A | Outside BMAP Area | 18 | 315000 | N/A | Town | TBD | N/A
Town of Sewall's Point | N/A | SP-30 | Indialucie | Installation of exfiltration system in wet retention area. | Exfiltration Trench | Completed | 2014 | 11 | 1.8 | North Mid-Estuary | 31.1 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | N/A | SP-31 | Quail Run Subdivision | Installation of exfiltration/swales. | BMP Treatment Train | Completed | 2015 | N/A | N/A | Outside BMAP Area | 3.5 | Not provided | N/A | Town | Not provided | N/A
Town of Sewall's Point | N/A | SP-32 | Septic Tank Elimination - Phase I | Conversion of existing septic tanks to sanitary sewer. | OSTDS Phase Out | Planned | TBD | TBD | N/A | North Mid-Estuary | 16.5 | 500000 | N/A | Town/ Florida Legislature | Not provided | N/A
Turnpike Enterprise | N/A | T-01 | Project 420735-1 Port St. Lucie Interchange Pond A | Not provided. | Dry Detention Pond | Completed | 2013 | 3.5 | 0.6 | North Fork | 3.6 | Not provided | N/A | Not provided | Not provided | N/A
Turnpike Enterprise | N/A | T-02 | Project 420735-1 Port St. Lucie Interchange Pond B | Not provided. | Wet Detention Pond | Completed | 2013 | 32.9 | 3.7 | North Fork | 20.6 | Not provided | N/A | Not provided | Not provided | N/A
Turnpike Enterprise | N/A | T-03 | Thomas B. Manuel Bridge North Pond | Not provided. | Dry Detention Pond | Completed | 2013 | 7.9 | 1.3 | South Fork | 9.8 | Not provided | N/A | Not provided | Not provided | N/A
Turnpike Enterprise | N/A | T-04 | Education Program | No fertilizer on rights-of-way, educational signage, illicit discharge training. | Education Efforts | Completed | N/A | 268 | 45 | North Fork, Basin 4/5, South Fork | N/A | Not provided | N/A | Not provided | Not provided | N/A
Turnpike Enterprise | N/A | T-05 | Street Sweeping | 1,944 lane miles swept and 28,323 lbs (or 12,847 kg) of debris collected. | Street Sweeping | Completed | N/A | 144 | 10 | North Fork, Basin 4/5, South Fork | N/A | Not provided | N/A | Not provided | Not provided | N/A
Troup-Indiantown WCD | N/A | TI-01 | C-44 Conservation Area | Not provided. | Land Preservation | Completed | 2013 | 23199 | 7496.7 | C-44/S-153 | 9135.1 | N/A | N/A | Not provided | Not provided | N/A
Troup-Indiantown WCD | N/A | TI-02 | 90% Implementation Agricultural BMPs | All Ag BMP enrollment now included in FDACS-01 | Agricultural BMPs | Canceled | 2013 | N/A | N/A | C-44/S-154 | N/A | N/A | N/A | N/A | N/A | N/A
Troup-Indiantown WCD | N/A | TI-03 | Removal of Drainage Areas | Minute Maid Rd. drainage improvements. | 100% On-Site Retention | Completed | 2013 | TBD | TBD | C-44/S-155 | 73 | 124000 | N/A | WCD | Not provided | N/A
Troup-Indiantown WCD | SFWMD/ USACE | TI-04 | C-44 Reservoir Area | Converting from conservation area to reservoir. | Land Use Change | Underway | 2018 | N/A | N/A | C-44/S-153, Basin 4/5, Basin 6 | 3485 | N/A | N/A | USACE | Not provided | N/A
Troup-Indiantown WCD | SFWMD/ USACE | TI-05 | C-44 STA Area | Converting from conservation area to STA. | Land Use Change | Underway | 2018 | N/A | N/A | C-44/S-153, Basin 4/5, Basin 7 | 6100 | N/A | N/A | SFMWD | Not provided | N/A
Town of Sewall's Point | TBD | SP-33 | Outfall Control Structures | Add Control Structures | Stormwater System Rehabilitation | Underway | TBD | TBD | TBD | North Mid-Estuary | TBD | 500000 | N/A | Town | TBD | TBD
Town of Sewall's Point | TBD | SP-34 | South Sewall's Point Road - Phase 2 | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Planned | TBD | TBD | TBD | North Mid-Estuary | 63.9 | TBD | N/A | Town | TBD | TBD
Town of Sewall's Point | TBD | SP-35 | South Sewall's Point Road - Phase 3 | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Planned | TBD | TBD | TBD | North Mid-Estuary | TBD | TBD | N/A | Town | TBD | TBD
Town of Sewall's Point | TBD | SP-36 | South Sewall's Point Road - Phase 4 | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Planned | TBD | TBD | TBD | North Mid-Estuary | TBD | TBD | N/A | Town | TBD | TBD
St. Lucie West Services District | N/A | SLWSD-01 | St. Lucie West Services District (SLWSD) Aquatic Harvesting | Not provided. | Aquatic Vegetation Harvesting | Canceled | N/A | N/A | N/A | North Fork | N/A | N/A | N/A | N/A | N/A | N/A
St. Lucie West Services District | SLWSD | SLWSD-02 | SLWSD Catch Basin Cleaning | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 84 | 52 | North Fork | N/A | 185600 | 10450 | SLWSD | Not provided | N/A
St. Lucie West Services District | DEP/ SLWSD | SLWSD-03 | SLWSD Water Management Improvement Project | Increase storage of existing wetland. | Wet Detention Pond | Completed | 2016 | 1196.4057 | 695.1481 | North Fork | 140 | 360704 | 8200 | DEP/ SLWSD | DEP - $159,658/ SLWSD - $201,046 | S0812
St. Lucie West Services District | SLWSD | SLWSD-04 | Lake Harvey | Construction of 4.41-acre wetland area and 2.25-acre flow-way to enhance water quality, storage, and hydraulic connectivity in SLWSD Basin 4E. | Hydrologic Restoration | Completed | 2017 | 726.106 | 269.4067 | North Fork | 333 | 534000 | 15500 | SLWSD | Not provided | N/A
Coordinating Agency | N/A | CA-01 | Ten Mile Creek Water Preserve Area | Control quantity and timing of water delivery to NFSLR by capturing and storing stormwater flows that originated in Ten Mile Creek Basin. | Hydrologic Restoration | Completed | 2009 | TBD | 8789 | North Fork, Ten Mile Creek | 658
Coordinating Agency | N/A | CA-02 | Indian River Lagoon-South | C-44 Reservoir/STA will capture, store and treat runoff from C-44/S-153 Basin prior to discharge to estuary. Reservoir will provide 50,600 ac-ft of water storage. Two reservoirs and STA in C-23/C-24 Basins also planned to treat 92,000 ac-ft of runoff. The STA will be completed in 2020, and the reservoir in 2022. | Regional Stormwater Treatment | Underway | 2020 | 187393 | 74957 | Ten Mile Creek, C-24, C-23, C-44/ S-153 | 10700
Coordinating Agency | N/A | CA-03 | Adams-Russakis Ranch WMA | 1,000-acre project area, which has estimated water storage benefit of 536 ac-ft/yr. | Dispersed Water Management (DWM) | Planned | 2020 | N/A | N/A | C-24 | 1000
Coordinating Agency | N/A | CA-04 | C-23/24 Interim Storage Section C Water Farm | 297-acre project area, which has estimated water storage benefit of 2,887 ac-ft/yr. | Dispersed Water Management (DWM) | Completed | 2017 | N/A | N/A | C-24 | 297
Coordinating Agency | N/A | CA-05 | Bluefield Grove Water Farm | A Public-private partnership project actively stores local stormwater runoff on 6,100 acres in C-23 Basin in St. Lucie County. Project is estimated to provide net annual average water storage benefit of 28,360 ac-ft/yr. | Dispersed Water Management (DWM) | Underway | 2020 | 26896 | 6173 | C-23 | 6100
Coordinating Agency | N/A | CA-06 | Bull Hammock Ranch WMA | 608-acre project area, which has estimated water storage benefit of 228 ac-ft/yr. | Dispersed Water Management (DWM) | Completed | 2015 | N/A | N/A | C-23 | 608
Coordinating Agency | N/A | CA-07 | Spur Land and Cattle Water Farm | 210-acre project area, which has estimated water storage benefit of 1,500 ac-ft/yr. | Dispersed Water Management (DWM) | Completed | 2014 | N/A | N/A | C-23 | 210
Coordinating Agency | N/A | CA-08 | Caulkins Water Farm Expansion | Public-private partnership that actively stores local stormwater runoff as well as water from Lake Okeechobee regulatory releases on 3,275 acres of privately-owned land along C-44 Canal. Project is estimated to provide net annual average water storage benefit of 60,000 ac-ft/yr. | Dispersed Water Management (DWM) | Completed | 2017 | 123238 | 16755 | C-44/S-153 | 3275
Coordinating Agency | N/A | CA-09 | Alderman-Deloney Ranch | 170-acre project area, which has estimated water storage benefit of 147 ac-ft/yr. | Dispersed Water Management (DWM) | Completed | 2012 | N/A | N/A | C-24 | 170
Coordinating Agency | N/A | CA-10 | C-23/24 Interim Storage Parcel B | 320-acre project area to provide shallow storage in C-24 Basin. | Dispersed Water Management (DWM) | Planned | TBD | N/A | N/A | C-24 | 320
Note on I117: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure why these were just slightly updated. Don't want to change these every year.

## Future Projects
Lead Entity | Project Number | Project Name | Description | Project Type | Project Status | Acres Treated | TN Reduction (lbs/yr) | TP Reduction (lbs/yr) | Cost Estimate | Cost Annual O&M | Basin
St. Lucie County | F-01 | Sunland Gardens Neighborhood Improvement Project | This project will include the construction of a stormwater collection system to include roadside swales, dry detention areas, and paved roadways for an older unimproved subdivision currently with outfalls directly to the waterways. | Dry Detention Pond | Future | 423 | TBD | TBD | 25000000 | TBD | North Fork
City of Stuart | F-02 | West Heart of Haney | Wetland restoration to improve water quality of stormwater discharging into St. Lucie River | Wetland Restoration/Filter Marsh | Future | TBD | TBD | TBD | TBD | TBD | North Mid-Estuary
City of Port St. Lucie | F-03 | St. Lucie River/C-23 Water Quality Project Future Phase | Water Farming Project – Pumps water from SFWMD C-23 Canal onto property for storage and retains rainfall in future phases. | Online Retention BMPs | Future | 7,641 ac-ft | 35320 | 7272 | 1476111 | 180640 | C-23
City of Port St. Lucie | F-04 | Veterans Memorial Water Quality Retrofit Projects 3-6 | Digging ponds, increasing storage. | Wet Detention Pond | Designed | 1,065 for all 6 projects | See PSL-32 | See PSL-32 | 1600000 | TBD | North Fork
City of Port St. Lucie | F-05 | Sagamore Basin STA East | Design and construct STA with control structure and associated piping. | Wet Detention Pond | 100 % Designed | TBD | TBD | TBD | 1100000 | TBD | North Fork
City of Port St. Lucie | F-06 | Sagamore Basin STA West | Design and construct STA with control structure and associated piping. | Wet Detention Pond | 100 % Designed | TBD | TBD | TBD | 1200000 | TBD | North Fork
City of Fort Pierce | F-07 | Georgia Avenue Basin Water Quality Improvements | Construction of control structure and 2 nutrient separating baffle boxes are proposed for this stormwater outfall, which is currently uncontrolled and discharging directly into IRL. | Baffle Boxes - Second Generation | Future | 217 | N/A | N/A | 980000 | TBD | North Fork
City of Fort Pierce | F-08 | Moore's Creek Linear Park - Phase 2 | Continuation of the linear park concept from 15th Street west to 29th Street. Project includes canal enlargement as a continued effort to provide better water quality to the IRL. | TBD | Future | TBD | N/A | N/A | 9813800 | TBD | North Fork
Martin County | F-09 | East Fork Creek STA | Design and construct STA with control structure and associated piping. | Wet Detention Pond | Future | TBD | TBD | TBD | 2350000 | TBD | South Fork, South Coastal
Martin County | F-10 | East Hansen Grant Retrofit – Phase III | Design and construct retention/detention facilities to treat water from commercial/industrial area of Stuart. | TBD | Future | TBD | TBD | TBD | 2275000 | TBD | South Fork
Martin County | F-11 | Horsehoe Point Road Exfiltration | Design and construct exfiltration trenches and roadway swales. | Exfiltration | Future | TBD | TBD | TBD | 250000 | TBD | South Coastal
Martin County | F-12 | Manatee Pocket SW Prong STA | Design and construct STA with control structure and associated piping. | Wet Detention Pond | Future | TBD | TBD | TBD | 1725000 | TBD | South Coastal
Martin County | F-13 | Rocky Point Exfiltration and Baffle Boxes | Design and construct exfiltration trenches, roadway swales and baffle boxes. | Exfiltration and Baffle Boxes | Future | TBD | TBD | TBD | 1000000 | TBD | South Coastal
Martin County | F-14 | Golden Gate Rehabilitation | Design and construct a deep water lake in the STA and recontour the entire facility. | Wet Detention Pond | Planning | TBD | TBD | TBD | 1000000 | TBD | South Coastal
Martin County | F-15 | AgTEC Regional STA | Design and construct 1,300-acre STA on 1,700-acre property adjacent to the C-23 canal. | Stormwater Treatment Area | Future | 1300 | TBD | 39683 | TBD | TBD | C-23