## Sheet1
Subbasin or Planning Unit | Project Name | Lead Entity | Project Partners | Project Type | Project Detail | Drainage Area (acres) | ERP # | Project Start | Project End | Project Cost | Funding Source(s) | Estimated Phosphorus Reduction (lbs/yr) | Phosphorus Reduction Calculation Method | Estimated Nitrogen Reduction (lbs/yr) | Nitrogen Reduction Calculation Method | Estimated BOD Reduction (mg/l concentration) | BOD Reduction Calculation Method | Status | Contact Name | Contact Phone | Contact Email | Comments
Coastal Unit | Fort Pierce - Heathcote Botanical Gardens Treatment Train | City of Fort Pierce | Heathcote Botanical Gardens, St. Lucie County, SFWMD, SJRWMD/Indian River Lagoon Program | Phase I: littoral zones, vegetative mats, rain gardens/bio swales, pervious pavement Phase II: expansion of lake, installation of weir, alum injection plant | Improve water quality by the utilization of a treatment train. The project serves the Virginia Avenue Canal drainage basin that outfalls to the IRL. Project will improve timing and reduce nutrient loads to the IRL. | 1242 | Unknown | Late 2012 | Late 2014 | Phase I: $1,050,000 | City of Fort Pierce Stormwater Utility, Heathcote Botanical Gardens, FDEP? | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Planned - partially funded | Jack Andrews | 772-460-2200 | jandrews@city-ftpierce.com
Coastal Unit | Moore's Creek Retrofit - Phases 3 & 4 | City of Fort Pierce | FDOT, FDEP, SFWMD, State of Florida, St. Lucie River Issues Team | Canal cross-section widening with littoral shelf and buffer plantings | Improve water quality and timing through increased detention and littoral shelves | 2382 | 950421-8 | March 2007 | March 2008 | 825000 | St. Lucie River Issues Team/FDOT, FDEP & SFWMD, City of Ft. Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Construction Complete | Tracy Telle | 772-460-2200 | ttelle@city-ftpierce.com
Coastal Unit | South Beach Baffle Boxes | City of Fort Pierce | FDEP, SFWMD, St. Lucie River Issues Team | 11 Baffle Boxes (1st Gen.) | Improve water quality by trapping sediment in the baffle boxes and increasing the volume of runoff treated in grassed swales. | 128 | Exempt | April 2005 | May 2006 | 573120.85 | FDEP, SFWMD, St. Lucie River Issues Team, City of Fort Pierce | 83 | Draft Stormwater Quality Handbook | 14 | Draft Stormwater Quality Handbook | Unknown | Unknown | Construction Complete | Tracy Telle | 772-460-2200 | ttelle@city-ftpierce.com
Coastal Unit | Moore's Creek Retrofit - Phase 2 | City of Fort Pierce | FDEP, SFWMD | 2 Control Structures 7 Baffle Boxes (2nd Gen.) | Improve water quality and timing through increased detention and by trapping sediment in the baffle boxes | 1680 | 020813-9 | December 2002 | July 2003 | 1480437.06 | FDEP, SFWMD, City of Fort Pierce | 395 | Draft Stormwater Quality Handbook | 376 | Draft Stormwater Quality Handbook | Unknown | Unknown | Construction Complete | Jack Andrews | 772-460-2200 | jandrews@city-ftpierce.com
Coastal Unit* | Moore's Creek Retrofit - Phases 3 & 4 | City of Fort Pierce | FDOT/FDEP/SFWMD/State of Florida/St. Lucie River Issues Team | Canal cross-section widening with littoral shelf and buffer plantings | Improve water quality and timing through increased detention and littoral shelves | ? | 950421-8 | March 2007 | March 2008 | 825000 | St. Lucie River Issues Team/FDOT, FDEP & SFWMD, City of Ft. Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Construction Complete | Christa Razem | 772-460-2200 | crazem@city-ftpierce.com
NFSLR | Water & Wastewater Expansion for USA 3-B, C, D, E, F, G, H, I, J, K, and M | City of Port St. Lucie |  | Extension of sanitary sewer collection system including construction of 116 miles of sanitary main, 11 neighborhood lift stations, and other appurtenances | This project improved the ground water quality. A total of 11,769 single-family residential home sites affected. As of 12-31-2008, 4,204 sites had connected to public sewer thereby preventing an estimated 1,051,000 gpd of raw sewage from entering the ground water table. 11,769 lots x 10,000 sq. ft. 117,690,000 total sq. ft. or 2,702 acres |  | 9/2000 | Capital $26,318,217 | Utility Bonds repaid by Non-Advalorem Assessments | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com | These projects (7 projects of extending sanitary sewers) improved water quality. A total of 45,494 single family residential home sites affected.As of August 2010 a total of 24, 868 sites had connected to public sewer thereby preventing an estimated 6,217,000 gallons per day of raw sewage from entering the ground water table. 24,868 lots x 10,000 sq. ft. 248,680,000 total sq. ft. or 5709 acres.
NFSLR | Water & Wastewater Expansion for USA 3-N and USA 4-F, I, J, l, M, N, O, P, and Q | City of Port St. Lucie |  | Extension of sanitary sewer collection system including construction of 102 miles of sanitary main, 10 neighborhood lift stations, and other appurtenances | This project improved ground water quality. A total of 9,972 single-family residential home sites affected. As of 12-31-2008, 3,197 sites had connected to public sewer thereby preventing an estimated 799,250 gpd of raw sewage from entering the ground water table. 9,972 lots x 10,000 sq. ft. 997,200,000 total sq. ft. or 2,289 acres |  | 9/2001 | Capital $20,030,852 | Utility Bonds repaid by Non-Advalorem Assessments | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Water & Wastewater Expansion for USA 4-E, H, K, A, B, C and D | City of Port St. Lucie |  | Extension of sanitary sewer collection system including construction of 78 miles of sanitary main, 8 neighborhood lift stations, and other appurtenances | This project improved ground water quality. A total of 6,511 single-family residential home sites affected. As of 12-31-2008, 2,336 sites had connected to public sewer thereby preventing an estimated 584,000 gpd of raw sewage from entering the ground water table. 6,511 lots x 10,000 sq. ft. 65,110,000 total sq. ft. or 1,492 Acres |  | 9/2002 | Capital $12,127,398 | Utility Bonds repaid by Non-Advalorem Assessments | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Water & Wastewater Expansion for USA 7-A and 5-H | City of Port St. Lucie |  | Extension of sanitary sewer collection system including construction of 28 miles of sanitary main, 2 neighborhood lift stations, and other appurtenances | This project improved the ground water quality. A total of 1,624 single-family residential home sites affected. As of 12-31-2008, 449 sites had connected to public sewer thereby preventing an estimated 112,250 gpd of raw sewage from entering the ground water table. 1,624 lots x 10,000 sq. ft. 16,240,000 Total sq. ft. or 373 Acres |  | 9/2003 | Capital $5,158,057 | Utility Bonds repaid by Non-Advalorem Assessments | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR, C-24 | Water & Wastewater Expansion for USA 5-F, G, E, D. B, and A | City of Port St. Lucie |  | Extension of sanitary sewer collection system including construction of 76 miles of sanitary main, 6 neighborhood lift stations, and other appurtenances | This project improved the ground water quality. A total of 7,965 single-family residential home sites affected. As of 12-31-2008, 2,504 sites had connected to public sewer thereby preventing an estimated 626,000 gpd of raw sewage from entering the ground water table. 7,965 lots x 10,000 sq. ft. 79,650,000 Total sq. ft. or 1,828 Acres |  | 9/2004 | Capital $16,158,057 | Utility Bonds repaid by Non-Advalorem Assessments | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR, C-23 | Water & Wastewater Expansion for USA 6-A, B, C, D. E, F and G | City of Port St. Lucie |  | Extension of sanitary sewer collection system including construction of 81 miles of sanitary main, 7 neighborhood lift stations, and other appurtenances | This project improved the quality of local ground water. A total of 6,570 single-family residential home sites affected. As of 12-31-2008, 1,360 sites had connected to public sewer thereby preventing an estimated 340,000 gpd of raw sewage from entering the ground water table.6,650 lots x 10,000 sq. ft. 66,500,000 Total sq. ft. or 1,526 Acres |  | 9/2005 | Capital $13,684,965 | Utility Bonds repaid by Non-Advalorem Assessments | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Water & Wastewater Expansion for USA 9-A, B, and C | City of Port St. Lucie |  | Extension of sanitary sewer collection system including construction of 18 miles of sanitary main, 3 neighborhood lift stations, and other appurtenances | This project improved ground water quality. A total of 1,083 single-family residential home sites affected. As of 12-31-2008, 68 sites had connected to public sewer thereby preventing an estimated 17,000 gpd of raw sewage from entering the ground water table.1,083 lots x 10,000 sq. ft. 10,830,000 Total sq. ft. or 1249 Acres |  | 9/2007 | Capital $2,756,177 | Utility Bonds repaid by Non-Advalorem Assessments | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Spanish Lakes Riverfront | City of Port St. Lucie | Wynne Building Corp. | Abandonment of private wastewater "package" treatment plant and connection to City's wastewater collection and treatment systems. Site had been identified as a threat plant in the July 1993 S.W.I.M Program for St. Lucie County, Fla. | This project helped remove environmental and ground water contamination that existed with the 100,000 gpd perc pond system associated with the previous privately owned and operated wastewater treatment system. |  | 2/2003 | Unknown | Funded by Wynne Building Corp. | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Vista St. Lucie | City of Port St. Lucie | Vista St. Lucie HOA | Abandomnent of private wastewater "package" treatment plant and connection to City's wastewater collection and treatment systems. Site had been identified as a threat plant in the July 1993 S.W.I.M Program for St. Lucie County, Fla. | This project helped remove environmental and ground water contamination threat that existed with the 125,000 gpd perc pond system associated with the previous privately owned and operated wastewater treatment system. |  | 4/2003 | Unknown | Funded by Vista St. Lucie HOA | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | St. Lucie Plaza | City of Port St. Lucie | Owner of St. Lucie Plaza | Abandonment of private wastewater "package" treatment plant and connection to City's wastewater collection and treatment systems. Site had been identified as a threat plant in the July 1993 S.W.I.M Program for St. Lucie County, Fla. | This project helped remove environmental and ground water contamination threat that existed with the 11,200 gpd perc pond system associated with the previous privately owned and operated wastewater treatment system. |  | 5/2003 | Unknown | Funded by St. Lucie Plaza's owner | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Port St. Lucie Professional Building | City of Port St. Lucie | Owner of Port St. Lucie Professional Building | Abandonment of private septic system and connection to City's wastewater collection and treatment systems. Site had been identified as a threat plant in the July 1993 S.W.I.M Program for St. Lucie County, Fla. | This project helped remove environmental and ground water contamination threat that existed with the 7,500 gpd drain field associated with with the previous privately owned and operated septic system. |  | 10/2003 | Unknown | Funded by Port St. Lucie Professional Building's owner | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | La Buona Vita | City of Port St. Lucie | La Buona Vita HOA | Abandonment of private wastewater "package" treatment plant and connection to City's wastewater collection and treatment systems. Site had been identified as a threat plant in the July 1993 S.W.I.M Program for St. Lucie County, Fla. | This project helped remove environmental and ground water contamination threat that existed with the 28,500 gpd perc pond system associated with the previous privately owned and operated wastewater treatment system. |  | 9/2006 | Unknown | Funded by La Buona Vita HOA | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Port St. Lucie Lanes | City of Port St. Lucie | Owner of Port St. Lucie Lanes | Abandonment of private wastewater "package" treatment plant and connection to City's wastewater collection and treatment systems. Site had been identified as a threat plant in the July 1993 S.W.I.M Program for St. Lucie County, Fla. | This project helped remove environmental and ground water contamination threat that existed with the 5,000 gpd drain field associated with with the previous privately owned and operated septic system. |  | 5/2009 | Unknown | Funded by La Buona Vita HOA | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Lift Stations - New, rehabilitations, piping and wetwell coatings | City of Port St. Lucie | CDBG Grant | These projects include construction of new sanitary lift stations, rehabilitations of leaking lift stations, and sealing of leaking wetwells,piping and valve vaults | These projects include the construction of 9 new lift stations, and the rehabbing of 13 other lift stations. This construction and rehabbing of lift stations has prevented overflowing, leaking and malfunctioning lift stations from discharging raw sewage into the City MS4, thus reducing nutrient loading to nearby waterways and the NFSLR. | 2000 | ongoing | 3810749 | Rates/R&R Fund | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing |  |  | Donna Rhoden | 772-873-6427 | drhoden@cityofpsl.com
NFSLR | Manhole and Sewer Main Replacement and Rehabs | City of Port St. Lucie |  | These projects consist of replacing and/or rehabbing sewer mains and manholes that were leaking raw sewage. | These projects successfully rehabbed or replaced sewer manholes and sewer mains to stop leakage of raw sewage into the City MS4 thus reducing nutrient loading to nearby waterways and the NFSLR | 2001 | ongoing | 2105402 | Rates/R&R Fund | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing |  |  | Donna Rhoden | 772-873-6428 | drhoden@cityofpsl.com
NFSLR | Woodstork Trail Design Districts 7, 8 and 9 | City of Port St. Lucie | PSL CRA, Kodak Company Greenway Awards Program, the Conservation Fund, DEP, EPA, SFWMD, St. Lucie River Issues Team and St. Lucie County | 4.6 acres of new filter marsh, 7.21 acres of new uplands and installation of baffle box.. | These improvements will enhance stormwater drainage and flood protection capacity, improve water quality and restore native vegetation and habitat. These improvements are for a 2500 acre drainage basin | 6/03 | 7/07 | Capital $3.3 M | 319, SFWMD grant, SLC grant, American Greenways grant, TIF | 141 | STEPL, 2007 | 1008 | STEPL, 2007 | Unknown | STEPL, 2007 | Construction and monitoring completed |  |  | Greg Oravec | 772-344-4371 | Goravec@cityofpsl.com
NFSLR | Wood Stork Trail Design District 6 | City of Port St. Lucie | PSL CRA, DEP, EPA, City Center Special Assessment District Property Owners | 7.74 acre wet detention area, .62 acres of sta, 3 baffle boxes | These improvements will enhance stormwater drainage and flood protection capacity, improve water quality and restore native vegetation and habitat. These improvements are for a 2500 acre drainage basin | 4/05 | 11/08 | Capital $825,500 | 319, City Center Special Assessments | The effectiveness of this project in reducing stormwater loadings will be quantified via water quality monitoring | unknown | The effectiveness of this project in reducing stormwater loadings will be quantified via water quality monitoring | unknown | The effectiveness of this project in reducing stormwater loadings will be quantified via water quality monitoring | unknown | Construction complete. Monitoring to commence. |  |  | Greg Oravec | 772-344-4371 | Goravec@cityofpsl.com
NFSLR | E-8 Waterway Ph 2 Water Quality Retrofit | City of Port St. Lucie | FDEP 319 Grant/SLR Issues Team | Control structures improvements, weirs, sediment removal, and construction of 2 STA's totalling 24.36 acres | These improvements will enhance stormwater drainage and flood protection capacity, improve water quality and restore native vegetation and habitat. These improvements are for a 2000 acre drainage basin | 3/06 | 2/09 | $1,600,000 (Capital) | Stormwater Utility / FDEP 319 Grant / SLRIT | 88 | STEPL, 2007 | 514 | STEPL, 2007 | Unknown | STEPL, 2007 | Construction complete. Monitoring underway |  |  | Larry Nadeau | 772-871-5104 | Lnadeau@cityofpsl.com
NFSLR | Howard Creek Stormwater Treatment Area (STA) | City of Port St. Lucie | St. Lucie River Issues Team (SLRIT) $965,596.95 | Construction of weir, 19 acre Stormwater Treatment Area (STA), littoral shelves and new plantings. | These improvements will enhance stormwater drainage and flood protection capacity, improve water quality and restore native vegetation and habitat. These improvements are for the Howard Creek drainage basin | 7/10 | 12/10 | $1,838,700 Capital | Stormwater Utility, SFWMD | 172 | STEPL, 2007 | 1722 | STEPL, 2007 | Unknown | STEPL, 2007 | Started; Planned and funded |  |  | Greg Oravec | 772-344-4371 | Goravec@cityofpsl.com
NFSLR | Eastern Watershed Improvement Project (EWIP) | City of Port St. Lucie | Seeking 319 grant; Seeking TMDL grant | Flood control, water quality, environmental restoration project consisting of ~65 acres of wet detention ponds, littoral shelves, and created wetlands | These improvements will enhance stormwater drainage and flood protection capacity, improve water quality and restore native vegetation and habitat. These improvements are for 3 drainage basins totaling 3560 acres. | 11/08 | 12/11 | Capital $34.7 M | Stormwater Utility | 1433 | STEPL, 2007 | 9136 | STEPL, 2007 | Unknown | STEPL, 2007 | Started; Planned and funded |  |  | Greg Oravec | 772-344-4371 | Goravec@cityofpsl.com | More details of this in EWIP description in 2012 SLWPP Update document
NFSLR | Crosstown Parkway Bridge Crossing | City of Port St. Lucie | St Lucie County | Storm Water Treatment Area. Water Quality improvements and wetland restoration | Provide natural storage and water purifying functions along the NFSLR floodplain for a 1000 acre drainage basin. Will eliminate agricultural runoff from a102 acre active citrus grove, restore/create 80+ acres of wetland habitat, and eliminate 100 acres of developable land adjacent to the NFSLR | 2000 | 2017 | 2000000 | Road and Bridge General Obligation Bond | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | In Permitting Planned and Funded |  |  | Patricia Roebling | 772-871-5174 | patr@cityofpsl.com
NFSLR | Crosstown Parkway Bridge Crossing | City of Port St. Lucie | FDEP | Water quality improvements within the NFSLR | 4 restoration projects, improvements will be achieved by reconnecting oxbows and isolated floodplains in the NFSLR. Areas excavated 3.23 acres. Open water acres improved 22.16 acres. Wetlands connected 28.05 acres. Estimated Cubic yards removed 49,444 | 2000 | 2017 | 2000000 | Road and Bridge General Obligation Bond | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | In Permitting Planned and Funded |  |  | Patricia Roebling | 772-871-5175 | patr@cityofpsl.com
NFSLR | Crosstown Parkway Bridge Crossing | City of Port St. Lucie | FDEP | Land Acquisition | The City agrees to purchase and convey to the FDEP 110 acres of wetlands and uplands located in the North Fork preserve area. The City also agrees to enhance the property by removal of exotics for a 5 year period. | 2000 | 2017 | Land - unknown Exotics - $700,000 | Road and Bridge General Obligation Bond | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | In Permitting Planned and Funded |  |  | Patricia Roebling | 772-871-5176 | patr@cityofpsl.com
NFSLR | Crosstown Parkway Bridge Crossing | City of Port St. Lucie | FDEP / St Lucie County | Recreational Enhancements - Trail | The City agrees to design, permit and construct a 10 foot wide trail, 2.5 miles long, with 5 boardwalk crossings in the Savannahs Recreational area | 2000 | 2017 | 1500000 | Road and Bridge General Obligation Bond | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | In Permitting Planned and Funded |  |  | Patricia Roebling | 772-871-5177 | patr@cityofpsl.com
NFSLR | Crosstown Parkway Bridge Crossing | City of Port St. Lucie | FDEP | Recreational Enhancements - Other | The City agrees to make improvements to Halipatiokee Canoe Launch, Savannah Preserve State Park Educational Center and Canoe / Kayak launch. Improvents include, new canoe / kayak boat launch, pavillion, boardwalks, restrooms, parking areas, 3000 ft2 addition to educational center, kiosks, entrance roads and entrance signs | 2000 | 2017 | 2000000 | Road and Bridge General Obligation Bond | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | In Permitting Planned and Funded |  |  | Patricia Roebling | 772-871-5178 | patr@cityofpsl.com
NFSLR | B-1, B-2, B-3 Water Control Structures (WCS) | City of Port St. Lucie | Natural Resources Conservation Service and SFWMD | WCS (Water Control Structure )and canal upgrades | WCS B-1, B-2, and B-3 protected the NFSLR from receiving uncontrolled E-8 Canal discharges. The system will stage appropriate discharge levels based on volume, retaining flows to a maximum. The Watershed B is a 2500 acre basin with thousands of homes. | 1/2007 | 5/2007 | $1.8 Million (Capital) | Stormwater utility and grant | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Hurricane Wilma
NFSLR | B-4 WCS | City of Port St. Lucie | Natural Resources Conservation Service and SFWMD | WCS and canal upgrades | New WCS retains maximum canal water prior to discharge | 7/2006 | 8/2006 | $40,000 (Capital) | Stormwater utility and grant | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Hurricane Wilma
NFSLR | E-8 Canal Cleaning/Dredging (PSL Blvd. to Savona Blvd) | City of Port St. Lucie | Natural Resources Conservation Service and SFWMD | Canal upgrades | Removal of sediment, exotics, invasive. Repaired failed embankment and stabilized all slopes | 4/2008 | 6/2008 | $525,340 (Capital) | Stormwater utility and grant | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Hurricane Wilma
NFSLR | E-8 Canal Cleaning/Dredging (Savona Blvd to Kensington St) | City of Port St. Lucie | Natural Resources Conservation Service and SFWMD | Canal upgrades | Removal of sediment, exotics, invasive. Repaired failed embankment and stabilized all slopes | 6/2008 | 9/2008 | $973,704 (Capital) | Stormwater utility and grant | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Hurricane Wilma
NFSLR | E-8 Canal Cleaning/Dredging (Kensington St to Logwood Rd) | City of Port St. Lucie |  | Canal upgrades | Removal of sediment, exotics, invasive. Repaired failed embankment and stabilized all slopes | 10/2008 | 1/2009 | $200,000 (Capital) | Stormwater utility and grant | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Hurricane Wilma
NFSLR | E-8 Canal Cleaning/Dredging (Logwood Rd to Import Rd) | City of Port St. Lucie |  | Canal upgrades | Removal of sediment, exotics, invasive. Minor slope stabilization | 10/2009 | 12/2009 | $100,000 (Maintenance) | Stormwater utility | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Regular Maintenance
NFSLR | E-8 Canal Cleaning/Dredging & WCS Improvements | City of Port St. Lucie | SFWMD | Canal & WCS upgrades | Removal of sediment, exotics, invasive. Repaired failed embankment, stabilized slopes, & WCS improvements | 2/2010 | 11/2010 | $400,000 (Capital) | Stormwater utility and grant | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Capital WQ Project
NFSLR | Dredging 8-Canals | City of Port St. Lucie | SFWMD | Canal dredging | Removal of approx. 18,000 CY of sediment/muck from 8 canals in the NFSLR | 5/2010 | 12/2010 | $406,410 (Capital) | Stormwater utility | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Capital WQ Project
C-23 | E-17 Canal WCS | City of Port St. Lucie | SFWMD | WCS and canal upgrades | New WCS added to retain maximum canal retention of water | 11/07 | 7/08 | 437000 | Stormwater Utility | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Capital WQ Project
NFSLR | Monterrey Waterway | City of Port St. Lucie | Natural Resources Conservation Service and SFWMD | WCS and canal upgrades | New WCS retains maximum canal water | 1/2006 | 7/2006 | $5.9 Million (Capital) | Stormwater utility and grant | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed |  |  | Larry Nadeau | 772-871-5104 | lnadeau@cityofpsl.com | Hurricane Wilma
Placed within the NFSLR, although it drains to the west side of the city into the SFSLR(WBID 3210 Tidal St. Lucie) | Poppleton Creek - Phase II and III (Phase I Acquisitions in 1999) | City of Stuart | City of Stuart/SLRIT/SFWMD | Muck sediment removal, creation of a 6.5 acre retention pond and 160' weir to stage up groundwater in basin; Habitat reconstruction (removal of exotics & replanting of native vegetation); Passive recreational improvements (nature trails, educational signage; public access/trailhead north of Central Parkway | To provide water quality treatment for older subdivisions within the basin, including Stormwater Quality, Habitat Reconstruction & Passive Recreation | 525 acres | 43-0211171-001 | Acquistions (1999-2003); Improvements Beginning 2004 | October, 2008 | 4371250 | Martin County & SLRIT Project Funds, Acquisitions via "Healthy Rivers" Referendum, and Community Trust Grant Funding, EPA 319 | SFWMD pre-project data indicate 102 kg/year TP (472 acres), EDR post-project data indicate 3.5 kg/year TP (271 acres), combined loads 47 kg/year, 54% reduction and well below TMDL reqt. | SFWMD and Environmental Data Resources water quality data | SFWMD pre-project data indicate 524 kg/year TN (472 acres), EDR post-project data indicate 116.5 kg/year TP (271 acres), combined loads 320 kg/year for 535 acre basin, substantially exceeding TMDL reduction requirements | SFWMD and Environmental Data Resources water quality data | Unknown | WBID 3210 is not impaired with regard to BOD | Construction Complete | Bill Griffin/Sam Amerson | (772) 288-5331 | samerson@ci.stuart.fl.us
Placed within the North Fork tidal basin, although it drains to the north side of the St. Lucie Middle Estuary via Haney Creek, just east of the Roosevelt Bridge (WBID 3193 St. Lucie River) | Haney Creek Project | City of Stuart | City of Stuart/Martin County/SLRIT | Creation of flow-through marsh and multiple wetlands and control structures to address stormwater quality, environmental restoration and preservation, greenways, passive recreation, and environmental education | To provide water quality treatment for residential and commercial land uses, increase ground water storage, and provide habitat recontruction, passive recreation and education | 800 acres | 43-01176-P | March 2002 | Open to public in 2006 | 4831411 | Martin County & SLRIT Project Funds, Acquisitions via "Healthy Rivers" Referendum, and Community Trust Grant Funding | Estimated pre-retrofit loading 0.44 lbs/acre/year TP (SFWMMD/Evergreen Engineering analysis 2008), anticipated to meet or exceed TMDL requirements when post-retrofit data are obtained. | SFMWD water quality data | TN concnetration at outfall: Geo Mean 0.786 mg/L (SFWMD/Evergreen Engineering analysis 2008) indicates 2.24 lbs/acre/year TN loading pre-retrofit, below TMDL requirement for WBID #3210 | SFWMD water quality data | Unknown |  | Construction Complete
South Fork St. Lucie (WBID 3210 Tidal St. Lucie) | Fraizer Creek Project | City of Stuart | City of Stuart/SLRIT/SFWMD | Muck sediment removal, stormwater retention/detention pond and upstream treatment train | 1.7 acre retention/detention pond with "v" notch weir to stage groundwater up, capture sediments behind the outfall to tide, and to provide low flows via gradual groundwater drawdown to moderate salinity in Frazier Creek | 503 acres | 43-00008-D | Mid 1990's | 2003 | 1702000 | City of Sturat & SLRIT Project Funds, Acquisitions via "Healthy Rivers" Referendum | TP concentration at outfall: Geo Mean 0.079 mg/L (SFWMMD/Evergreen Engineering analysis 2008), annual loading of 0.26 lbs/acre/year TP meets TMDL | SFWMD water quality data | TN concentration at outfall: Geo Mean 0.660 mg/L (SFWMMD/Evergreen Engineering analysis 2008), 2.13 lbs/acre/year more than meets TMDL | SFWMD water quality data | Unknown |  | construction complete
South Fork (WBID 3210 Tidal St. Lucie | Crescent Basin Project | City of Stuart | City of Stuart/SRIT | Stormwater retention | Construction of retention area at the intersections of Palm City Road and Pine Avenue | 6.7 acres | FDEP Grant Agreement S0070 | January 2002 | March 2003 | 180000 | City of Stuart/SLRIT | No Data |  | No Data |  | Unknown |  | construction complete
Drains to the north side of the city into the St. Lucie River (WBID 3193 St. Lucie River) | Krueger Creek Project | City of Stuart | City of Stuart/SLRIT | Installation of baffle boxes | Removal of "ooze" sediments and installation of four baffle boxes | 300 acres | 43-01134-P | March 2000 | November 2001 | 432000 | City of Stuart/SLRIT/ SFWMD | No Data |  | No Data |  | Unknown |  | construction complete
South Fork, St. Lucie River (WBID 3210, 3193A, and 3193) | City Wide Baffle Box Project | City of Stuart | City of Stuart | Installation of baffle boxes | Installation of 1st and 2nd generation baffle boxes on all 34 direct piped outfalls to the St. Lucie River within the city | 1742 acres | 43-01156-P | April 2000 | January 2009 | est. $275,000 | City of Stuart/SLRIT/ EPA 319 | No Data |  | No Data |  | Unknown |  | construction complete |  |  |  | Although all direct stormwater outfalls from City are baffled, much of the remaining acreage in the City does not discharge to tide frequently or at all. This is evident from the lack of storm sewers in much of the City.
North Fork St. Lucie | FM# 230108-1 (Pond 3) | FDOT | NA | Wet detention | This project widened SR 68 from a two-lane roadway to a four-lane roadway. Water quality treatment was not previously permitted for the two-lane roadway and treatment is now being provided for the four-lane roadway (0.83 ac-ft). (This drainage basin is divided between SLE and IRL BMAP Basins; approximately 75% of the drainage area is located within the SLE Basin) | 3.35 | 56-01515 (000828-20) | 2002-07-29 | 2/10/2005 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | FM# 230108-1 (Pond 4) | FDOT | NA | Wet detention | This project widened SR 68 from a two-lane roadway to a four-lane roadway. Water quality treatment was not previously permitted for the two-lane roadway and treatment is now being provided for the four-lane roadway (0.98 ac-ft). | 7.06 | 56-01515 (000828-20) | 2002-07-29 | 2/10/2005 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | FM# 230132-1 (System No. 1) | FDOT | NA | Dry detention | This project widened SR 615 from a two-lane roadway to a four-lane roadway and constructed a new roadway segment; however water quality treatment is provided for the future expansion to a six-lane roadway (0.52 ac-ft). (This drainage basin is divided between SLE and IRL BMAPs; approximately 80% of the drainage area is located within the SLE Basin) | 2.8 | 56-01278 (970220-7) | 1998 | 5/18/2001 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
C-24 | FM# 230262-4 | FDOT | NA | Dry detention | This project widened SR 70 from a two-lane roadway to a four-lane roadway; however water quality treatment is provided for the future expansion to a six-lane roadway (8 ac-ft). | 101.97 | 56-01326 (040227-20) | 5/1/2006 | 7/30/2008 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | FM# 230262-5 | FDOT | NA | Dry detention | SR 70: This project widened a two-lane roadway to a four-lane roadway; however water quality treatment is provided for the future expansion to a six-lane roadway (15.43 ac-ft). CR 712: This project included widening of this roadway and construction of a dry detention pond. | 146.51 | 56-01326 (040601-10) | 6/4/2007 | 4/29/2010 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
C-24 | FM# 230262-3 | FDOT | NA | Dry detention | This project widened SR 70 from a two-lane roadway to a four-lane roadway; however water quality treatment is provided for the future expansion to a six-lane roadway (15.30 ac-ft). | 194.94 | 56-01326 (051013-8) | 9/8/2009 | Est. of Completion = 5/25/2012 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Started | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
C-23/C-24 | FM# 230262-2 | FDOT | NA | Dry detention | This project widened SR 70 from a two-lane roadway to a four-lane roadway; however water quality treatment is provided for the future expansion to a six-lane roadway (22.14 ac-ft). | 238.17 | 56-01326 (051013-8) | 1/31/2011 | Est. of Completion = 6/16/2014 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Started | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
C-23/C-24/ North Fork St. Lucie | FM# 230262 Regional Canal | FDOT | NA | Wet detention | As part of the SR 70 widening project, FDOT relocated an existing canal and constructed a regional canal to accommodate ~20,000 acres of adjacent agricultural land. | Will be provided upon completion | 56-01326 | 5/1/2006 | Est. of Completion = 6/16/2014 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Started | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | FM# 230295-1 | FDOT | NA | Dry detention | This project widened SR 716 from a five-lane roadway to a six-lane roadway. For water quality treatment, three existing interconnected wet detention ponds were modified into dry detention ponds (2.26 ac-ft). | 17.12 | 56-00792 (990723-10) | 8/6/2001 | 3/24/2003 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | SPN 99004-1585 | FDOT | NA | Dry detention | This project widened SR 5 from a six-lane roadway to an eight-lane roadway (volume provided = 4.92 ac-ft). | 30.77 | 43-00884 (980107-2) | 1998 | 1/9/2003 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | SPN 99004-1585 (Lake 3) | FDOT | NA | Wet detention | This project widened SR 5 from a six-lane roadway to an eight-lane roadway. Lake 3 will provide full water quality for Sub-basin 2A. | 13.1 | 43-00884 (980107-2) | 1998 | 1/9/2003 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 228758-1 | FDOT | NA | Dry detention Exfiltration trench | This is a bridge replacement project for SR 732 over the ICWW; water quality treatment was not previously permitted for this site (volume provided = 5.48 ac-ft). | 18.55 | 43-01243 (000719-12) | 12/5/2001 | 1/13/2006 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 228819-1 (Basins A and B) | FDOT | NA | Dry detention pretreatment Wet detention | This project includes the reconstruction of one bridge and the construction of two new bridges for A1A over the ICWW (volume provided = 2.17 ac-ft.) | 16.4 | 43-01561 (040205-8) | 2003-07-18 | 5/16/2007 | Preparing estimates | Currently researching as part of cost estimates | [6 empty] | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 228819-1 (Basin C) | FDOT | NA | Dry detention | This project includes the reconstruction of one bridge and the construction of two new bridges for A1A over the ICWW. Water quality treatment is provided by three interconnected ponds (volume provided = 1.15 ac-ft.) | 16.2 | 43-01561 (040205-8) | 2003-07-18 | 5/16/2007 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 228819-1 (Basin D) | FDOT | NA | Exfiltration trench | This project includes the reconstruction of one bridge and the construction of two new bridges for A1A over the ICWW (volume provided = 0.19 ac-ft.) | 4.41 | 43-01561 (040205-8) | 2003-07-18 | 5/16/2007 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 228819-1 (Basin E) | FDOT | NA | Exfiltration trench | This project includes the reconstruction of one bridge and the construction of two new bridges for A1A over the ICWW (volume provided = 0.31 ac-ft.) | 4.79 | 43-01561 (040205-8) | 2003-07-18 | 5/16/2007 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 228821-1 (West) | FDOT | NA | Dry detention Exfiltration trench | This is a bridge replacement project for A1A over the St. Lucie River; water quality treatment was not previously permitted for this site (volume provided = 1.22 ac-ft). | 5.12 | 43-00948 (960809-7) | 1997 | 4/26/2001 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 228821-1 (East) | FDOT | NA | Exfiltration trench | This is a bridge replacement project for A1A over the St. Lucie River; water quality treatment was not previously permitted for this site (volume provided = 1.3 ac-ft). | 4.65 | 43-00948 (960809-7) | 1997 | 4/26/2001 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
South Fork St. Lucie | FM# 228831-1 | FDOT | NA | Dry detention | This is a bridge replacement project for SR 714 over the Turnpike; water quality treatment is provided for the additional impervious area (0.83 ac-ft). | 9.13 | 43-00966 (970523-15) | 1997 | 3/2/2000 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
South Fork St. Lucie | FM# 228851-1 (Basin A) | FDOT | NA | Dry detention | This is a milling and resurfacing project for SR 5; however water quality treatment was not previously permitted for this site (volume provided = 1.42 ac-ft). | 14.12 | 43-01475 (030422-8) | 11/8/2004 | 8/3/2006 | Preparing estimates | Currently researching as part of cost estimates | [6 empty] | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
South Fork St. Lucie | FM# 228851-1 | FDOT | NA | Dry detention | This is a milling and resurfacing project for SR 5; however water quality treatment was not previously permitted for this site (volume provided = 2.02 ac-ft). | 25.72 | 43-01475 (030422-8) | 11/8/2004 | 8/3/2006 | Preparing estimates | Currently researching as part of cost estimates | [6 empty] | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
South Fork St. Lucie | FM# 228801-1 | FDOT | NA | Dry detention | This project widened SR 5 from a four-lane roadway to a six-lane roadway. Water quality treatment was not previously permitted for the four-lane roadway and is now being provided with this project (4.28 ac-ft). | 88.68 | 43-01112 (990611-6) | 6/18/2001 | 11/13/2003 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
South Fork St. Lucie | FM# 405504-1 | FDOT | NA | Dry detention | This project modified a previously permitted system to serve additional buildings and parking at the rest areas on SR 9 (3.24 ac-ft). | 53.56 | 43-00904 (030804-7) | 3/7/2003 | 2/25/2005 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 405167-1 | FDOT | NA | Dry retention | This is a 3R project for A1A; water quality treatment was not previously permitted. Treatment is provided for the additional impervious area (0.63 ac-ft). | 38.07 | 43-01396 (021122-7) | 1/9/2004 | 4/22/2005 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | FM# 230288-2 | FDOT | FDOT/St. Lucie County/NSLRWCD | Wet detention | This project widened SR 5 from a four-lane roadway to a six-lane roadway. Water quality treatment was provided for SR 5 and 420 acres of existing development surrounding the area that did not have treatment. FDOT constructed three wet detention ponds that provide 39.2 ac-ft of treatment. St. Lucie County responsible for Operation and Maintenance. | 44.4 | 56-02099 (040525-9) | 8/31/2005 | 5/11/2009 | NA | NA | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
Coastal Unit | FM# 230296-1 | FDOT | NA | Dry | This A1A project added a 5-foot paved shoulder on each side of the roadway and an 8-foot wide sidewalk (for a portion of the project). Water quality treatment was provided for the additional impervious areas (9.06 ac-ft). | 88.91 | 56-02339-P (030909-13) | 2004 | 2009-03-31 | NA | Legislative Funding | NA | NA | NA | NA |  |  | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
North Fork St. Lucie | Canals 23 & 28 Retrofit for Stormwater Treatment & Attenuation | FDOT | NSLRWCD, St. Lucie County, FDOT | Construction of ponds & installation of water control structures for area retrofit. Inclusion of District canals into pond footprints. | Construction of ponds & installation of water control structures to provide attenuation & water quality as a retrofit to developed area in the US 1 corridor. Stormwater model developed for project design. | Drainage basin from Rio Mar Drive to Midway Road in US 1 corridor. Approximately 100 acres directly benefited. | 56-02099-P | MAR 2005 | FEB 2010 (Some related bank repair work ongoing) | Unknown (Primarily funded by FDOT) | FDOT, SLC, NSLRWCD | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Primary construction completed. Related bank repair work ongoing. | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
C-23 | FM# 231812-2 | FDOT | NA | Wet detention | This project is for the construction of a Weigh-in-Motion station to serve southbound I-95. Water quality treatment is provided for the facility and access ramps (3.94 ac-ft). | 32.44 | 43-00196-S (080926-6) | 7/6/2009 | Est. of Completion = August 2011 | Preparing estimates | Currently researching as part of cost estimates | [6 empty] | Started | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
C-24 | FM# 426373-3 | FDOT | NA | Wet detention | This project modified the existing I-95/St. Lucie West Boulevard Interchange and drainage system (9.15 ac-ft provided). | 122.95 | 56-01168-S (070323-14) | 2009 | 2011-01-20 | Preparing estimates | Currently researching as part of cost estimates | [6 empty] | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
C-23/North Fork St. Lucie | FM# 419890-1 | FDOT | City of Port St. Lucie | Wet and dry detention | This project was for the construction of a new interchange at I-95 and Becker Road (volume required = 9.76 ac-ft, volume provided = 14.56 ac-ft). | 41.96 | 79-00151-S (061103-31) | 2008 | 2010-01-11 | Preparing estimates | Currently researching as part of cost estimates | [6 empty] | Completed | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
South Fork St. Lucie | FM# 230978-1 | FDOT | NA | Wet and dry detention | This project is for the construction of a new bridge over the South Fork of the St. Lucie River. An additional 50% of water quality treatment volume will be provided (volume provided = 10.49 ac-ft). | Will be provided upon completion | 43-02393-P (091021-8) | 10/21/2009 | Est. of Completion = 6/30/2013 | Preparing estimates | Currently researching as part of cost estimates | [6 empty] | Started | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
St Lucie River | Ridgeland Court Retrofit | Sewall's Point |  | Exfiltration/Baffle Box |  |  |  |  | 3/2000; 7/2001; 4/2002
Indian River | Palm Court/Knowles | Sewall's Point |  | Baffle Box |  |  |  |  | 3/2000; 1/2006
Indian River | Delano Lane | Sewall's Point |  | Exfiltration System |  |  |  |  | 2/2000
Indian River | Captain Cove | Sewall's Point |  | Baffle Box |  |  |  |  | 3/2000
| Town Commons Park | Sewall's Point |  | Water Quality Treatment/Dry Detention |  |  |  |  | 7/2001
Indian River | Quail Run Park | Sewall's Point |  | Direct Link to a Detention Area prior to discharge to Indian River |  |  |  |  | 3/2000
Indian River | Heritage Park | Sewall's Point |  | Addition Stormwater Retrofit Area iin a developed Subdivision |  |  |  |  | 3/2000
Indian River | Via Lucindia | Sewall's Point |  | Exfiltration Pipe |  |  |  |  | 3/2000
Indian River | Island Road | Sewall's Point |  | Exfiltration Pipe with Baffle Box |  |  |  |  | 7/2001
Indian River | Rio Vista Park | Sewall's Point |  | Baffle Box/Erosion Control for Outfall to Indian River |  |  |  |  | 3/2000; 7/2001
Indian River | India Lucie | Sewall's Point |  | Retrofit of weir/Retention Area for Baffle Boxes (2), old subdivison without Retention to directly discharge to Indian River |  |  |  |  | 3/2000; 3/2003
Indian River | Simara Street | Sewall's Point |  | Erosion control/Bank Stabilization |  |  |  |  | 3/2006
St Lucie River | Highpoint West | Sewall's Point |  | Baffle Box |  |  |  |  | 3/2000
Indian River | Mandalay | Sewall's Point |  | Baffle Box |  |  |  |  | 3/2000
Indian River | Highpoint East | Sewall's Point |  | Baffle Box |  |  |  |  | 3/2000
Indian River | Perriwinkle | Sewall's Point |  | Baffle Box |  |  |  |  | 3/2000
| Palm Road | Sewall's Point |  | Swales |  |  |  |  | 6/2008
| Riverview | Sewall's Point |  | Baffle Box |  |  |  |  | 7/2001
| Pineapple Lane | Sewall's Point |  | Outfall Exfiltration |  |  |  |  | 7/2001
| Copaire | Sewall's Point |  | Baffle Box |  |  |  |  | 4/2002
| Homewood Park/S Sewall's Point Rd | Sewall's Point |  | Retention Area with Pervious Flexi-Pave and Exfiltration Pipe |  |  |  |  | 3/2000; 12/2008
Drains to the east side of the city into the St. Lucie River (WBID 3193 St. Lucie River | Airport Ditch Project | Joint effort between City of Stuart and Martin County | City of Stuart/Martin County/SFWMD | Airport Ditch stormwater retention/detention facilites | Conversion of two uncontrolled drainage ditches to tide into retention/detention facilities controled by "v" notch weirs | 846 acres | 43-01107-P | 1999 | August 2003 | 766756 | SLRIT/SFWMD/ FEMA/Martiin Airport/EPA 319 | TP concentration at outfall: Geo Mean 0.088 mg/L (SFWMMD/Evergreen Engineering analysis 2008), 0.28 lbs/acre/year TP to WBID # 3193 | SFWMD water quality data | TN cConcentration at outfall: Geo Mean 0.820 mg/L (SFWMMD/Evergreen Engineering analysis 2008), 2.64 lbs/acre/year TN to WBID #3193 | SFWMD water quality data | Unknown |  | construction complete |  |  |  | Approximately 2/3 of this basin in within Martin County jurisdiction
Coastal Unit* | Salerno Creek Stormwater Quality Retrofit Phase 2 | Martin County | FDOT/NEP/State of Florida/St. Lucie River Issues Team | Wier installation, ditch reconstruction, exotic removal and native planting | provide water quality treatment for older subdivisions within the basin | ? | N/A | April 2006 | January 2007 | 300000 | Issues Team/FDOT/NEP/Martin County | 5 kg/yr (11.0 #/yr) (reported removal rate 71%) | Unknown | Unknown | Unknown | 109 (reported removal rate 65%) |  | Construction Complete | Gary Roderick | 772-219-4980 | groderic@martin.fl.us
South Fork St. Lucie River** | Old Palm City Water Quality Improvement Project | Martin County | Martin County/ 319 Project (Fed/State) | This project provided for the construction of a 2-acre detention area and the creation of a 1.5 acre wetland area in Old Palm City for the treatment of stormwater flowing from west to east into the South Fork of the St. Lucie River and into the Indian River Lagoon. | Stormwater runoff previously discharged from Old Palm City into the South Fork of the St. Lucie River via a road swale system with scattered catch basins and culverts at road intersections. The project consisted of three portions: (1) the 30th Street Pond; 2) the outfall system, and 3) the Cornell and 32nd St STA. The drainage/watershed area was highly urbanized prior to these water quality and flood protection enhancements, and this project was principally designed to provide water quality treatment for the (previously) untreated stormwater discharges to the St. Lucie River. | ? | ? | May 2003 | March 2004 | $1,246,104 (MC share $690, 999) | Martin County & Federal/FDEP 319 Grant | Estimated 6.9 kg/yr (15.2 #/yr) - Six storm events were monitored; 4 wet season/2 dry season | Initial Estimates unknown - (However, monitoring events on file in 319 Project File G00034) | Estimated 21.4 kg/yr (47.2#/yr) | Initial Estimates unknown - (However, monitoring events on file in 319 Project File G00034) | Estimated 250 kg/yr | Initial Estimates unknown - (However, monitoring events on file in 319 Project File G00034) | Construction complete | Greg Nolte/Gary Roderick (& Final Reports on File: Dave Worley, FDEP-NPS section) | 772-219-4980 | groderic@martin.fl.us
Coastal | Cedar Point WQ Retrofit | Martin County | SFWMD - FDEP | Wet detention and swales | 1.7 acre feet of WQ treatment - 0.36 inches | 57 | NA | 10/01 | 10/04 | 398027 | ad valorem - slrit | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Golden Gate WQ Retrofit Phases I, II, III | Martin County | SFWMD - FDEP | Wet detention, dry detention and swales | 17.4 acre feet of WQ treatment - 0.91 inches | 229 | 43-01255-P | 01/01 | 03/04 | 2630515 | ad valorem - 319 - slrit - srf | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Hibiscus Park WQ Retrofit Phases I and II | Martin County | SFWMD - FDEP | Wet detention and swales | 0.4 acre feet of WQ treatment - 1.06 inches | 4.5 | 43-01196-P | 01/01 | 07/07 | 1390574 | ad valorem - slri | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Indian River Drive Baffle Boxes | Martin County | SFWMD - FDEP | Baffle Boxes (2nd generation) |  |  | 43-02319-P | 08/08 | 05/10 | 734100 | ad valorem - slrit - tmdl | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Warner Creek/Leilani Heights WQ Retrofit Phase | Martin County | SFWMD - FDEP | Exfiltration Trenches and swales | 8.0 acre feet of WQ treatment - 0.14 inches | 700 | 43-00971-P | 10/02 | 08/11 | 3500000 | ad valorem - slrit - 319 | [6 empty] | Phase I under construction - Phase II planned | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Manatee Creek WQ Retrofit Phases I, II, III | Martin County | SFWMD - FDEP | Wet detention and swales | 30.4 acre feet of WQ treatment - 0.44 inches | 833 | 43-02364P | 10/03 | 06/11 | 7500000 | ad valorem - slrit - tmdl - 319 - NEEP - srf | [6 empty] | Phase I constructed - Phases II and III under construction | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Poinciana Gardens WQ Retrofit Phases I and II | Martin County | SFWMD - FDEP | Wet detention and swales | 10.6 acre feet of WQ treatment - 0.68 inches | 188 | 43-01265-P | 01/01 | 07/03 | 2960547 | ad valorem - slrit | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Salerno Creek WQ Retrofit | Martin County | SFWMD - FDEP | Wet detention and swales | 54.5 acre feet of WQ treatment - 1.03 inches | 633 | 43-01196-P | 10/01 | 05/03 | 4715074 | ad valorem - slrit - 319 - fdot | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
South St. Lucie - IRL WBID 3210 | Coral Gardens WQ Retrofit | Martin County | SFWMD - FDEP | Wet detention and swales | 8.5 acre feet of WQ treatment - 0.05 inches | 2260 | 43-01510-P | 03/01 | 05/05 | 2321860 | ad valorem - slrit - srf | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
South St. Lucie - IRL WBID 3210 | Fern Creek WQ Retrofit | Martin County | SFWMD - FDEP | Wet detention and swales | 29.8 acre feet of WQ treatment - 0.81 inches | 443 | 43-01508-P | 01/01 | 04/05 | 2660200 | ad valorem - slrit - srf | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
South St. Lucie - IRL WBID 3210 | Old Palm City WQ Retrofit Phases I, II, and III | Martin County | SFWMD - FDEP - FEMA | Wet detention, swales and bio-filter | 8.1 acre feet of WQ treatment - 0.51 inches | 192 | 43-01273-P 43-02326-P | 01/01 | 11/03 | 1544600 | advalorem - 319 - fema | [6 empty] | Phases I and II complete - Pase III to be completed 8/11 | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
South St. Lucie - IRL WBID 3194B | North River Shores Baffle Boxes | Martin County | SFWMD - FDEP | Baffle Boxes (2nd generation) |  |  | 43-01140-P | 01/01 | 03/02 | 1310000 | ad valorem - slrit | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
South St. Lucie - IRL WBID 3194B | Palm Lake Park WQ Retrofit | Martin County | SFWMD - FDEP | Wet detention and swales | 7.7 acre feet of WQ treatment - 1.16 inches | 80 | 43-01254-P | 06/01 | 02/03 | 1750000 | ad valorem - slrit | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
South St. Lucie - IRL | Tropical Farms WQ Retrofit | Martin County | SFWMD - FDEP | Wet detention and swales | 43.2 acre feet of WQ treatment - 1.11 inches | 468 | 43-02200-P | 04/06 | 12/10 | 3850500 | ad valorem - slrit - tmdl | 88.18 |  | 462.96 |  |  |  | Under Construction | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal | Banner Lake | Martin County |  | Septic to Central Sewer Conversion | 116 single family residential units | [6 empty] | 743 | DEP | 2922 | DEP
Coastal | Hobe Sound Commercial | Martin County |  | Septic to Central Sewer Conversion | 49 single family residential and commercial units | [6 empty] | 313 | DEP | 1234 | DEP
Coastal | Rio | Martin County |  | Septic to Central Sewer Conversion | 68 single family residential and 3 commercial units | [6 empty] | 436 | DEP | 1713 | DEP |  |  |  | John Polley | (772) 223-7942 | jpolley@martin.fl.us
South St. Lucie - IRL - WBID 3194B | North River Shores Phase I and Phase II | Martin County |  | Septic to Central Sewer Conversion | 435 single and multi family residential units | [5 empty] | neep | 2787 | DEP | 10958 | DEP |  |  | Phase I complete = 435 Proposed Phase II = 315 S.F. | John Polley | (772) 223-7942 | jpolley@martin.fl.us
South St. Lucie - IRL - WBID 3211 | Seagate Harbor | Martin County |  | Septic to Central Sewer Conversion | 450 single and multi family residential units | [6 empty] | 2884 | DEP | 11336 | DEP |  |  |  | John Polley | (772) 223-7942 | jpolley@martin.fl.us
Coastal | Rio/St. Lucie WQ Retrofit | Martin County | SFWMD - FDEP | Wet detention and swales | 3.0 acre feet of WQ treatment - 0.35 inches | 104 | 43-01932-P | 10/03 | 09/08 | 354161 | ad valorem - slrit - srf - irlnep | [6 empty] | Completed | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
North Fork St. Lucie | SLRIT Grant 2000-2001: Vegetation Control & Bank Restoration | NSLRWCD | SLRIT | Diversion structure construction; installation of gated risers, vegetation booms, trash racks; water quality testing expansion; canal bank restoration & exotic vegetation removal. | Reduced flow to North Fork with installation of C-25 Diversion Structure. Retrofits or improvements for water quality & better water mgmt at approx. 13 sites. Mechanical removal of exotic vegetation to prevent transport downstream. | Large-scale scope that ranged across most of District. NSLRWCD is 65,000 acres in size. | Exempt | NOV 2001 | MAY 2003 | 929000 | NSLRWCD/ SLRIT 50/50 contribution match | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | SLRIT Grant 2002-2003: Water Quality Best Management Practices | NSLRWCD | SLRIT | Removal of exotic vegetation & canal bank stabilization. Increased frequency and breadth of water quality testing. | Mechanical removal of exotic vegetation & stabilization of canal banks at approximately 43 sites around the NSLRWCD. | Project focused primarily on western half of District. Approximately 32,500 acres benefited. | Exempt | JUL 2002 | JAN 2005 | 360000 | NSLRWCD/ SLRIT 50/50 contribution match | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | SLRIT Grant 2004-2005: Water Quality Best Management Practices | NSLRWCD | SLRIT | Removal of exotic vegetation & canal bank stabilization. Increased frequency and breadth of water quality testing. | Mechanical removal of exotic vegetation & stabilization of canal banks at approximately 37 sites around the NSLRWCD. Water quality testing at approximately 10 sites around the District. | Project focused primarily on developing corridors of the District. Approximately 40,000 acres benefited. | Exempt | APR 2005 | JUL 2005 | 586700 | NSLRWCD/ SLRIT 50/50 contribution match | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie C-24 in different spreadsheet | SLRIT Grant 2007-2008: Water Control Structure Retrofits | NSLRWCD | SLRIT | Installation of adjustable gates on water control structures to improve efficiency of water levels & better manage sediment transport downstream. | Installation of adjustable gates on 4 water control structures around the SR 70 corridor, upstream of Ten Mile Creek. | Direct water control benefit to approximately 1,500 acres & estimated secondary water quality benefit to approximately 7,000 acres. | Exempt / Coordination with FDOT SR 70 Widening (SFWMD Permit No. 56-01326-P) | MAR 2008 | JUN 2009 | 60000 | NSLRWCD/ SLRIT 50/50 contribution match | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | SLRIT Grant 2008-2009: Best Management Practices | NSLRWCD | SLRIT | Removal of exotic vegetation & related canal bank stabilization. | Mechanical removal of exotic vegetation & stabilization of canal banks at approximately 17 sites around the NSLRWCD. | Project focused primarily on 6 miles of canal in central and western areas of the District. Approximately 30,000 acres benefited. | Exempt | MAR 2009 | JAN 2010 | 120000 | NSLRWCD/ SLRIT 50/50 contribution match | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | SLRIT Grant 2010-2011: Watershed Water Quality Improvements | NSLRWCD | SLRIT | Removal of exotic vegetation & related canal bank stabilization. | Mechanical removal of exotic vegetation & stabilization of canal banks at approximately 11 sites around the NSLRWCD. | Project focuses primarily on 12 miles of canal in the center of the District. Approximately 22,000 acres benefited. | Exempt | FEB 2010 | Ongoing | 50000 | NSLRWCD/ SLRIT 50/50 contribution match | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | Debris Removal & Slope Stabilization following 2004 Hurricanes | NSLRWCD | NRCS | Invasive vegetation removed from District canal system. Blockages removed and bank restabilization provided to restore District system & prevent future damages. | Invasive vegetation and blockages removed from approximately 14 sites in the NSLRWCD. Slope restabilization and/ or revegetation provided as necessary to prevent future bank failures/ sediment transport. | Project restored areas in 3 major canals of District system, as well as multiple sites on lateral canals. Approximately 50,000 acres benefited. | Exempt | APR 2005 | JUN 2006 | $2 million | NSLRWCD/ NRCS | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | Debris Removal & Slope Stabilization following 2005 Hurricanes | NSLRWCD | NRCS/ St. Lucie County | Invasive vegetation removed from District canal system. Blockages removed and bank restabilization provided to restore District system & prevent future damages. | Invasive vegetative and blockages removed at 10 sites in NSLRWCD. Slope restoration with rubble riprap provided at 3 sites. | Project restored areas in Ten Mile Creek, directly upstream of the North Fork, and at 7 lateral canals around District. Approximately 26,000 acres benefited. | Exempt | AUG 2006 | MAY 2007 | 580000 | NSLRWCD, NRCS, SLC | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3886 | tom.mcgowan@aecom.com
North Fork St. Lucie | Header Canal - Slope Restoration following Tropical Storm Fay | NSLRWCD | NRCS/ St. Lucie County | Canal bank restoration and embankment repair. | Western canal bank restoration with turf reinforcement mat, rubble riprap and roadside swale with inlets for approximately 2.5 miles along Header Canal. | Project repaired portion of main canal in District system. Approximately 6,000 acres directly impacted, indirect benefit to approx. 16,000 acres. | Exempt | JAN 2009 | MAR 2010 | $5.1 million | NSLRWCD, St. Lucie County & NRCS | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | Five Mile Creek - Slope Restoration following Tropical Storm Fay | NSLRWCD | NRCS | Canal bank restoration and embankment repair. | Canal bank restoration with turf reinforcement mat and rubble riprap approximately 1.0 miles along Five Mile Creek and NSLRWCD Canal Nos. 5 & 35. | Project repaired canal directly upstream of North Fork of St. Lucie River. Approximately 5,500 acres benefited. | Exempt | JAN 2009 | MAR 2010 | $2.2 million | NSLRWCD/ NRCS | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | Varn Structure at Gordy Road/ Ten Mile Creek - Structural Improvements following Tropical Storm Fay | NSLRWCD | NRCS | Canal bank restoration and embankment repair at major water control structure. | Embankment restoration with rubble riprap at the primary control structure along Ten Mile Creek. | Project repaired embankment around primary control structure in District, located in Ten Mile Creek. Approximately 40,000 acres benefited. | Exempt | JAN 2009 | MAR 2010 | 77000 | NSLRWCD/ NRCS | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | Canal 9A Retrofit | NSLRWCD | N/A | Relocation of lateral canal and related structural improvements. | Relocation of portion of lateral canal and replacement/ repair of drainage and water control facilities. Stormwater model developed for project design. | Drainage basin from Edwards Road to Five Mile Creek, directly upstream of North Fork. Approximately 90 acres benefited. | 56-01476-P | FEB 2001 | Unknown (Est. 2002) | Unknown | NSLRWCD | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Completed | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
C-23 |  | SFWMD | Martin County/SFWMD/FDEP |  | 19,055 acres Conservation - Natural Area Storage - 41.6% | 45835 | [5 empty] | 18673 | SLRWPP | 72157 | SLRWPP |  |  |  | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
C-44 |  | SFWMD | Martin County/SFWMD/FDEP |  | 10,832 acres Conservation - Natural Area Storage - 9.4% | 115500 | [5 empty] | 10615 | SLRWPP | 41018 | SLRWPP |  |  |  | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
C-44 | CERP Reservoir/STA | SFWMD | Martin County/SFWMD/FDEP |  | 12,037 acres Res/STA - 10.4% | 115500 | [5 empty] | 57540 | IRL - CERP | 187391 | IRL - CERP |  |  |  | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
Coastal |  | FDEP | Martin County/SFWMD/FDEP |  | 4,468 acres Conservation - Natural Area Storage - 23.2% | 19290 | [5 empty] | 4378 | SLRWPP | 16919 | SLRWPP |  |  |  | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
South St. Lucie - IRL |  | FDEP | Martin County/SFWMD/FDEP |  | 7,148 acres Conservation - Natural Area Storage - 11.2% | 63976 | [5 empty] | 7005 | SLRWPP | 27068 | SLRWPP |  |  |  | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
North St. Lucie |  | FDEP | Martin County/SFWMD/FDEP |  | 611 acres Conservation - Natural Area Storage - 10.2% | 5964 | [5 empty] | 599 | SLRWPP | 2314 | SLRWPP |  |  |  | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
North Fork of the St. Lucie River (3194) | Platt’s Creek Stormwater Treatment Facility | St. Lucie County | St. Lucie County/Federal/State | "First-Flush" capture and diversion (0.66" R.F.) with wet detention and alum injection. | Water quality treatment for a 1000+ acre watershed (mixed residential/commercial w/ OSTD.) 170 cfs pump station to 16 acre pond capturing ~ 84 acre-feet and release through 2 F.C.W. to NFSLR with 60% - 90% TP removal. | 1000+ acres | SFWMD Permit #56-00003-M | March 2004 | October, 2007. Alum injection system complete June, 2008. | $3,539,475 ($5300,000 in 319 Grant) | St. Lucie County & Federal/FDEP Grant Match | Average of 75.5% = 507 Lb/Yr. | Straight calculation and averaging of 20 data points from 3/2009 to 4/2010 using Influent and effluent laboratory results. Weight estimated using 49% capture rate of total RF to creek. | Average -2.5% ; Median 5% = 266 Lb/Yr. (Substantial increase in TKN from pond negates 80% removal of NOX) | Straight calculation and averaging of 20 data points from 3/2009 to 4/2010 using Influent and effluent laboratory results. Weight estimated using 49% capture rate of total RF to creek. | Average -2.9%; Median 0% = 0 Lb/Yr. (Most values at or just above laboratory detection limit of 2.0 mg/L) | Straight calculation and averaging of 20 data points from 3/2009 to 4/2010 using Influent and effluent laboratory results. Weight estimated using 49% capture rate of total RF to creek. | Complete. | Jason Bessey/Don West ( & Final Reports on File: Dave Worley, FDEP, NPS Section - G00064) | 772-462-1668 | besseyj@stlucieco.gov
North Fork of the St. Lucie River (3194) | Indian River Estates Stormwater Improvements (Phase I and II) | St. Lucie County | St. Lucie County/Federal/State | Pump station diviersion to a two-cell-series wet detention system with alum injection | Stormwater diversion from 1200 acre (~3200 homes w/ OSTD) subdivision providing 32 ac/ft primary storage. Redirects 100% of the stormwater away from the NFSLR to the IRL via the Northern Savannas Preserve | 1200 Acres | SFWMD Permit #56-01710-P | January, 2008 | January, 2009. Alum enhancement complete August, 2009. | $4,471,114.00 Pump Station; $140,030.75 Alum Enhancement | St. Lucie County & Federal/FDEP Grant Match | Average 33% = 432 Lbs/Yr. (ultimately 100% as flows no longer to SLR) | Averaging of 19 data points from 3/2009 to 3/2010 using Influent and effluent laboratory results and assigned loading rates from spreadsheet model. *see DEP Grant final report* | Average 19% = 1,968 Lbs/Yr. (ultimately 100% as flows no longer to SLR) | Averaging of 19 data points from 3/2009 to 3/2010 using Influent and effluent laboratory results and assigned loading rates from spreadsheet model. *see DEP Grant final report* | Average 4% = 1,207 Lbs/Yr. (ultimately 100% as flows no longer to SLR) | Averaging of 19 data points from 3/2009 to 3/2010 using Influent and effluent laboratory results and assigned loading rates from spreadsheet model. *see DEP Grant final report* | Phase I complete (pump station and detention system) Phase II collection system to start end of year 2010 | Jason Bessey/Don West ( & Final Reports on File: Dave Worley, FDEP, NPS Section - G00065) | 772-462-1668 | besseyj@stlucieco.gov
North Fork of the St. Lucie River (3194) | River Park Water Quality Improvement | St. Lucie County | St. Lucie County/Federal/State | Baffle Box (2 large-plus sedimentation basin) | Retrofit 2 outfalls to capture ~60% TSS and 90% gross solids from entering NFSLR | 150 Acres | ? | January, 2006 | November, 2006 | 323483 | St. Lucie County & Federal/FDEP Grant Match | Average 38% = 74 Lbs/Yr. | Literature search estimate (Baffle Box Removal Efficiencies in Brevard County) Weight using spreadsheet model loading rates. | Average 10% = 155 Lbs/Yr. | Literature search estimate (Baffle Box Removal Efficiencies in Brevard County) Weight using spreadsheet model loading rates. | Assuming 5% = 236 Lbs/Yr. | Literature search estimate (Little data found- assume 5%) Weight using spreadsheet model loading rates. | Complete | Jason Bessey/Don West ( & Final Reports on File: Dave Worley, FDEP, NPS Section - G00065) | 772-462-1668 | besseyj@stlucieco.gov
North Fork of the St. Lucie River (3194) | White City- Canal 'D' | St. Lucie County | St. Lucie County/Federal/State | Stormwater re-route with control structure and sediment trap | Installation of a control structure for retention within canal and re-route (around pasture) through sediment chamber | 50 Acres | SFWMD Permit #56-02915-P | December, 2008 | April. 2009 | 282360 | St. Lucie County & Federal/FDEP Grant Match | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Complete | Jason Bessey/Don West ( & Final Reports on File: Dave Worley, FDEP, NPS Section - G00065) | 772-462-1668 | besseyj@stlucieco.gov
North Fork of the St. Lucie River (3194) | White City- Citrus/Seager Stormwater Improvement | St. Lucie County | St. Lucie County/Federal/State | Wet Detention | Construction of a 4 acre detention pond and re-construction of area grassed swales | 50 Acres | ? | 2011 | 2012 | Approx. $1,862,859 (including purchased land) | St. Lucie County & Federal/FDEP Grant Match | Estimating 65 Lbs/Yr. 66% removal | Literature estimation of wet pond efficiencies using spreadsheet loading factors | Estimating 222 Lbs/Yr. 43% removal | Literature estimation of wet pond efficiencies using spreadsheet loading factors | Estimating 79 Lbs/Yr. 5% removal | Literature estimation of wet pond efficiencies using spreadsheet loading factors | Planned and funded | Jason Bessey/Don West ( & Final Reports on File: Dave Worley, FDEP, NPS Section - G00065) | 772-462-1668 | besseyj@stlucieco.gov
C-24, North St. Lucie | Pond A - Project 420735-1 (2009) Port St. Lucie Interchange Ponds | Turnpike FDOT |  | Dry Detention Outfall structure C-2 | 0.5 foot Treatment (Has Bleed Down) | 3.4 acres | [5 empty] | 40% |  | 30% |  | 50% |  | completed | Kevin Stewart | 407-264-3417 | Kevin.stewart@dot.state.fl.us
North St Lucie | Pond B - Project 420735-1 (2009) Port St. Lucie Interchange Ponds | Turnpike FDOT |  | Wet Detention Outfal Structure D-3 | 3 feet of Treatment (No Bleed Down) | 14.7 Acres | [5 empty] | 100% |  | 100% |  | 100% |  | completed | Kevin Stewart | 407-264-3417 | Kevin.stewart@dot.state.fl.us
Tidal St Lucie | Thomas B Manuel Bridge North Pond (2005) | Turnpike FDOT |  | Dry Detention Outfall | additional Volume provided (15%) | 11.3 Acres | [5 empty] | 46% | (40(1+.15)%) | 34.5% | (30(1+.15)%) |  |  | completed | Kevin Stewart | 407-264-3417 | Kevin.stewart@dot.state.fl.us
C-24 | Verano CDD - CDD 1 and Center CDD Master Surface Water Mangement System | Verano CDD | Not Applicable | Wet Detention | Multi-use development located on the northside of the C-24 with approximately 1,041 units planned with associated master surface water system, potable water, and sewer. Approximately 73.6 acre of wet detention to treat and attenuate surface water runoff. | 472.7 acres | 56-00674-S | 2005 | Ongoing |  | Port St. Lucie Stormwater Utility reimbursed funds | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | Ongoing | Scott Morton Tom McGowan Amy Eason | 561-682-9500 772-286-3883 772-286-3883 | smorton@kolterprop.com | This project is under construction. This area has been converted from Agriculture to Residential. A master surface water management system has been designed and partially built as of 2011.
C-24 | Verano CDD - CDD 2, 3, 4, and 5 Master Surface Water Management System | Verano CDD | Not Applicable | Wet Detention | Multi-use development located on the southside of the C-24 with approximately 4,350 units planned with associated master surface water system, potable water, and sewer. Approximately 362.7 acre of wet detention to treat and attenuate surface water runoff. | 2,532.7 acres | 56-01648-P | 2012 | 2022 |  | Port St. Lucie Stormwater Utility reimbursed funds | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | To be provided at a later date. | Envisioned | Scott Morton Tom McGowan Amy Eason | 561-682-9500 772-286-3883 772-286-3883 | smorton@kolterprop.com | This project is conceptually permitted. The existing landuse is agriculture, but is proposed to change to a mixed use development. The landuse used to determine the initial loadings have changed and needs to be provided to FDEP.
LIST Activities: For Provisional Credits for Nutrient Reductions from Non-Structural Activities Here: |  |  |  | Examples include Education and Outreach Programs (information, pamplets or brochures distributed on pollution prevention, public service announcements, etc.); Implementation of Florida Friendly Landscaping via land development Codes, Ordinances, other local authority; Street Sweeping Activities, etc. and other activities as outlined in the Provisional BMAP Credit Information provided at the 3/25/10 St. Lucie BMAP Meeting
NFSLR, C-24, C-23 | Catch Basin Cleaning | City of Port St Lucie |  | Remove pollutants/sediments from catch basins prior to reaching waterways | Routine Maintenance Cleaning from 2006 to Present - 490 catch basins cleaned - 84.5 tons of sediments removed. Emergency Cleaning After Hurricanes Francis/Jeanne/Fay 4332 Catch basins cleaned - ~720 tons | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4130 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Fertilizer Ordinance 10-12 | City of Port St Lucie |  | Ordinance to reduce excessive nutrient and pathogen runoff into waterbodies. | The ordinance regulates the proper use of fertilizer, requires training of commercial and institutional fertilizer applicators, establishes training and licensing requirements, establishes a prohibidited application period, specifies allowable fertilizer application rates and methods, fertilizer free zones, low maintenance zones, and exemptions. | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4131 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Landscaping/Irrigation Code Sec 153 | City of Port St Lucie |  | Codes to preserve and protect existing vegetation, promote water conservation, and encourage greater use of native cold-tolerant and drought tolerant landscape material | The provision for landscaping and the retention of natural plant growth reduces erosion, provides shade, buffers imcompatible uses, aids in urban temperature control. Also includes specific water conservation measures to minimize water use, conserve energy, and limit nutrient loading to surface waters. | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4132 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Pet Waste Code Sec 92.16 | City of Port St Lucie |  | Code to control pet waste from entering the storm system. | Requires residents to clean pet waste, thus reducing pathogen and nutrient runoff to surface waters. | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4133 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Public Service Announcements (PSA's) | City of Port St Lucie |  | Public Service Announcements developed locally and shown on local Government channel for educational purposes on stormwater runoff pollution. | The following PSA's have been developed and broadcast on local cable with an estimated viewer audience of 88,500 subscribers. Riversmart Intro - 393 showings Riversmart Car washing - 1517 showings Riversmart Fertilizer - 1228 showings Riversmart Pet waste - 1012 showings Hotline PSA - 4066 showings | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4134 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Stormwater Educational Shows on PSLTV20 | City of Port St Lucie | UF-IFAS, SFWMD, FDEP | The Cityof Port St Lucie is broadcasting other stormwater educational shows to help educate the public about stormwater runoff pollution | These stormwater runoff educational shows consist of locally developed shows, and shows developed from other entities such as UF-IFAS, FDEP, and SFWMD. Locally developed programs: When it Rains it Drains - 744 showings E-8 retrofit - 261 showings All other showings - 8090 showings | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4135 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Webpage - Stormwater Education | City of Port St Lucie |  | Stormwater related webpages on the City of Port St Lucie webpage | NPDES Main webpage Hotline webpage Healthy Household Habits webpage Illicit Discharge webpage Pollutants that can cause harm webpage Srorm Drain webpage Total webpage hits - 8860 | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4136 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Public Education | City of Port St Lucie |  | Outreach Program to educate the public on stormwater runoff pollution | Educational pamphlets on pollution prevention, enviroscape presentations, educational posters, utility bill inserts and messages, localized mailings. Total educated - 1,353,139 | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4137 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Industry/Business Education | City of Port St Lucie |  | Outreach Program to educate Industry/Business on stormwater runoff pollution | Industry/Business educational pamphlets/handouts. Total Educated - 3460 | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4138 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Youth Education | City of Port St Lucie |  | Outreach Program to educate school children on stormwater runoff pollution | Youth education about stormwater pollution in local schools. Total educated - 1172 | unknown | unknown | unknown | unknown | unknown | unknown | On Hold | [6 empty] | Dale Majewski | 772-344-4139 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Municipal Training | City of Port St Lucie |  | Program to educate municipal employees on stormwater runoff pollution | The City annually trains employees with various presentations and training video to educate employees on BMP's to minimize stormwater runoff pollution from municipal facilities. Total educated - 1760 | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4140 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | FDEP Qualified Stormwater Inspector Training | City of Port St Lucie |  | FDEP certification program | The City has had 62 employees trained as a FDEP Qualified Stormwater Inspector | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4141 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Illicit Discharge Detection and Elimination (IDDE) Training | City of Port St Lucie |  | Program to educate municipal employees on detecting illicit discharges | The City annually trains selected employees on identifying and eliminating illicit discharges to the MS4. Total educated - 116 | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4142 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | IDDE inspections | City of Port St Lucie |  | Program designed with guidance from the Center for Watershed Protection Manual on illicit discharge detection and elimination. | MS4 Outfalls surveyed - 1273 Industrial/Business Outfalls surveyed - 1723 ~20 miles of Drainage Right of Ways surveyed for illicit discharges per year. | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4143 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Construction Site Inspections | City of Port St Lucie |  | Program where trained FDEP qualified stormwater inspectors for the city monitor active construction jobs in the city to ensure compliance | The City performs pre-construction meetings along with SFWMD for construction sites to educate contractors on NPDES quidelines and expectations. Construction site inspections are performed while the project is active to ensure compliance with City codes and FDEP compliance. Total Inspections - 6700 | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4144 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Do Not Pollute Stencil Program | City of Port St Lucie |  | Outreach program in the City where storm drains are stenciled to remind people that stormwater runoff drains to the river. | 758 inlets throughout the City have been stenciled. | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4145 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Stormwater Pollution Hotline and Notice | City of Port St Lucie |  | Outreach program designed for the public to be able to report stormwater pollution, such as dumping, turbid releases, failing septic tanks and other stormwater pollution. | Hotline phone number established for residents of the City to call in for any sign of stormwater runoff pollution. Notices with hotline number are posted on every active construction site. Total calls - 157 | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4146 | dmajewski@cityofpsl.com
NFSLR, C-24, C-23 | Aquatic Vegetation Control | City of Port St Lucie |  | Aquatic Vegetation Control in STA,s and Retention Ponds | The City contracts aquatic personnel to treat waterways to control exotic species, prevent drainage blockages, and maintain healthy native vegetation to promote nutrient uptake. ~4,000 acres per year. | unknown | unknown | unknown | unknown | unknown | unknown | Ongoing | [6 empty] | Dale Majewski | 772-344-4147 | dmajewski@cityofpsl.com
| Florida Yards and Neighborhoods Program | University of Florida, IFAS Extension | City of Stuart/Martin County | Provides education and outreach programs for citizens and govt. employees about pollution prevention, water resource protection, Florida friendly gardens, pesticide/fertilizer use, irrigation conservation, etc.
| City of Stuart Stormwater Calendar | City of Stuart |  | Educational information about pollution prevention, recycling, water conservation, and household hazardous waste. Approx. 18,000 distributed in 2009
| "Fertilizer Facts" Brochure | City of Stuart |  | Public education on proper use of fertilizer and effects of overuse to the environment. Conservative est. of 100-200 distributed/ year
| Street Sweeping | City of Stuart |  | Downtown 3 times per week. Other areas from twice/week to once/month. 92 Street miles and 22 parking lots swept each month. Approx. 130 tons of debris removed/yr.
| Sediment Removal from Storm Systems | City of Stuart |  | Clean pipe systems, catch basins/manholes, and baffle boxes. Approx. 50 tons of sediment/vegetation removed city systems. 34 Baffle Boxes, 6,500 ft of pipe, and approx. 100 Catch Basins (based on field inspections) thoroughly cleaned each yr.
| Illicit Detection Program | City of Stuart |  | All City Operations employees trained to report suspected illegal dumping. Stormwater employees began conducting field screening in 2009 at outfalls and ponds. Read pH and Temp. Field test for Ammonia, Nitrate, Phosphorus, and Sulfides
| Stormwater Hotline | City of Stuart |  | 24 hr voice mail service for public to report illegal dumping or other pollution issues
| "Doggie Pot" Stations at Park Facilities | City of Stuart |  | Stations located in park areas throughout the city
| City of Stuart Website | City of Stuart |  | Information posted for watershed improvements, stormwater, water, recycling, and water conservation
| Household Hazardous Waste Collection Site (Hazmobile) | City of Stuart | City of Stuart/Martin County | HHHW collection every 2nd Wednesday/month. Approx. 18,000 pounds collected/yr
| Pollution Prevention Information Inserts in Utility Bills | City of Stuart |  | Information about pollution prevention, illegal dumping, water conservation sent out with utility bills once or twice/yr. Approx. 5,000 distributed ea. mailing/yr
| Training for Public Employees: Green Industry BMP’s and Florida-Friendly Landscape Management | University of Florida, IFAS Extension | City of Stuart/Martin County | 6 week course each year for city Parks, Turf and Grounds, Streets and Stormwater employees. Training includes pesticide/fertilizer use, spill prevention, and protection of water resources.
| City of Stuart Neighborhoods Cleanup Program | City of Stuart |  | Neighborhood cleanup efforts throughout the city engaging and educating residents about keeping their neighborhoods clean. Approx. 25 tons of bulk debris and 20 tons of vegetation collected since November 2009.
All Basins | FDOT4 Street Sweeping | FDOT | NA | Non-structural activity | FDOT4 conducts street sweeping activities on state roads throughout the District. | NA | NA | NA | Ongoing | NA | NA | NA | NA | NA | NA |  |  | Ongoing | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
All Basins | Education Activities | FDOT | NA | Non-structural activity | See environmental education evaluation form for details. | NA | NA | NA | Ongoing | NA | NA | NA | NA | NA | NA |  |  | Ongoing | Ivette Leiva | 954-777-4221 | ivette.leiva@dot.state.fl.us
C-44 | Restricts the application of A and B residuals in Martin County | Martin County |  | County Ordinance Sec. 159.101 - setback requirements from wetlands and waters | During the calendar year 2001 - 27.0M lbs of residuals cotaining 1.56M lbs of P and .504 M lbs N | 115500 |  |  | 03/01 | [8 empty] | Since 2001 there has been no recorded spreading of A or B residuals in the County | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
| Martin County shares funding for the Florida Yards and Neighborhoods program | Martin County, City of Stuart, St. Luice County and the City of Port St. Luice | University of Florida/IFAS | [15 empty] | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
| Martin County either has or is implementing ordinances on landscaping, irrigation, fertilizer and pet waste | Martin County |  | Landscape ordinance (Div. 15) - Irrigation (Sec 4.662.B and 4.663.D) - Pet Waste (Sec 9.92.B) | [13 empty] | Martin County Fertilzer Ord. scheduled to be adopted by the end of year | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
| Martin County provides numerous PSA and FY&N programs on it's pubically maintained Ch. 20 | Martin County | [16 empty] | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
| Information pamphlets are avaialbe as part of NPDES Phase II requirements | Martin County |  |  | Pamphlets incl. -Pollution prevention-fertilizer - landscaping- water conservation- septic | [13 empty] | Gary N. Roderick | (772) 219-4980 | groderic@martin.fl.us
| Website are provided through FY&N on reducing Nutrients for home owners and businesses | Martin County | Martin County - University of Florida IFAS |  | http://martin.ifas.ufl.edu/FYN.shtml | [13 empty] | Fred Burkey | (772) 288-5654 | burkey@ifas.ufl.us
| Martin County continally inspect its MS4 facilities for illicit discharges as part of NPDES Phase II | Martin County |  |  | Martin County Utilities (772) 221-1442 | [13 empty] | John Polley | (772) 223-7942 | jpolley@martin.fl.us
North Fork St. Lucie, Coastal Unit | Street Sweeping | City of Fort Pierce | N/A | The City of Fort Pierce operates 1 sweeper 4 days per week removing pollutants/sediments from streets prior to reaching waterways. | Total miles swept - 17,200 miles Total debris collected - 18,686 CY |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Nick Mimms | 772-460-2200 | nmimms@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Inlet Cleaning | City of Fort Pierce | N/A | Remove pollutants/sediments from inlets prior to reaching waterways. | Routine Maintenance Cleaning Inlets cleaned - 7,830 Debris collected - 42,500 CY |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Nick Mimms | 772-460-2201 | nmimms@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Erosion and Sediment Control Ordinance K-421 | City of Fort Pierce | N/A | Ordinance defining erosion and sediment control requirements on construction sites. | Requires an Erosion and Sediment Control Plan for all land disturbing activities over 5,000 sf and outlines design requirements. Defines inspection requirements and enforcement actions. |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2197 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Illicit Discharge Ordinance L-06 | City of Fort Pierce | N/A | Ordinance defining and prohibiting illicit discharges. | Defines illicit discharges and prohibitions. Includes enforcement actions and monitoring of discharges to the MS4. |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2198 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Stormwater Educational Shows | City of Fort Pierce | UF-IFAS, SFWMD, FDEP | Broadcasting of stormwater educational shows to help educate the public about stormwater runoff pollution. | These stormwater runoff educational shows consist of shows developed from other entities such as UF-IFAS, FDEP, and SFWMD. |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2199 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Public Education | City of Fort Pierce | N/A | Program to educate the public on stormwater runoff pollution. | Educational pamphlets on pollution prevention, educational posters, utility bill inserts and messages, localized mailings. Total mailings - 25,500 Total brochures distributed - 1,300 |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2200 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Community Outreach | City of Fort Pierce | UF-IFAS | Outreach program to educate residents on the impacts of pointless personal pollution. | Number of residents reached through educational classes, pamphlets, and seminars - 74,322 |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2201 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Public Involvement | City of Fort Pierce | Martin County, St. Lucie County, Indian River County | Keep Fort Pierce Beautiful, Treasure Coast Waterway Cleanup | Total trash collected - 10,789 lbs Total volunteers - 200 |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2202 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Industry/Business Education | City of Fort Pierce | N/A | Outreach Program to educate Industry/Business on stormwater runoff pollution. | Industry/Business educational pamphlets/handouts. |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2201 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Municipal Training | City of Fort Pierce | N/A | Program to educate municipal employees on stormwater runoff pollution. | The City annually trains employees with various presentations and training video to educate employees on BMP's to minimize stormwater runoff pollution from municipal facilities. Total educated - 166 |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2202 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Illicit Discharge Detection and Elimination (IDDE) Training | City of Fort Pierce | N/A | Program to educate municipal employees on detecting illicit discharges. | The City annually trains selected employees on identifying and eliminating illicit discharges to the MS4. Total educated - |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2203 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | IDDE inspections | City of Fort Pierce | N/A | Program designed with guidance from the Center for Watershed Protection Manual on illicit discharge detection and elimination. | MS4 Outfalls inspected - 25 Industrial/Business Outfalls surveyed - 4 |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2204 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Construction Site Inspections | City of Fort Pierce | N/A | Program where City construction inspectors monitor active construction sites to ensure compliance. | The City performs pre-construction meetings along with SFWMD for construction sites to educate contractors on NPDES quidelines and expectations. Construction site inspections are performed while the project is active to ensure compliance with City codes and FDEP compliance. |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2205 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Storm Drain Inlet Stencil Program | City of Fort Pierce | N/A | Outreach program in the City where storm drains are stenciled to remind people that stormwater runoff drains to the Lagoon. | 850 inlets throughout the City have been stenciled. 191 stencils inspected to date. |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2206 | jandrews@city-ftpierce.com
North Fork St. Lucie, Coastal Unit | Stormwater Pollution Hotline | City of Fort Pierce | N/A | Outreach program designed for the public to be able to report stormwater pollution, such as dumping, turbid releases, failing septic tanks and other stormwater pollution. | Hotline phone number established for residents of the City to call in for any sign of stormwater runoff pollution. Notices with hotline number are posted on every active construction site. Hotline pamphlets distributed - 1,300 |  | N/A | N/A | N/A | N/A | City of Fort Pierce | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Jack Andrews | 772-460-2207 | jandrews@city-ftpierce.com
North Fork St. Lucie | Water Quality Sampling | NSLRWCD | Harbor Branch | Periodic testing of District canals for various nutrient levels. | Periodic testing primarily made on semi-annual basis at 12 sites around District. Some quarterly testing done to monitor changes after improvement projects. | 65,000 acres | Exempt | 2000 (initial start 1990) | Ongoing | $105,000 (YR 2000 to present) | NSLRWCD | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | Water Quality Criteria adopted as part of NSLRWCD Permit Application Criteria | NSLRWCD | N / A | Adoption of Water Quality criteria in review of proposed development. | Adoption of water quality criteria in permit application documentation, to reflect standards adopted by SFWMD. | 65,000 acres | Exempt | 2010 | Ongoing | 7000 | NSLRWCD | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork St. Lucie | Canal Maintenance Program | NSLRWCD | N / A | Ongoing maintenance program of over 200 miles of canal. | Ongoing maintenance primarily by mechanical means to keep canals free of exotic and decaying vegetation and manage sedimentation. Mowing of bank areas and structural/bank repairs as needed. | 65,000 acres | Exempt | 2000 (initial start 1919) | Ongoing | $4.2 million (YR 2000 to present) | NSLRWCD | Unknown | Unknown | Unknown | Unknown | Unknown | Unknown | Ongoing | Tom McGowan, District Engineer | 772-286-3883 | tom.mcgowan@aecom.com
North Fork of the St. Lucie River | Florida Yards and Neighborhoods Program | St Lucie County |  | PSAs over radio; Public educational events with distribution of materials | In two years, held 69 events with 1875 attendees; 1158 educational documents distributed; 487 radio airings of spot advertising/short programs; 18 TV programs on stormwater management topics, with 117 airings |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | Website with dedicated Stormwater section | St Lucie County |  | Education | About 125 hits/month to website |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | Ordinances | St Lucie County |  |  | Pet Waste; Landscape Plans for Bldg permit applications (irrigation, fertilizer) |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | MS4 Ordinance and inspection/enforcement program | St Lucie County |  | Ordinance and inspection/enforcement program to prohibit non-stormwater discharges to County's MS4 | Ordinance in May, 2007. In 2 years, 297 investigations with 1519 tons of material removed |  |  | 2007 | Ongoing
North Fork of the St. Lucie River | Street Sweeping | St Lucie County |  |  | 430 Tons of material for past 2 years |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | Illicit discharge hotline and inspection program | St Lucie County | [5 empty] | 2003 | Ongoing
North Fork of the St. Lucie River | Education that targets Ag community | St Lucie County |  | Education for ag | Stormwater/pollution prevention outreach, with face-to-face training, brochure on Ag BMPs; in two years, held 37 activities, with 4204 participants, 1706 educational materials distributed |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | Oxbow Eco-Center | St Lucie County |  | Education | 35,000 visitors per year. In two years, 412 programs presented with 18,242 participants. Also, school field trips; in 2 years, 3600 students visited; 3 educato training events |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | Clean Stormwater- Clean River Outreach Program | St Lucie County |  | Education | In 2 years, 2 presentations on "Know the Flow", with 75 participants |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | NPDES Implementation with Public Education/Participation | St Lucie County |  | Education | Master and Junior Gardener training, Florida Yard Certification program, neighborhood/homeowner assessment; In 2 years, 325 activities, with 32,269 participants |  |  | 2003 | Ongoing
North Fork of the St. Lucie River | Pesticide Applicator training | St Lucie County |  | Education | in 2 years, 70 courses, with 1955 students, 1951 educational materials distributed;