## BMAP All
Entity Type | Completed Code | Project Number | Project Name | Project Type | Status | TN Reduction (lbs/yr) | TP Reduction (lbs/yr)
Ag | C | N/A | Agricultural Land Use Changes | Land use change | Completed | 171776.4 | 54191.1 | LU Change Completed TN | 171776.4 | LU Change Completed TP | 54191.1
LG | C | FP-2 | Moore's Creek Retrofit – Phases 3 and 4 | Wet detention | Completed | 102.1 | 38.5
LG | C | FP-6 | Virginia Avenue Outfall Canal | Wet detention | Completed | 233.1 | 99.1
LG | C | PSL-1 | Woodstork Trail Design Districts 7, 8, and 9 | 1st generation baffle box | Completed | 3.8 | 4
LG | C | PSL-2 | Wood Stork Trail Design District 6 | 1st generation baffle box | Completed | 2.7 | 2.3
LG | C | PSL-3 | Howard Creek Stormwater Treatment Area (STA) | Wet detention | Completed | 523 | 212.2
LG | C | PSL-4 | Eastern Watershed Improvement Project (EWIP) | Wet detention ponds | Completed | 618.3 | 360.9
LG | C | PSL-5 | B-1 and B-2 Water Control Structures (WCS) | Water control structure | Completed | 2526.6 | 993.8
LG | C | PSL-6 | B-3 WCS | Water control structure | Completed | 2372.3 | 931.7
LG | C | PSL-7 | E-8 Waterway Phase 1 Water Quality Retrofit | Wet detention – STAs | Completed | 763.7 | 664
LG | C | PSL-8 | E-17 Canal WCS | Water control structure | Completed | 181.2 | 0
LG | C | S-1 | Poppleton Creek – Phase II and III | Wet detention pond | Completed | 1299.3 | 575.9
LG | C | S-2 | Airport Ditch Project | Retention/detention | Completed | 899.7 | 532.2
LG | C | S-3 | Crescent Basin Project | Stormwater retention | Completed | 197.6 | 41.6
LG | C | S-4 | Krueger Creek Project | 1st generation baffle boxes | Completed | 7 | 6.8
LG | C | S-8 | North Point CRA Drainage Basin | 1st generation baffle box | Completed | 24 | 22.8
LG | C | S-9 | Anchorage Drainage Basin | 1st generation baffle box | Completed | 0.5 | 0.4
LG | C | S-10 | Downtown Drainage Basin | 1st generation baffle boxes | Completed | 2.4 | 2.3
LG | C | S-11 | Hildebrad Basin | CDS unit | Completed | 0 | 6.1
LG | C | S-12 | Landfill Basin | Closed basin | Completed | 167.3 | 25.9
LG | C | S-13 | South Fork Drainage Basin | 1st generation baffle boxes | Completed | 16 | 16.2
LG | C | S-15 | Eldorado Heights | Retention/closed basin | Completed | 133.6 | 27.1
LG | C | MC-1 | Cedar Point Water Quality Retrofit | Wet detention and swales | Completed | 71.5 | 33.6
LG | C | MC-2 | Indian River Drive Baffle Boxes | 2nd generation baffle boxes | Completed | 30.8 | 5.6
LG | C | MC-3 | Warner Creek/Leilani Heights Water Quality Retrofit Phase I | Exfiltration trenches and swales | Completed | 229.9 | 49.3
LG | C | MC-4 | Warner Creek Phase II | Dry detention | Completed | 6.3 | 1.4
LG | C | MC-5 | Warner Creek Phase III – Beacon 21 | Wet detention | Completed | 1291.1 | 597.1
LG | C | MC-6 | Manatee Creek Water Quality Retrofit Phases I, II, and III | Wet detention | Completed | 6 | 3.8
LG | C | MC-7 | Rio/St. Lucie Water Quality Retrofit – Phase 1 | Exfiltration trenches and swales | Completed | 41.1 | 11
LG | C | MC-8 | Rio/St. Lucie Water Quality Retrofit – Phase 2 | Wet detention | Completed | 190 | 73.7
LG | C | MC-9 | Salerno Creek Water Quality Retrofit | Wet detention | Completed | 407.6 | 134
LG | C | MC-10 | Coral Gardens Water Quality Retrofit | Wet detention | Completed | 1376.1 | 936.2
LG | C | MC-11 | Fern Creek Water Quality Retrofit | Wet detention | Completed | 684.7 | 257.9
LG | C | MC-12 | Old Palm City Water Quality Retrofit Phases I, II, and III | Wet detention, swales | Completed | 244.4 | 95.5
LG | C | MC-13 | North River Shores Baffle Boxes | 1st generation baffle boxes | Completed | 3.6 | 3.8
LG | C | MC-14 | Palm Lake Park Water Quality Retrofit | Wet detention | Completed | 107.9 | 41.6
LG | C | MC-15 | Tropical Farms Water Quality Retrofit | Wet detention | Completed | 944.5 | 308.5
LG | C | MC-16 | Septic to Central Sewer Conversions | Septic to sewer conversion | Completed | Not quantified | Not quantified
LG | C | MC-23* | Golden Gate Water Quality Retrofit Phases I, II | Dry detention | Completed | Not quantified | Not quantified
LG | C | MC-24* | Golden Gate Water Quality Retrofit Phase III | 2nd generation baffle boxes and wet detention | Completed | Not quantified | Not quantified
LG | C | MC-25* | Hibiscus Park Water Quality Retrofit Phases I and II | Wet detention | Completed | Not quantified | Not quantified
LG | C | MC-26* | Poinciana Gardens Water Quality Retrofit Phases I and II | Wet detention | Completed | Not quantified | Not quantified
LG | C | MC-27* | Willoughby Creek Muck Dredging | Muck removal | Completed | Not quantified | Not quantified
LG | C | MC-28* | Manatee Pocket Dredging | Muck removal | Completed | Not quantified | Not quantified
LG | C | SLC-1 | Platt’s Creek Stormwater Treatment Facility | Wet detention with alum injection | Completed | 676 | 306.4
LG | C | SLC-2 | Indian River Estates Stormwater Improvements (Phase I and II) | Wet detention with alum injection | Completed | 1841.2 | 706.6
LG | C | SLC-3 | Prima Vista | 2nd generation baffle box | Completed | 76.2 | 13.9
LG | C | SLC-4 | Bay Street | 2nd generation baffle box | Completed | 34.6 | 6.3
LG | C | SLC-1 | Platt’s Creek Stormwater Treatment Facility | Wet detention with alum injection | Completed | 906.7 | 364.6
LG | C | SLC-9 | White City – Citrus/Seager Stormwater Improvement | Wet detention with polyacrylamide logs | Completed | 71.2 | 25.7
LG | C | SP-1 | Ridgeland Court Retrofit | Baffle box | Completed | 0.1 | 0.1
LG | C | SP-2 | Palm Court/Knowles | Baffle box | Completed | 0.2 | 0.2
LG | C | SP-3 | Captain Cove | Baffle box | Completed | 0.1 | 0.1
LG | C | SP-4 | Quail Run Park | Dry detention | Completed | 0.1 | 0
LG | C | SP-5 | Heritage Park | Dry retention | Completed | 7 | 1.5
LG | C | SP-6 | Via Lucindia | Exfiltration | Completed | 8.4 | 1.9
LG | C | SP-7 | Rio Vista Park | Baffle box | Completed | 0.5 | 0.5
LG | C | SP-8 | India Lucie | Wet retention | Completed | 43.6 | 17.8
LG | C | SP-9 | India Lucie | Baffle box | Completed | 0.1 | 0.1
LG | C | SP-10 | Periwinkle | Baffle box | Completed | 0.3 | 0.2
LG | C | SP-11 | Palm Road | Swales | Completed | 0.5 | 0.1
LG | C | SP-12 | Riverview | Baffle box | Completed | 0.2 | 0.2
LG | C | SP-13 | Pineapple Lane | Exfiltration | Completed | 0 | 0
LG | C | SP-14 | Copaire | Baffle box | Completed | 0 | 0
LG | C | SP-15 | Homewood Park/South Sewall's Point Road | Retention | Completed | 45.6 | 10.2
LG | C | SP-17 | State Road A1A | Exfiltration | Completed | 52.1 | 10.4
LG | C | SP-20* | Delano Lane | Exfiltration | Completed | Not quantified | Not quantified
LG | C | SP-21* | Town Commons Park | Dry detention | Completed | Not quantified | Not quantified
LG | C | SP-22* | Island Road | Baffle box | Completed | Not quantified | Not quantified
LG | C | SP-23* | Highpoint West | Baffle box | Completed | Not quantified | Not quantified
LG | C | SP-24* | Mandalay (Marguerita) | Baffle box | Completed | Not quantified | Not quantified
LG | C | SP-25* | Highpoint East | Baffle box | Completed | Not quantified | Not quantified
LG | C | FP-3 | Street Sweeping – 4,314 Cubic Yards | Street sweeping | Ongoing | 5569 | 3571
LG | C | FP-4 | Inlet Cleaning – 2,762 Cubic Yards | Inlet cleaning | Ongoing | 4300 | 2641
LG | C | FP-5 | Stormwater Education Shows, Pamphlets, Presentations, Storm Drain Stenciling, Illicit Discharge Program | Education and outreach | Ongoing | 170.4 | 38.8
LG | C | PSL-10 | Water and Wastewater Expansion | Septic tank phaseout | Ongoing | Not quantified | Not quantified
LG | C | PSL-11 | Street Sweeping | Street sweeping | Ongoing | 676 | 434
LG | C | PSL-12 | Swale Maintenance | Sediment removal | Ongoing | 7649 | 3097
LG | C | PSL-13 | Catch Basin Cleaning | Catch basin cleaning | Ongoing | 21 | 13
LG | C | PSL-14 | FYN; Fertilizer, Landscaping, Irrigation, and Pet Waste Ordinances; PSAs, Stormwater Educational Shows, Website, Outreach Programs, Stencil Program, Stormwater Pollution Hotline | Education and outreach | Ongoing | 9388.9 | 2100.9
LG | C | PSL-15 | Tiffany Channel | Stormwater reuse | Ongoing | 32.9 | 7.6
LG | C | PSL-16 | Patio STA | Stormwater reuse | Ongoing | 11.4 | 2.6
LG | C | PSL-17 | Mary STA | Stormwater reuse | Ongoing | 7.6 | 1.7
LG | C | PSL-18 | Leithgow STA | Stormwater reuse | Ongoing | 7.4 | 1.7
LG | C | PSL-19 | Cane Slough 1/Elks STA | Stormwater reuse | Ongoing | 33.2 | 7.3
LG | C | PSL-20 | Cane Slough 2/Azzi STA | Stormwater reuse | Ongoing | 23.9 | 5.2
LG | C | PSL-21 | Loutus STA | Stormwater reuse | Ongoing | 22.5 | 4.8
LG | C | PSL-22 | Howard Creek STA | Stormwater reuse | Ongoing | 33.9 | 7.1
LG | C | PSL-23 | Bur St, STA | Stormwater reuse | Ongoing | 0.6 | 0.1
LG | C | PSL-24 | St. Lucie West Services District Aquatic Harvesting | Aquatic harvesting | Ongoing | Not quantified | Not quantified
LG | C | PSL-25 | St. Lucie West Services District Catch Basin Cleaning | Catch basin cleaning | Ongoing | 84 | 52
LG | C | S-5 | Street Sweeping – 260 tons/yr | Street sweeping | Ongoing | 275 | 176
LG | C | S-6 | Sediment Removal from Storm Systems – 50 tons/yr | BMP cleanout | Ongoing | 54 | 33
LG | C | S-7 | FYN; Landscaping, Irrigation, Fertilizer, Pet Waste Ordinances; Brochure, Website, Information Inserts, City Calendar, Doggie Pot Stations, Neighborhood Cleanup Program | Education and outreach | Ongoing | 839.9 | 186.4
LG | C | S-14 | Neighborhood Initiated Sewer Expansion Program | Removal of septic tanks | Ongoing | Not quantified | Not quantified
LG | C | MC-18 | Street Sweeping | Street sweeping | Ongoing | 108 | 69
LG | C | MC-19 | Baffle Box and Structure Cleanout | Clean out | Ongoing | 397 | 161
LG | C | MC-20 | FYN; Landscaping, Irrigation, Fertilizer, and Pet Waste Ordinances; PSAs, Pamphlets, Website, Illicit Discharge Program | Education and outreach | Ongoing | 6048.7 | 1342.1
LG | C | SLC-5 | FYN; Pet Waste, Landscape, Irrigation, and Fertilizer Ordinances; PSAs, Website, Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program | Education and outreach | Ongoing | 1086.8 | 247.6
LG | C | SLC-6 | Street Sweeping | Street sweeping | Ongoing | 210.6 | 135.2
LG | C | SLC-7 | Catch Basin Cleanout | Clean out | Ongoing | 170.3 | 104.6
LG | C | SLC-8 | Platt's Creek Sump Cleanout | Clean out | Ongoing | 1181.6 | 511.5
LG | C | SLC-10 | FYN; Pet Waste, Landscape, Irrigation, and Fertilizer Ordinances; PSAs, Website, Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program | Education and outreach | Ongoing | 1425.7 | 364.3
LG | C | SLC-11 | Street Sweeping | Street sweeping | Ongoing | 113.4 | 72.8
LG | C | SLC-12 | Catch Basin Cleanout | Clean out | Ongoing | 91.7 | 56.4
LG | C | SLC-13 | Platt's Creek Sump Cleanout | Clean out | Ongoing | 1566.4 | 600.5
LG | C | SP-18 | Fertilizer Ordinance | Education | Ongoing | 8.9 | 1.9
LG | C | SP-19 | Street Sweeping – 19 Cubic Yards | Street sweeping | Ongoing | 25 | 16 | Local Govt Completed TN | 61109.1 | Local Govt Completed TP | 24647.7
LG | I | MC-17 | Danforth Creek – Phase 1 | Wet detention | Construction | 2434.7 | 1010.7
LG | I | SP-16 | Pedway/Greenway | Exfiltration/ pervious paver | Construction | 6.2 | 1.4
LG | I | SP-27* | Extend Pedway/Greenway | Exfiltration/ pervious paver | Construction | Not quantified | Not quantified
LG | I | SP-28* | Mandalay (Marguerita) | Dry detention | Construction | Not quantified | Not quantified
LG | I | SP-29* | Baffle Boxes | 1st and 2nd generation baffle boxes | Construction | Not quantified | Not quantified
LG | I | FP-1 | Heathcote Botanical Gardens Treatment Train | Alum | Planned | 350 | 144.4
LG | I | PSL-26 | St. Lucie West Services District Wastewater Facility Upgrade | Wastewater facility upgrade | Planned | Not quantified | Not quantified
LG | I | SP-26* | High Point Exfiltration | Exfiltration/swales | Planned | Not quantified | Not quantified
LG | I | MC-21 | FM# 230978-1 Indian Street Bridge (Pond East) | Dry detention | Started | 5.1 | 1.1
LG | I | MC-22 | FM# 230978-1 Indian Street Bridge (Pond West) | Wet detention | Started | 0.2 | 0.1 | Local Govt Incomplete TN | 2796.2 | Local Govt Incomplete TP | 1157.7
Transportation | C | FDOT-1 | FM# 230108-1 (Pond 3) | Wet detention | Completed | 2.7 | 0.9
Transportation | C | FDOT-2 | FM# 230108-1 (Pond 4) | Wet detention | Completed | 2.9 | 1.3
Transportation | C | FDOT-3 | FM# 230262-4 | Dry detention | Completed | 69.2 | 18
Transportation | C | FDOT-4 | FM# 230262-5 | Dry detention | Completed | 60 | 15.3
Transportation | C | FDOT-5 | FM# 230262-3 | Dry detention | Completed | 168.4 | 37.8
Transportation | C | FDOT-7 | FM# 230295-1 | Dry detention | Completed | 8.6 | 1.6
Transportation | C | FDOT-8 | SPN 99004-1585 | Dry detention | Completed | 15.5 | 2.9
Transportation | C | FDOT-9 | SPN 99004-1585 (Lake 3) | Wet detention | Completed | 14.4 | 5.2
Transportation | C | FDOT-10 | FM# 228819-1 (Basin A and B) | Wet detention | Completed | 0.2 | 0.1
Transportation | C | FDOT-11 | FM# 228821-1 (West 1 A) | Exfiltration trench | Completed | 5.1 | 1.1
Transportation | C | FDOT-12 | FM# 228821-1 (East) | Exfiltration trench | Completed | 1.8 | 0.4
Transportation | C | FDOT-16 | FM# 228831-1 | Dry detention | Completed | 3.2 | 0.9
Transportation | C | FDOT-14 | FM# 228801-1 | Dry detention | Completed | 1 | 0.2
Transportation | C | FDOT-15 | FM# 405504-1 | Dry detention | Completed | 23.9 | 4.9
Transportation | C | FDOT-16 | FM# 230288-2 | Wet detention | Completed | 62.9 | 22.3
Transportation | C | FDOT-17 | FM# 419890-1 | Wet and dry detention | Completed | 1.9 | 1.7
Transportation | C | FDOT-22 | State Road 615 Midway Road to Edwards Road (Basin B-1) | Wet detention | Completed | 5.4 | 1.8
Transportation | C | FDOT-23 | State Road 615 Midway Road to Edwards Road (Basin E) | Wet detention | Completed | 5.8 | 2
Transportation | C | FDOT-24 | FM# 410717-1 State Road 70 Widening Kings Highway to Jenkins Road (West Basin) | Dry detention | Completed | 3.1 | 0.6
Transportation | C | FDOT-25 | State Road 713 (King's Highway) Turn Lanes | Swales | Completed | 0 | 0
Transportation | C | FDOT-26 | Johnson Honda of Stuart Turn Lane (Basin A and B) | Exfiltration trench | Completed | 0.1 | 0
Transportation | C | FDOT-27 | FM# 228852-1 State Road 76 Drainage Improvements at Cabana Point (Pond 9A) | Wet detention | Completed | 9.7 | 3.1
Transportation | C | FDOT-28 | FM# 228852-1 Osprey Ridge Planned Unit Development (PUD) – State Road 76 Improvements | Exfiltration trench | Completed | 0.1 | 0
Transportation | C | FDOT-29 | FM# 228852-1 State Road 76 Improvements – Kanner Professional Center | Exfiltration trench | Completed | 0.2 | 0
Transportation | C | FDOT-30* | FM# 228851-1 (Basin A) | Dry detention | Completed | Not quantified | Not quantified
Transportation | C | FDOT-31* | FM# 228851-1 | Dry detention | Completed | Not quantified | Not quantified
Transportation | C | FDOT-32** | FM# 230132-1 (System No. 1) | Dry detention | Completed | Not quantified | Not quantified
Transportation | C | FDOT-33** | FM# 228758-1 | Dry detention | Completed | Not quantified | Not quantified
Transportation | C | FDOT-34** | FM# 228819-1 (Basin C) | Dry detention | Completed | Not quantified | Not quantified
Transportation | C | FDOT-35** | FM# 228819-1 (Basin D) | Exfiltration trench | Completed | Not quantified | Not quantified
Transportation | C | FDOT-36** | FM# 228819-1 (Basin E) | Exfiltration trench | Completed | Not quantified | Not quantified
Transportation | C | FDOT-37** | FM# 405167-1 | Dry retention | Completed | Not quantified | Not quantified
Transportation | C | FDOT-38** | FM# 230296-1 | Dry swales | Completed | Not quantified | Not quantified
Transportation | C | FDOT-39** | FM# 230297-1 State Road A1A Roadway Improvements Phase 3 | Exfiltration trench | Completed | Not quantified | Not quantified
Transportation | C | FDOT-40** | FM# 228758-1 State Road 702 Jensen Beach Causeway | Dry detention | Completed | Not quantified | Not quantified
Transportation | C | T-1 | Project 420735-1 Port St. Lucie Interchange Pond A | Dry detention | Completed | 1.8 | 0.3
Transportation | C | T-2 | Project 420735-1 Port St. Lucie Interchange Pond B | Wet detention | Completed | 16 | 2.1
Transportation | C | T-3 | Thomas B. Manuel Bridge North Pond | Dry detention | Completed | 5.4 | 1
Transportation | C | FDOT-18 | Street Sweeping | Street sweeping | Ongoing | 1419 | 910
Transportation | C | FDOT-19 | Pamphlets | Education | Ongoing | 31.3 | 6.4 | Transportation Completed TN | 1939.6 | Transportation Completed TP | 1041.9
Transportation | I | FDOT-6 | FM# 230262-2 | Dry detention | Started | 109.8 | 35.6
Transportation | I | FDOT-20 | FM# 230978-1 Indian Street Bridge (Pond East) | Dry detention | Started | 1.7 | 0.4
Transportation | I | FDOT-21 | FM# 230978-1 Indian Street Bridge (Pond West) | Wet detention | Started | 0.1 | 0 | Transportation Incomplete TN | 111.6 | Transportation Incomplete TP | 36
WCD | C | HSL-1 | Hobe Sound Polo Club | Wet detention, dry detention | Completed | 3097.2 | 1013.8
WCD | C | HSL-2 | Changes in Agricultural Land Uses | Land use change | Completed | 7000 | 2258.8
WCD | C | NSLRWCD-1 | SLRIT Grant 2000–2001: Vegetation Control & Bank Restoration | Control structures | Completed | 982.9 | 0
WCD | C | NSLRWCD-2 | SLRIT Grant 2007–2008: Water Control Structure Retrofits | Control structure | Completed | 1372 | 0
WCD | C | NSLRWCD-3 | Canals 23 and 28 Retrofit for Stormwater Treatment and Attenuation | Control structure | Completed | 11 | 0
WCD | C | NSLRWCD-5 | Changes in Agricultural Land Uses | Land use change | Completed | 45621.1 | 14444.7
WCD | C | NSLRWCD-7 | Change from Agricultural to Urban | Land use change | Completed | 839.2 | 208
WCD | C | TI-1 | C-44 Conservation Area | Conservation | Completed | 23199 | 7496.7
WCD | C | NSLRWCD-4 | Canal Maintenance Program | Vegetation harvesting | Ongoing | Not quantified | Not quantified
WCD | C | NSLRWCD-8 | Ideal Grove Hybrid Wetland Treatment Technology | Wetlands, chemical treatment | Ongoing | 330 | 127 | WCD Completed TN | 82452.4 | WCD Completed TP | 25549
WCD | I | HSL-3 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 191 | 29.5
WCD | I | NSLRWCD-6 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 16979.9 | 3513.4
WCD | I | PM-1 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 926.2 | 91.7
WCD | I | TI-2 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 1856.3 | 445.8 | WCD Incomplete TN | 19953.4 | WCD Incomplete TP | 4080.4
[5 empty] | Totals | 340138.7 | 110703.8 |  | 340138.7 |  | 110703.8

## BMAP completed
Project Number | Project Name | Project Type | Status | TN Reduction (lbs/yr) | TP Reduction (lbs/yr)
FP-2 | Moore's Creek Retrofit – Phases 3 and 4 | Wet detention | Completed | 102.1 | 38.5
FP-6 | Virginia Avenue Outfall Canal | Wet detention | Completed | 233.1 | 99.1
PSL-1 | Woodstork Trail Design Districts 7, 8, and 9 | 1st generation baffle box | Completed | 3.8 | 4
PSL-2 | Wood Stork Trail Design District 6 | 1st generation baffle box | Completed | 2.7 | 2.3
PSL-3 | Howard Creek Stormwater Treatment Area (STA) | Wet detention | Completed | 523 | 212.2
PSL-4 | Eastern Watershed Improvement Project (EWIP) | Wet detention ponds | Completed | 618.3 | 360.9
PSL-5 | B-1 and B-2 Water Control Structures (WCS) | Water control structure | Completed | 2526.6 | 993.8
PSL-6 | B-3 WCS | Water control structure | Completed | 2372.3 | 931.7
PSL-7 | E-8 Waterway Phase 1 Water Quality Retrofit | Wet detention – STAs | Completed | 763.7 | 664
PSL-8 | E-17 Canal WCS | Water control structure | Completed | 181.2 | 0
S-1 | Poppleton Creek – Phase II and III | Wet detention pond | Completed | 1299.3 | 575.9
S-2 | Airport Ditch Project | Retention/detention | Completed | 899.7 | 532.2
S-3 | Crescent Basin Project | Stormwater retention | Completed | 197.6 | 41.6
S-4 | Krueger Creek Project | 1st generation baffle boxes | Completed | 7 | 6.8
S-8 | North Point CRA Drainage Basin | 1st generation baffle box | Completed | 24 | 22.8
S-9 | Anchorage Drainage Basin | 1st generation baffle box | Completed | 0.5 | 0.4
S-10 | Downtown Drainage Basin | 1st generation baffle boxes | Completed | 2.4 | 2.3
S-11 | Hildebrad Basin | CDS unit | Completed | 0 | 6.1
S-12 | Landfill Basin | Closed basin | Completed | 167.3 | 25.9
S-13 | South Fork Drainage Basin | 1st generation baffle boxes | Completed | 16 | 16.2
S-15 | Eldorado Heights | Retention/closed basin | Completed | 133.6 | 27.1
FDOT-1 | FM# 230108-1 (Pond 3) | Wet detention | Completed | 2.7 | 0.9
FDOT-2 | FM# 230108-1 (Pond 4) | Wet detention | Completed | 2.9 | 1.3
FDOT-3 | FM# 230262-4 | Dry detention | Completed | 69.2 | 18
FDOT-4 | FM# 230262-5 | Dry detention | Completed | 60 | 15.3
FDOT-5 | FM# 230262-3 | Dry detention | Completed | 168.4 | 37.8
FDOT-7 | FM# 230295-1 | Dry detention | Completed | 8.6 | 1.6
FDOT-8 | SPN 99004-1585 | Dry detention | Completed | 15.5 | 2.9
FDOT-9 | SPN 99004-1585 (Lake 3) | Wet detention | Completed | 14.4 | 5.2
FDOT-10 | FM# 228819-1 (Basin A and B) | Wet detention | Completed | 0.2 | 0.1
FDOT-11 | FM# 228821-1 (West 1 A) | Exfiltration trench | Completed | 5.1 | 1.1
FDOT-12 | FM# 228821-1 (East) | Exfiltration trench | Completed | 1.8 | 0.4
FDOT-16 | FM# 228831-1 | Dry detention | Completed | 3.2 | 0.9
FDOT-14 | FM# 228801-1 | Dry detention | Completed | 1 | 0.2
FDOT-15 | FM# 405504-1 | Dry detention | Completed | 23.9 | 4.9
FDOT-16 | FM# 230288-2 | Wet detention | Completed | 62.9 | 22.3
FDOT-17 | FM# 419890-1 | Wet and dry detention | Completed | 1.9 | 1.7
FDOT-22 | State Road 615 Midway Road to Edwards Road (Basin B-1) | Wet detention | Completed | 5.4 | 1.8
FDOT-23 | State Road 615 Midway Road to Edwards Road (Basin E) | Wet detention | Completed | 5.8 | 2
FDOT-24 | FM# 410717-1 State Road 70 Widening Kings Highway to Jenkins Road (West Basin) | Dry detention | Completed | 3.1 | 0.6
FDOT-25 | State Road 713 (King's Highway) Turn Lanes | Swales | Completed | 0 | 0
FDOT-26 | Johnson Honda of Stuart Turn Lane (Basin A and B) | Exfiltration trench | Completed | 0.1 | 0
FDOT-27 | FM# 228852-1 State Road 76 Drainage Improvements at Cabana Point (Pond 9A) | Wet detention | Completed | 9.7 | 3.1
FDOT-28 | FM# 228852-1 Osprey Ridge Planned Unit Development (PUD) – State Road 76 Improvements | Exfiltration trench | Completed | 0.1 | 0
FDOT-29 | FM# 228852-1 State Road 76 Improvements – Kanner Professional Center | Exfiltration trench | Completed | 0.2 | 0
FDOT-30* | FM# 228851-1 (Basin A) | Dry detention | Completed | Not quantified | Not quantified
FDOT-31* | FM# 228851-1 | Dry detention | Completed | Not quantified | Not quantified
FDOT-32** | FM# 230132-1 (System No. 1) | Dry detention | Completed | Not quantified | Not quantified
FDOT-33** | FM# 228758-1 | Dry detention | Completed | Not quantified | Not quantified
FDOT-34** | FM# 228819-1 (Basin C) | Dry detention | Completed | Not quantified | Not quantified
FDOT-35** | FM# 228819-1 (Basin D) | Exfiltration trench | Completed | Not quantified | Not quantified
FDOT-36** | FM# 228819-1 (Basin E) | Exfiltration trench | Completed | Not quantified | Not quantified
FDOT-37** | FM# 405167-1 | Dry retention | Completed | Not quantified | Not quantified
FDOT-38** | FM# 230296-1 | Dry swales | Completed | Not quantified | Not quantified
FDOT-39** | FM# 230297-1 State Road A1A Roadway Improvements Phase 3 | Exfiltration trench | Completed | Not quantified | Not quantified
FDOT-40** | FM# 228758-1 State Road 702 Jensen Beach Causeway | Dry detention | Completed | Not quantified | Not quantified
HSL-1 | Hobe Sound Polo Club | Wet detention, dry detention | Completed | 3097.2 | 1013.8
HSL-2 | Changes in Agricultural Land Uses | Land use change | Completed | 7000 | 2258.8
MC-1 | Cedar Point Water Quality Retrofit | Wet detention and swales | Completed | 71.5 | 33.6
MC-2 | Indian River Drive Baffle Boxes | 2nd generation baffle boxes | Completed | 30.8 | 5.6
MC-3 | Warner Creek/Leilani Heights Water Quality Retrofit Phase I | Exfiltration trenches and swales | Completed | 229.9 | 49.3
MC-4 | Warner Creek Phase II | Dry detention | Completed | 6.3 | 1.4
MC-5 | Warner Creek Phase III – Beacon 21 | Wet detention | Completed | 1291.1 | 597.1
MC-6 | Manatee Creek Water Quality Retrofit Phases I, II, and III | Wet detention | Completed | 6 | 3.8
MC-7 | Rio/St. Lucie Water Quality Retrofit – Phase 1 | Exfiltration trenches and swales | Completed | 41.1 | 11
MC-8 | Rio/St. Lucie Water Quality Retrofit – Phase 2 | Wet detention | Completed | 190 | 73.7
MC-9 | Salerno Creek Water Quality Retrofit | Wet detention | Completed | 407.6 | 134
MC-10 | Coral Gardens Water Quality Retrofit | Wet detention | Completed | 1376.1 | 936.2
MC-11 | Fern Creek Water Quality Retrofit | Wet detention | Completed | 684.7 | 257.9
MC-12 | Old Palm City Water Quality Retrofit Phases I, II, and III | Wet detention, swales | Completed | 244.4 | 95.5
MC-13 | North River Shores Baffle Boxes | 1st generation baffle boxes | Completed | 3.6 | 3.8
MC-14 | Palm Lake Park Water Quality Retrofit | Wet detention | Completed | 107.9 | 41.6
MC-15 | Tropical Farms Water Quality Retrofit | Wet detention | Completed | 944.5 | 308.5
MC-16 | Septic to Central Sewer Conversions | Septic to sewer conversion | Completed | Not quantified | Not quantified
MC-23* | Golden Gate Water Quality Retrofit Phases I, II | Dry detention | Completed | Not quantified | Not quantified
MC-24* | Golden Gate Water Quality Retrofit Phase III | 2nd generation baffle boxes and wet detention | Completed | Not quantified | Not quantified
MC-25* | Hibiscus Park Water Quality Retrofit Phases I and II | Wet detention | Completed | Not quantified | Not quantified
MC-26* | Poinciana Gardens Water Quality Retrofit Phases I and II | Wet detention | Completed | Not quantified | Not quantified
MC-27* | Willoughby Creek Muck Dredging | Muck removal | Completed | Not quantified | Not quantified
MC-28* | Manatee Pocket Dredging | Muck removal | Completed | Not quantified | Not quantified
NSLRWCD-1 | SLRIT Grant 2000–2001: Vegetation Control & Bank Restoration | Control structures | Completed | 982.9 | 0
NSLRWCD-2 | SLRIT Grant 2007–2008: Water Control Structure Retrofits | Control structure | Completed | 1372 | 0
NSLRWCD-3 | Canals 23 and 28 Retrofit for Stormwater Treatment and Attenuation | Control structure | Completed | 11 | 0
NSLRWCD-5 | Changes in Agricultural Land Uses | Land use change | Completed | 45621.1 | 14444.7
NSLRWCD-7 | Change from Agricultural to Urban | Land use change | Completed | 839.2 | 208
SLC-1 | Platt’s Creek Stormwater Treatment Facility | Wet detention with alum injection | Completed | 676 | 306.4
SLC-2 | Indian River Estates Stormwater Improvements (Phase I and II) | Wet detention with alum injection | Completed | 1841.2 | 706.6
SLC-3 | Prima Vista | 2nd generation baffle box | Completed | 76.2 | 13.9
SLC-4 | Bay Street | 2nd generation baffle box | Completed | 34.6 | 6.3
SLC-1 | Platt’s Creek Stormwater Treatment Facility | Wet detention with alum injection | Completed | 906.7 | 364.6
SLC-9 | White City – Citrus/Seager Stormwater Improvement | Wet detention with polyacrylamide logs | Completed | 71.2 | 25.7
SP-1 | Ridgeland Court Retrofit | Baffle box | Completed | 0.1 | 0.1
SP-2 | Palm Court/Knowles | Baffle box | Completed | 0.2 | 0.2
SP-3 | Captain Cove | Baffle box | Completed | 0.1 | 0.1
SP-4 | Quail Run Park | Dry detention | Completed | 0.1 | 0
SP-5 | Heritage Park | Dry retention | Completed | 7 | 1.5
SP-6 | Via Lucindia | Exfiltration | Completed | 8.4 | 1.9
SP-7 | Rio Vista Park | Baffle box | Completed | 0.5 | 0.5
SP-8 | India Lucie | Wet retention | Completed | 43.6 | 17.8
SP-9 | India Lucie | Baffle box | Completed | 0.1 | 0.1
SP-10 | Periwinkle | Baffle box | Completed | 0.3 | 0.2
SP-11 | Palm Road | Swales | Completed | 0.5 | 0.1
SP-12 | Riverview | Baffle box | Completed | 0.2 | 0.2
SP-13 | Pineapple Lane | Exfiltration | Completed | 0 | 0
SP-14 | Copaire | Baffle box | Completed | 0 | 0
SP-15 | Homewood Park/South Sewall's Point Road | Retention | Completed | 45.6 | 10.2
SP-17 | State Road A1A | Exfiltration | Completed | 52.1 | 10.4
SP-20* | Delano Lane | Exfiltration | Completed | Not quantified | Not quantified
SP-21* | Town Commons Park | Dry detention | Completed | Not quantified | Not quantified
SP-22* | Island Road | Baffle box | Completed | Not quantified | Not quantified
SP-23* | Highpoint West | Baffle box | Completed | Not quantified | Not quantified
SP-24* | Mandalay (Marguerita) | Baffle box | Completed | Not quantified | Not quantified
SP-25* | Highpoint East | Baffle box | Completed | Not quantified | Not quantified
TI-1 | C-44 Conservation Area | Conservation | Completed | 23199 | 7496.7
T-1 | Project 420735-1 Port St. Lucie Interchange Pond A | Dry detention | Completed | 1.8 | 0.3
T-2 | Project 420735-1 Port St. Lucie Interchange Pond B | Wet detention | Completed | 16 | 2.1
T-3 | Thomas B. Manuel Bridge North Pond | Dry detention | Completed | 5.4 | 1
N/A | Agricultural Land Use Changes | Land use change | Completed | 171776.4 | 54191.1
MC-17 | Danforth Creek – Phase 1 | Wet detention | Construction | 2434.7 | 1010.7
SP-16 | Pedway/Greenway | Exfiltration/ pervious paver | Construction | 6.2 | 1.4
SP-27* | Extend Pedway/Greenway | Exfiltration/ pervious paver | Construction | Not quantified | Not quantified
SP-28* | Mandalay (Marguerita) | Dry detention | Construction | Not quantified | Not quantified
SP-29* | Baffle Boxes | 1st and 2nd generation baffle boxes | Construction | Not quantified | Not quantified
HSL-3 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 191 | 29.5
NSLRWCD-6 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 16979.9 | 3513.4
PM-1 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 926.2 | 91.7
TI-2 | 90% Implementation Agricultural BMPs | Agricultural BMPs | Ongoing | 1856.3 | 445.8
FP-3 | Street Sweeping – 4,314 Cubic Yards | Street sweeping | Ongoing | 5569 | 3571
FP-4 | Inlet Cleaning – 2,762 Cubic Yards | Inlet cleaning | Ongoing | 4300 | 2641
FP-5 | Stormwater Education Shows, Pamphlets, Presentations, Storm Drain Stenciling, Illicit Discharge Program | Education and outreach | Ongoing | 170.4 | 38.8
PSL-10 | Water and Wastewater Expansion | Septic tank phaseout | Ongoing | Not quantified | Not quantified
PSL-11 | Street Sweeping | Street sweeping | Ongoing | 676 | 434
PSL-12 | Swale Maintenance | Sediment removal | Ongoing | 7649 | 3097
PSL-13 | Catch Basin Cleaning | Catch basin cleaning | Ongoing | 21 | 13
PSL-14 | FYN; Fertilizer, Landscaping, Irrigation, and Pet Waste Ordinances; PSAs, Stormwater Educational Shows, Website, Outreach Programs, Stencil Program, Stormwater Pollution Hotline | Education and outreach | Ongoing | 9388.9 | 2100.9
PSL-15 | Tiffany Channel | Stormwater reuse | Ongoing | 32.9 | 7.6
PSL-16 | Patio STA | Stormwater reuse | Ongoing | 11.4 | 2.6
PSL-17 | Mary STA | Stormwater reuse | Ongoing | 7.6 | 1.7
PSL-18 | Leithgow STA | Stormwater reuse | Ongoing | 7.4 | 1.7
PSL-19 | Cane Slough 1/Elks STA | Stormwater reuse | Ongoing | 33.2 | 7.3
PSL-20 | Cane Slough 2/Azzi STA | Stormwater reuse | Ongoing | 23.9 | 5.2
PSL-21 | Loutus STA | Stormwater reuse | Ongoing | 22.5 | 4.8
PSL-22 | Howard Creek STA | Stormwater reuse | Ongoing | 33.9 | 7.1
PSL-23 | Bur St, STA | Stormwater reuse | Ongoing | 0.6 | 0.1
PSL-24 | St. Lucie West Services District Aquatic Harvesting | Aquatic harvesting | Ongoing | Not quantified | Not quantified
PSL-25 | St. Lucie West Services District Catch Basin Cleaning | Catch basin cleaning | Ongoing | 84 | 52
S-5 | Street Sweeping – 260 tons/yr | Street sweeping | Ongoing | 275 | 176
S-6 | Sediment Removal from Storm Systems – 50 tons/yr | BMP cleanout | Ongoing | 54 | 33
S-7 | FYN; Landscaping, Irrigation, Fertilizer, Pet Waste Ordinances; Brochure, Website, Information Inserts, City Calendar, Doggie Pot Stations, Neighborhood Cleanup Program | Education and outreach | Ongoing | 839.9 | 186.4
S-14 | Neighborhood Initiated Sewer Expansion Program | Removal of septic tanks | Ongoing | Not quantified | Not quantified
FDOT-18 | Street Sweeping | Street sweeping | Ongoing | 1419 | 910
FDOT-19 | Pamphlets | Education | Ongoing | 31.3 | 6.4
MC-18 | Street Sweeping | Street sweeping | Ongoing | 108 | 69
MC-19 | Baffle Box and Structure Cleanout | Clean out | Ongoing | 397 | 161
MC-20 | FYN; Landscaping, Irrigation, Fertilizer, and Pet Waste Ordinances; PSAs, Pamphlets, Website, Illicit Discharge Program | Education and outreach | Ongoing | 6048.7 | 1342.1
NSLRWCD-4 | Canal Maintenance Program | Vegetation harvesting | Ongoing | Not quantified | Not quantified
NSLRWCD-8 | Ideal Grove Hybrid Wetland Treatment Technology | Wetlands, chemical treatment | Ongoing | 330 | 127
SLC-5 | FYN; Pet Waste, Landscape, Irrigation, and Fertilizer Ordinances; PSAs, Website, Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program | Education and outreach | Ongoing | 1086.8 | 247.6
SLC-6 | Street Sweeping | Street sweeping | Ongoing | 210.6 | 135.2
SLC-7 | Catch Basin Cleanout | Clean out | Ongoing | 170.3 | 104.6
SLC-8 | Platt's Creek Sump Cleanout | Clean out | Ongoing | 1181.6 | 511.5
SLC-10 | FYN; Pet Waste, Landscape, Irrigation, and Fertilizer Ordinances; PSAs, Website, Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program | Education and outreach | Ongoing | 1425.7 | 364.3
SLC-11 | Street Sweeping | Street sweeping | Ongoing | 113.4 | 72.8
SLC-12 | Catch Basin Cleanout | Clean out | Ongoing | 91.7 | 56.4
SLC-13 | Platt's Creek Sump Cleanout | Clean out | Ongoing | 1566.4 | 600.5
SP-18 | Fertilizer Ordinance | Education | Ongoing | 8.9 | 1.9
SP-19 | Street Sweeping – 19 Cubic Yards | Street sweeping | Ongoing | 25 | 16
FP-1 | Heathcote Botanical Gardens Treatment Train | Alum | Planned | 350 | 144.4
PSL-26 | St. Lucie West Services District Wastewater Facility Upgrade | Wastewater facility upgrade | Planned | Not quantified | Not quantified
SP-26* | High Point Exfiltration | Exfiltration/swales | Planned | Not quantified | Not quantified
FDOT-6 | FM# 230262-2 | Dry detention | Started | 109.8 | 35.6
FDOT-20 | FM# 230978-1 Indian Street Bridge (Pond East) | Dry detention | Started | 1.7 | 0.4
FDOT-21 | FM# 230978-1 Indian Street Bridge (Pond West) | Wet detention | Started | 0.1 | 0
MC-21 | FM# 230978-1 Indian Street Bridge (Pond East) | Dry detention | Started | 5.1 | 1.1
MC-22 | FM# 230978-1 Indian Street Bridge (Pond West) | Wet detention | Started | 0.2 | 0.1
|  |  | Total | 317277.5 | 105429.7

## 1st year completed
Entity Type | Entity | Project Number | Project Name | TN Reduction (lbs/yr) | TP Reduction (lbs/yr)
Ag | Agriculture | N/A | BMP Enrollment | 108158.2 | 24788.5
LG | City of Fort Pierce | FP-5 | Fertilizer Ordinance | 85.2 | 19.4
LG | City of Port St. Lucie | PSL-9 | Water and Wastewater Expansion | 34206.5 | 0
LG | City of Stuart | S-14 | Neighborhood Initiated Sewer Expansion Program | 1340.7 | 0
LG | City of Stuart | S-16 | Amerigo Avenue Drainage Improvements | 37.4 | 7.3
LG | City of Stuart | S-18 | Non-Discharge Areas | 1038.2 | 233.3
LG | City of Stuart | S-19 | Baffle Boxes Throughout the City | 10.8 | 10.5
LG | City of Stuart | S-20 | CDS Units Throughout the City | 0 | 6.4
LG | Martin County | MC-16 | Septic to Central Sewer Conversions | 15396.2 | 0
LG | Martin County | MC-21 | FM# 230978-1 Indian Street Bridge (Pond East) | 5.1 | 1.1
LG | Martin County | MC-22 | FM# 230978-1 Indian Street Bridge (Pond West) | 0.2 | 0.1
LG | Martin County | MC-29 | Rio Water Quality Retrofit | 162.9 | 36.1
LG | Town of Sewall’s Point | SP-16 | Pedway/Greenway | 6.2 | 1.4
LG | Town of Sewall’s Point | SP-26* | High Point Exfiltration | Not quantified | Not quantified
LG | Town of Sewall’s Point | SP-30 | Exfiltration | 61.8 | 7.8
Transportation | FDOT D4 | FDOT-20 | FM# 230978-1 Indian Street Bridge (Pond East) | 1.7 | 0.4
Transportation | FDOT D4 | FDOT-21 | FM# 230978-1 Indian Street Bridge (Pond West) | 0.1 | 0
| Total |  | Total Reductions in Reporting Period | 160511.2 | 25112.3
| Total |  | Local Govt (LG Reductions) | 52351.2 | 323.4
| Total |  | Transporation Reductions | 1.8 | 0.4
| Total |  | Agricultural Reductions | 108158.2 | 24788.5

## New Proj. Added 1st year
New Projects Added in the 2014 Annual Report
Entity Type | Completed Code | Project Number | Project Name | Project Type | Acres Treated | Project Cost | End Date | Status | TN Reduction (lbs/yr) | TP Reduction (lbs/yr)
LG | C | MC-26* | Poinciana Gardens Water Quality Retrofit Phases I and II | Wet detention | 188 | 2960547 | 2003-07-01 | Completed | Not quantified | Not quantified
LG | C | MC-27* | Willoughby Creek Muck Dredging | Muck removal | N/A | 13200000 | 2012-07-01 | Completed | Not quantified | Not quantified
LG | C | MC-28* | Manatee Pocket Dredging | Muck removal | N/A | 1000000 | 2012-07-01 | Completed | Not quantified | Not quantified
LG | C | MC-29 | Rio Water Quality Retrofit | Exfiltration and second-generation baffle boxes | 45 | 696800 | 2014-05-19 | Completed | 162.9 | 36.1
LG | C | MC-30 | Old Palm City Beemats | Floating wetland vegetation islands |  | $21, 996 | 2013-09-26 | Completed | Not quantified | Not quantified
LG | C | S-16 | Amerigo Avenue Drainage Improvements | Dry detention | 9.9 | 772000 | 2014-04-01 | Completed | 37.4 | 7.3
LG | C | S-18 | Nondischarge Areas | Nondischarge (8 areas) | 217.6 | N/A | N/A | Completed | 1038.2 | 233.3
LG | C | S-19 | Baffle Boxes Throughout the City | First-generation baffle boxes (22 total) | 474.9 | Unknown | Various | Completed | 10.8 | 10.5
LG | C | S-20 | CDS Units Throughout the City | CDS units (12 total) | 65.9 | Unknown | Various | Completed | 0 | 6.4
LG | C | SP-30 | Indialucie | Exfiltration | 31.1 |  | 2014 | Completed | 61.8 | 7.8
LG | I | PSL-27 | Lansdown Basin | Second-generation baffle box | 115.2 | Included in PSL-25 cost | 2014-11-01 | Construction started May 2014 | 89.8 | 16.3
LG | I | PSL-28 | Streamlet/Manth Basin | Second-generation baffle box | 41.7 | Included in PSL-25 cost | 2014-11-01 | Construction started May 2014 | 32.8 | 6
LG | I | PSL-29 | Walters Basin | Second-generation baffle box | 179.5 | Included in PSL-25 cost | 2014-11-01 | Construction started May 2014 | 140.2 | 25.3
LG | I | PSL-30 | St. Lucie West Services District Water Management Improvement Project | Wet detention pond | Not quantified | Not quantified | 2014-11-01 | Construction started May 2014 | 454.5 | 326.9
LG | I | S-17 | Haney Creek Project | Flow-through marsh, wetlands | 626.4 | Unknown | Unknown | Under way | 513.7 | 207.3
Transportation | C | T-1 | Project 420735-1 Port St. Lucie Interchange Pond A | Dry detention | 3.6 |  |  | Completed | 1.8 | 0.3
Transportation | C | T-2 | Project 420735-1 Port St. Lucie Interchange Pond B | Wet retention | 20.6 |  |  | Completed | 16 | 2.1
Transportation | C | T-3 | Thomas B. Manuel Bridge North Pond | Dry detention | 9.8 |  |  | Completed | 5.4 | 1
Transportation | I | FDOT-41 | FM# 419250-2 State Road 710 Bridge Replacement – 100A, 100B, and 200 | Dry detention | 17.4 | Unknown |  | Started | 3.8 | 0.3
Transportation | I | FDOT-42 | FM# 419250-2 State Road 710 Bridge Replacement – 300 and 500 | Dry detention | 28.4 | Unknown |  | Started | 7.9 | 1
Transportation | I | FDOT-43 | FM# 413046-1 State Road 9 Widening | Dry retention | 152 | Unknown |  | Started | 75.2 | 14.1
Transportation | I | FDOT-44 | FM# 423022-1 CR 68 Orange Avenue | Dry detention | 5.62 | Unknown |  | Started | Not quantified | Not quantified
[6 empty] | Transportation, New Proj. Incompleted TN |  |  | 86.9
[6 empty] | Transportation, New Proj. Incomplete TP |  |  | 15.4
[6 empty] | Transportation, New Proj. Completed TN |  |  | 23.2
[6 empty] | Transportation, New Proj. Completed TP |  |  | 3.4
[6 empty] | Local Govt New Proj, Completed TN |  |  | 1311.1
[6 empty] | Local Govt New Proj TP |  |  | 301.4
[6 empty] | Local Govt New Proj, Incomplete TN |  |  | 1231
[6 empty] | Local Govt New Proj, Incomplete TP |  |  | 581.8

## 2nd year completed
July 1, 2014 through June 30, 2015
Entity | Entity | Project Number | Project Name | TN Reduction (lbs/yr) | TP Reduction (lbs/yr)
Ag | Agriculture | N/A | Agricultural BMP Enrollment through | 111151.03 | 25283.48
June 30, 2015
LG | City of Fort Pierce | FP-1 | Heathcote Botanical Gardens Treatment Train, also known as Indian Hills Recreation Area Stormwater Improvements | 232.7 | 98.9
LG | City of Port St. Lucie | PSL-9 | Water and Wastewater Expansion | TBQ | TBQ
LG | City of Port St. Lucie | PSL-25 | Atlantis Basin | 91.1 | 16.6
LG | City of Port St. Lucie | PSL-26 | Evergreen Basin | 189.9 | 34.7
LG | City of Port St. Lucie | PSL-27 | Lansdown Basin | 89.8 | 16.3
LG | City of Port St. Lucie | PSL-28 | Streamlet/Manth Basin | 32.8 | 6
LG | City of Port St. Lucie | PSL-29 | Walters Basin | 140.2 | 25.3
LG | Martin County | MC-31 | Bessey Creek Hybrid Wetland Treatment Technology | 6038 | 1466
LG | Town of Sewall’s Point | SP-31 | Quail Run Subdivision | TBQ | TBQ
LG | St. Lucie County | SLC-14 | Platt’s Creek Compensatory Mitigation Project | Not quantified | Not quantified
Transport | FDOT District 4 | FDOT-6 | FM# 230262-2 | 109.8 | 35.6
Transport | FDOT District 4 | FDOT-41 | FM# 419250-2 State Road 710 Bridge Replacement – 100A, 100B, and 200 | 3.8 | 0.3
Transport | FDOT District 4 | FDOT-42 | FM# 419250-2 State Road 710 Bridge Replacement – 300 and 500 | 7.9 | 1
Transport | FDOT District 4 | FDOT-43 | FM# 413046-1 State Road 9 Widening | 75.2 | 14.1
Transport | FDOT District 4 | FDOT-44 | FM# 423022-1 CR 68 Orange Avenue | Not quantified | Not quantified
Transport | FDOT District 4 | FDOT-45 | FM# 230108-1 SR 68 Orange Ave (40% credit) | 1.04 | 0.48
|  | Total | Total Reductions in Reporting Period | 118163.27 | 26998.76
|  | Total | Local Govt (LG Reductions) | 6814.5 | 1663.8
|  | Total | Transporation Reductions | 197.74 | 51.48
|  | Total | Agricultural Reductions | 111151.03 | 25283.48

## New Projects Added 2nd year
Project Number | Project Name | Project Type | Acres Treated | Project Cost | End Date | Status | TN Reduction (lbs/yr) | TP Reduction (lbs/yr)
MC-31** | Bessey Creek Hybrid Wetland Treatment Technology | Stormwater Treatment | 2675 | 3000000 | 2015-05-01 | Completed | 6085 | 1474
MC-32 | Danforth Creek Hybrid Wetland Treatment Technology | Stormwater Treatment | 2419 | 3000000 | 2015-09-01 | Under Construction | 5274 | 1281
FDOT-45 | FM# 230108-1 SR 68 Orange Ave (40% credit) | Wet detention | 17.8 |  | 2015-02-05 | Completed | 1.04 | 0.48
SLC-14 | Platt’s Creek Wetland Compensatory Project | Floodplain restoration | 311 | 2600000 | 2015-07-28 | Completed | Not quantified | Not quantified
SP-31 | Quail Run Subdivision | Exfiltration and baffle box | 3.5 |  | 2015-04-01 | Completed | Not quantified | Not quantified
Transportation, New Proj. Incompleted TN/TP
|  |  |  | Transportation, New Proj. Completed TN /TP |  |  | 1.04 | 0.48
|  |  |  | Local Govt New Proj, Completed TN/TP |  |  | 6085 | 1474
|  |  |  | Local Govt New Proj, Incomplete TN /TP |  |  | 5274 | 1281
Bessey Creek (Wildwood Calculation)
TN in | 1.5 | mg/L
TN out | 0.79 | mg/L
TP in | 0.214 | mg/L
TP out | 0.042 | mg/L
Flow | 1027 | Mgal/year
TN reduction | 6081.2778 | lbs/year
TP reduction | 1473.211 | lbs/year
** reductions are based on analytical data (influent and effluent nutrient concentrations) provided by county
County indicated the TN reduction was 6,085 and TP reduction was 1,474
Danforth (Wildwood Calculation)
TN in | 1.5 | mg/L
TN out | 0.79 | mg/L
TP in | 0.214 | mg/L
TP out | 0.042 | mg/L
Flow | 897 | Mgal/year
TN reduction | 5311.4958 | lbs/year
TP reduction | 1286.7286 | lbs/year
assumed will have same influent and effluent data as Bessey

## Graphs
TN Starting Load | Total Project Reductions (lbs/yr) | 2015 TN Load | TN Allocation
2429832 | 595951.97 | 1833880.03 | 1136633
Adjusted Total Required Reductions (From BMAP, Page 55 of document)* |  |  | 1053414
Phase 1 Required Reduction (30% of assigned total required reductions) |  |  | 316024.2
BMAP I Target (Starting Load - Phase 1 Required Reduction) |  |  | 2113807.8
% ot Total Required Reductions Achieved |  |  | 56.57%
TP Starting Load | Total Project Reductions (lbs/yr) | 2015 TP Load | TP Allocation
597552 | 157540.76 | 440011.24 | 127016
Adjusted Total Required Reductions (From BMAP, Page 56 of document)* |  |  | 404166
Phase 1 Required Reduction (30% of assigned total required reductions) |  |  | 121249.8
BMAP I Target (Starting Load - Phase 1 Required Reduction) |  |  | 476302.2
% ot Total Required Reductions Achieved |  |  | 38.98%
*Not sure why the total reduction was adjusted. It does not equal the starting Load minus the allocation.
The numbers adjusted numbers are in the final BMAP document.
BMAP I Target:
2,113,807.8 lbs/yr of TN
BMAP I Target:
476,302.2 lbs/yr of TP

## 2014 Summary Statistics
St. Lucie Reductions--2014 Data
All reductions in lbs/yr | All BMAP Reductions (Completed and Incomplete) |  |  |  | Reductions Completed in BMAP When Adopted |  |  |  | Incomplete Reductions in BMAP When Adopted |  |  |  | Additional Reductions Completed in Year 1 (2013-2014) |  |  |  | New, Completed Projects Added in 2014 |  |  |  | New, Uncompleted Projects Added in 2014
| TN | % of Total | TP | % of Total | TN | % of Total | TP | % of Total | TN | % of Total | TP | % of Total | TN | % of Total | TP | % of Total | TN | % of Total | TP | % of Total | TN | % of Total | TP | % of Total
LU Change Away from Agriculture/Not In WCDs | 171776.4 | 50.5% | 54191.1 | 48.95% | 171776.4 | 54.14% | 54191.1 | 51.4% | 0 | 0% | 0 | 0% | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Agriculture (includes area in WCDs) |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Cities/Counties/Towns | 63905.3 | 18.79% | 25805.4 | 23.31% | 61109.1 | 19.26% | 24647.7 | 23.38% | 2796.2 | 12.23% | 1157.7 | 21.95% | 0 | #DIV/0! | 0 | #DIV/0! | 1311.1 | 98.26% | 301.4 | 98.88% | 1231 | 93.41% | 581.8 | 97.42%
FDOT and Turnpike | 2051.2 | 0.603% | 1077.9 | 0.9737% | 1939.6 | 0.6113% | 1041.9 | 0.9882% | 111.6 | 0.4882% | 36 | 0.6826% | 0 | #DIV/0! | 0 | #DIV/0! | 23.2 | 1.739% | 3.4 | 1.115% | 86.9 | 6.594% | 15.4 | 2.579%
WCDs | 102405.8 | 30.11% | 29629.4 | 26.76% | 82452.4 | 25.99% | 25549 | 24.23% | 19953.4 | 87.28% | 4080.4 | 77.37% | 0 | #DIV/0! | 0 | #DIV/0! | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0%
Total | 340138.7 | 100% | 110703.8 | 100% | 317277.5 | 100% | 105429.7 | 100% | 22861.2 | 100% | 5274.1 | 100% | 0 | #DIV/0! | 0 | #DIV/0! | 1334.3 | 100% | 304.8 | 100% | 1317.9 | 100% | 597.2 | 100%
Percentage of Original BMAP Reductions |  |  |  |  | 93.28% |  | 95.24% |  | 6.721% |  | 4.764% |  | Includes new, completed projects added in 2014
St. Lucie Calculations
Starting Load | 2429832 |  | 597552
Allocation (from graph sheet) | 1136633 |  | 127016
Calculated Total Required Reductions | 1293199 |  | 470536
Assigned Total Required Reductions (use for calcs) | 1053414 |  | 404166
Phase 1 Required Reductions (30% of total reductions) | 316024.2 |  | 121249.8
All BMAP Reductions without Ag BMP Estimates | 340138.7 |  | 110703.8
Ag Reductions with Projected 90% Enrollment | 197216.6 |  | 40442
Grand Total BMAP Estimated Reductions with Ag Reductions | 537355.3 |  | 151145.8
% of Reductions Addressed by BMAP Projects, with Ag BMPs | 51.01% |  | 37.4%
Reductions Complete as of BMAP Adoption | 317277.5 |  | 105429.7
% of Total Reductions Complete At Adoption | 30.12% |  | 26.09%
Reductions Complete as of 2014 Annual Report | 317277.5 |  | 105429.7
% of Total Reductions Complete After Year 1 (2014) | 30.12% |  | 26.09%
Summary of Reductions (Totals) | TN | TN % of Total | TP | TP % of Total
Reductions Completed When BMAP Adopted | 317277.5 | 92.56% | 105429.7 | 94.47%
Incomplete Reductions When BMAP Adopted | 22861.2 | 6.669% | 5274.1 | 4.726%
New Completed Projects from 2014 Report | 1334.3 | 0.3892% | 304.8 | 0.2731%
New Incomplete Projects from 2014 Report | 1317.9 | 0.3845% | 597.2 | 0.5351%
Total Reductions Related to St. Lucie BMAP | 342790.9 | 100% | 111605.8 | 100%
Briefing Package Reductions | TN |  | TP
MS4s | 61781.4 |  | 25399
Nonpoint Source | 110012.8 |  | 31113.7
Agriculture (BMPs and LU changes) | 368993 |  | 94633.1
Total Briefing Package Reductions Described | 540787.2 |  | 151145.8
| 51.34% |  | 37.4%
Numbers from briefing package tables