## Sheet1
ProjID | OriginalAdoption | PlanStatus | PlanSubType | BMAPID | UniqueProjectID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber
3287 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDACS-01 | FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on 2013 BMAP model. Acres Treated based on FDACS OAWP December 2018 Enrollment and FSAID V. | Agricultural BMPs | Completed | N/A | 142282 | 32403 | Primary BMAP Area | 155521 | N/A | N/A | TBD | TBD | N/A
3411 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDACS-02 | FDACS | N/A | FDACS-02 | Credit for Changes in Land Use | Changes in Ag LU. Differences btw 2004 SFWMD coverage and LU at time of BMAP adoption identified by FDACS using aerial imagery, local field staff knowledge. Includes acres that are fallow or out of production, or converted to urban/nonAg use in basin. | Land Use Change | Completed | N/A | 171776 | 54191 | Primary BMAP Area | N/A | N/A | N/A | N/A | N/A | N/A
3410 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-01 | FDOT | N/A | FDOT-01 | FM# 230108-1 (Ponds 2 & 3) | Widening and new late construction on State Road (SR) 68 from SR 9 to east of County Road (CR)-607A (40% credit, remaining 60% to Central Indian River Lagoon (CIRL). | Wet Detention Pond | Completed | 2013 | 1 | 0 | Primary BMAP Area | 18 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3414 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-02 | FDOT | N/A | FDOT-02 | FM# 230108-1 | Combined with FDOT-01. | Wet Detention Pond | Completed | 2013 | N/A | N/A | Primary BMAP Area | 18 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3355 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-03 | FDOT | N/A | FDOT-03 | FM# 230262-4 | Road widening of SR 70 from west of Rim Ditch Canal to west of Header Canal. | Dry Detention Pond | Completed | 2008 | 69 | 18 | Primary BMAP Area | 102 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3212 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-04 | FDOT | N/A | FDOT-04 | FM# 230262-5 | Road widening of SR 70 from Turnpike to Berman Rd. | Dry Detention Pond | Completed | 2010 | 60 | 15 | Primary BMAP Area | 124 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3354 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-05 | FDOT | N/A | FDOT-05 | FM# 230262-3 | Road widening of SR 70 from Okeechobee County line, east 10.2 miles. | Dry Detention Pond | Completed | 2012 | 168 | 38 | Primary BMAP Area | 195 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3340 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-06 | FDOT | N/A | FDOT-06 | FM# 230262-2 | Road widening of SR 70 from Okeechobee County line, east 10.2 miles. | Dry Detention Pond | Completed | 2015 | 110 | 36 | Primary BMAP Area | 238 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3352 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-07 | FDOT | N/A | FDOT-07 | FM# 230295-1 | Road widening of SR 716 from Westmore-land Bridge to SR 5. | Dry Detention Pond | Completed | 2003 | 9 | 2 | Primary BMAP Area | 17 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3365 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-08 | FDOT | N/A | FDOT-08 | SPN 99004-1585 | Road widening of SR 5 from Jensen Beach Blvd to Port St. Lucie Blvd. | Dry Detention Pond | Completed | 2003 | 16 | 3 | Primary BMAP Area | 31 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3350 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-09 | FDOT | N/A | FDOT-09 | SPN 99004-1585 (Lake 3) | Road widening of SR A1A from Sewalls Point Rd. to west of MacArthur Blvd. | Wet Detention Pond | Completed | 2003 | 14 | 5 | Primary BMAP Area | 13 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3349 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-10 | FDOT | N/A | FDOT-10 | FM# 228819-1 (Basin A and B) | SR A1A Ernest Lyons Bridge replacement. | Wet Detention Pond | Completed | 2007 | 0.2 | 0.1 | Primary BMAP Area | 0 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3348 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-11 | FDOT | N/A | FDOT-11 | FM# 228821-1 (West 1 A) | SR A1A Evans Crary Senior Bridge replacement. | Exfiltration Trench | Completed | 2001 | 5 | 1 | Primary BMAP Area | 2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3347 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-12 | FDOT | N/A | FDOT-12 | FM# 228821-1 (East) | SR A1A Evans Crary Senior Bridge replacement. | Exfiltration Trench | Completed | 2001 | 2 | 0 | Primary BMAP Area | 1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3346 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-13 | FDOT | N/A | FDOT-13 | FM# 228831-1 | Bridge replacement at SR 714 crossing over Florida's Turnpike. | Dry Detention Pond | Completed | 2000 | 3 | 1 | Primary BMAP Area | 9 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3345 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-14 | FDOT | N/A | FDOT-14 | FM# 228801-1 | Road widening of SR 5 from Seabranch Blvd to north of Salerno Rd. | Dry Detention Pond | Completed | 2003 | 1 | 0 | Primary BMAP Area | 2 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3344 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-15 | FDOT | N/A | FDOT-15 | FM# 405504-1 | SR 9 rest area improvements. | Dry Detention Pond | Completed | 2005 | 24 | 5 | Primary BMAP Area | 54 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3343 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-16 | FDOT | N/A | FDOT-16 | FM# 230288-2 | Road widening of SR 5 from Rio Mar Dr. to Midway Rd. | Wet Detention Pond | Completed | 2009 | 63 | 22 | Primary BMAP Area | 44 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3342 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-17 | FDOT | City of Port St. Lucie | FDOT-17 | FM# 419890-1 | Construction of interchange at SR 9 and Becker Rd. | BMP Treatment Train | Completed | 2010 | 2 | 2 | Primary BMAP Area | 42 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3377 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-18 | FDOT | N/A | FDOT-18 | Street Sweeping | Not provided. | Street Sweeping | Completed | N/A | 1419 | 910 | Primary BMAP Area | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A
3351 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-19 | FDOT | N/A | FDOT-19 | Public Education | Pamphlets. | Education Efforts | Completed | N/A | 31 | 6 | Primary BMAP Area | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A
3353 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-20 | FDOT | Martin County | FDOT-20 | FM# 230978-1 Indian St. Bridge (Pond East) | New bridge crossing on CR 714 from west of Mapp Rd. to east of SR 76 on Indian St. | Dry Detention Pond | Completed | 2014 | 2 | 0 | Primary BMAP Area | 21 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3390 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-21 | FDOT | N/A | FDOT-21 | FM# 230978-1 Indian St. Bridge (Pond West) | New bridge crossing on CR 714 from west of Mapp Rd. to east of SR 76 on Indian St. | Wet Detention Pond | Completed | 2014 | 0.1 | 0 | Primary BMAP Area | 34 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3389 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-22 | FDOT | N/A | FDOT-22 | State Road 615 Midway Rd. to Edwards Rd. (Basin B-1) | Not provided. | Wet Detention Pond | Completed | 2009 | 5 | 2 | Primary BMAP Area | 8 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3388 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-23 | FDOT | N/A | FDOT-23 | State Road 615 Midway Rd. to Edwards Rd. (Basin E) | Not provided. | Wet Detention Pond | Completed | 2009 | 6 | 2 | Primary BMAP Area | 9 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3387 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-24 | FDOT | N/A | FDOT-24 | FM# 410717-1 SR 70 Widening Kings Highway (Hwy.) to Jenkins Rd. (West Basin) | Road widening on SR 70 from Kings Hwy. to Jenkins Rd. | Dry Detention Pond | Completed | 2012 | 3 | 1 | Primary BMAP Area | 6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3386 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-25 | FDOT | N/A | FDOT-25 | SR 713 (King's Hwy.) Turn Lanes | Not provided. | Grass swales without swale blocks or raised culverts | Completed | 2013 | 0 | 0 | Primary BMAP Area | 1 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3385 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-26 | FDOT | N/A | FDOT-26 | Johnson Honda of Stuart Turn Lane (Basin A and B) | Not provided. | Exfiltration Trench | Completed | 2010 | 0.1 | 0 | Primary BMAP Area | 0 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3384 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-27 | FDOT | N/A | FDOT-27 | FM# 228852-1 SR 76 Drainage Improvements at Cabana Point (Pond 9A) | SR 76 drainage improvements at Cabana Point. | Wet Detention Pond | Completed | 2006 | 10 | 3 | Primary BMAP Area | 5 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3383 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-28 | FDOT | N/A | FDOT-28 | FM# 228852-1 Osprey Ridge Planned Unit Development (PUD) - SR 76 Improvements | SR 76 Osprey Ridge PUD drainage improvements. | Exfiltration Trench | Completed | 2007 | 0.1 | 0 | Primary BMAP Area | 0 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3382 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-29 | FDOT | N/A | FDOT-29 | FM# 228852-1 SR 76 Improvements – Kanner Professional Center. | SR 76 improvements – Kanner Professional Center. | Exfiltration Trench | Completed | 2009 | 0.2 | 0 | Primary BMAP Area | 0 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3381 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-30 | FDOT | N/A | FDOT-30 | FM# 228851-1 (Basin A) | Resurfacing of SR 5 from just north of Bridge Rd. to just north of SE Dharyls St. | Dry Detention Pond | Completed | 2004 | TBD | TBD | Special Project BMAP Area | 14 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3380 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-31 | FDOT | N/A | FDOT-31 | FM# 228851-1 | Resurfacing of SR 5 from just north of Bridge Rd. to just north of SE Dharyls St. | Dry Detention Pond | Completed | 2004 | TBD | TBD | Special Project BMAP Area | 26 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3366 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-32 | FDOT | N/A | FDOT-32 | FM# 230132-1 (System No. 1) | Road widening of SR 615 between Ave. Q and Industrial Ave. | Dry Detention Pond | Completed | 2001 | TBD | TBD | Special Project BMAP Area | 3 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3378 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-33 | FDOT | N/A | FDOT-33 | FM# 228758-1 | SR 732 bridge replacement over Intracoastal Waterway. | Dry Detention Pond | Completed | 2006 | TBD | TBD | Special Project BMAP Area | 19 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3391 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-34 | FDOT | N/A | FDOT-34 | FM# 228819-1 (Basin C) | Road reconstruction and construction of 2 new bridges on SR A1A from Sewall's Point Rd. to west of MacArthur Blvd. | Dry Detention Pond | Completed | 2007 | TBD | TBD | Special Project BMAP Area | 16 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3376 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-35 | FDOT | N/A | FDOT-35 | FM# 228819-1 (Basin D) | Road reconstruction and construction of 2 new bridges on SR A1A from Sewall's Point Rd. to west of MacArthur Blvd. | Exfiltration Trench | Completed | 2007 | TBD | TBD | Special Project BMAP Area | 4 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3375 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-36 | FDOT | N/A | FDOT-36 | FM# 228819-1 (Basin E) | Road reconstruction and construction of 2 new bridges on SR A1A from Sewall's Point Rd. to west of MacArthur Blvd. | Exfiltration Trench | Completed | 2007 | TBD | TBD | Special Project BMAP Area | 5 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3374 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-37 | FDOT | N/A | FDOT-37 | FM# 405167-1 | Resurfacing of SR A1A from Hutchinson House West North to Martin County. | On-line Retention BMPs | Completed | 2005 | TBD | TBD | Special Project BMAP Area | 30 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3373 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-38 | FDOT | N/A | FDOT-38 | FM# 230296-1 | Shoulder widening and drainage improvements on SR A1A from C-1 Intake Canal to Fort Pierce city limits. | Grass swales without swale blocks or raised culverts | Completed | 2009 | TBD | TBD | Special Project BMAP Area | 89 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3372 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-39 | FDOT | N/A | FDOT-39 | FM# 230297-1 SR A1A Roadway Improvements Phase 3 | Roadway improvements on SR A1A from Blue Heron Blvd to Gulfstream Ave. | Exfiltration Trench | Completed | 2010 | TBD | TBD | Special Project BMAP Area | 6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3371 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-40 | FDOT | N/A | FDOT-40 | FM# 228758-1 SR 702 Jensen Beach Causeway | New roadway construction on SR 702 from Indian River Dr. to SR A1A. | Dry Detention Pond | Completed | 2008 | TBD | TBD | Special Project BMAP Area | 34 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3370 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-41 | FDOT | N/A | FDOT-41 | FM# 419250-2 SR 710 Bridge Replacement – 100A, 100B, and 200 | Big John Monahon Bridge replacement on SR 710 from SW Trail Dr. to east of SR 76 connector ramps. | Dry Detention Pond | Completed | 2015 | 3 | 0 | Primary BMAP Area | 17 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3369 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-42 | FDOT | N/A | FDOT-42 | FM# 419250-2 SR 710 Bridge Replacement – 300 and 500 | Big John Monahon Bridge replacement on SR 710 from SW Trail Dr. to east of SR 76 connector ramps. | Dry Detention Pond | Completed | 2015 | 7 | 1 | Primary BMAP Area | 28 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3368 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-43 | FDOT | N/A | FDOT-43 | FM# 413046-1 SR 9 Widening | Road widening on SR 9 from Okeechobee Rd. to south of Indrio Rd. | On-line Retention BMPs | Completed | 2015 | 75 | 14 | Primary BMAP Area | 152 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3338 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-44 | FDOT | N/A | FDOT-44 | FM# 423022-1 CR 68 Orange Ave. | County to provide geographic information system (GIS) data for county road; proposed split of 25 % to FDOT and 75 % to St. Lucie County. | Dry Detention Pond | Completed | 2015 | TBD | TBD | Primary BMAP Area | 6 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3379 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-45 | FDOT | N/A | FDOT-45 | FM# 230108-1 SR 68 Orange Ave. (40% credit) | Combined with FDOT-1. | Wet Detention Pond | Completed | 2005 | N/A | N/A | Primary BMAP Area | 18 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3341 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-46 | FDOT | St. Lucie County | FDOT-46 | 231440-2 Midway Rd. Widening, 25th St. to US 1 (Pond 1 and 2) | Road widening on Midway Rd. from SR 68 to SR 5. | Wet Detention Pond | Underway | 2020 | 0.2 | 0.4 | Primary BMAP Area | 17 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3312 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-47 | FDOT | St. Lucie County | FDOT-47 | 231440-2 Midway Rd. Widening, 25th St. to US 1 (Pond 3 and 4) | Road widening on Midway Rd. from SR 68 to SR 5. | Wet Detention Pond | Underway | 2020 | 0.2 | 0.5 | Primary BMAP Area | 14 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3311 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-48 | FDOT | St. Lucie County | FDOT-48 | 231440-2 Midway Rd. Widening, 25th St. to US 1 (Pond 5) | Road widening on Midway Rd. from SR 68 to SR 5. | Wet Detention Pond | Underway | 2020 | 0.2 | 0.6 | Primary BMAP Area | 11 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3310 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-49 | FDOT | N/A | FDOT-49 | 230978-2 CR 714 Martin Highway Widening – Danforth Basin | Road widening on CR 714 (Martin Hwy.) from east of Turnpike to just west of Mapp Rd. | Wet Detention Pond | Completed | 2016 | 3 | 4 | Primary BMAP Area | 17 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3309 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-50 | FDOT | N/A | FDOT-50 | 230978-2 CR 714 Martin Hwy. Widening – Wetlands Basin | Road widening on CR 714 (Martin Hwy.) from east of Turnpike to just west of Mapp Rd. | Wet Detention Pond | Completed | 2016 | 2 | 2 | Primary BMAP Area | 12 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3308 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-51 | FDOT | N/A | FDOT-51 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 1 | Road widening on SR 76 from I-95 to Monterey Rd. | Dry Detention Pond | Underway | 2019 | 2 | 1 | Primary BMAP Area | 5 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3307 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-52 | FDOT | N/A | FDOT-52 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 2A | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 2 | 1 | Primary BMAP Area | 7 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3306 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-53 | FDOT | N/A | FDOT-53 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 2B | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 3 | 1 | Primary BMAP Area | 15 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3305 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-54 | FDOT | N/A | FDOT-54 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 3 | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 5 | 4 | Primary BMAP Area | 25 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3304 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-55 | FDOT | N/A | FDOT-55 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 4 | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 3 | 2 | Primary BMAP Area | 12 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3303 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-56 | FDOT | N/A | FDOT-56 | 422641-3 SR 76 Widening from I-95 to Monterey Rd. Pond 8 | Road widening on SR 76 from I-95 to Monterey Rd. | Wet Detention Pond | Underway | 2019 | 3 | 2 | Primary BMAP Area | 11 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3289 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-57 | FDOT | N/A | FDOT-57 | Fertilizer Application Cessation | No longer applying routine fertilizer. | Fertilizer Cessation | Completed | 2016 | TBD | TBD | Primary BMAP Area | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A
3301 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-58 | FDOT | N/A | FDOT-58 | FM# 432705-1 | Road widening of SR 710 from north of Indiantown Rd to just south of bridge over C-44 Canal. | Grass swales without swale blocks or raised culverts | Underway | 2020 | 8 | 0 | Primary BMAP Area | 121 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3313 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FDOT-59 | FDOT | N/A | FDOT-59 | FM# 432705-1 | Road widening of SR 710 from north of Indiantown Rd to just south C-44 Canal bridge. | Grass swales without swale blocks or raised culverts | Underway | 2020 | 3 | 1 | Primary BMAP Area | 38 | Not provided | Not provided | Florida Legislature | Not provided | N/A
3299 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-01 | City of Fort Pierce | DEP | FP-01 | Indian Hills Recreation Area (Phase I) Stormwater Improvements | Treatment train of 6 different BMPs are joined to improve water quality of stormwater runoff discharging into IRL. Also known as Heathcote Botanical Gardens Treatment Train. | BMP Treatment Train | Completed | 2015 | N/A | N/A | Special Project BMAP Area | 1242 | 3000000 | 113000 | DEP | $1,410,000 | SO579
3298 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-02 | City of Fort Pierce | N/A | FP-02 | Moore's Creek Retrofit –Phases 3 and 4 | Channelized stormwater conveyance system reconfigured to provide increased detention areas, littoral shelves and meandering creek characteristics. | Wet Detention Pond | Completed | 2010 | N/A | N/A | Special Project BMAP Area | 1887 | 7946935 | 92500 | Not provided | Not provided | N/A
3297 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-03 | City of Fort Pierce | N/A | FP-03 | Street Sweeping | City removes cubic yards of debris by street sweeping activities. | Street Sweeping | Completed | N/A | 2020 | 1295 | Primary BMAP Area | N/A | Not provided | 89617 | City's stormwater utility | Not provided | N/A
3296 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-04 | City of Fort Pierce | N/A | FP-04 | Inlet Cleaning | City cleans storm inlets citywide and disposes of waste. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 65 | 40 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3295 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-05 | City of Fort Pierce | N/A | FP-05 | Education Program | City delivers educational programs to public through trade associations, HOAs, or other means. Educates on hazards associated with illicit discharge, fertilizer use, the importance of water quality, and stormwater pollution protection. | Education Efforts | Completed | N/A | 215 | 49 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3294 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-06 | City of Fort Pierce | N/A | FP-06 | Virginia Ave. Outfall Canal | Stabilization of eroded canal banks as result of 2008 Tropical Storm Fay using rock rip-rap and gabion basket wall construction. | Shoreline Stabilization | Completed | 2008 | N/A | N/A | Special Project BMAP Area | 161 | 3462572 | 1500 | Not provided | Not provided | N/A
3293 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-07 | City of Fort Pierce | N/A | FP-07 | Moore's Creek Retrofit Phase 2 | Not provided. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2008 | N/A | N/A | Special Project BMAP Area | 1680 | 1480437 | Not provided | Not provided | Not provided | N/A
3292 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-08 | City of Fort Pierce | N/A | FP-08 | South Beach Baffle Boxes | Not provided. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2005 | N/A | N/A | Special Project BMAP Area | 128 | 557003 | Not provided | Not provided | Not provided | N/A
3291 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-09 | City of Fort Pierce | DEP | FP-09 | Veterans Park Stormwater Improvements | Improvements to existing stormwater facility to incorporate BMPs along with pervious parking, lake construction, and bio swales. | BMP Treatment Train | Completed | 2016 | N/A | N/A | Special Project BMAP Area | 44 | 2367000 | Not provided | DEP | $807,500 | SO696/ G0417
3290 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-10 | City of Fort Pierce | N/A | FP-10 | North 2nd St. (Seaway Dr. Jorth to Taylor Creek Marina) | Project entails complete reconstruction of 2nd Street including drainage conveyance/storage, utility upgrades and replacement, roadway widening and reconstruction, sidewalk on west side, and landscaping and lighting improvements. | Wet Detention Pond | Completed | 2017 | N/A | N/A | Special Project BMAP Area | Not provided | 1909176 | Not provided | Not provided | Not provided | N/A
3325 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-11 | City of Fort Pierce | DEP | FP-11 | Indian Hills Recreation Area (Phase II) Stormwater Improvements | Reestablishment of wetlands and pervious paver parking areas. | Wetland Restoration | Completed | 2016 | TBD | TBD | Primary BMAP Area | 61 | 2337485 | Not provided | DEP | $1,410,000 | S0579
3327 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-12 | City of Fort Pierce | N/A | FP-12 | Ave. F (US Hwy. 1 to 6th Street) | Drainage improvements along Avenue F will include curb inlets, 100 linear feet (LF) of exfiltration trench, complete curb replacement, and roadway resurfacing. | Exfiltration Trench | Completed | 2017 | N/A | N/A | Special Project BMAP Area | Not provided | 186327 | Not provided | Not provided | Not provided | N/A
3302 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-FP-13 | City of Fort Pierce | N/A | FP-13 | Mechanical Removal of Water Lettuce at Moore's Creek Between N 10th St. and N 13th St. | "One time" mechanical removal of water lettuce at Moore's Creek between N 10th Street and N 13th Street. | Aquatic Vegetation Harvesting | Completed | Not provided | N/A | N/A | Special Project BMAP Area | 0.04 | 10740 | N/A | Not provided | Not provided | N/A
3337 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-HSL-01 | Hobe St. Lucie Conservancy District | Not provided | HSL-01 | Hobe Sound Polo Club | Not provided. | BMP Treatment Train | Completed | 2013 | 3097 | 1014 | Primary BMAP Area | 1736 | Not provided | Not provided | Not provided | Not provided | N/A
3336 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-HSL-02 | Hobe St. Lucie Conservancy District | Not provided | HSL-02 | Changes in Agricultural Land Uses | Not provided. | Land Use Change | Completed | 2013 | 7000 | 2259 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3335 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-HSL-03 | Hobe St. Lucie Conservancy District | Not provided | HSL-03 | 90% Implementation Agricultural BMPs | Not provided. | Agricultural BMPs | Completed | 2013 | 191 | 30 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3334 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-01 | Martin County | SFWMD/ DEP | MC-01 | Cedar Point Water Quality Retrofit | 1.7 ac-ft of water quality treatment (0.36 inches). | BMP Treatment Train | Completed | 2004 | 72 | 34 | Primary BMAP Area | 31 | 398027 | Not provided | DEP | $127,000 | SO101
3333 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-02 | Martin County | SFWMD/ DEP | MC-02 | Indian River Drive Baffle Boxes | Six second generation baffle boxes | Baffle Boxes- Second Generation | Completed | 2010 | 31 | 6 | Primary BMAP Area | 39 | 741827 | Not provided | DEP/ SFWMD | SFWMD - $187,000/ DEP - $208,137 | SO363
3332 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-03 | Martin County | SFWMD/ DEP | MC-03 | Warner Creek/Leilani Heights Water Quality Retrofit Phase I | 8.0 ac-ft of water quality treatment (0.14 inches). | BMP Treatment Train | Completed | 2011 | 230 | 49 | Primary BMAP Area | 70 | 541854 | Not provided | DEP/ SFWMD | DEP - $558,625/ SFWMD - $825,000/ SFWMD - $704,375 | G0264
3331 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-04 | Martin County | SFWMD/ DEP | MC-04 | Warner Creek Phase II | 0.36 acre dry detention area with control structure | Dry Detention Pond | Completed | 2012 | 6 | 1 | Primary BMAP Area | 15 | 1750338 | Not provided | DEP/ SFWMD | N/A | G0265
3330 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-05 | Martin County | SFWMD/ DEP | MC-05 | Warner Creek Phase III –Beacon 21 | 2.96 acre wet detention area with control structure weir | Wet Detention Pond | Completed | 2012 | 1291 | 597 | Primary BMAP Area | 1354 | 2122935 | Not provided | DEP/ SFWMD | N/A | G0266
3329 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-06 | Martin County | SFWMD/ DEP | MC-06 | Manatee Creek Water Quality Retrofit Phases I, II, and III | 30.4 ac-ft of water quality treatment (0.44 inches). | BMP Treatment Train | Completed | 2012 | 6 | 4 | Primary BMAP Area | 16 | 7026439 | Not provided | DEP/ SFWMD | DEP - $1,833,992/ SFWMD - $2,591,205 | OT040740/ SO0257
3328 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-07 | Martin County | SFWMD/ DEP | MC-07 | Rio/St. Lucie- Water Quality Retrofit -Phase 1 | 3.0 ac-ft of water quality treatment (0.35 inches). | BMP Treatment Train | Completed | 2006 | 41 | 11 | Primary BMAP Area | 8 | 354161 | Not provided | DEP | $300,179 | SO100
3314 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-08 | Martin County | SFWMD/ DEP | MC-08 | Rio/St. Lucie- Water Quality Retrofit -Phase 2 | 5.1 ac-ft of additional water quality treatment and control structures on existing lakes (0.7 inches). | Wet Detention Pond | Completed | 2008 | 190 | 74 | Primary BMAP Area | 120 | 998170 | Not provided | DEP | $776,170 | OT050685
3326 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-09 | Martin County | SFWMD/ DEP | MC-09 | Salerno Creek Water Quality Retrofit | 54.5 ac-ft of water qualtiy treatment (1.03 inches). | BMP Treatment Train | Completed | 2003 | 408 | 134 | Primary BMAP Area | 208 | 4715074 | Not provided | DEP | $1,541,568 | OT060149/ WAP068/ WM800/ SP379
3339 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-10 | Martin County | SFWMD/ DEP | MC-10 | Coral Gardens Water Quality Retrofit | 8.5 ac-ft of water quality treatment (0.05 inches). | BMP Treatment Train | Completed | 2005 | 1376 | 936 | Primary BMAP Area | 2008 | 2321860 | Not provided | DEP | $2,009,741 | OT040741/ SO116
3324 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-11 | Martin County | SFWMD/ DEP | MC-11 | Fern Creek Water Quality Retrofit | 29.8 ac-ft of water quality treatment (0.81 inches). | BMP Treatment Train | Completed | 2005 | 685 | 258 | Primary BMAP Area | 607 | 2660200 | Not provided | DEP | $761,141 | SO078/ WAP027
3323 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-12 | Martin County | SFWMD/ DEP/ FEMA | MC-12 | Old Palm City Water Quality Retrofit Phases I, II, and III | 8.1 ac-ft of water quality treatment (0.51 inches). | BMP Treatment Train | Completed | 2004 | 244 | 96 | Primary BMAP Area | 141 | 4576473 | Not provided | DEP/ SFWMD/ FEMA | DEP - $851,156/ SFWMD - $1,200,000/ FEMA - $593,553 | G0034/ OT060148
3322 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-13 | Martin County | SFWMD/ DEP | MC-13 | North River Shores Baffle Boxes | Installation of +20 Baffle Boxes | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 4 | 4 | Primary BMAP Area | 187 | 1310000 | Not provided | DEP | $500,000 | SP557
3321 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-14 | Martin County | SFWMD/ DEP | MC-14 | Palm Lake Park Water Quality Retrofit | 7.7 ac-ft of water quality treatment (1.16 inches). | BMP Treatment Train | Completed | 2003 | 108 | 42 | Primary BMAP Area | 80 | 1741098 | Not provided | DEP | $1,480,936 | WAP026
3320 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-15 | Martin County | SFWMD/ DEP | MC-15 | Tropical Farms Water Quality Retrofit | 43.2 ac-ft of water quality treatment (1.11 inches). | BMP Treatment Train | Completed | 2010 | 945 | 309 | Primary BMAP Area | 470 | 4047219 | Not provided | DEP/ SFWMD | SFWMD - $1,412,000/ DEP - $1,180,589 | OT060152/ SO361
3319 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-16 | Martin County | N/A | MC-16 | Septic to Central Sewer Conversions | 1,121 single-family and multifamily residential and commercial units in five neighborhoods. | OSTDS Phase Out | Completed | 2014 | 15386 | N/A | Primary BMAP Area | N/A | 28678946 | Not provided | NEEPP - North River Shores neighborhood | Not provided | N/A
3318 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-17 | Martin County | SFWMD | MC-17 | Danforth Creek – Phase 1 | 8.1 acre wet detention pond with littoral plantings and control structure | Regional Stormwater Treatment | Completed | 2014 | 2435 | 1011 | Primary BMAP Area | 2459 | 1869255 | Not provided | SFWMD | $1,035,515 | N/A
3317 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-18 | Martin County | N/A | MC-18 | Street Sweeping | Not provided. | Street Sweeping | Completed | N/A | 119 | 76 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3316 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-19 | Martin County | N/A | MC-19 | Baffle Box and Structure Cleanout | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 266 | 163 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3400 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-20 | Martin County | N/A | MC-20 | Education Program | FYN; landscaping, irrigation, fertilizer, and pet waste ordinances; PSAs, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 6049 | 1342 | Primary BMAP Area | N/A | Not provided | Not provided | County | $60,000 | N/A
3300 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-21 | Martin County | FDOT | MC-21 | FM# 230978-1 Indian St. Bridge (Pond East) | Not provided. | Dry Detention Pond | Completed | 2014 | 5 | 1 | Primary BMAP Area | 21 | Not provided | Not provided | Not provided | Not provided | N/A
3367 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-22 | Martin County | FDOT | MC-22 | FM# 230978-1 Indian St. Bridge (Pond West) | Not provided. | Wet Detention Pond | Completed | 2014 | 0 | 0 | Primary BMAP Area | 34 | Not provided | Not provided | Not provided | Not provided | N/A
3446 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-23 | Martin County | DEP | MC-23 | Golden Gate Water Quality Retrofit Phases I, II | Treatment train system, baffle boxes, dry detention & 5.61 ac-ft of wet detention | BMP Treatment Train | Completed | 2003 | TBD | TBD | Special Project BMAP Area | 202 | 2046145 | Not provided | DEP | $1,322,772 | WAP030/ G0012
3445 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-24 | Martin County | DEP | MC-24 | Golden Gate Water Quality Retrofit Phase III | Treatment train system, baffle boxes, & 2.26 ac-ft of wet detention | BMP Treatment Train | Completed | 2004 | TBD | TBD | Special Project BMAP Area | 27 | 584371 | Not provided | DEP | $313,060 | SO105
3444 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-25 | Martin County | DEP | MC-25 | Hibiscus Park Water Quality Retrofit Phases I and II | 1.24 ac-ft of Wet Detention volume | Wet Detention Pond | Completed | 2007 | TBD | TBD | Special Project BMAP Area | 5 | 1390574 | Not provided | DEP | $687,715 | OT050696
3443 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-26 | Martin County | DEP | MC-26 | Poinciana Gardens Water Quality Retrofit Phases I and II | Treatment Train system, 87.36 ac-ft of wet detention and baffle box | BMP Treatment Train | Completed | 2003 | TBD | TBD | Special Project BMAP Area | 188 | 2960547 | Not provided | DEP | $2,235,091 | WAP025
3442 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-27 | Martin County | N/A | MC-27 | Willoughby Creek Muck Dredging | Not provided. | Muck Removal/Restoration Dredging | Completed | 2012 | TBD | TBD | Special Project BMAP Area | N/A | 13200000 | Not provided | Not provided | Not provided | N/A
3441 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-28 | Martin County | N/A | MC-28 | Manatee Pocket Dredging | Not provided. | Muck Removal/Restoration Dredging | Completed | 2012 | TBD | TBD | Special Project BMAP Area | N/A | 1000000 | Not provided | Not provided | Not provided | N/A
3440 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-29 | Martin County | SFWMD/ DEP | MC-29 | Rio Water Quality Retrofit | Exfiltration Trenches & Baffle Boxes | BMP Treatment Train | Completed | 2014 | 163 | 36 | Primary BMAP Area | 50 | 696800 | Not provided | DEP/ SFWMD | DEP - $240,000/ SFWMD - $310,000 | SO642
3448 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-30 | Martin County | N/A | MC-30 | Old Palm City Beemats | Not provided. | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Completed | 2013 | TBD | TBD | Primary BMAP Area | N/A | 21996 | Not provided | Not provided | Not provided | N/A
3438 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-31 | Martin County | FDACS | MC-31 | Bessey Creek Hybrid Wetland Treatment Technology (HWTT) | Not provided. | Hybrid wetland treatment technology (HWTT) | Completed | 2015 | 6081 | 1473 | Primary BMAP Area | 2675 | 3000000 | Not provided | FDACS | $3,000,000 | N/A
3437 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-32 | Martin County | FDACS | MC-32 | Danforth Creek HWTT | Not provided. | Hybrid wetland treatment technology (HWTT) | Completed | 2016 | 5274 | 1281 | Primary BMAP Area | 2419 | 3000000 | Not provided | FDACS | $3,000,000 | N/A
3436 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-33 | Martin County | N/A | MC-33 | Hoke Library Rain Garden | Not provided. | LID- Rain Gardens | Completed | 2015 | Not provided | Not provided | Primary BMAP Area | Not provided | 4372 | Not provided | Not provided | Not provided | N/A
3447 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-34 | Martin County | N/A | MC-34 | Halpatiokee Park Rain Garden | Not provided. | LID- Rain Gardens | Completed | 2015 | Not provided | Not provided | Primary BMAP Area | Not provided | 1500 | Not provided | Not provided | Not provided | N/A
3434 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-35 | Martin County | DEP | MC-35 | Manatee Pocket SW Prong Baffle Box | Not provided. | Baffle Boxes- Second Generation | Completed | 2016 | 255.4 | 45.9 | Primary BMAP Area | 236 | 232505 | Not provided | DEP | $100,000 | S0759
3433 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-36 | Martin County | DEP | MC-36 | Martin County Golf Course WQ | Not provided. | Wet Detention Pond | Completed | 2016 | 547.6 | 205.4 | Primary BMAP Area | 207 | 156255 | Not provided | DEP | $50,000 | S0765
3432 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-37 | Martin County | DEP | MC-37 | All American Ditch | Not provided. | Regional Stormwater Treatment | Completed | 2016 | 428 | 169.3 | Primary BMAP Area | 268 | 5165376 | Not provided | DEP | $3,000,000 | S0758/ G0414
3431 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-38 | Martin County | SFWMD | MC-38 | Hilltop Street Exfiltration Trench | Not provided. | Exfiltration Trench | Completed | 2016 | 47.1 | 10.6 | Primary BMAP Area | 15 | 264774 | Not provided | SFWMD | $100,000 | N/A
3430 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-39 | Martin County | N/A | MC-39 | Willoughby Creek STA | Not provided. | BMP Treatment Train | Underway | 2019 | TBD | TBD | Primary BMAP Area | TBD | Not provided | Not provided | Not provided | Not provided | N/A
3429 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-40 | Martin County | N/A | MC-40 | Savannah Road Exfiltration Trench | Not provided. | BMP Treatment Train | Underway | 2020 | TBD | TBD | Primary BMAP Area | TBD | Not provided | Not provided | Not provided | Not provided | N/A
3428 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-41 | Martin County | N/A | MC-41 | Old Palm City Phase IV | Not provided. | BMP Treatment Train | Planned | 2021 | TBD | TBD | Primary BMAP Area | TBD | TBD | TBD | N/A | N/A | N/A
3427 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-MC-42 | Martin County | N/A | MC-42 | South Savannas Weir | Not provided. | Control Structure | Planned | 2020 | TBD | TBD | Primary BMAP Area | TBD | TBD | TBD | TBD | TBD | N/A
3435 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-01 | North St. Lucie River WCD | St. Lucie River Issues Team (SLRIT) | NSLRWCD-01 | SLRIT Grant 2000–2001: Vegetation Control & Bank Restoration | Installation of C-25 diversion structure which regulates flow from the North St. Lucie River Water Control District (NSLRWCD) C-44/ North Emergency Relief Canal to SFWMD C-25. In addition, installation of 3 risers with adjustable gates. | Control Structure | Completed | 2003 | 983 | 0 | Primary BMAP Area | 4173 | 929000 | Not provided | NSLRWCD/ SLRIT 50/50 contribution match | Not provided | N/A
3458 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-02 | North St. Lucie River WCD | St. Lucie River Issues Team (SLRIT) | NSLRWCD-02 | SLRIT Grant 2007–2008: WCS Retrofits | Installation of adjustable gates on WCS to improve efficiency of water levels and better manage sediment transport downstream. | Control Structure | Completed | 2010 | 1372 | 0 | Primary BMAP Area | 4701 | 77000 | Not provided | NSLRWCD/ SLRIT 50/50 contribution match | Not provided | N/A
3449 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-03 | North St. Lucie River WCD | St. Lucie County, FDOT | NSLRWCD-03 | Canals 23 and 28 Retrofit for Stormwater Treatment and Attenuation | Construction of ponds and installation of WCS for area retrofit. Inclusion of WMD canals into pond footprints. | Control Structure | Completed | 2009 | 11 | 0 | Primary BMAP Area | 44 | Not provided | Not provided | FDOT/ St. Lucie County/ NSLRWCD | Not provided | N/A
3450 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-04 | North St. Lucie River WCD | N/A | NSLRWCD-04 | Canal Maintenance Program | Maintenance program on over 200 miles of canal. | Aquatic Vegetation Harvesting | Completed | 2013 | Not provided | Not provided | Primary BMAP Area | 66225 | 4200000 | Not provided | NSLRWCD | Not provided | N/A
3451 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-05 | North St. Lucie River WCD | N/A | NSLRWCD-05 | Changes in Agricultural Land Uses | Not provided. | Land Use Change | Completed | 2013 | 45621 | 14445 | Primary BMAP Area | 1055 | N/A | N/A | N/A | N/A | N/A
3452 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-06 | North St. Lucie River WCD | N/A | NSLRWCD-06 | 90% Implementation Agricultural BMPs | Not provided. | Agricultural BMPs | Completed | 2013 | 19972 | 4308 | Primary BMAP Area | N/A | N/A | N/A | N/A | N/A | N/A
3457 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-07 | North St. Lucie River WCD | N/A | NSLRWCD-07 | Change from Agricultural to Urban | Not provided. | Land Use Change | Completed | 2013 | 839 | 208 | Primary BMAP Area | N/A | N/A | N/A | N/A | N/A | N/A
3453 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-08 | North St. Lucie River WCD | N/A | NSLRWCD-08 | Ideal Grove Hybrid Wetland Treatment Technology | Not provided. | Hybrid wetland treatment technology (HWTT) | Completed | 2013 | 330 | 127 | Primary BMAP Area | 238 | 217929 | Not provided | Not provided | Not provided | N/A
3454 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-09 | North St. Lucie River WCD | Not provided | NSLRWCD-09 | Structure 81-1-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 124 | 24 | Primary BMAP Area | 2582 | Not provided | Not provided | Not provided | Not provided | N/A
3455 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-10 | North St. Lucie River WCD | Not provided | NSLRWCD-10 | Structure 82-2-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 23 | 5 | Primary BMAP Area | 674 | Not provided | Not provided | Not provided | Not provided | N/A
3456 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-11 | North St. Lucie River WCD | Not provided | NSLRWCD-11 | Structure 83-2-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 27 | 5 | Primary BMAP Area | 484 | Not provided | Not provided | Not provided | Not provided | N/A
3459 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-NSLRWCD-12 | North St. Lucie River WCD | Not provided | NSLRWCD-12 | Structure 85-1-2 | Installation of new control structure as part of Okeechobee Rd. improvements project. | Control Structure | Completed | 2010 | 64 | 12 | Primary BMAP Area | 961 | Not provided | Not provided | Not provided | Not provided | N/A
3426 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PM-01 | Pal Mar WCD | Not provided | PM-01 | 90% Implementation Agricultural BMPs | Not provided. | Agricultural BMPs | Completed | 2013 | 926 | 92 | Primary BMAP Area | N/A | N/A | N/A | N/A | N/A | N/A
3393 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-01 | City of Port St. Lucie | DEP/ SFWMD/ SLC/ American Greenways/ Tax-Increment Financing (TIF) | PSL-01 | Woodstork Trail Design Districts 7, 8, and 9 | 4.6 acres of new filter marsh, 7.21 acres of new uplands, and installation of baffle box. | BMP Treatment Train | Completed | 2007 | 4 | 4 | Primary BMAP Area | 229 | 3300000 | 1122000 | DEP/ SFWMD/ SLC/ American Greenways/ TIF | Not provided | G0140
3407 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-02 | City of Port St. Lucie | DEP/ City Center Special Assessments | PSL-02 | Wood Stork Trail Design District 6 | 7.74-acre wet detention area, .62-acre STA, and 3 baffle boxes. | BMP Treatment Train | Completed | 2008 | 3 | 2 | Primary BMAP Area | 81 | 825500 | N/A | DEP/ City Center Special Assessments | Not provided | G0178
3406 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-03 | City of Port St. Lucie | DEP/ SFWMD | PSL-03 | Howard Creek STA | Construction of weir, 45-acre STA, littoral shelves, and new plantings. | BMP Treatment Train | Completed | 2010 | 523 | 212 | Primary BMAP Area | 436 | N/A | N/A | DEP/ SFWMD | Not provided | S0507
3405 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-04 | City of Port St. Lucie | N/A | PSL-04 | Eastern Watershed Improvement Project | Flood control, water quality, environmental restoration project consisting of 27 acres of wet detention ponds, littoral shelves, and created wetlands. | BMP Treatment Train | Completed | 2011 | 618 | 361 | Primary BMAP Area | 850 | 36000000 | N/A | City | Not provided | N/A
3404 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-05 | City of Port St. Lucie | NRCS/ SFWMD | PSL-05 | B-1 and B-2 WCS | WCS B-1, B-2, and B-3 protected North Fork of St. Lucie River (NFSLR) from receiving uncontrolled E-8 Canal discharges. System will stage appropriate discharge levels based on volume, retaining maximum flows. | Control Structure | Completed | 2007 | 2527 | 994 | Primary BMAP Area | 1748 | 1800000 | 621000 | City/ NRCS/ SFWMD | Not provided | N/A
3403 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-06 | City of Port St. Lucie | NRCS/ SFWMD | PSL-06 | B-3 WCS | Not provided | Control Structure | Completed | 2007 | 2372 | 932 | Primary BMAP Area | 1641 | N/A | N/A | City/ NRCS/ SFWMD | Not provided | N/A
3402 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-07 | City of Port St. Lucie | DEP | PSL-07 | E-8 Waterway Phase 1 Water Quality Retrofit | Control structure improvements, weirs, sediment removal, and construction of 2 STAs totaling 24.36 acres. Improvements will enhance stormwater drainage and flood protection capacity, improve water quality and restore native vegetation and habitat. | BMP Treatment Train | Completed | 2010 | 764 | 664 | Primary BMAP Area | 1610 | 400000 | N/A | DEP | Not provided | S0239
3356 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-08 | City of Port St. Lucie | SFWMD | PSL-08 | E-17 Canal WCS | New WCS added to retain maximum flows. | Control Structure | Completed | 2008 | 181 | 0 | Primary BMAP Area | 984 | 437000 | N/A | City | Not provided | N/A
3357 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-09 | City of Port St. Lucie | N/A | PSL-09 | Water and Wastewater Expansion | Multiple phase-outs of septic tanks from 2013 to 2017. | OSTDS Phase Out | Completed | 2017 | 34198 | N/A | Primary BMAP Area | N/A | 91075666 | 3700000 | City | N/A | N/A
3358 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-10 | City of Port St. Lucie | N/A | PSL-10 | Street Sweeping | Not provided. | Street Sweeping | Completed | N/A | 676 | 434 | Primary BMAP Area | N/A | Not provided | 448000 | City | Not provided | N/A
3359 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-11 | City of Port St. Lucie | N/A | PSL-11 | Swale Maintenance | Not provided. | BMP Cleanout | Completed | N/A | 7649 | 3097 | Primary BMAP Area | N/A | Not provided | 780000 | City | Not provided | N/A
3360 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-12 | City of Port St. Lucie | N/A | PSL-12 | Catch Basin Cleaning | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 21 | 13 | Primary BMAP Area | N/A | Not provided | N/A | City | Not provided | N/A
3361 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-13 | City of Port St. Lucie | N/A | PSL-13 | Education Program | Florida Yards and Neighborhoods (FYN) Program; fertilizer, landscape, irrigation, and pet waste ordinances; PSAs; stormwater educational shows; website; outreach programs; Stencil Program; and stormwater pollution hotline. | Education Efforts | Completed | N/A | 9389 | 2101 | Primary BMAP Area | N/A | Not provided | Not provided | City | Not provided | N/A
3362 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-14 | City of Port St. Lucie | N/A | PSL-14 | Tiffany Channel | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 33 | 8 | Primary BMAP Area | N/A | N/A | 1900000 | City | Not provided | N/A
3363 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-15 | City of Port St. Lucie | N/A | PSL-15 | Patio STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 11 | 3 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3364 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-16 | City of Port St. Lucie | N/A | PSL-16 | Mary STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 8 | 2 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3273 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-17 | City of Port St. Lucie | N/A | PSL-17 | Leithgow STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 7 | 2 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3274 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-18 | City of Port St. Lucie | N/A | PSL-18 | Cane Slough 1/ Elks STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 33 | 7 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3282 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-19 | City of Port St. Lucie | N/A | PSL-19 | Cane Slough 2/ Azzi STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 24 | 6 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3256 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-20 | City of Port St. Lucie | N/A | PSL-20 | Loutus STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 23 | 5 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3257 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-21 | City of Port St. Lucie | N/A | PSL-21 | Howard Creek STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 34 | 7 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3270 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-22 | City of Port St. Lucie | N/A | PSL-22 | Bur St. STA | Landscape irrigation is drawn from stormwater in channel. | Stormwater Reuse | Completed | Prior to 2013 | 1 | 0 | Primary BMAP Area | N/A | N/A | N/A | City | Not provided | N/A
3260 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-23 | City of Port St. Lucie | N/A | PSL-23 | St. Lucie West Services District (SLWSD) Aquatic Harvesting | Not provided. | Aquatic Vegetation Harvesting | Canceled | N/A | N/A | N/A | Not Provided | N/A | N/A | N/A | N/A | N/A | N/A
3250 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-24 | City of Port St. Lucie | SLWSD | PSL-24 | SLWSD Catch Basin Cleaning | Not provided. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 84 | 52 | Primary BMAP Area | N/A | 185600 | 10450 | SLWSD | Not provided | N/A
3262 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-25 | City of Port St. Lucie | N/A | PSL-25 | Atlantis Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 91 | 17 | Primary BMAP Area | 116 | 628000 | N/A | City | Not provided | N/A
3251 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-26 | City of Port St. Lucie | N/A | PSL-26 | Evergreen Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 190 | 35 | Primary BMAP Area | 241 | N/A | N/A | City | Not provided | N/A
3269 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-27 | City of Port St. Lucie | N/A | PSL-27 | Lansdown Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 90 | 16 | Primary BMAP Area | 189 | N/A | N/A | City | Not provided | N/A
3268 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-28 | City of Port St. Lucie | N/A | PSL-28 | Streamlet/Manth Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 33 | 6 | Primary BMAP Area | 89 | N/A | N/A | City | Not provided | N/A
3267 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-29 | City of Port St. Lucie | N/A | PSL-29 | Walters Basin | Installation of 2nd-generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 140 | 25 | Primary BMAP Area | 32 | N/A | N/A | City | Not provided | N/A
3266 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-30 | City of Port St. Lucie | DEP/ SLWSD | PSL-30 | SLWSD Water Management Improvement Project | Increase storage of existing wetland. | Wet Detention Pond | Completed | 2016 | 454 | 326 | Primary BMAP Area | 140 | 360704 | 8200 | DEP/ SLWSD | DEP - $159,658/ SLWSD - $201,046 | S0812
3265 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-31 | City of Port St. Lucie | DEP/ SFWMD | PSL-31 | McCarty Ranch Extension Phases I - VI | Water Farming Project – Pumps water from SFWMD C-23 Canal onto property for storage and retains rainfall on multiple phases of project. | Dispersed Water Management (DWM) | Underway | 2023 | TBD | TBD | Primary BMAP Area | TBD | 3663383 | 180640 | City/ DEP/ SFWMD | Not provided | NF028
3264 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-32 | City of Port St. Lucie | N/A | PSL-32 | Veterans Memorial Water Quality Retrofit | Installing control structures, digging ponds, and increasing storage. | BMP Treatment Train | Underway | 2025 | 2961 | 1005 | Primary BMAP Area | 1065 | 3834193 | N/A | City/ SFWMD | SFWMD - $125,000 | N/A
3263 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-PSL-33 | City of Port St. Lucie | SLWSD | PSL-33 | Lake Harvey | Construction of 4.41-acre wetland area and 2.25-acre flow-way to enhance water quality, storage, and hydraulic connectivity in SLWSD Basin 4E. | Hydrologic Restoration | Completed | 2017 | 20 | 6 | Primary BMAP Area | 333 | 534000 | 15500 | SLWSD | Not provided | N/A
3255 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-01 | City of Stuart | DEP/ SFWMD/ Healthy Rivers/ Florida Communities Trust (FCT) | S-01 | Poppleton Creek – Phase II and III | Muck sediment removal, creation of 6.5-acre retention pond, and 160-foot weir. Habitat reconstruction; passive recreational improvements. 4 continuous deflective seperation (CDS) baffle box units and street sweeping in basin. | BMP Treatment Train | Completed | 2008 | 1299 | 576 | Primary BMAP Area | 629 | 4371250 | Not provided | DEP/ SFWMD/ Healthy Rivers/ FCT | Not provided | S0278/ G0083
3254 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-02 | City of Stuart | SFWMD/ Federal Emergency Management Agency (FEMA)/Martin County | S-02 | Airport Ditch Project | Conversion of 2 uncontrolled drainage ditches to tide into retention/detention facilities controlled by "v" notch weirs. | On-line Retention BMPs | Completed | 2003 | 900 | 532 | Primary BMAP Area | 894 | 766756 | Not provided | SFWMD/ FEMA/ Martin County | Not provided | N/A
3253 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-03 | City of Stuart | SFWMD | S-03 | Crescent Basin Project | Stormwater retention through three first generation baffle boxes. | On-line Retention BMPs | Completed | 2003 | 198 | 42 | Primary BMAP Area | 59 | 180000 | Not provided | City/ SFWMD | Not provided | N/A
3252 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-04 | City of Stuart | DEP/ SFWMD | S-04 | Krueger Creek Project | Removal of "ooze" sediments and installation of 4 baffle boxes plus 2 CDS units in 2010. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2001 | 7 | 7 | Primary BMAP Area | 310 | 432000 | Not provided | City/ SFWMD/ DEP | Not provided | WAP015/ G0083
3258 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-05 | City of Stuart | N/A | S-05 | Street Sweeping | Pavement cleaning by sweeping, vacuum, or washing. | Street Sweeping | Completed | N/A | 111 | 71 | Primary BMAP Area | N/A | 33000 | Not provided | City | Not provided | N/A
3221 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-06 | City of Stuart | N/A | S-06 | Sediment Removal from Storm Systems | Removal and proper disposal of sediment captured by catch basin inserts. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 97 | 59 | Primary BMAP Area | N/A | N/A | 75000 | City | Not provided | N/A
3228 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-07 | City of Stuart | N/A | S-07 | Education Program | FYN Program. City ordinances for landscaping, irrigation, fertilizer, and pet waste management. City stormwater website. Stormwater calendars. Pollution prevention information posted on electronic billboards 365 days/year from 12 PM to 1 PM. | Education Efforts | Completed | N/A | 840 | 186 | Primary BMAP Area | N/A | 30150 | Not provided | City | Not provided | N/A
3231 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-08 | City of Stuart | SFWMD/ Healthy Rivers | S-08 | North Point CRA Drainage Basin | There is 1 existing 1st-generation baffle box and street sweeping in basin, existing FDOT swale along basin's east boundary, and 2 FDOT retention/detention ponds near the Roosevelt Bridge. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 24 | 23 | Primary BMAP Area | 1084 | 1339000 | Not provided | City/ SFWMD/ Healthy Rivers | Not provided | N/A
3232 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-09 | City of Stuart | DEP/ Florida Inland Navigation District (FIND)/ Healthy Rivers | S-09 | Anchorage Drainage Basin | There is 1 existing 1st-generation baffle box and 3 FDOT dry detention ponds in basin. Ponds receive runoff from roadways and portion of Roosevelt Bridge. Street swept in basin. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 1 | 0 | Primary BMAP Area | 21 | 766500 | Not provided | City/ DEP/ FIND/ Healthy Rivers | Not provided | Not provided
3233 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-10 | City of Stuart | DEP | S-10 | Downtown Drainage Basin | Drainage basin contains 4 1st-generation baffle boxes and 4 CDS units installed between 2000 and 2012; 3 catch basin filter baskets installed in 2010-11. Streets swept 12 times per month. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 2 | 2 | Primary BMAP Area | 117 | 275000 | Not provided | City/ DEP | Not provided | G0083
3234 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-11 | City of Stuart | DEP | S-11 | Hildebrad Basin | 1 CDS unit and 7 catch basin filter baskets installed in 2010-11; includes street sweeping in basin. | Hydrodynamic Separators | Completed | 2009 | 0 | 6 | Primary BMAP Area | 67 | 388480 | Not provided | City/ DEP | Not provided | G0083
3248 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-12 | City of Stuart | N/A | S-12 | Landfill Basin | Landfill closed; ongoing groundwater monitoring, zero discharge. Closed basin with no outfall. | 100% On-site Retention | Completed | 2013 | 167 | 26 | Primary BMAP Area | 71 | 29144 | Not provided | City | Not provided | N/A
3227 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-13 | City of Stuart | N/A | S-13 | South Fork Drainage Basin | There are 2 1st-generation baffle boxes in northwest portion of basin and 1 unimproved ditch along south side of SE Ruhnkee St. that flows to wooded area on west side of basin boundary within city jurisdiction. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 16 | 16 | Primary BMAP Area | 663 | Not provided | Not provided | City | Not provided | N/A
3226 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-14 | City of Stuart | DEP | S-14 | Neighborhood Initiated Sewer Expansion Program | Sewer expansion program to phase out septic tanks by expanding sewer service into areas of city using low pressure sewer system piping along road rights-of-way and individual residential grinder pump station at each home. | OSTDS Phase Out | Completed | 2013 | 1341 | N/A | Primary BMAP Area | N/A | 3200000 | Not provided | City/ DEP | Not provided | S0793/ S0821
3225 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-15 | City of Stuart | N/A | S-15 | Eldorado Heights | Area of land within the south-central area of Stuart city limits that does not discharge to surface waterbody or adjacent basin. | Closed Basin | Completed | 2012 | 134 | 27 | Primary BMAP Area | 30 | 779000 | Not provided | City | Not provided | N/A
3224 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-16 | City of Stuart | Martin Memorial Health Systems/ SFWMD | S-16 | Amerigo Avenue Drainage Improvements | Construction of dry retention areas to eliminate street flooding, provide water quality treatment, and TMDL reductions. | Dry Detention Pond | Completed | 2014 | 37 | 7 | Primary BMAP Area | 10 | 679557 | Not provided | City/ Martin Memorial Health Systems/ SFWMD | Not provided | N/A
3222 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-17 | City of Stuart | Martin County/ Healthy Rivers/ FCT/ DEP | S-17 | Haney Creek Project – Phase I - IV | Creation of flow-through marsh and multiple wetlands and control structures to address stormwater quality, environmental restoration and preservation, greenways, passive recreation, and environmental education. | Filter Marsh | Completed | 2016 | 513 | 207 | Primary BMAP Area | 626 | 4831411 | 9600 | Martin County/ Healthy Rivers/ FCT/ DEP | Not provided | WAP031
3229 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-18 | City of Stuart | N/A | S-18 | Nondischarge Areas | Area within eastern city limits with no stormwater infrastructure and no outfalls discharging to adjacent basin. | Non-contributing Basin | Completed | 2014 | 1038 | 233 | Primary BMAP Area | 218 | N/A | N/A | City | Not provided | N/A
3220 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-19 | City of Stuart | DEP | S-19 | Baffle Boxes (22) Throughout City | Concrete structures containing a series of sediment settling chambers separated by baffles. Boxes are vacuum cleaned base on sediment depth inspection by city stormwater staff. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2014 | 11 | 11 | Primary BMAP Area | 475 | N/A | Not provided | City/ DEP | Not provided | G0083
3219 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-20 | City of Stuart | DEP | S-20 | CDS Units Throughout City | Hydrodynamic separators that capture, sediment, trap debris, and separate floating oils from runoff. CDS units are vacuum cleaned based on sediment depth inspections by city stormwater staff. | Hydrodynamic Separators | Completed | 2014 | 0 | 6 | Primary BMAP Area | 66 | N/A | Not provided | City/ DEP | Not provided | G0083
3218 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-21 | City of Stuart | N/A | S-21 | SW South Carolina Dr. Drainage Project | Installation of a stormwater conveyance system and 1st-generation baffle box in a residential area to eliminate unrestricted sheet flow to St. Lucie River. | Stormwater System Rehabilitation | Completed | 2016 | TBD | TBD | Primary BMAP Area | 3 | 100936 | Not provided | City | Not provided | N/A
3217 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-22 | City of Stuart | DEP | S-22 | Poppleton Creek Tidal Wetlands Creation and Restoration | Construct tidal red mangrove wetlands on 4.3 acres of city-owned property south of and adjacent to Poppleton Creek east of Palm City Rd. Project will clear exotic vegetation and create tidal wetlands. | Wetland Restoration | Completed | 2018 | TBD | TBD | Primary BMAP Area | 525 | 270200 | TBD | City/ DEP | Not provided | G0363
3216 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-23 | City of Stuart | DEP | S-23 | East Heart of Haney Creek Wetlands Restoration | Restore eastern third of Heart of Haney Creek to wetlands by creating system of berms and weirs within 6 acres of exotic cleared area. | Wetland Restoration | Underway | 2019 | TBD | TBD | Primary BMAP Area | 395 | 220000 | TBD | City/ DEP | DEP - $90,000/ City - $110,000 | S0891
3215 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-S-24 | City of Stuart | DEP/ Healthy Rivers | S-24 | Frazier Creek Pond | Construction of wet detention pond to eliminate unrestricted flow from ditch to tide. | Wet Detention Pond | Completed | 2002 | TBD | TBD | Primary BMAP Area | 379 | 1702000 | Not provided | City/ DEP/ Healthy Rivers | Not provided | WAP016
3214 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-001a | St. Lucie County MS4 | N/A | SLC-001a | Platt’s Creek Stormwater Treatment Facility | Wet detention with alum injection. | Wet Detention Pond | Completed | 2008 | 676 | 306 | Primary BMAP Area | 311 | 3539475 | Not provided | County | Not provided | N/A
3418 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-001b | St. Lucie County Non-MS4 | N/A | SLC-001b | Platt’s Creek Stormwater Treatment Facility | Not provided. | Wet Detention Pond | Completed | 2008 | 907 | 365 | Primary BMAP Area | 564 | N/A | Not provided | Not provided | Not provided | N/A
3392 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-002 | St. Lucie County MS4 | N/A | SLC-002 | Indian River Estates Stormwater Improvements (Phases I and II) | Wet detention with alum injection. | Wet Detention Pond | Completed | 2009 | 1841 | 707 | Primary BMAP Area | 1004 | 4471114 | Not provided | County | Not provided | N/A
3439 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-003 | St. Lucie County MS4 | N/A | SLC-003 | Prima Vista | Not provided. | Baffle Boxes- Second Generation | Completed | 2006 | 76 | 14 | Primary BMAP Area | 97 | 323483 | Not provided | Not provided | Not provided | N/A
3408 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-004 | St. Lucie County MS4 | N/A | SLC-004 | Bay Street | Not provided. | Baffle Boxes- Second Generation | Completed | 2006 | 35 | 6 | Primary BMAP Area | 44 | N/A | Not provided | Not provided | Not provided | N/A
3398 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-005 | St. Lucie County MS4 | N/A | SLC-005 | Education Program | FYN; pet waste, landscape, irrigation, and fertilizer ordinances; PSAs; website; Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program. St.Lucie Water Champions. | Education Efforts | Completed | N/A | 1087 | 248 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3397 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-006 | St. Lucie County MS4 | N/A | SLC-006 | Street Sweeping | Materials are collected from road ways and the gutters using a street sweeper truck. | Street Sweeping | Completed | N/A | 211 | 135 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3396 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-007 | St. Lucie County MS4 | N/A | SLC-007 | Catch Basin Cleanout | Catch basins are cleaned out on a rotational basis using a vactruck. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 170 | 105 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3395 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-008 | St. Lucie County MS4 | N/A | SLC-008 | Platt's Creek Sump Cleanout | Not provided. | BMP Cleanout | Completed | N/A | 1182 | 512 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3394 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-009 | St. Lucie County Non-MS4 | DEP | SLC-009 | White City – Citrus/Seager Stormwater Improvement | Wet detention with polyacrylamide logs. | Wet Detention Pond | Completed | 2016 | 71 | 26 | Primary BMAP Area | 39 | 1862859 | Not provided | DEP/ County | Not provided | G0382
3416 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-010 | St. Lucie County Non-MS4 | N/A | SLC-010 | Education Program | FYN; pet waste, landscape, irrigation, and fertilizer ordinances; PSAs; website; Illicit Discharge Program, Eco-Center, Clean Stormwater–Clean River Program, St.Lucie Water Champions. | Education Efforts | Completed | N/A | 1426 | 364 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3399 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-011 | St. Lucie County Non-MS4 | N/A | SLC-011 | Street Sweeping | Materials are collected from road ways and the gutters using a street sweeper truck. | Street Sweeping | Completed | N/A | 113 | 73 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3401 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-012 | St. Lucie County Non-MS4 | N/A | SLC-012 | Catch Basin Cleanout | Catch basins are cleaned out on a rotational basis using a vactruck. | BMP Cleanout | Completed | N/A | 92 | 56 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3424 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-013 | St. Lucie County Non-MS4 | N/A | SLC-013 | Platt's Creek Sump Cleanout | Not provided. | BMP Cleanout | Completed | N/A | 1566 | 601 | Primary BMAP Area | N/A | Not provided | Not provided | Not provided | Not provided | N/A
3423 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-014 | St. Lucie County MS4 | City of Port St. Lucie | SLC-014 | Platt’s Creek Compensatory Mitigation Project | Not provided. | Floodplain Restoration | Completed | 2015 | Not provided | Not provided | Primary BMAP Area | 311 | 2600000 | Not provided | Not provided | Not provided | N/A
3422 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-015 | St. Lucie County Non-MS4 | N/A | SLC-015 | IRL South C23/C24 Comprehensive Everglades Restoration Program (CERP) Buffer – Teague Preserve Re-watering Project | Not provided. | Hydrologic Restoration | Underway | Not provided | TBD | TBD | Primary BMAP Area | TBD | 400000 | TBD | Not provided | Not provided | N/A
3421 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-016 | St. Lucie County Non-MS4 | N/A | SLC-016 | Melville Rd. Master Drainage Plan | Not provided. | Stormwater System Rehabilitation | Underway | 2024 | TBD | TBD | Primary BMAP Area | 175 | 5000000 | TBD | County | Not provided | N/A
4594 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-017 | St. Lucie County MS4 | N/A | SLC-017 | Swales Material Collection | Road side swale cleanout and retrofitting. | BMP Cleanout | Completed | N/A | TBD | TBD | Primary BMAP Area | Not provided | Not provided | Not provided | Not provided | Not provided | N/A
4595 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SLC-018 | St. Lucie County Non-MS4 | N/A | SLC-018 | Swales Material Collection | Road side swale cleanout and retrofitting. | BMP Cleanout | Completed | N/A | TBD | TBD | Primary BMAP Area | Not provided | Not provided | Not provided | Not provided | Not provided | N/A
3420 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-01 | Town of Sewall's Point | SFWMD | SP-01 | Ridgeland Court Retrofit | Installation of exfiltration/baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 0 | 0 | Primary BMAP Area | 6 | Not provided | 300000 | Town/SFWMD | Not provided | N/A
3419 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-02 | Town of Sewall's Point | SFWMD | SP-02 | Palm Court/Knowles | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | 0 | 0 | Primary BMAP Area | 13 | Not provided | N/A | Town/SFWMD | Not provided | N/A
3409 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-03 | Town of Sewall's Point | SFWMD | SP-03 | Captain Cove | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | 0 | 0 | Primary BMAP Area | 5 | Not provided | N/A | Town/SFWMD | Not provided | N/A
3417 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-04 | Town of Sewall's Point | SFWMD | SP-04 | Quail Run Park | Installation of direct link to a detention area prior to discharge to Indian River. | Dry Detention Pond | Completed | 2000 | 0 | 0 | Primary BMAP Area | 0 | Not provided | N/A | Town/SFWMD | Not provided | N/A
3425 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-05 | Town of Sewall's Point | N/A | SP-05 | Heritage Park | Installation of stormwater retrofit area in developed subdivision. | Stormwater System Rehabilitation | Completed | 2000 | 7 | 2 | Primary BMAP Area | 5 | Not provided | N/A | Town | Not provided | N/A
3288 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-06 | Town of Sewall's Point | SFWMD | SP-06 | Via Lucindia | Installation of exfiltration pipe. | Exfiltration Trench | Completed | 2000 | 8 | 2 | Primary BMAP Area | 3 | Not provided | N/A | Town/SFWMD | Not provided | N/A
3415 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-07 | Town of Sewall's Point | SFWMD | SP-07 | Rio Vista Park | Installation of baffle boxes/ erosion control for outfall to Indian River. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 1 | 1 | Primary BMAP Area | 24 | Not provided | N/A | Town/SFWMD | Not provided | N/A
3315 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-08 | Town of Sewall's Point | N/A | SP-08 | India Lucie | Installation of retrofit of weir/ retention area with 2 baffle boxes in old subdivision without retention to directly discharge to Indian River. | Stormwater System Rehabilitation | Completed | 2003 | 44 | 18 | Primary BMAP Area | 31 | Not provided | N/A | Martin County | Not provided | N/A
3413 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-09 | Town of Sewall's Point | FEMA | SP-09 | India Lucie | Installation of retrofit of weir/ retention area with 2 baffle boxes in old subdivision without retention to directly discharge to Indian River. | Stormwater System Rehabilitation | Completed | 2006 | 0 | 0 | Primary BMAP Area | 6 | Not provided | N/A | Town/ FEMA | Not provided | N/A
3412 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-10 | Town of Sewall's Point | SFWMD | SP-10 | Periwinkle | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | 0 | 0 | Primary BMAP Area | 16 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3213 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-11 | Town of Sewall's Point | N/A | SP-11 | Palm Road | Installation of grass swales. | Grass swales without swale blocks or raised culverts | Completed | 2008 | 1 | 0 | Primary BMAP Area | 1 | Not provided | N/A | Town | Not provided | N/A
3238 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-12 | Town of Sewall's Point | SFWMD | SP-12 | Riverview | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 0 | 0 | Primary BMAP Area | 10 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3240 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-13 | Town of Sewall's Point | N/A | SP-13 | Pineapple Lane | Installation of outfall exfiltration. | Exfiltration Trench | Completed | 2002 | 0 | 0 | Primary BMAP Area | 6 | Not provided | N/A | Town | Not provided | N/A
3223 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-14 | Town of Sewall's Point | TOSP | SP-14 | Copaire | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | 0 | 0 | Primary BMAP Area | 2 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3247 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-15 | Town of Sewall's Point | TOSP | SP-15 | Homewood Park/South Sewall's Point Road | Installation of retention area with pervious Flexi-Pave and exfiltration pipe. | On-line Retention BMPs | Completed | 2009 | 46 | 10 | Primary BMAP Area | 14 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3246 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-16 | Town of Sewall's Point | DEP/ SFWMD | SP-16 | Pedway/ Greenway | Installation of exfiltration/ pervious paver sidewalk. | BMP Treatment Train | Completed | 2014 | 6 | 1 | Primary BMAP Area | 2 | Not provided | N/A | Town/ DEP/ SFWMD | Not provided | G0333
3245 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-17 | Town of Sewall's Point | FDOT | SP-17 | State Road A1A | Installation of outfall exfiltration. | Exfiltration Trench | Completed | 2012 | 52 | 10 | Primary BMAP Area | 12 | Not provided | N/A | FDOT | Not provided | N/A
3244 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-18 | Town of Sewall's Point | N/A | SP-18 | Education Program | Fertilizer ordinance. | Education Efforts | Completed | N/A | 9 | 2 | Primary BMAP Area | N/A | N/A | N/A | Town | N/A | N/A
3243 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-19 | Town of Sewall's Point | N/A | SP-19 | Street Sweeping | 19 cubic yards of debris collected through street sweeping. | Street Sweeping | Completed | N/A | 25 | 16 | Primary BMAP Area | N/A | Not provided | N/A | Town | N/A | N/A
3242 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-20 | Town of Sewall's Point | N/A | SP-20 | Delano Lane | Installation of exfiltration system. | Exfiltration Trench | Completed | 2000 | TBD | TBD | Special Project BMAP Area | 1 | Not provided | N/A | Town | Not provided | N/A
3241 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-21 | Town of Sewall's Point | N/A | SP-21 | Town Commons Park | Installation of water quality treatment/dry detention. | Dry Detention Pond | Completed | 2002 | TBD | TBD | Special Project BMAP Area | 1 | Not provided | N/A | Town | Not provided | N/A
3230 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-22 | Town of Sewall's Point | N/A | SP-22 | Island Road | Installation of exfiltration pipe with baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2002 | TBD | TBD | Special Project BMAP Area | 5 | Not provided | N/A | Town | Not provided | N/A
3239 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-23 | Town of Sewall's Point | SFWMD | SP-23 | Highpoint West | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | TBD | TBD | Special Project BMAP Area | 8 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3249 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-24 | Town of Sewall's Point | SFWMD | SP-24 | Mandalay (Marguerita) | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | TBD | TBD | Special Project BMAP Area | 15 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3237 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-25 | Town of Sewall's Point | SFWMD | SP-25 | Highpoint East | Installation of baffle box. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 2000 | TBD | TBD | Special Project BMAP Area | 16 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3236 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-26 | Town of Sewall's Point | SFWMD | SP-26 | High Point Exfiltration | Installation of exfiltration/swales. | BMP Treatment Train | Completed | 2014 | TBD | TBD | Special Project BMAP Area | 6 | Not provided | N/A | Town/ SFWMD | Not provided | N/A
3235 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-27 | Town of Sewall's Point | N/A | SP-27 | Extend Pedway/Greenway | Extension of existing pervious pedway by 9,000 LF to include pervious pavers and exfiltration. | BMP Treatment Train | Completed | 2016 | 16 | 109 | Special Project BMAP Area | 28 | 201483 | N/A | Town | Not provided | N/A
3272 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-28 | Town of Sewall's Point | DEP/ SFWMD | SP-28 | South Sewell's Point Road - Phase 1 Mandalay (Marguerita) | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Underway | TBD | TBD | TBD | Special Project BMAP Area | 21 | 2000000 | N/A | Town/ DEP/ SFWMD | Town - $1,400,000/ DEP - $600,000 | NS029
3275 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-29 | Town of Sewall's Point | N/A | SP-29 | Baffle Boxes | Installation of baffle boxes in various locations. | Baffle Boxes- First Generation (hydrodynamic separator) | Underway | TBD | TBD | TBD | Special Project BMAP Area | 18 | 315000 | N/A | Town | TBD | N/A
3286 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-30 | Town of Sewall's Point | N/A | SP-30 | Indialucie | Installation of exfiltration system in wet retention area. | Exfiltration Trench | Completed | 2014 | 62 | 8 | Primary BMAP Area | 31 | Not provided | N/A | Town | Not provided | N/A
3277 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-31 | Town of Sewall's Point | N/A | SP-31 | Quail Run Subdivision | Installation of exfiltration/swales. | BMP Treatment Train | Completed | 2015 | TBD | TBD | Primary BMAP Area | 4 | Not provided | N/A | Town | Not provided | N/A
3271 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-32 | Town of Sewall's Point | N/A | SP-32 | Septic Tank Elimination - Phase I | Conversion of existing septic tanks to sanitary sewer. | OSTDS Phase Out | Planned | TBD | TBD | N/A | Primary BMAP Area | 17 | 500000 | N/A | Town/ Florida Legislature | Not provided | N/A
4596 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-33 | Town of Sewall's Point | TBD | SP-33 | Outfall Control Structures | Add Control Structures | Stormwater System Rehabilitation | Underway | TBD | TBD | TBD | Primary BMAP Area | TBD | 500000 | N/A | Town | TBD | TBD
4597 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-34 | Town of Sewall's Point | TBD | SP-34 | South Sewall's Point Road - Phase 2 | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Planned | TBD | TBD | TBD | Primary BMAP Area | 64 | TBD | N/A | Town | TBD | TBD
4598 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-35 | Town of Sewall's Point | TBD | SP-35 | South Sewall's Point Road - Phase 3 | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Planned | TBD | TBD | TBD | Primary BMAP Area | TBD | TBD | N/A | Town | TBD | TBD
4599 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-SP-36 | Town of Sewall's Point | TBD | SP-36 | South Sewall's Point Road - Phase 4 | Installation of exfiltration system/baffle boxes and STA. | BMP Treatment Train | Planned | TBD | TBD | TBD | Primary BMAP Area | TBD | TBD | N/A | Town | TBD | TBD
3278 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-T-01 | Turnpike Authority | N/A | T-01 | Project 420735-1 Port St. Lucie Interchange Pond A | Not provided. | Dry Detention Pond | Completed | 2013 | 2 | 0 | Primary BMAP Area | 4 | Not provided | N/A | Not provided | Not provided | N/A
3279 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-T-02 | Turnpike Authority | N/A | T-02 | Project 420735-1 Port St. Lucie Interchange Pond B | Not provided. | Wet Detention Pond | Completed | 2013 | 16 | 2 | Primary BMAP Area | 21 | Not provided | N/A | Not provided | Not provided | N/A
3280 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-T-03 | Turnpike Authority | N/A | T-03 | Thomas B. Manuel Bridge North Pond | Not provided. | Dry Detention Pond | Completed | 2013 | 5 | 1 | Primary BMAP Area | 10 | Not provided | N/A | Not provided | Not provided | N/A
3281 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-T-04 | Turnpike Authority | N/A | T-04 | Education Program | No fertilizer on rights-of-way, educational signage, illicit discharge training. | Education Efforts | Completed | N/A | TBD | TBD | Primary BMAP Area | N/A | Not provided | N/A | Not provided | Not provided | N/A
3283 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-T-05 | Turnpike Authority | N/A | T-05 | Street Sweeping | 1,944 lane miles swept and 28,323 lbs (or 12,847 kg) of debris collected. | Street Sweeping | Completed | N/A | 144 | 10 | Primary BMAP Area | N/A | Not provided | N/A | Not provided | Not provided | N/A
3284 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-TI-01 | Troup-Indiantown WCD | N/A | TI-01 | C-44 Conservation Area | Not provided. | Land Preservation | Completed | 2013 | 23199 | 7497 | Primary BMAP Area | 9135 | N/A | N/A | Not provided | Not provided | N/A
3285 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-TI-02 | Troup-Indiantown WCD | N/A | TI-02 | 90% Implementation Agricultural BMPs | Not provided. | Agricultural BMPs | Completed | 2013 | 1856 | 446 | Primary BMAP Area | N/A | N/A | N/A | Not provided | Not provided | N/A
3261 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-TI-03 | Troup-Indiantown WCD | N/A | TI-03 | Removal of Drainage Areas | Minute Maid Rd. drainage improvements. | 100% On-Site Retention | Completed | 2013 | TBD | TBD | Primary BMAP Area | 73 | 124000 | N/A | WCD | Not provided | N/A
3259 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-TI-04 | Troup-Indiantown WCD | SFWMD/ USACE | TI-04 | C-44 Reservoir Area | Converting from conservation area to reservoir. | Land Use Change | Underway | 2018 | N/A | N/A | Primary BMAP Area | 3485 | N/A | N/A | USACE | Not provided | N/A
3276 | 2013-06-11 | Adopted | Northern Everglades | STLU | STLU-TI-05 | Troup-Indiantown WCD | SFWMD/ USACE | TI-05 | C-44 STA Area | Converting from conservation area to STA. | Land Use Change | Underway | 2018 | N/A | N/A | Primary BMAP Area | 6100 | N/A | N/A | SFMWD | Not provided | N/A