## Intro
DROPDOWN MENUS
Project Type |  | Project Status | Location | Yes
100% On-site Retention | Structural | Planned | PFA | No
Agricultural BMPs | Non-structural | Underway | Inside Springshed | N/A
Alum Injection Systems | Trade | Completed | Not Provided
Aquatic Vegetation Harvesting |  | Cancelled | TBD
Baffle Boxes- First Generation (hydrodynamic separator)
Baffle Boxes- Second Generation
Baffle Boxes- Second Generation with Media
Biological/ Bacteria Treatment
Biosorption Activated Media (BAM)
Bioswales
BMP Cleanout
BMP Treatment Train
Catch Basin Inserts/Inlet Filter Cleanout
Closed Basin
Control Structure
Creating/ Enhancing Living Shoreline
Creating/ Enhancing Oyster Reefs
Credit Trade
Dairy Remediation
Decommission/ Abandonment
Deep Injection Well
Denitrification Walls
Dispersed Water Management (DWM)
Dry Detention Pond
Education Efforts
Enhanced Public Education
Exfiltration Trench
Exotic Vegetation Removal
Fertilizer Cessation
Fertilizer Reduction
Filter Marsh
Fish Harvesting
Floating Islands/ Managed Aquatic Plant Systems (MAPS)
Floodplain Restoration
Golf Course or Sports Field BMPs
Grass swales with swale blocks or raised culverts
Grass swales without swale blocks or raised culverts
Hybrid wetland treatment technology (HWTT)
Hydrodynamic Separators
Hydrologic Restoration
Impoundment
Industrial Facility Upgrades
Land Acquisition
Land Preservation
Land Use Change
LID- Green Roofs
LID- Other
LID- Rain Gardens
LID- Tree Boxes/Tree Wells
Macroalgal Harvesting
Monitoring/Data Collection
Muck Removal/Restoration Dredging
Natural Wetlands as Filters
Non-contributing Basin
Off-line Retention BMPs
On-line Retention BMPs
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement
OSTDS Phase Out
Pervious Pavement
Pervious Pavers
Plugging Artesian Wells
Reclaimed Water
Regional Stormwater Treatment
Regulations, Ordinances, and Guidelines
Retention/Detention BMP Retrofit with Nutrient Reducing Media
Retention/Detention BMP with Nutrient Reducing Media
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance
Sanitary Sewer Inspections
SAV Planting
Shoreline Stabilization
Stormwater Aeration System
Stormwater Reuse
Stormwater System Rehabilitation
Stormwater Treatment Areas (STAs)
Street Sweeping
Study
Turbidity Reducing Polymers (e.g., Floc logs ®)
Vegetated Buffers
Wastewater Service Area Expansion
Wet Detention Pond
Wetland Restoration
Wetland Treatment
WWTF Disposal Site
WWTF Diversion to Reuse
WWTF Nutrient Reduction
WWTF Upgrade
FIB- Stormwater
FIB- Source Identification Activities
FIB- Sanitary Sewer
FIB- OSTDS
FIB- Trash Cleanup of Impaired Waterbody

## Gemini All Projects
ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | Structural, Non-structural, or Trade | (Original) Project Status | Year Added | Attachments | BMAP | Latitude | Longitude | Start Date | Nitrogen Source Addressed by Project | 2019 STAR Priority Projects (1-5)
5079 | City of Sanford | N/A | SAN-001 | Street Sweeping | Street sweeping throughout the city. | Street Sweeping | Completed | N/A | 187.4158 | 399.33 | Inside Springshed | N/A | N/A | 17054.4 | City/Stormwater Utility | N/A | N/A | Non-structural | Ongoing | 2018 | N/A | Gemini Springs | N/A | N/A | Ongoing | UTF
5080 | City of Sanford | Seminole County | SAN-002 | Education Efforts | FYN, landscaping ordinance, irrigation ordinance, PSAs, pamphlets, website, Illicit Discharge Program. | Education Efforts | Completed | N/A | 111.4232 | N/A | Inside Springshed | N/A | N/A | TBD | City/Stormwater Utility | N/A | N/A | Non-structural | Ongoing | 2018 | N/A | Gemini Springs | N/A | N/A | Ongoing | UTF
5081 | City of DeBary | N/A | DB-01 | Fertilizer Ordinance | Citywide fertilizer ordinance to reduce application. | Regulations, Ordinances, and Guidelines | Completed | N/A | 25 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Ongoing | 2018 | Copy of the revised ordinance | Gemini Springs | N/A | N/A | Ongoing | UTF
5082 | City of DeBary | N/A | DB-02 | Illicit Discharge Education | Website, pamphlets, inspection program, call-in number. | Education Efforts | Completed | N/A | 50 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Ongoing | 2018 | City website link, PDFs | Gemini Springs | N/A | N/A | Ongoing | UTF
5083 | City of DeBary | N/A | DB-03 | Irrigation Ordinance | Citywide restrictions on irrigation practices. | Regulations, Ordinances, and Guidelines | Completed | N/A | 25 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Ongoing | 2018 | Copy of Ordinance | Gemini Springs | N/A | N/A | Ongoing | UTF
5084 | City of DeBary | Volusia County/ SJRWMD/ DEP | DB-04 | Gemini Springs Septic Tank Abatement Program | Phase I: 360 septic tanks will be removed and converted to central sewer during the first 5 years (overall 1,200 septic tanks will be converted in the next 15 years). | OSTDS Phase Out | Planned | 2025 | 3301 | N/A | PFA | 360 | 9720000 | 10000 | City of DeBary/ Volusia County/ TBD | TBD | TBD | Structural | Planned | 2018 | Copy of 4/4/2018 City Council Meeting Minutes approving the Program and PowerPoint Presentation | Gemini Springs | N/A | N/A | TBD | OSTDS
5085 | FDOT District 5 | N/A | FDOT-01 | SR 46 | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2012 | 6.9304 | 7.4 | Inside Springshed | 48.2 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.8114 | -81.3588 | Not provided | UTF
5086 | FDOT District 5 | N/A | FDOT-02 | 77160-3404-02 (Pond 1-NW) | On-line retention BMPs. Completion date of project outside the project collection period. No credit assigned. | On-line Retention BMPs | Completed | 2004 | N/A | N/A | Inside Springshed | 25.5 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.7534 | -81.3632 | 2004 | UTF
5087 | FDOT District 5 | N/A | FDOT-03 | 77160-3404-06 (Pond 4-11) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 38.5 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.8221 | -81.3383 | 2004 | UTF
5088 | FDOT District 5 | N/A | FDOT-04 | 77160-3404-05 (Pond 4-1) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 32.4 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.817 | -81.3338 | 2004 | UTF
5089 | FDOT District 5 | N/A | FDOT-05 | 77160-3404-07 (Pond 5) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 30.5 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.8237 | -81.3281 | 2004 | UTF
5090 | FDOT District 5 | N/A | FDOT-06 | 77160 3436 (pond A, A-1) | Wet detention pond. | Wet Detention Pond | Completed | 2012 | 31.1655 | 19.8 | Inside Springshed | 56.5 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.785 | -81.3528 | 2000 | UTF
5091 | FDOT District 5 | N/A | FDOT-07 | 77160-3439-01 (Pond 1) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2006 | N/A | N/A | Inside Springshed | 20.3 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.7831 | -81.3532 | 2010 | UTF
5092 | FDOT District 5 | N/A | FDOT-08 | FM 242702 79110-3403-06 (RR-3) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 53.1 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.8468 | -81.3127 | 2001 | UTF
5093 | FDOT District 5 | N/A | FDOT-08a | FM 242702 79110-3403-04 & 05 (Pond QQ3 & QQ-5)(RR-3) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 47.6 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Completed | 2018 | Provided during BMAP Development | Gemini Springs | 28.9475 | -81.252 | 2001 | UTF
5094 | FDOT District 5 | N/A | FDOT-09 | FM 437100-1 Dry Detention Pond | The project entails construction of a new state-of-the-art Regional Transportation Management Center (RTMC) for the Florida Department of Transportation and the Florida Highway Patrol Dispatch. There is a pond being built with the project. | On-line Retention BMPs | Underway | 2020 | 0.06 | 0 | Inside Springshed | 6.61 | Not provided | Not provided | Florida Legislature | N/A | N/A | Structural | Underway | 2018 | Not provided | Gemini Springs | 28.8006 | -81.345 | 2017 | UTF
5095 | City of Lake Mary | N/A | LM-01 | Fertilizer ordinance | Fertilizer ordinance. | Regulations, Ordinances, and Guidelines | Completed | N/A | 17 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Completed | 2018 | Ordinance | Gemini Springs | N/A | N/A | 2017 | UTF
5096 | Seminole County | Not provided | SC-01 | Elder RSF | RSF to collect and treat stormwater runoff. Completion daate of project is outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2007 | N/A | N/A | Not provided | 229.7 | 3884496 | 19251 | Not provided | Not provided | N/A | Structural | Completed | 2018 | Not provided | Gemini Springs | Not provided | Not provided | Not provided | UTF
5097 | Seminole County | Not provided | SC-02 | Lockhart Smith RSF | RSF to collect and treat stormwater runoff. Completion daate of project is outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2007 | N/A | N/A | Not provided | 2757 | 3504755 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2018 | Not provided | Gemini Springs | Not provided | Not provided | Not provided | UTF
5098 | Seminole County | Not provided | SC-03 | Street Sweeping | Street sweeping throughout the county. | Street Sweeping | Completed | N/A | 9 | 135.1 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2018 | Not provided | Gemini Springs | N/A | N/A | Not provided | UTF
5099 | Seminole County | Not provided | SC-04 | Education Efforts | FYN, landscaping ordinance, irrigation ordinance, pet waste ordinance, PSAs, pamphlets, website, Illicit Discharge Program and standard credit for fertilizer ordinance. | Education Efforts | Completed | N/A | 822.0554 | 282.3 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2018 | Not provided | Gemini Springs | N/A | N/A | Not provided | UTF
5100 | Seminole County | Altamonte/ Casselberry/ Lake Mary/ Longwood/ Oviedo | SC-05 | Seminole County Fertilizer Ordinance | Reduction of nitrogen and phosphorus sources, through public education and restrictions on usage. | Regulations, Ordinances, and Guidelines | Completed | N/A | TBD | Not provided | Inside Springshed | 14267 | 150000 | 65000 | Ad valorem/ FFL | City - $28,000/ County - $37,000 | NF034 | Non-structural | Completed | 2018 | adopted ordinance, leaching calculations | Gemini Springs | N/A | N/A | 2018-10-01 | UTF
5101 | Seminole County | Not provided | SC-06 | Black Bear Wilderness Area | Previous land use = natural land; management focus = preservation, passive recreation; acreage = 1,650. | Land Acquisition | Underway | 2015 | N/A | N/A | Not provided | N/A | Not provided | Not provided | Not provided | Not provided | Not provided | Non-structural | Underway | 2018 | Not provided | Gemini Springs | Not provided | Not provided | Not provided | UTF
5102 | Seminole County | Not provided | SC-07 | Gravity Main Testing and Repairs | Lateral repairs, gravity main repairs, smoke test and seal laterals. | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Completed | Prior to 2015 | N/A | N/A | Inside Springshed | N/A | 401878 | Not provided | Not provided | Not provided | Not provided | Structural | Completed | 2018 | Not provided | Gemini Springs | Not provided | Not provided | Not provided | WWTF
5103 | Seminole County | Not provided | SC-08 | Lift Station Rehab | Seal wet well and rehabilitate lines (Wilson School LS, Breckenridge LS, Stockbridge LS, Lake Forest #5 LS, Buckingham LS, Retreat at Wekiva LS, Aster Farms LS, Bel-Aire #3 LS, Bel-Aire #1 LS, Heathrow Master LS). | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Completed | Prior to 2015 | N/A | N/A | Inside Springshed | N/A | 324353 | Not provided | Not provided | Not provided | Not provided | Structural | Completed | 2018 | Not provided | Gemini Springs | Not provided | Not provided | Not provided | WWTF
5104 | Volusia County | Not provided | VC-01 | Education and Outreach | Public education about fertilizer, wastewater, lawn clippings, pet waste, water conservation. | Education Efforts | Completed | N/A | 0 | 0 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2018 | Not provided | Gemini Springs | N/A | N/A | 2012 | UTF
5105 | Volusia County | Not provided | VC-02 | Street Sweeping | Street sweeping. | Street Sweeping | Completed | N/A | 661.3433 | 2007 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2018 | Not provided | Gemini Springs | N/A | N/A | 2012 | UTF
5106 | Volusia County | Not provided | VC-03 | Lemon Bluff Road | Grass swales without swale blocks or raised culverts. | Grass swales with swale blocks or raised culverts | Completed | 2011 | 1.3945 | 1.1 | Not provided | 1.8 | 145000 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2018 | Not provided | Gemini Springs | Not provided | Not provided | 2012 | UTF
5107 | Volusia County | Not provided | VC-04 | Lemon Bluff Road Ramp | Grass swales without swale blocks or raised culverts. | Grass swales with swale blocks or raised culverts | Completed | 2011 | 0.1479 | 0.1 | Not provided | 0.2 | 55550 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2018 | Not provided | Gemini Springs | Not provided | Not provided | 2012 | UTF
5108 | Volusia County | Not provided | VC-05 | DeBary Avenue Expansion | DeBary Avenue - Doyle Rd. expansion. | Wet Detention Pond | Completed | 2012 | 8.663 | 10.3 | Not provided | 123.3 | Not provided | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2018 | Not provided | Gemini Springs | Not provided | Not provided | 2012 | UTF
5109 | Volusia County | Not provided | VC-06 | Lake Winnemissett Non-contributing Basin | Non-contributing basin, not included in the TMDL model. | Non-contributing Basin | Completed | N/A | 139.0089 | 93.8 | Inside Springshed | 1003.3 | N/A | N/A | N/A | N/A | N/A | Non-structural | Completed | 2018 | Not provided | Gemini Springs | N/A | N/A | 2012 | UTF
5110 | Volusia County | Not provided | VC-07 | Roadside Ditch Cleaning | Ongoing roadside ditch cleaning throughout county. | BMP Cleanout | Completed | N/A | TBD | N/A | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Ongoing | 2018 | Not provided | Gemini Springs | N/A | N/A | 2016 | UTF
5111 | Volusia County | Not provided | VC-08 | Fertilizer ordinance | Fertilizer restrictions including summer ban on nitrogen and phosphorus. | Regulations, Ordinances, and Guidelines | Completed | N/A | 0 | 0 | Inside Springshed | N/A | Not provided | Not provided | Volusia County | Not provided | N/A | Non-structural | Ongoing | 2018 | Not provided | Gemini Springs | N/A | N/A | 2015 | UTF
5112 | FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification - Farm Fertilizer | Enrollment and verification of farm fertilizer BMPs by agricultural producers. Acres Treated based on FDACS December 2019 NOI Enrollment and FSAID VI. Reductions based on efficiencies referenced in the BMAP and 100% NOI Enrollment. | Agricultural BMPs | Underway | N/A | 68 | N/A | Inside Springshed | 34.2087 | TBD | TBD | FDACS | TBD | N/A | Non-structural | Underway | 2018 | Not provided | Gemini Springs | N/A | N/A | 2018 | FF
5113 | FDACS | Agricultural Producers | FDACS-02 | BMP Implementation and Verification - Livestock Waste | Enrollment and verification of livestock waste BMPs by agricultural producers. Acres Treated based on FDACS December 2019 NOI Enrollment and FSAID VI. Reductions based on efficiencies referenced in the BMAP and 100% NOI Enrollment. | Agricultural BMPs | Underway | N/A | 5.8 | N/A | Inside Springshed | 195.757 | TBD | TBD | FDACS | TBD | N/A | Non-structural | Underway | 2018 | Not provided | Gemini Springs | N/A | N/A | 2018 | LW
5114 | Golf Courses | TBD | GC-01 | Golf Course Reduction Credits | 10 % BMP credit on golf course load to groundwater, assuming 100 % BMP implementation by golf course owners. | Fertilizer Reduction | Planned | TBD | 239.652 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Planned | 2018 | Not provided | Gemini Springs | N/A | N/A | 2018 | STF
5115 | Golf Courses | N/A | GC-02 | Golf Course Reduction Credits | 6 % BMP credit on sports field load to groundwater, assuming 100 % BMP implementation. | Fertilizer Reduction | Planned | TBD | 3.6421 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Planned | 2018 | Not provided | Gemini Springs | N/A | N/A | 2018 | STF
5116 | Wastewater Utilities | TBD | WU-01 | WWTF Policy Reductions | Achieved by WWTF policy if implemented BMAP-wide, achieving 3 or 6 mg/L. | WWTF Upgrade | Planned | TBD | 1020 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A | Structural | Planned | 2018 | Not provided | Gemini Springs | N/A | N/A | 2018 | WWTF
5117 | Various | DEP | OSTDS-01 | Enhancement of Existing OSTDS - Voluntary | Upgrade, replacement, modification, addition of effective nitrogen reducing features, initial connection to a central sewer system, or other action to reduce nutrient loading, voluntarily taken by the owner of an OSTDS within the BMAP. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Underway | N/A | TBD | N/A | Inside Springshed | N/A | TBD | N/A | DEP | TBD | TBD | Structural | N/A | 2018 | 2018 BMAP Appendix D | Gemini Springs | N/A | N/A | 2018 | OSTDS
5118 | Various | DEP | OSTDS-02 | Enhancement of Existing OSTDS - Required | Upgrade, replacement, modification, addition of effective nitrogen reducing features, initial connection to a central sewer system, or other action taken to comply with the OSTDS Remediation Plan for the group of systems identified for remediation. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Planned | TBD | TBD | N/A | PFA | N/A | TBD | N/A | DEP | TBD | TBD | Structural | N/A | 2018 | 2018 BMAP Appendix D | Gemini Springs | N/A | N/A | TBD | OSTDS
Note on O2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $17/mile
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prior to project collection period of 2009.
Note on J23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7,421 submitted by stakeholder. Needs to be verified through monitoring.
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lateral repair – 1512 Cherry Rdg., 2067 North Umbria, 169 Killarney Ct., Shadowmoss. Gravity main repair – 844 Preserve Terr., International Dr. and County Road 46A, Lake Rena Dr. Smoke test and seal laterals – Alaqua Lakes, Heathrow Woods # 1 & 2 LS, Lake Forest 1 & 2, Lake Forest 1 & 2. Additional work – Lake Forest 3 & 4, Aster Farms.
Note on J27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Volusia County does not have a UTF load obligation for this springshed. No reduction could be calculated.
Note on J33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40,350 initial reduction submitted by stakeholder. TBD until verified. Credit would be 8,526 lb-N/yr once attenuated and recharged. Confirm what percentage of work was conducted in the springshed and ask Moira whether ditch cleaning is a credit or load to groundwater. Full credit amount was also requested in LHM. Reply: Volusia County has no UTF loading in the SRWB.
Note on J34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Volusia County does not have a UTF load obligation for this springshed. No reduction could be calculated.
Note on I35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FDACS has proposed changing these to N/A. The original completion date had been set to indicate that 100% reductions need to be reached by the end of the BMAP. This was mistakenly listed as 2023 previously and was updated to 2033 in 2019.

## Append Existing 032320
ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber
5079 | City of Sanford | N/A | SAN-001 | Street Sweeping | Street sweeping throughout the city. | Street Sweeping | Completed | N/A | 187.4158 | 399.33 | Inside Springshed | N/A | N/A | 17054.4 | City/Stormwater Utility | N/A | N/A
5080 | City of Sanford | Seminole County | SAN-002 | Education Efforts | FYN, landscaping ordinance, irrigation ordinance, PSAs, pamphlets, website, Illicit Discharge Program. | Education Efforts | Completed | N/A | 111.4232 | N/A | Inside Springshed | N/A | N/A | TBD | City/Stormwater Utility | N/A | N/A
5081 | City of DeBary | N/A | DB-01 | Fertilizer Ordinance | Citywide fertilizer ordinance to reduce application. | Regulations, Ordinances, and Guidelines | Completed | N/A | 25 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A
5082 | City of DeBary | N/A | DB-02 | Illicit Discharge Education | Website, pamphlets, inspection program, call-in number. | Education Efforts | Completed | N/A | 50 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A
5083 | City of DeBary | N/A | DB-03 | Irrigation Ordinance | Citywide restrictions on irrigation practices. | Regulations, Ordinances, and Guidelines | Completed | N/A | 25 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A
5084 | City of DeBary | Volusia County/ SJRWMD/ DEP | DB-04 | Gemini Springs Septic Tank Abatement Program | Phase I: 360 septic tanks will be removed and converted to central sewer during the first 5 years (overall 1,200 septic tanks will be converted in the next 15 years). | OSTDS Phase Out | Planned | 2025 | 3301 | N/A | PFA | 360 | 9720000 | 10000 | City of DeBary/ Volusia County/ TBD | TBD | TBD
5085 | FDOT District 5 | N/A | FDOT-01 | SR 46 | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2012 | 6.9304 | 7.4 | Inside Springshed | 48.2 | Not provided | Not provided | Florida Legislature | N/A | N/A
5086 | FDOT District 5 | N/A | FDOT-02 | 77160-3404-02 (Pond 1-NW) | On-line retention BMPs. Completion date of project outside the project collection period. No credit assigned. | On-line Retention BMPs | Completed | 2004 | N/A | N/A | Inside Springshed | 25.5 | Not provided | Not provided | Florida Legislature | N/A | N/A
5087 | FDOT District 5 | N/A | FDOT-03 | 77160-3404-06 (Pond 4-11) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 38.5 | Not provided | Not provided | Florida Legislature | N/A | N/A
5088 | FDOT District 5 | N/A | FDOT-04 | 77160-3404-05 (Pond 4-1) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 32.4 | Not provided | Not provided | Florida Legislature | N/A | N/A
5089 | FDOT District 5 | N/A | FDOT-05 | 77160-3404-07 (Pond 5) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 30.5 | Not provided | Not provided | Florida Legislature | N/A | N/A
5090 | FDOT District 5 | N/A | FDOT-06 | 77160 3436 (pond A, A-1) | Wet detention pond. | Wet Detention Pond | Completed | 2012 | 31.1655 | 19.8 | Inside Springshed | 56.5 | Not provided | Not provided | Florida Legislature | N/A | N/A
5091 | FDOT District 5 | N/A | FDOT-07 | 77160-3439-01 (Pond 1) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2006 | N/A | N/A | Inside Springshed | 20.3 | Not provided | Not provided | Florida Legislature | N/A | N/A
5092 | FDOT District 5 | N/A | FDOT-08 | FM 242702 79110-3403-06 (RR-3) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 53.1 | Not provided | Not provided | Florida Legislature | N/A | N/A
5093 | FDOT District 5 | N/A | FDOT-08a | FM 242702 79110-3403-04 & 05 (Pond QQ3 & QQ-5)(RR-3) | Wet detention pond. Completion date of project outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2004 | N/A | N/A | Inside Springshed | 47.6 | Not provided | Not provided | Florida Legislature | N/A | N/A
5094 | FDOT District 5 | N/A | FDOT-09 | FM 437100-1 Dry Detention Pond | The project entails construction of a new state-of-the-art Regional Transportation Management Center (RTMC) for the Florida Department of Transportation and the Florida Highway Patrol Dispatch. There is a pond being built with the project. | On-line Retention BMPs | Underway | 2020 | 0.06 | 0 | Inside Springshed | 6.61 | Not provided | Not provided | Florida Legislature | N/A | N/A
5095 | City of Lake Mary | N/A | LM-01 | Fertilizer ordinance | Fertilizer ordinance. | Regulations, Ordinances, and Guidelines | Completed | N/A | 17 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A
5096 | Seminole County | Not provided | SC-01 | Elder RSF | RSF to collect and treat stormwater runoff. Completion daate of project is outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2007 | N/A | N/A | Not provided | 229.7 | 3884496 | 19251 | Not provided | Not provided | N/A
5097 | Seminole County | Not provided | SC-02 | Lockhart Smith RSF | RSF to collect and treat stormwater runoff. Completion daate of project is outside the project collection period. No credit assigned. | Wet Detention Pond | Completed | 2007 | N/A | N/A | Not provided | 2757 | 3504755 | Not provided | Not provided | Not provided | N/A
5098 | Seminole County | Not provided | SC-03 | Street Sweeping | Street sweeping throughout the county. | Street Sweeping | Completed | N/A | 9 | 135.1 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A
5099 | Seminole County | Not provided | SC-04 | Education Efforts | FYN, landscaping ordinance, irrigation ordinance, pet waste ordinance, PSAs, pamphlets, website, Illicit Discharge Program and standard credit for fertilizer ordinance. | Education Efforts | Completed | N/A | 822.0554 | 282.3 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A
5100 | Seminole County | Altamonte/ Casselberry/ Lake Mary/ Longwood/ Oviedo | SC-05 | Seminole County Fertilizer Ordinance | Reduction of nitrogen and phosphorus sources, through public education and restrictions on usage. | Regulations, Ordinances, and Guidelines | Completed | N/A | TBD | Not provided | Inside Springshed | 14267 | 150000 | 65000 | Ad valorem/ FFL | City - $28,000/ County - $37,000 | NF034
5101 | Seminole County | Not provided | SC-06 | Black Bear Wilderness Area | Previous land use = natural land; management focus = preservation, passive recreation; acreage = 1,650. | Land Acquisition | Underway | 2015 | N/A | N/A | Not provided | N/A | Not provided | Not provided | Not provided | Not provided | Not provided
5102 | Seminole County | Not provided | SC-07 | Gravity Main Testing and Repairs | Lateral repairs, gravity main repairs, smoke test and seal laterals. | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Completed | Prior to 2015 | N/A | N/A | Inside Springshed | N/A | 401878 | Not provided | Not provided | Not provided | Not provided
5103 | Seminole County | Not provided | SC-08 | Lift Station Rehab | Seal wet well and rehabilitate lines (Wilson School LS, Breckenridge LS, Stockbridge LS, Lake Forest #5 LS, Buckingham LS, Retreat at Wekiva LS, Aster Farms LS, Bel-Aire #3 LS, Bel-Aire #1 LS, Heathrow Master LS). | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Completed | Prior to 2015 | N/A | N/A | Inside Springshed | N/A | 324353 | Not provided | Not provided | Not provided | Not provided
5104 | Volusia County | Not provided | VC-01 | Education and Outreach | Public education about fertilizer, wastewater, lawn clippings, pet waste, water conservation. | Education Efforts | Completed | N/A | 0 | 0 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A
5105 | Volusia County | Not provided | VC-02 | Street Sweeping | Street sweeping. | Street Sweeping | Completed | N/A | 661.3433 | 2007 | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A
5106 | Volusia County | Not provided | VC-03 | Lemon Bluff Road | Grass swales without swale blocks or raised culverts. | Grass swales with swale blocks or raised culverts | Completed | 2011 | 1.3945 | 1.1 | Not provided | 1.8 | 145000 | Not provided | Not provided | Not provided | N/A
5107 | Volusia County | Not provided | VC-04 | Lemon Bluff Road Ramp | Grass swales without swale blocks or raised culverts. | Grass swales with swale blocks or raised culverts | Completed | 2011 | 0.1479 | 0.1 | Not provided | 0.2 | 55550 | Not provided | Not provided | Not provided | N/A
5108 | Volusia County | Not provided | VC-05 | DeBary Avenue Expansion | DeBary Avenue - Doyle Rd. expansion. | Wet Detention Pond | Completed | 2012 | 8.663 | 10.3 | Not provided | 123.3 | Not provided | Not provided | Not provided | Not provided | N/A
5109 | Volusia County | Not provided | VC-06 | Lake Winnemissett Non-contributing Basin | Non-contributing basin, not included in the TMDL model. | Non-contributing Basin | Completed | N/A | 139.0089 | 93.8 | Inside Springshed | 1003.3 | N/A | N/A | N/A | N/A | N/A
5110 | Volusia County | Not provided | VC-07 | Roadside Ditch Cleaning | Ongoing roadside ditch cleaning throughout county. | BMP Cleanout | Completed | N/A | TBD | N/A | Inside Springshed | N/A | Not provided | Not provided | Not provided | Not provided | N/A
5111 | Volusia County | Not provided | VC-08 | Fertilizer ordinance | Fertilizer restrictions including summer ban on nitrogen and phosphorus. | Regulations, Ordinances, and Guidelines | Completed | N/A | 0 | 0 | Inside Springshed | N/A | Not provided | Not provided | Volusia County | Not provided | N/A
5112 | FDACS | Agricultural Producers | FDACS-01 | BMP Implementation and Verification - Farm Fertilizer | Enrollment and verification of farm fertilizer BMPs by agricultural producers. Acres Treated based on FDACS December 2019 NOI Enrollment and FSAID VI. Reductions based on efficiencies referenced in the BMAP and 100% NOI Enrollment. | Agricultural BMPs | Underway | N/A | 68 | N/A | Inside Springshed | 34.2087 | TBD | TBD | FDACS | TBD | N/A
5113 | FDACS | Agricultural Producers | FDACS-02 | BMP Implementation and Verification - Livestock Waste | Enrollment and verification of livestock waste BMPs by agricultural producers. Acres Treated based on FDACS December 2019 NOI Enrollment and FSAID VI. Reductions based on efficiencies referenced in the BMAP and 100% NOI Enrollment. | Agricultural BMPs | Underway | N/A | 5.8 | N/A | Inside Springshed | 195.757 | TBD | TBD | FDACS | TBD | N/A
5114 | Golf Courses | TBD | GC-01 | Golf Course Reduction Credits | 10 % BMP credit on golf course load to groundwater, assuming 100 % BMP implementation by golf course owners. | Fertilizer Reduction | Planned | TBD | 239.652 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A
5115 | Golf Courses | N/A | GC-02 | Golf Course Reduction Credits | 6 % BMP credit on sports field load to groundwater, assuming 100 % BMP implementation. | Fertilizer Reduction | Planned | TBD | 3.6421 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A
5116 | Wastewater Utilities | TBD | WU-01 | WWTF Policy Reductions | Achieved by WWTF policy if implemented BMAP-wide, achieving 3 or 6 mg/L. | WWTF Upgrade | Planned | TBD | 1020 | N/A | Inside Springshed | N/A | N/A | N/A | N/A | N/A | N/A
5117 | Various | DEP | OSTDS-01 | Enhancement of Existing OSTDS - Voluntary | Upgrade, replacement, modification, addition of effective nitrogen reducing features, initial connection to a central sewer system, or other action to reduce nutrient loading, voluntarily taken by the owner of an OSTDS within the BMAP. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Underway | N/A | TBD | N/A | Inside Springshed | N/A | TBD | N/A | DEP | TBD | TBD
5118 | Various | DEP | OSTDS-02 | Enhancement of Existing OSTDS - Required | Upgrade, replacement, modification, addition of effective nitrogen reducing features, initial connection to a central sewer system, or other action taken to comply with the OSTDS Remediation Plan for the group of systems identified for remediation. | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Planned | TBD | TBD | N/A | PFA | N/A | TBD | N/A | DEP | TBD | TBD
Note on O2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $17/mile
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Prior to project collection period of 2009.
Note on J23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7,421 submitted by stakeholder. Needs to be verified through monitoring.
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lateral repair – 1512 Cherry Rdg., 2067 North Umbria, 169 Killarney Ct., Shadowmoss. Gravity main repair – 844 Preserve Terr., International Dr. and County Road 46A, Lake Rena Dr. Smoke test and seal laterals – Alaqua Lakes, Heathrow Woods # 1 & 2 LS, Lake Forest 1 & 2, Lake Forest 1 & 2. Additional work – Lake Forest 3 & 4, Aster Farms.
Note on J27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Volusia County does not have a UTF load obligation for this springshed. No reduction could be calculated.
Note on J33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 40,350 initial reduction submitted by stakeholder. TBD until verified. Credit would be 8,526 lb-N/yr once attenuated and recharged. Confirm what percentage of work was conducted in the springshed and ask Moira whether ditch cleaning is a credit or load to groundwater. Full credit amount was also requested in LHM. Reply: Volusia County has no UTF loading in the SRWB.
Note on J34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Volusia County does not have a UTF load obligation for this springshed. No reduction could be calculated.
Note on I35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: FDACS has proposed changing these to N/A. The original completion date had been set to indicate that 100% reductions need to be reached by the end of the BMAP. This was mistakenly listed as 2023 previously and was updated to 2033 in 2019.

## OSTDS Education
This is table D-2 of the BMAP and is not updated regularly. Do not use for updates, STAR, or summary statistics.
Lead Entity | Activity Number | Activity Name | Description of Activity | Project Type | Activity Status | Estimated Start Date | Estimated Completion Date | Nitrogen Source Addressed by Project | Cost Estimate | Funding Source | Funding Amount
UF–IFAS | IFAS-E-01 | OFS OSTDS Campaign, Phase 1 | Implement social marketing campaign that links septic systems to springs | Public Education Efforts | Planned | 2018 | 2020 | OSTDS | 30000 | Not Provided | Not Provided
UF–IFAS | IFAS-E-02 | OFS OSTDS Campaign, Phase 2 | Create online clearinghouse of fact sheets, videos, PSAs, etc. | Public Education Efforts | Planned | 2018 | 2018 | OSTDS | 7000 | Not Provided | Not Provided
UF–IFAS | IFAS-E-03 | OFS OSTDS Campaign, Phase 3 | Presentations to realtors and distribution of information kits for home buyers | Public Education Efforts | Planned | 2018 | 2018 | OSTDS | 10000 | Not Provided | Not Provided
UF–IFAS | IFAS-E-04 | OFS OSTDS Campaign, Phase 4 | Six to eight septic system workshops for elected officials | Public Education Efforts | Planned | 2018 | 2019 | OSTDS | 5000 | Not Provided | Not Provided
UF–IFAS | IFAS-E-05 | OFS OSTDS Campaign, Phase 5 | Homeowner workshops with field demonstrations | Public Education Efforts | Planned | 2018 | 2020 | OSTDS | 25000 | Not Provided | Not Provided

## Summary Info
Total Completed Projects Cost, Reductions, and Number of Projects |  | Total Underway and Planned Projects Cost and Reductions
2020 Status
Row Labels | Count of ProjectStatus
Completed | 30
Planned | 5
Underway | 5
Grand Total | 40

## Progress Charts 030620
ProjectStatus | Completed | Year | Project Reductions (TN) | 5-Year Milestone | 10-Year Milestone | 15-Year Milestone | Total Reductions Required
|  | 2018 | 2095.5479
Row Labels | Sum of TNReduction(lbs/yr) | 2019 | 2095.5479
2004 | 0 | 2020
2006 | 0 | 2021
2007 | 0 | 2022
2011 | 1.5424 | 2023 |  | 4281
2012 | 46.7589 | 2024
N/A | 2047.2465 | 2025
Prior to 2015 | 0 | 2026
Grand Total | 2095.5479 | 2027
|  | 2028 |  |  | 11416
2029
2030
2031
2032
|  | 2033 |  |  |  | 14270
2034
2035
2036
2037
|  | 2038 |  |  |  |  | 14270

## 2017 Load Reduction to Springs
[5 empty] | Source | Attenuation Factor | Portion that Leaches to Groundwater
ProjectStatus | Completed |  |  |  | Atmospheric Deposition | 0.9 | 0.1
[5 empty] | OSTDS | 0.5 | 0.5
Sum of TNReduction(lbs/yr) |  |  |  |  | Sports Turfgrass Fertilizer | 0.7 | 0.3
2095.5479 |  |  |  |  | Farm Fertilizer | 0.7 | 0.3
[5 empty] | Livestock Waste | 0.8 | 0.2
[5 empty] | Urban Feritlizer | 0.7 | 0.3
[5 empty] | WWTF- RIB | 0.25 | 0.75
[5 empty] | WWTF- Sprayfield | 0.6 | 0.4
[5 empty] | WWTF- Reuse | 0.75 | 0.25
Total Required Reductions (lbs-N/yr) |  | 14270
5-year Target Reductions (lbs-N/yr) (30 %) |  | 4281
10-year Target Reductions (lbs-N/yr) (50 %) |  | 7135
15-year Target Reductions (lbs-N/yr) (20 %) |  | 2854
Completed and Committed Project Reductions (lbs-N/yr) |  | 2095.5479
Recharge | Acres | Rate | % Acres | Averages
High | 39754.1501 | 0.9 | 0.74698 | 0.67229
Medium | 893.9371 | 0.5 | 0.016797 | 0.0083986
Low | 12571.4679 | 0.1 | 0.23622 | 0.023622
Totals Acres | 53219.5551 | Weighted Recharge |  | 0.70431

## Project Type Check 082719
ProjectType |  | Project Type | Structural/Non Structural
Street Sweeping | Non-structural | 100% On-site Retention | Structural
Education Efforts | Non-structural | Agricultural BMPs | Use Past Designation
Regulations, Ordinances, and Guidelines | Non-structural | Alum Injection Systems | Structural
OSTDS Phase Out | Structural | Aquatic Vegetation Harvesting | Non-structural
Bioswales | Structural | Baffle Boxes- First Generation (hydrodynamic separator) | Structural
On-line Retention BMPs | Structural | Baffle Boxes- Second Generation | Structural
Wet Detention Pond | Structural | Baffle Boxes- Second Generation with Media | Structural
Land Acquisition | Non-structural | Biological/ Bacteria Treatment | Structural
Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Structural | Biosorption Activated Media (BAM) | Structural
Grass swales with swale blocks or raised culverts | Structural | Bioswales | Structural
Non-contributing Basin | Non-structural | BMP Cleanout | Non-structural
BMP Cleanout | Non-structural | BMP Treatment Train | Structural
Agricultural BMPs | Use Past Designation | Catch Basin Inserts/Inlet Filter Cleanout | Non-structural
Fertilizer Reduction | Non-structural | Closed Basin | Non-structural
WWTF Upgrade | Structural | Control Structure | Structural
Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Structural | Creating/ Enhancing Living Shoreline | Structural
|  | Creating/ Enhancing Oyster Reefs | Structural
|  | Credit Trade | Trade
|  | Dairy Remediation | Structural
|  | Decommission/ Abandonment | Non-structural
|  | Deep Injection Well | Structural
|  | Denitrification Walls | Structural
|  | Dispersed Water Management (DWM) | Structural
|  | Dry Detention Pond | Structural
|  | Education Efforts | Non-structural
|  | Enhanced Public Education | Non-structural
|  | Exfiltration Trench | Structural
|  | Exotic Vegetation Removal | Non-structural
|  | Fertilizer Cessation | Non-structural
|  | Fertilizer Reduction | Non-structural
|  | Filter Marsh | Structural
|  | Fish Harvesting | Non-structural
|  | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Structural
|  | Floodplain Restoration | Structural
|  | Golf Course or Sports Field BMPs | Non-structural
|  | Grass swales with swale blocks or raised culverts | Structural
|  | Grass swales without swale blocks or raised culverts | Structural
|  | Hybrid wetland treatment technology (HWTT) | Structural
|  | Hydrodynamic Separators | Structural
|  | Hydrologic Restoration | Structural
|  | Impoundment | Structural
|  | Industrial Facility Upgrades | Structural
|  | Land Acquisition | Non-structural
|  | Land Preservation | Non-structural
|  | Land Use Change | Non-structural
|  | LID- Green Roofs | Structural
|  | LID- Other | Structural
|  | LID- Rain Gardens | Structural
|  | LID- Tree Boxes/Tree Wells | Structural
|  | Macroalgal Harvesting | Non-structural
|  | Monitoring/Data Collection | Non-structural
|  | Muck Removal/Restoration Dredging | Non-structural
|  | Natural Wetlands as Filters | Non-structural
|  | Non-contributing Basin | Non-structural
|  | Off-line Retention BMPs | Structural
|  | On-line Retention BMPs | Structural
|  | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Structural
|  | OSTDS Phase Out | Structural
|  | Pervious Pavement | Structural
|  | Pervious Pavers | Structural
|  | Plugging Artesian Wells | Structural
|  | Reclaimed Water | Structural
|  | Regional Stormwater Treatment | Structural
|  | Regulations, Ordinances, and Guidelines | Non-structural
|  | Retention/Detention BMP Retrofit with Nutrient Reducing Media | Structural
|  | Retention/Detention BMP with Nutrient Reducing Media | Structural
|  | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Structural
|  | Sanitary Sewer Inspections | Non-structural
|  | SAV Planting | Structural
|  | Shoreline Stabilization | Structural
|  | Stormwater Aeration System | Structural
|  | Stormwater Reuse | Structural
|  | Stormwater System Rehabilitation | Structural
|  | Stormwater Treatment Areas (STAs) | Structural
|  | Street Sweeping | Non-structural
|  | Study | Non-structural
|  | Turbidity Reducing Polymers (e.g., Floc logs ®) | Non-structural
|  | Vegetated Buffers | Non-structural
|  | Wastewater Service Area Expansion | Structural
|  | Wet Detention Pond | Structural
|  | Wetland Restoration | Structural
|  | Wetland Treatment | Structural
|  | WWTF Disposal Site | Structural
|  | WWTF Diversion to Reuse | Structural
|  | WWTF Nutrient Reduction | Structural
|  | WWTF Upgrade | Structural
|  | FIB- Stormwater | Bacteria
|  | FIB- Source Identification Activities | Bacteria
|  | FIB- Sanitary Sewer | Bacteria
|  | FIB- OSTDS | Bacteria
|  | FIB- Trash Cleanup of Impaired Waterbody | Bacteria

## Changes
011020- Added pivot table in summary tab, deleted project charts, deleted NOI enrollment tab, moved attenuation and recharge tab load reductions to land, changed the STAR title to Summary Info, changed milestone to target on load reduction tab, and added a note at the top of OSTDS Tab as well as copied attenuation and recharge data to 2017 load reductions tab as per suggested changes in 1-09-20 email/phone call
02052020- added project IDs from 2019 STAR, new projects may still need IDs generated from Access
022720- SOP and duplicates check, Milestone Line graph creation