## Harney-Monroe All Projects
ProjID | LeadEntity | Partners | ProjectNumber | ProjectName | ProjectDescription | ProjectType | ProjectStatus | EstimatedCompletionDate | TNReduction(lbs/yr) | TPReduction(lbs/yr) | Location | AcresTreated | CostEstimate | CostAnnualO&M | FundingSource | FundingAmount | DEPContractAgreementNumber | Structural, Non-structural, or Trade | Original Project Status | Year Added | Attachments | BMAP | Latitude | Longitude | Start Date | 2019 STAR Priority Projects (1-5)
2153 | City of DeBary | N/A | DB-01 | Non-contributing Basin | Non-contributing Basin, not included in the TMDL model. | Non-contributing Basin | Completed | 2012 | 6522.5 | 1036.8 | N/A | Not provided | N/A | N/A | City of DeBary | N/A | N/A | Non-structural | Underway | 2012 | Not provided | Harney-Monroe | N/A | N/A | N/A
2165 | City of DeBary | N/A | DB-02 | Non-contributing Basin | Non-contributing Basin, not included in the TMDL model. | Non-contributing Basin | Completed | 2012 | 7039.2 | 1170.2 | N/A | Not provided | N/A | N/A | City of DeBary | N/A | N/A | Non-structural | Underway | 2012 | Not provided | Harney-Monroe | N/A | N/A | N/A
2164 | City of DeBary | N/A | DB-03 | Citywide Fertilizer Ordinance | Reduction of fertilizer application (Ordinance 04-17). | Regulations, Ordinances, and Guidelines | Completed | N/A | 31.7241 | 4.7101 | N/A | N/A | N/A | N/A | City of DeBary | N/A | N/A | Non-structural | Underway | 2017 | Copy of the revised ordinance | Harney-Monroe | N/A | N/A | Not provided
2163 | City of DeBary | N/A | DB-04 | Public Education and Ordinances | FYN; Irrigation Ordinance; Pet Waste Ordinance; PSAs, website, brochures, and inspection program for illicit discharges. | Education Efforts | Completed | N/A | 317.2406 | 47.1008 | N/A | N/A | Not provided | N/A | City of DeBary | Not provided | N/A | Non-structural | Underway | 2017 | City website link, PDFs | Harney-Monroe | N/A | N/A | Not provided
5244 | City of DeBary | N/A | DB-05 | Citywide Lake Monitoring Program | Quarterly lake monitoring sampling. | Monitoring/Data Collection | Completed | N/A | N/A | N/A | N/A | N/A | 65000 | N/A | City of DeBary Stormwater Assessment Fee | 65000 | N/A | Non-structural | Underway/Ongoing | 2019 | N/A | Harney-Monroe | N/A | N/A | Not provided
5245 | City of DeBary | N/A | DB-06 | BMP Clean Out | Clean out of BMPs, an average of 150 cubic yards of material per year collected in the contributing watershed. | BMP Cleanout | Completed | N/A | 362 | 113 | N/A | N/A | 3500 | 3500 | City of DeBary | N/A | N/A | Non-structural | Underway/Ongoing | 2019 | N/A | Harney-Monroe | N/A | N/A | Not provided
2162 | City of Deltona | Not provided | DEL-01 | McGarity Kirkhill Regional Treatment Facility | Retrofit project to treat surface water runoff from a residential area in the city. | Wet Detention Pond | Completed | 2012 | 344.6 | 91.8 | N/A | 277.2 | 1500000 | 50000 | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2161 | City of Deltona | Not provided | DEL-02 | DRA GC-5 | Water quality treatment for a residential area. | On-line Retention BMPs | Completed | 2012 | 25.5 | 4.3 | N/A | 10.5 | 120000 | 6000 | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2160 | City of Deltona | Not provided | DEL-03 | Swales | Swales throughout the city. | Bioswales | Completed | 2012 | 4820.2 | 728.6 | N/A | 2368.7 | 2000000 | 100000 | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2159 | City of Deltona | Not provided | DEL-04 | Lake Gleason Control Structure | Proposed control structure to increase storage in Lake Gleason. | Wet Detention Pond | Completed | 2013 | 672 | 188.4 | N/A | 581.6 | 150000 | 3000 | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2184 | City of Deltona | Not provided | DEL-05 | Education Efforts | FYN, irrigation ordinance, pet waste ordinance, PSAs, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 1270 | 206.4 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2183 | City of Deltona | Not provided | DEL-06 | Catch Basin Maintenance | Catch basin cleanout throughout the city. | Catch Basin Inserts/Inlet Filter Cleanout | Completed | N/A | 19.1 | 10.4 | N/A | Not provided | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2182 | City of Deltona | Not provided | DEL-07 | Leland Stormwater Lift Station | Stormwater is pumped into Alexander Avenue Water Resources Facility (AAWRF) for treatment. The AAWRF treats up to 4MGD of surface water and stormwater used to augment the Public Access Reuse (PAR) systems for Deltona and Volusia County. | Stormwater Reuse | Completed | 2019 | 441.0113 | 28.7017 | N/A | N/A | 2400000 | 20000 | Deltona/ SJRWMD/ DEP | Not provided | WW641830 | Structural | Completed | 2015 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2181 | City of Deltona | Not provided | DEL-08 | Tivoli/Wheeling Stormwater Lift Station | Stormwater is pumped into Alexander Avenue Water Resources Facility (AAWRF) for treatment. The AAWRF treats up to 4MGD of surface water and stormwater used to augment the Public Access Reuse (PAR) systems for Deltona and Volusia County. | Stormwater Reuse | Completed | 2019 | 631.4969 | 40.2824 | N/A | Not provided | 2000000 | 20000 | Deltona/ SJRWMD/ DEP | Not provided | WW641830 | Structural | Completed | 2015 | Not provided | Harney-Monroe | N/A | N/A | 2013
2167 | City of Deltona | DEP | DEL-09 | Brickell Stormwater Management System | Treatment of stormwater flow from a major outfall, prior to discharge to Lake Monroe. The existing flow will be diverted through a natural wetland, for filtering, and pond to a set elevation before flowing over a weir to existing outfall. | Natural Wetlands as Filters | Completed | 2018 | 186 | 73 | N/A | 288 | 600000 | 10000 | DEP | 315000 | NF004 | Non-structural | Planned | 2017 | Not provided | Harney-Monroe | 28.8687 | -81.2443 | 2017-08-22
5246 | City of Deltona | SJRWMD/ DEP | DEL-10 | Lake Monroe Surface Water Intake (Future) | Stormwater is pumped into Alexander Avenue Water Resources Facility (AAWRF) for treatment. The AAWRF treats up to 4MGD of surface water and stormwater used to augment the Public Access Reuse (PAR) systems for Deltona and Volusia County. | Reclaimed Water | Planned | 2022 | TBD | TBD | N/A | N/A | 14300000 | TBD | Deltona/ SJRWMD/ DEP | TBD | TBD | Structural | Planned | 2019 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
5247 | City of Deltona | N/A | DEL-11 | DRA GC4 | Water quality treatment for a residential basin within the BMAP area. | On-line Retention BMPs | Planned | 2022 | 36.46 | 5.45 | N/A | 26.44 | 250000 | 8000 | Not provided | Not provided | Not provided | Structural | Planned | 2019 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
5248 | City of Deltona | N/A | DEL-12 | DRA GC7 | Water quality treatment for a residential basin within the BMAP area. | On-line Retention BMPs | Planned | 2022 | 5.74 | 1.84 | N/A | 13.7 | 200000 | 8000 | Not provided | Not provided | Not provided | Structural | Planned | 2019 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
5249 | City of Deltona | SJRWMD/ DEP | DEL-13 | Norwood Stormwater Lift Station (Future) | Stormwater is pumped into Alexander Avenue Water Resources Facility (AAWRF) for treatment. The AAWRF treats up to 4MGD of surface water and stormwater used to augment the Public Access Reuse (PAR) systems for Deltona and Volusia County. | Stormwater Reuse | Planned | 2024 | TBD | TBD | N/A | Not provided | TBD | TBD | Deltona | TBD | N/A | Structural | Planned | 2019 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
5250 | City of Deltona | SJRWMD/ DEP | DEL-14 | Saxon/I-4 Stormwater Lift Station (Future) | Stormwater is pumped into Alexander Avenue Water Resources Facility (AAWRF) for treatment. The AAWRF treats up to 4MGD of surface water and stormwater used to augment the Public Access Reuse (PAR) systems for Deltona and Volusia County. | Stormwater Reuse | Planned | 2029 | TBD | TBD | N/A | 16.23 | TBD | TBD | Deltona/ SJRWMD/ DEP | TBD | N/A | Structural | Planned | 2019 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2179 | City of DeLand | Not provided | DL-01 | Education Efforts | FYN Program, irrigation ordinance, fertilizer ordinance, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 9.1 | 0.7 | N/A | Not provided | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2191 | FDACS | N/A | FDACS-01 | Reductions Changes | Credit for changes in land use. | Land Use Change | Completed | 2012 | 15043.1 | 2953.3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Underway | 2012 | Not provided | Harney-Monroe | N/A | N/A | N/A
2177 | FDACS | N/A | FDACS-02 | Reductions Area | Reductions from non-contributing area. | Non-contributing Basin | Completed | 2012 | 1416.6 | 241.4 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Underway | 2012 | Not provided | Harney-Monroe | N/A | N/A | N/A
2176 | FDACS | N/A | FDACS-03 | BMP Enrollment | Enrollment and verification of BMPs by agricultural producers. | Agricultural BMPs | Completed | 2013 | 4046.8 | 800.2 | N/A | N/A | N/A | N/A | FDACS | N/A | N/A | Non-structural | Completed | 2013 | Not provided | Harney-Monroe | N/A | N/A | N/A
2175 | FDACS | N/A | FDACS-03b | BMP Enrollment | Enrollment and verification of BMPs by agricultural producers. | Agricultural BMPs | Completed | 2014 | 3747.1 | 684.9 | N/A | N/A | N/A | N/A | FDACS | N/A | N/A | Non-structural | Completed | 2014 | Not provided | Harney-Monroe | N/A | N/A | N/A
2174 | FDACS | N/A | FDACS-03c | BMP Enrollment | Enrollment and verification of BMPs by agricultural producers. | Agricultural BMPs | Completed | 2015 | 8252 | 1538.6 | N/A | N/A | N/A | N/A | FDACS | N/A | N/A | Non-structural | Completed | 2015 | Not provided | Harney-Monroe | N/A | N/A | N/A
2173 | FDACS | N/A | FDACS-03d | BMP Enrollment | Enrollment and verification of BMPs by agricultural producers. | Agricultural BMPs | Completed | 2016 | 10723 | 1903 | N/A | N/A | N/A | N/A | FDACS | N/A | N/A | Non-structural | Completed | 2016 | Not provided | Harney-Monroe | N/A | N/A | N/A
4834 | FDACS | Agricultural Producers | FDACS-03e | BMP Implementation and Verification | Enrollment and verification of BMPs by agricultural producers. Reductions based on HSPF model. Acres treated based on FDACS OAWP December 2019 Enrollment and FSAID VI. | Agricultural BMPs | Completed | N/A | 6354 | 1054 | N/A | 5716 | TBD | TBD | FDACS | TBD | N/A | Non-structural | Completed | 2018 | GIS Provided | Harney-Monroe | N/A | N/A | N/A
2172 | FDOT District 5 | N/A | FDOT-01 | 79070-3547-02 (Pond pond 2) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 19.7 | 2.2 | N/A | 21.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0188 | -81.2145 | 2003
2171 | FDOT District 5 | N/A | FDOT-02 | 79070-3547-03 (Pond pond 3) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 11.7 | 0.6 | N/A | 24.9 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0218 | -81.2047 | 2003
2170 | FDOT District 5 | N/A | FDOT-03 | 79070-3547-04 (Pond pond 4) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 15.8 | 0.8 | N/A | 35.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0254 | -81.1932 | 2003
2169 | FDOT District 5 | N/A | FDOT-04 | 79070-3547-06 (Pond pond 6) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 13.6 | 0.7 | N/A | 18.8 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0284 | -81.1516 | 2003
2168 | FDOT District 5 | N/A | FDOT-05 | 79070-3546-03 (Pond pond 9) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 13.3 | 8.6 | N/A | 13.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0171 | -81.1047 | 2003
2185 | FDOT District 5 | N/A | FDOT-06 | 79070-3546-02 (Pond pond 8) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 25.4 | 6.2 | N/A | 44.3 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0206 | -81.1113 | 2003
2186 | FDOT District 5 | N/A | FDOT-07 | 79070-3547-05 (Pond pond 5) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 25.2 | 2.7 | N/A | 33.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0293 | -81.172 | 2003
2187 | FDOT District 5 | N/A | FDOT-08 | 79070-3546-01 (Pond pond 7) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 19.9 | 1.4 | N/A | 26.9 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0263 | -81.1362 | 2003
2188 | FDOT District 5 | N/A | FDOT-09 | 79070-3546-04 (Pond pond 10) | Wet detention pond. | Wet Detention Pond | Completed | 2007 | 3.8 | 2.7 | N/A | 3.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0121 | -81.0846 | 2003
2189 | FDOT District 5 | N/A | FDOT-10 | 79110-xxx3-08 (Pond 4) | FM 408463-1 wet detention pond. | Wet Detention Pond | Completed | 2008 | 8.2 | 1.6 | N/A | 8.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.9925 | -81.2452 | 2010
2155 | FDOT District 5 | N/A | FDOT-11 | 79110-xxx (Pond 5) | Wet detention pond. | Wet Detention Pond | Completed | 2008 | 27.2 | 6.2 | N/A | 22.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.9993 | -81.2422 | 2008
2180 | FDOT District 5 | N/A | FDOT-12 | 79110-xxx (Pond 6) | Wet detention pond. | Wet Detention Pond | Completed | 2008 | 13.6 | 2.8 | N/A | 10.7 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.002 | -81.2425 | 2010
2178 | FDOT District 5 | N/A | FDOT-13 | 79110-xxx (Pond 7) | Wet detention pond. | Wet Detention Pond | Completed | 2008 | 38.3 | 7.7 | N/A | 30 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0102 | -81.238 | 2010
2144 | FDOT District 5 | N/A | FDOT-14 | 79110-xxx4-01 (Pond 1 and 1A) | Wet detention pond 1 and 1A. | Wet Detention Pond | Completed | 2012 | 54.4 | 11 | N/A | 35.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.968 | -81.2523 | 2010
2145 | FDOT District 5 | N/A | FDOT-14b | 79110-xxx4-02 (Pond 1A) | Wet detention pond. Credits included in FDOT-14. | Wet Detention Pond | Completed | 2012 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | N/A | N/A | 2010
2146 | FDOT District 5 | N/A | FDOT-15 | 79110-xxx4-03 (Pond 2 and 2A) | Wet detention pond 2 and 2A. | Wet Detention Pond | Completed | 2012 | 65.3 | 13.3 | N/A | 38.7 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0185 | -81.2292 | 2010
2147 | FDOT District 5 | N/A | FDOT-15b | 79110-xxx4-04 (Pond 2A) | Dry detention pond. Credits included in FDOT-15. | Dry Detention Pond | Completed | 2012 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | N/A | N/A | 2010
2148 | FDOT District 5 | N/A | FDOT-16 | 79110-xxx4-05 (Pond 14) | Wet detention pond. | Wet Detention Pond | Completed | 2012 | 43.8 | 8 | N/A | 24.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.9119 | -81.2702 | 2010
2149 | FDOT District 5 | N/A | FDOT-17 | SR 415 - missing from model | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2012 | 90.1 | 28.3 | N/A | 133.9 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8197 | -81.1858 | Not provided
2150 | FDOT District 5 | N/A | FDOT-18 | SR 44 - missing from model | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2012 | 34.1 | 10.5 | N/A | 43.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 29.0152 | -81.2406 | Not provided
2151 | FDOT District 5 | N/A | FDOT-19 | SR 46 - missing from model | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2012 | 32.8 | 7.4 | N/A | 48.2 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8114 | -81.3588 | Not provided
2152 | FDOT District 5 | N/A | FDOT-20 | 77160-3404-02 (Pond 1-NW) | On-line retention BMPs. | On-line Retention BMPs | Completed | 2004 | 94.2 | 13.4 | N/A | 25.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.7584 | -81.3633 | 2004
2166 | FDOT District 5 | N/A | FDOT-21 | 77160-3404-06 (Pond pond 4-11) | Wet detention pond. | Wet Detention Pond | Completed | 2004 | 102.5 | 24.4 | N/A | 38.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8221 | -81.3383 | 2004
2154 | FDOT District 5 | N/A | FDOT-22 | 77160-3404-05 (Pond pond 4-1) | Wet detention pond. | Wet Detention Pond | Completed | 2004 | 44.9 | 12.4 | N/A | 32.4 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.817 | -81.3338 | 2004
2143 | FDOT District 5 | N/A | FDOT-23 | 77160-3404-07 (Pond 5) | Wet detention pond. | Wet Detention Pond | Completed | 2004 | 47.4 | 8.6 | N/A | 30.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8237 | -81.3281 | 2004
2215 | FDOT District 5 | N/A | FDOT-24 | 77160 3436 (pond A, A-1) | Wet detention pond. | Bioswales | Completed | 2012 | 147.5 | 19.8 | N/A | 56.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8319 | -81.3226 | 2000
2156 | FDOT District 5 | N/A | FDOT-25 | 77160-3439-01 (Pond 1) | Wet detention pond. | Wet Detention Pond | Completed | 2006 | 7.4 | 0.7 | N/A | 20.3 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.7831 | -81.3532 | 2010
2190 | FDOT District 5 | N/A | FDOT-26 | FM 242702 79110-3403-04 & 05 (Pond QQ3 & QQ-5) | Wet detention pond. | Wet Detention Pond | Completed | 2004 | 56.4 | 11.7 | N/A | 47.6 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8318 | -81.3253 | 2001
2157 | FDOT District 5 | N/A | FDOT-26b | FM 242702 79110-3403-04 & 05 (Pond QQ3 & QQ-5) | Wet detention pond. Credits included in FDOT-26. | Wet Detention Pond | Completed | 2004 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | N/A | N/A | 2001
2158 | FDOT District 5 | N/A | FDOT-27 | FM 242702 79110-3403-06 (RR-3) | Wet detention pond. | Wet Detention Pond | Completed | 2004 | 68.1 | 16.9 | N/A | 53.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8468 | -81.3127 | 2001
2220 | FDOT District 5 | N/A | FDOT-28 | FM 242702 79110-3403-07 (Pond SS-2) | Wet detention pond. | Wet Detention Pond | Completed | 2006 | 91.9 | 26.3 | N/A | 87.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8739 | -81.285 | 2001
2230 | FDOT District 5 | N/A | FDOT-29 | FM 242702 Roadside Swale | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2004 | 93.8 | 13.5 | N/A | 35 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8587 | -81.296 | 2001
2222 | FDOT District 5 | N/A | FDOT-30 | FM 242702 Roadside Swale | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2006 | 39.5 | 5.7 | N/A | 13.3 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8679 | -81.2865 | 2001
2218 | FDOT District 5 | N/A | FDOT-31 | SR 415 - missing from model | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2012 | 39.1 | 8.5 | N/A | 65.1 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8647 | -81.1622 | Not provided
2233 | FDOT District 5 | N/A | FDOT-32 | Education Efforts | Education efforts. | Education Efforts | Completed | N/A | 101.1 | 13.3 | N/A | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | N/A | N/A | 2004
2237 | FDOT District 5 | N/A | FDOT-33 | Street Sweeping | Street sweeping. | Street Sweeping | Completed | N/A | 410 | 263 | N/A | N/A | Not provided | Not provided | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2012 | Provided during BMAP Development | Harney-Monroe | N/A | N/A | 2004
2223 | FDOT District 5 | N/A | FDOT-34 | Noncontributing Area in DeBary | Noncontributing area in DeBary. | Non-contributing Basin | Completed | N/A | 194.9 | 27.9 | N/A | 39.2 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Underway | 2012 | See DEP Model | Harney-Monroe | N/A | N/A | N/A
2219 | FDOT District 5 | N/A | FDOT-35 | Noncontributing Area in Volusia County | Noncontributing area in Volusia County. | Non-contributing Basin | Completed | N/A | 117.6 | 19 | N/A | 22.7 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Underway | 2012 | See DEP Model | Harney-Monroe | N/A | N/A | N/A
2193 | FDOT District 5 | N/A | FDOT-36 | SR 415 – Pond A (built under 407355-1) | Wet detention pond. | Wet Detention Pond | Completed | 2016 | 6.8 | 1.5 | N/A | 4.3 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Underway | 2012 | Provided during BMAP Development | Harney-Monroe | 28.7983 | 81.2092 | 2012
2142 | FDOT District 5 | N/A | FDOT-37 | FM: 407355-3 SR 415 – Pond B | Wet detention pond. | Wet Detention Pond | Completed | 2016 | 7.9 | 0.8 | N/A | 8.5 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Underway | 2012 | Provided during BMAP Development | Harney-Monroe | 28.7976 | -81.2136 | 2012
2194 | FDOT District 5 | N/A | FDOT-38 | SR 415 – Exfiltration Trench | Exfilitration trench. | On-line Retention BMPs | Completed | 2016 | 11.6 | 0.4 | N/A | 22 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Underway | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8071 | -81.2075 | 2012
2195 | FDOT District 5 | N/A | FDOT-39 | FM: 407355-3 SR 415 – Pond H (in database as Pond 1) | Wet detention pond. | Wet Detention Pond | Completed | 2016 | 10.2 | 2.4 | N/A | 9.9 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Underway | 2012 | Provided during BMAP Development | Harney-Monroe | 28.8168 | -81.1858 | 2012
2205 | FDOT District 5 | N/A | FDOT-40 | FM: 240216-2 SR 46 – Pond 1 (possibly modified and built by others) | Wet detention pond. | Wet Detention Pond | Completed | 2019 | 25.8 | 6.3 | N/A | 18 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Not Started (funded for 2018) | 2012 | Provided during BMAP Development | Harney-Monroe | 28.7894 | -81.2469 | 2012
2196 | FDOT District 5 | N/A | FDOT-41 | Fertilizer Cessation | Elimination of fertilizer use along state highway system. Removal of TN & TP loading. | Fertilizer Cessation | Completed | 2016 | 712 | 0 | N/A | 278.38 | Not provided | N/A | Florida Legislature | Not provided | N/A | Non-structural | Completed | 2016 | Provided during BMAP Development | Harney-Monroe | N/A | N/A | 2012
2221 | FDOT District 5 | N/A | FDOT-42 | FM: 408464 SR 400 Widening (from SR 44 to East of I-95) | Basin B Pond B. | Wet Detention Pond | Completed | 2016 | 51.8 | 1.1 | N/A | 15.74 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2016 | Provided during BMAP Development | Harney-Monroe | 29.036 | -81.213 | 2012
2197 | FDOT District 5 | N/A | FDOT-43 | FM: 408464 SR 400 Widening (from SR 44 to East of I-95) | Basin E Pond E. | Wet Detention Pond | Completed | 2016 | 59.1 | 1.4 | N/A | 15.88 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Completed | 2016 | Provided during BMAP Development | Harney-Monroe | 29.064 | -81.187 | 2012
5251 | FDOT District 5 | N/A | FDOT-44 | FM: 240200-3-52-01 | SR 46 (Wekiva Parkway) from Orange Blvd. to N. Oregon St./Wayside Dr. | Wet Detention Pond | Underway | 2021 | 17.6 | 6.6 | N/A | 18.68 | Not provided | Not provided | Florida Legislature | Not provided | N/A | Structural | Underway | 2019 | Provided in 2019 project collection | Harney-Monroe | 28.8089 | -81.3466 | Not provided
2198 | City of Lake Helen | Not provided | LH-01 | Education Efforts | Irrigation ordinance, pet waste ordinance, pamphlets, website. | Education Efforts | Completed | N/A | 30.8 | 4.5 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
4383 | City of Lake Helen | Volusia County | LH-02 | Main Street Exfiltration | Retrofit project to treat runoff from the Main Street drainage basin prior to discharging to Lake Helen. | Exfiltration Trench | Completed | Prior to 2018 | Not provided | Not provided | N/A | 5.7 | Not provided | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2018 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
4384 | City of Lake Helen | Volusia County | LH-03 | Connecticut Avenue Exfiltration | Retrofit project to treat runoff from the Connecticut Avenue drainage basin prior to discharging to Lake Helen. | Exfiltration Trench | Completed | Prior to 2018 | Not provided | Not provided | N/A | 3.2 | Not provided | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2018 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
4385 | City of Lake Helen | Volusia County | LH-04 | Tangerine Avenue Bioswale | Retrofit project to treat runoff from the Tangerine drainage basin prior to discharging to Lake Helen. | Bioswales | Underway | 2020 | TBD | TBD | N/A | 1.5 | 40000 | 3000 | City of Lake Helen | Not provided | N/A | Structural | Underway | 2018 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2199 | City of Lake Mary | Seminole County | LM-01 | Education Efforts | FYN, landscape ordinance, irrigation ordinance, pet waste ordinance, PSAs, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 361.5 | 52.2 | N/A | N/A | N/A | 5500 | City of Lake Mary Stormwater Fund | 5500 | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | 10/2012
2200 | City of Lake Mary | N/A | LM-02 | Street Sweeping | Sweeping of 53.58 curb miles per year. | Street Sweeping | Completed | N/A | 9.6 | 6.4 | N/A | N/A | N/A | 13000 | City of Lake Mary Stormwater Fund | 13000 | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | 10/2012
2201 | City of Orange City | N/A | OC-01 | Education Efforts | Irrigation ordinance, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 6 | 1 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
5252 | City of Orange City | N/A | OC-02 | Stormwater Inlet Cleaning and Maintenance | Municipal operation pollution prevention and good housekeeping which occurs annually. | BMP Cleanout | Completed | N/A | 7 | 3 | N/A | N/A | 20000 | 18687 | Orange City | 18687 | N/A | Non-structural | Completed | 2019 | N/A | Harney-Monroe | N/A | N/A | Not provided
2202 | City of Sanford | DEP/ HUD | S-01 | Cloud Branch Phase I | Drainage/water quality improvements. | Wet Detention Pond | Completed | 2007 | 647.3 | 173.9 | N/A | 187 | 3491375 | Not provided | City/ Stormwater Utility/ DEP SRF | Not provided | Not provided | Structural | Completed | 2012 | Previously Provided | Harney-Monroe | 28.7997 | -81.2774 | Not provided
2217 | City of Sanford | DEP | S-02 | Cloud Branch Phase II | Drainage/water quality improvements. | Wet Detention Pond | Completed | 2007 | 1390.1 | 405.6 | N/A | 379.7 | 3072693 | Not provided | City/ Stormwater Utility/ DEP SRF | Not provided | Not provided | Structural | Completed | 2012 | Previously Provided | Harney-Monroe | 28.804 | -81.2785 | Not provided
2204 | City of Sanford | N/A | S-03 | Street Sweeping | Street sweeping throughout the city. | Street Sweeping | Completed | N/A | 8866.5 | 3993.3 | N/A | N/A | N/A | 170544 | City/ Stormwater Utility | N/A | N/A | Non-structural | Ongoing | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2192 | City of Sanford | Seminole County | S-04 | Education Efforts | FYN, landscaping ordinance, irrigation ordinance, PSAs, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 2069.9 | 324.5 | N/A | N/A | N/A | 2000 | City/ Stormwater Utility | N/A | N/A | Non-structural | Ongoing | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2206 | City of Sanford | N/A | S-05 | Sanford Avenue Baffle Box | 2nd generation baffle box. | Baffle Boxes- Second Generation | Completed | 2015 | 5.5 | 0.7 | N/A | N/A | 2400000 | Not provided | City/ Storwmater Utility/ Community Redevelopment Agency (CRA) | Not provided | N/A | Structural | Completed | 2014 | KMZ | Harney-Monroe | 28.8107 | -81.2649 | Not provided
2207 | City of Sanford | DEP | S-06 | Mill Creek Wet Detention Pond | Wet detention pond. | Wet Detention Pond | Completed | 2004 | 1465.6 | 433.8 | N/A | 412.1 | 2085959 | Not provided | City/ Stormwater Utility/ DEP SRF | Not provided | Not provided | Structural | Completed | 2014 | Previously Provided | Harney-Monroe | 28.7935 | -81.2864 | Not provided
2208 | City of Sanford | HUD | S-07 | Baffle Boxes on 2nd St. | 1st generation baffle boxes. | Baffle Boxes- First Generation (hydrodynamic separator) | Completed | 1997 | 9 | 6.7 | N/A | 200.1 | 1891082 | Not provided | City/ Stormwater Utility/ DEP SRF/ Community Development Block Grant (CDBG) | Not provided | Not provided | Structural | Completed | 2014 | Previously Provided | Harney-Monroe | 28.8108 | -81.2669 | Not provided
2209 | City of Sanford | DEP | S-08 | WWTP Reclaimed Water Nutrient Reduction | Upgrade to WWTP treatment process that will reduce the concentration of TN from 20mg/L to 4 mg/L and TP from 4mg/L to 1 mg/L in the reclaimed water; 0.376 MGD to Lake Monroe directly. | WWTF Nutrient Reduction | Underway | 2020 | 9992.106 | 749.556 | N/A | Not provided | 16000000 | 100000 | City/ DEP SRF | Not provided | Not provided | Structural | Planned & Funded | 2017 | N/A | Harney-Monroe | 28.8152 | -81.2832 | 2017
2203 | Seminole County | Not provided | SC-01 | Club II RSF | RSF to collect and treat stormwater runoff. | Wet Detention Pond | Completed | 2007 | 1333.3 | 395.6 | N/A | 422.7 | 2334682 | 20095 | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2210 | Seminole County | Not provided | SC-02 | Midway RSF | RSF to collect and treat stormwater runoff. | Wet Detention Pond | Completed | 2009 | 408.4 | 118.4 | N/A | 121.8 | 2163151 | 26662 | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2216 | Seminole County | Not provided | SC-03 | Elder RSF | RSF to collect and treat stormwater runoff. | Wet Detention Pond | Completed | 2007 | 519.2 | 134.4 | N/A | 229.7 | 3884496 | 19251 | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2214 | Seminole County | Not provided | SC-04 | Lockhart RSF | RSF to collect and treat stormwater runoff. | Wet Detention Pond | Completed | 2007 | 3201.1 | 840.1 | N/A | 2757 | 3504755 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2213 | Seminole County | Not provided | SC-05 | Street Sweeping | Street sweeping throughout the county. | Street Sweeping | Completed | N/A | 300 | 135.1 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2212 | Seminole County | Not provided | SC-06 | Education Efforts | FYN, landscaping ordinance, irrigation ordinance, pet waste ordinance, PSAs, pamphlets, website, illicit discharge program. | Education Efforts | Completed | N/A | 1875.8 | 282.3 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2211 | Seminole County | Altamonte/ Casselberry/ Lake Mary/ Longwood/ Oviedo | SC-07 | Seminole County Fertilizer Ordinance | Reduction of Nitrogen and Phosporus sources, through public education and restrtictions on usage. | Regulations, Ordinances, and Guidelines | Completed | N/A | TBD | N/A | N/A | 14267 | 150000 | 65000 | Ad valorem taxes/ FFL cost shares | City - $28,000/ County - $37,000 | NF034 | Non-structural | Completed | 2017 | Adopted ordinance, leaching calculations | Harney-Monroe | N/A | N/A | 2018-10-01
2232 | Seminole County | Not provided | SC-08 | Midway Phase II, Ditch Diversion | Addition of a ditch bottom inlet and regrading to route untreated runoff into Pond 4 of the existing RSF. | Wet Detention Pond | Completed | 2016 | 175 | 35 | N/A | 25 | 59300 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2017 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2229 | Turnpike Enterprise | Not provided | T-01 | Street Sweeping | SR 417 MM 51-55 16 CM Mainline per cycle 6 CM Ramps per cycle 24 Total Curb Miles per month or 288 Curb Miles per year Aprox 93,312 lbs or 42,325.61 Kg of dry material. | Street Sweeping | Completed | N/A | 53 | 34 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2234 | Turnpike Enterprise | Not provided | TP-02 | Education Efforts | No fertilizer on right-of-ways, illicit discharge training. | Education Efforts | Completed | N/A | TBD | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Non-structural | Underway | 2017 | Not provided | Attached | N/A | N/A | Not provided
2235 | Volusia County | Not provided | VC-01 | Education and Outreach | Education efforts. | Education Efforts | Completed | N/A | 1391.9 | 201 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2236 | Volusia County | Not provided | VC-02 | Street Sweeping | Street sweeping. | Street Sweeping | Completed | N/A | 3130 | 2007 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2231 | Volusia County | Not provided | VC-03 | Lemon Bluff Road | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2011 | 6.6 | 1.1 | N/A | 1.8 | 145000 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2228 | Volusia County | Not provided | VC-04 | Lemon Bluff Road Ramp | Grass swales without swale blocks or raised culverts. | Bioswales | Completed | 2011 | 0.7 | 0.1 | N/A | 0.2 | 55550 | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2227 | Volusia County | Not provided | VC-05 | DeBary Avenue Expansion | DeBary Avenue - Doyle Road expansion. | Wet Detention Pond | Completed | 2012 | 41 | 10.3 | N/A | 123.3 | Not provided | Not provided | Not provided | Not provided | N/A | Structural | Completed | 2012 | Not provided | Harney-Monroe | Not provided | Not provided | Not provided
2226 | Volusia County | Not provided | VC-06 | Lake Winnemissett Non-contributing Basin | Non-contributing Basin, not included in the TMDL model. | Non-contributing Basin | Completed | 2012 | 657.9 | 93.8 | N/A | 1003.3 | N/A | N/A | N/A | N/A | N/A | Non-structural | Completed | 2012 | Not provided | Harney-Monroe | N/A | N/A | N/A
2225 | Volusia County | Not provided | VC-07 | Roadside Ditch Cleaning | Ongoing roadside ditch cleaning throughout county. | BMP Cleanout | Completed | N/A | 905 | 556 | N/A | N/A | Not provided | Not provided | Not provided | Not provided | N/A | Non-structural | Ongoing | 2016 | Not provided | Harney-Monroe | N/A | N/A | Not provided
2224 | Volusia County | VC/ DEP/ SJRWMD | VC-08 | Gemini Springs Baffle Boxes | Installation of two baffle boxes. | Baffle Boxes- Second Generation | Completed | 2018 | 850 | 135 | N/A | 208 | 381900 | Not provided | DEP/ SJRWMD | DEP - $95,000/ SJRWMD - $95,000 | NS034 | Structural | Planned | 2017 | Not provided | Harney-Monroe | 28.868 | 81.298 | 2018-09-01
5253 | Volusia County | N/A | VC-09 | Fertilizer Ordinance | Fertilizer restrictions including summer ban on nitrogen and phosphorus. | Regulations, Ordinances, and Guidelines | Completed | N/A | TBD | N/A | N/A | N/A | Not provided | Not provided | Volusia County General Fund | N/A | N/A | Non-structural | Completed | 2019 | Not provided | Harney-Monroe | N/A | N/A | 2019
5254 | Volusia County | VC/ SJRWMD | VC-10 | Thornby Park Improvement Project | Installation of baffle boxes and upflow filtration system. | Baffle Boxes- Second Generation | Planned | 2020 | TBD | TBD | N/A | 65 | 476354 | Not provided | VC/ SJRWMD | TBD | TBD | Structural | Planned | 2019 | Not provided | Harney-Monroe | N/A | N/A | 2020
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These numbers were reduced in 2019 to reflect only the starting load from the contributing basin as there were two non-contributing basins included in the original starting load.
Note on J18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stakeholder submitted reductions in 2019 of 36.46 TN and 5.45 TP Reply: Spoke with MRH on 1/31/20 who agreed that the caluclations submitted take the delta and seem reasonable. Reduction amounts accepted.
Note on J19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stakeholder submitted reductions in 2019 of 1.84 TP and 5.74 TN. Reply: Spoke with MRH on 1/31/20 who agreed that the caluclations submitted take the delta and seem reasonable. Reduction amounts accepted.
Note on O87: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $17/mile
Note on I90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This was added in 2014, but received submission from stakeholder listed completion as 2004. Think it may be 2014. Need to confirm.
Note on D91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Laura Savag project missing from model
Note on J92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.376MGDx35,433lbs/MGD Removed x 0.75
Note on K92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.376MGDx2,658lbs/MGD Removed x 0.75
Note on J101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stakeholder submitted reductions of TN = 144 and TP = 34 using Sansalone Lane Mile Method. Recalcualted using weight provided and MS4 tool.
Note on J109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stakeholder submitted new reductions as 40,350 TN and 16,337 TP. Need weight to verify. New reductions left in for this year.

## Load Reductions
Entity-specific Load Reductions
Notes:
1 BMAP Tables 11,15,18
2BMAP Tables 15, 18
3BMAP Tables 12,16,18
4BMAP Tables 16, 18
5 The reductions below are dependent on the accuracy of the Non-contributing basin estimates for City of DeBary which were determined in 2012.
ProjectStatus | Completed
Row Labels | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | TN Starting Load1 (lbs/yr) | Phase I TN Required Reduction (lbs/yr) | Phase I TN Reductions Still Needed (lbs/yr) | Phase I TN Required Reductions Achieved (%) | Total TN Required Reduction2 (lbs/yr) | TN Reductions Still Needed (lbs/yr) | Total TN Required Reductions Achieved (%) | TP Starting Load3 (lbs/yr) | Phase I TP Required Reduction (lbs/yr) | Phase I TN Reductions Still Needed (lbs/yr) | Phase I TP Required Reductions Achieved (%) | Total TP Required Reduction4 (lbs/yr) | TP Reductions Still Needed (lbs/yr) | Total TP Required Reductions Achieved (%)
City of DeBary | 14272.6646 | 2371.8108 | 19906.5 | 1880.2 | -12392.4646 | 759.1% | 3760.4 | -10512.2646 | 379.6% | 3149 | 86.4 | -2285.4108 | 2745% | 172.8 | -2199.0108 | 1373%
City of DeLand | 9.1 | 0.7 | 192 | - | - | - | - | - | - | 14.8 | - | - | - | - | - | -
City of Deltona | 8223.9082 | 1298.8841 | 25399.8 | 3608.7 | -4615.2082 | 227.9% | 7217.4 | -1006.5082 | 113.9% | 4128.2 | 388.3 | -910.5841 | 334.5% | 776.6 | -522.2841 | 167.3%
City of Lake Helen | 30.8 | 4.5 | 2052.4 | - | - | - | - | - | - | 297 | - | - | - | - | - | -
City of Lake Mary | 371.1 | 58.6 | 6572 | - | - | - | - | - | - | 948.9 | - | - | - | - | - | -
City of Orange City | 13 | 4 | 105.4 | - | - | - | - | - | - | 16.6 | - | - | - | - | - | -
City of Sanford | 14453.9 | 5338.5 | 41398.4 | 10360 | -4093.9 | 139.5% | 20720 | 6266.1 | 69.76% | 6490.8 | 1339.55 | -3998.95 | 398.5% | 2679.1 | -2659.4 | 199.3%
FDACS | 43228.6 | 8121.4 | 130168.2 | 21141 | -22087.6 | 204.5% | 42282 | -946.6 | 102.2% | 29970 | 6885.1 | -1236.3 | 118% | 13770.2 | 5648.8 | 58.98%
FDOT District 5 | 3071.9 | 615.4 | 10112 | 1232 | -1839.9 | 249.3% | 2464 | -607.9 | 124.7% | 1325 | - | - | - | - | - | -
Seminole County | 7812.8 | 1940.9 | 34105 | 3973.5 | -3839.3 | 196.6% | 7947 | 134.2 | 98.31% | 5133 | 155.45 | -1630 | 1149% | 310.9 | -1630 | 624.3%
Turnpike Enterprise | 53 | 34 | 1240 | - | - | - | - | - | - | 109 | - | - | - | - | - | -
Volusia County | 6133.1 | 2869.3 | 26512 | 1633 | -4500.1 | 375.6% | 3266 | -2867.1 | 187.8% | 3829 | - | - | - | - | - | -
Grand Total | 97673.8728 | 22657.995 | 297763.7 | 43828.4 | -53368.4728 | 222.9% | 87656.8 | -9540.0728 | 111.4% | 55411.3 | 8854.8 | -10061.245 | 255.9% | 17709.6 | -1361.895 | 127.9%
Year Added | (Multiple Items)
Count of ProjectStatus | Column Labels
Row Labels | Completed | Planned | Underway | Grand Total
City of DeBary | 6 |  |  | 6
City of DeLand | 1 |  |  | 1
City of Deltona | 9 | 5 |  | 14
City of Lake Helen | 3 |  | 1 | 4
City of Lake Mary | 2 |  |  | 2
City of Orange City | 2 |  |  | 2
City of Sanford | 7 |  | 1 | 8
FDACS | 7 |  |  | 7
FDOT District 5 | 46 |  | 1 | 47
Seminole County | 8 |  |  | 8
Turnpike Enterprise | 2 |  |  | 2
Volusia County | 9 | 1 |  | 10
Grand Total | 102 | 6 | 3 | 111

## Summary Info
ProjectStatus | Completed
Sum of CostEstimate | Sum of CostAnnualO&M | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | Count of ProjectStatus
34478443 | 553239 | 105089.6728 | 23926.295 | 102
ProjectStatus | (Multiple Items)
Sum of CostEstimate | Sum of CostAnnualO&M | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr)
31266354 | 119000 | 10051.906 | 763.446
Number of Projects Added by Year
ProjectStatus | (Multiple Items)
Row Labels | Count of Year Added
2012 | 75
2013 | 1
2014 | 4
2015 | 3
2016 | 5
2017 | 8
2018 | 4
2019 | 11
Grand Total | 111
Number of projects completed in 2019 and Number of ongoing projects
Count of ProjectStatus | Column Labels
Row Labels | 2019 | N/A | Grand Total
Completed | 3 | 28 | 31
Grand Total | 3 | 28 | 31
Row Labels | Count of ProjectType
Agricultural BMPs | 5
Baffle Boxes- First Generation (hydrodynamic separator) | 1
Baffle Boxes- Second Generation | 3
Bioswales | 11
BMP Cleanout | 3
Catch Basin Inserts/Inlet Filter Cleanout | 1
Dry Detention Pond | 1
Education Efforts | 11
Exfiltration Trench | 2
Fertilizer Cessation | 1
Land Use Change | 1
Monitoring/Data Collection | 1
Natural Wetlands as Filters | 1
Non-contributing Basin | 6
On-line Retention BMPs | 5
Reclaimed Water | 1
Regulations, Ordinances, and Guidelines | 3
Stormwater Reuse | 4
Street Sweeping | 6
Wet Detention Pond | 43
WWTF Nutrient Reduction | 1
Grand Total | 111

## Progress Charts
ProjectStatus | Completed |  | Year | TN Project Reductions | 5-Year Milestone | Total Reductions Required
|  |  | 2012 | 74474.5646 |  | 87656
Row Labels | Sum of TNReduction(lbs/yr) | Sum of TPReduction(lbs/yr) | 2013 | 79193.3646 |  | 87656
1997 | 9 | 6.7 | 2014 | 82940.4646 |  | 87656
2004 | 1972.9 | 534.7 | 2015 | 91197.9646 |  | 87656
2006 | 138.8 | 32.7 | 2016 | 102955.3646 |  | 87656
2007 | 7239.4 | 1975.5 | 2017 | 102955.3646 | 43828 | 87656
2008 | 87.3 | 18.3 | 2018 | 103991.3646 |  | 87656
2009 | 408.4 | 118.4 | 2019 | 105089.6728 |  | 87656
2011 | 7.3 | 1.2 | 2020 |  |  | 87656
2012 | 36417.7 | 6437.3 | 2021 |  |  | 87656
2013 | 4718.8 | 988.6 | 2022 |  |  | 87656
2014 | 3747.1 | 684.9 | 2023 |  |  | 87656
2015 | 8257.5 | 1539.3 | 2024 |  |  | 87656
2016 | 11757.4 | 1945.6 | 2025 |  |  | 87656
2019 | 1098.3082 | 75.2841 | 2026 |  |  | 87656
N/A | 28193.7646 | 9359.8108 | 2027 |  |  | 87656
2018 | 1036 | 208 | 2028 |  |  | 87656
Prior to 2018 | 0 | 0 | 2029 |  |  | 87656
Grand Total | 105089.6728 | 23926.295 | 2030 |  |  | 87656
|  |  | 2031 |  |  | 87656
|  |  | 2032 |  |  | 87656
|  |  | Year | TP Project Reductions | 5-Year Milestone | Total Reductions Required
|  |  | 2012 | 18484.6108 |  | 17710
|  |  | 2013 | 19473.2108 |  | 17710
|  |  | 2014 | 20158.1108 |  | 17710
|  |  | 2015 | 21697.4108 |  | 17710
|  |  | 2016 | 23643.0108 |  | 17710
|  |  | 2017 | 23643.0108 | 8582 | 17710
|  |  | 2018 | 23851.0108 |  | 17710
|  |  | 2019 | 23926.295 |  | 17710
|  |  | 2020 |  |  | 17710
|  |  | 2021 |  |  | 17710
|  |  | 2022 |  |  | 17710
|  |  | 2023 |  |  | 17710
|  |  | 2024 |  |  | 17710
|  |  | 2025 |  |  | 17710
|  |  | 2026 |  |  | 17710
|  |  | 2027 |  |  | 17710
|  |  | 2028 |  |  | 17710
|  |  | 2029 |  |  | 17710
|  |  | 2030 |  |  | 17710
|  |  | 2031 |  |  | 17710
|  |  | 2032 |  |  | 17710
Note on F2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start with Year Adopted
Note on G2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert pivot table to the left. First reduction should be the sum of the years before the adoption, adopted year, and N/A (ongoing) activities.
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start with Year Adopted
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Insert pivot table to the left. First reduction should be the sum of the years before the adoption, adopted year, and N/A (ongoing) activities.

## Project Type Check 022520
ProjectType |  | Project Type | Structural/Non Structural | Min/Max of Project IDs | Sum of ProjID | Count of ProjID
Non-contributing Basin | Non-structural | 100% On-site Retention | Structural | 2142 | 285917 | 111
Regulations, Ordinances, and Guidelines | Non-structural | Agricultural BMPs | Use Past Designation | 5254
Education Efforts | Non-structural | Alum Injection Systems | Structural
Monitoring/Data Collection | Non-structural | Aquatic Vegetation Harvesting | Non-structural
BMP Cleanout | Non-structural | Baffle Boxes- First Generation (hydrodynamic separator) | Structural
Wet Detention Pond | Structural | Baffle Boxes- Second Generation | Structural
On-line Retention BMPs | Structural | Baffle Boxes- Second Generation with Media | Structural
Bioswales | Structural | Biological/ Bacteria Treatment | Structural
Catch Basin Inserts/Inlet Filter Cleanout | Non-structural | Biosorption Activated Media (BAM) | Structural
Stormwater Reuse | Structural | Bioswales | Structural
Natural Wetlands as Filters | Non-structural | BMP Cleanout | Non-structural
Reclaimed Water | Structural | BMP Treatment Train | Structural
Land Use Change | Non-structural | Catch Basin Inserts/Inlet Filter Cleanout | Non-structural
Agricultural BMPs | Use Past Designation | Closed Basin | Non-structural
Dry Detention Pond | Structural | Control Structure | Structural
Street Sweeping | Non-structural | Creating/ Enhancing Living Shoreline | Structural
Fertilizer Cessation | Non-structural | Creating/ Enhancing Oyster Reefs | Structural
Exfiltration Trench | Structural | Credit Trade | Trade
Baffle Boxes- Second Generation | Structural | Dairy Remediation | Structural
Baffle Boxes- First Generation (hydrodynamic separator) | Structural | Decommission/ Abandonment | Non-structural
WWTF Nutrient Reduction | Structural | Deep Injection Well | Structural
|  | Denitrification Walls | Structural
|  | Dispersed Water Management (DWM) | Structural
|  | Dry Detention Pond | Structural
|  | Education Efforts | Non-structural
|  | Enhanced Public Education | Non-structural
|  | Exfiltration Trench | Structural
|  | Exotic Vegetation Removal | Non-structural
|  | Fertilizer Cessation | Non-structural
|  | Fertilizer Reduction | Non-structural
|  | Filter Marsh | Structural
|  | Fish Harvesting | Non-structural
|  | Floating Islands/ Managed Aquatic Plant Systems (MAPS) | Structural
|  | Floodplain Restoration | Structural
|  | Golf Course or Sports Field BMPs | Non-structural
|  | Grass swales with swale blocks or raised culverts | Structural
|  | Grass swales without swale blocks or raised culverts | Structural
|  | Hybrid wetland treatment technology (HWTT) | Structural
|  | Hydrodynamic Separators | Structural
|  | Hydrologic Restoration | Structural
|  | Impoundment | Structural
|  | Industrial Facility Upgrades | Structural
|  | Land Acquisition | Non-structural
|  | Land Preservation | Non-structural
|  | Land Use Change | Non-structural
|  | LID- Green Roofs | Structural
|  | LID- Other | Structural
|  | LID- Rain Gardens | Structural
|  | LID- Tree Boxes/Tree Wells | Structural
|  | Macroalgal Harvesting | Non-structural
|  | Monitoring/Data Collection | Non-structural
|  | Muck Removal/Restoration Dredging | Non-structural
|  | Natural Wetlands as Filters | Non-structural
|  | Non-contributing Basin | Non-structural
|  | Off-line Retention BMPs | Structural
|  | On-line Retention BMPs | Structural
|  | Onsite Sewage Treatment and Disposal System (OSTDS) Enhancement | Structural
|  | OSTDS Phase Out | Structural
|  | Pervious Pavement | Structural
|  | Pervious Pavers | Structural
|  | Plugging Artesian Wells | Structural
|  | Reclaimed Water | Structural
|  | Regional Stormwater Treatment | Structural
|  | Regulations, Ordinances, and Guidelines | Non-structural
|  | Retention/Detention BMP Retrofit with Nutrient Reducing Media | Structural
|  | Retention/Detention BMP with Nutrient Reducing Media | Structural
|  | Sanitary Sewer and Wastewater Treatment Facility (WWTF) Maintenance | Structural
|  | Sanitary Sewer Inspections | Non-structural
|  | SAV Planting | Structural
|  | Shoreline Stabilization | Structural
|  | Stormwater Aeration System | Structural
|  | Stormwater Reuse | Structural
|  | Stormwater System Rehabilitation | Structural
|  | Stormwater Treatment Areas (STAs) | Structural
|  | Street Sweeping | Non-structural
|  | Study | Non-structural
|  | Turbidity Reducing Polymers (e.g., Floc logs ®) | Non-structural
|  | Vegetated Buffers | Non-structural
|  | Wastewater Service Area Expansion | Structural
|  | Wet Detention Pond | Structural
|  | Wetland Restoration | Structural
|  | Wetland Treatment | Structural
|  | WWTF Disposal Site | Structural
|  | WWTF Diversion to Reuse | Structural
|  | WWTF Nutrient Reduction | Structural
|  | WWTF Upgrade | Structural