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LANGUAGE TO BE INCLUDED IN SCOPE OF SERVICES (A.K.A., GRANT WORK PLAN) IF RESEARCH QA EXHIBIT USED:


1. DELIVERABLES
The following lists the expected deliverables that are associated with the quality assurance requirements of this Grant:
a. When reporting grant field or analytical research results, the Grantee shall submit statements about data usability per Section 8 of Exhibit D.
b. [bookmark: _GoBack]The Grantee shall submit the Grant QA Plan as described in Section 9 of Exhibit D to the DEP Grant Manager no later than [120] days [or SPECIFY OTHER TIMEFRAME] prior to the commencement of field and laboratory activities. Failure to submit the QA Plan in this required timeframe shall result in a delay of approval to begin work until the document has been submitted to the Department and approved (or conditionally approved) by the DEP Grant Manager.
(i) The Grantee may submit a version of the QA Plan to the Department for approval no more than three times.  If the Grantee fails to obtain approval for the QA Plan after the third (final) submission to the Department, the DEP Grant Manager may suspend or terminate the Grant per the remedies included in the Grant.
(ii) Within [45] days [or SPECIFY OTHER TURNAROUND TIME] of receipt of the QA Plan by the Department, the Department shall review and either approve the QA Plan or provide comments to the Grantee as to why the QA Plan is not approved. If further revisions are needed, the Grantee shall then have [15] days [or SPECIFY OTHER TURNAROUND TIME] from the receipt of review comments to respond. The Department shall respond to all revisions to the QA Plan within [30] days [or SPECIFY OTHER TURNAROUND TIME] of receipt of any revisions.
(iii) If the review of the QA Plan by the Department is delayed beyond sixty (60) days after the QA Plan is received by the Department, through no fault of the Grantee, the Grantee shall have the option, after the QA Plan is approved, of requesting an extension in the term of the Grant for a time not to exceed the period of delayed review and approval. This option must be exercised at least sixty (60) days prior to the current termination date of the Grant. The Department shall then determine whether the request for an extension is allowed.
(iv) If any significant changes in sampling project design, changes in the project analyte list, changes in procedures or test methods, changes in equipment, or changes in key personnel occur, the Grantee shall submit appropriate revisions of the QA Plan to the DEP Grant Manager for review in writing. The proposed revisions may not be implemented until they have been approved (or conditionally approved) by the DEP Grant Manager. If the Grantee fails to submit the required revisions, the DEP Grant Manager may suspend or terminate the Grant per the remedies included in the Grant.

