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1. DELIVERABLES
The following lists the expected deliverables that are associated with the quality assurance requirements of this Contract:
a. An initial planning review technical audit as specified in Section 5.b.i. of Exhibit D shall be completed by the Contractor after the second completed sampling and analysis event, but no later than the fourth [SPECIFY OPTIONAL TIMEFRAME, AS APPLICABLE].  The Contractor shall submit a report of this initial planning review audit within one month of the review, and that report shall include a statement of usability as described in Section 5.b.iii. of Exhibit D.
b. Ongoing planning review technical audits shall be conducted annually thereafter for the remainder of the Contract, if applicable to the duration of the Contract, as described in Section 5.b.ii. of Exhibit D. The Contractor shall submit a report of each annual planning review audit with a statement of usability (Section 5.b.iii), within one month of the review.
c. The Contractor shall submit the Contract Quality Assurance Plan (QA Plan) as described in Section 6 of Exhibit D to the DEP Contract manager no later than [120] days [or SPECIFY OTHER TIMEFRAME] prior to the commencement of field and laboratory activities. Failure to submit the QA Plan in this required timeframe shall result in a delay of approval to begin work until the document has been submitted to the Department and approved (or conditionally approved) by the DEP Contract manager. 
[The Contract manager may opt to not require a QA Plan for Contractors who will not be designing a sampling scheme or a research project and are only providing standard sampling and/or analytical services to the Department.  In those cases, the Contract shall include the Standard QA Exhibit, but state that the requirements of Section 6 of the Exhibit are waived and a QA Plan is not required.]
(i) The Contractor may submit a version of the QA Plan to the Department for approval no more than three times.  If the Contractor fails to obtain approval for the QA Plan after the third (final) submission to the Department, the DEP Contract manager may suspend or terminate the Contract per the remedies included in the Contract.
(ii) Within [45] days [or SPECIFY OTHER TURNAROUND TIME] of receipt of the QA Plan by the Department, the Department shall review and either approve the QA Plan or provide comments to the Contractor as to why the QA Plan is not approved. If further revisions are needed, the Contractor shall then have [15] days [or SPECIFY OTHER TURNAROUND TIME] from the receipt of review comments to respond. The Department shall respond to all revisions to the QA Plan within [30] days [or SPECIFY OTHER TURNAROUND TIME] of receipt of any revisions.
(iii) If the review of the QA Plan by the Department is delayed beyond sixty (60) days after the QA Plan is received by the Department, through no fault of the Contractor, the Contractor shall have the option, after the QA Plan is approved, of requesting an extension in the term of the Contract for a time not to exceed the period of delayed review and approval. This option must be exercised at least sixty (60) days prior to the current termination date of the Contract. The Department shall then determine whether the request for an extension is allowed.
(iv) If any significant changes in sampling project design, changes in the project analyte list, changes in procedures or test methods, changes in equipment, or changes in key personnel occur, the Contractor shall submit appropriate revisions of the QA Plan to the DEP Contract manager for review in writing. The proposed revisions may not be implemented until they have been approved (or conditionally approved) by the DEP Contract manager. If the Contractor fails to submit the required revisions, the DEP Contract manager may suspend or terminate the Contract per the remedies included in the Contract.

