## TasksExport - 2021-10-20T131455
Ten Mile Canal Maintenance Task Tracking
Lee County Transportation/Operations
Flow Way | Actual Stop Date | Task ID | Activity | Total Cost | Work Units Completed | Work Unit Type | Status
23054 | 2017-08-22 13:10 | 182138 | Mowing | 85.5 | 1 | ea | Completed
23054 | 2017-08-22 13:10 | 182138 | Mowing | 85.5 | 1 | ea | Completed
23054 | 2017-08-23 10:59 | 181143 | Erosion Repair | 4264.9 |  |  | Completed | Units of measure guide
23054 | 2017-08-23 10:59 | 181143 | Erosion Repair | 4264.9 |  |  | Completed
14155 | 2017-08-25 | 183652 | Mowing | 805.6 | 6.4 | ea | Completed | Aquatic Treatment – acres
14155 | 2017-08-29 10:13 | 182146 | Mowing | 256.5 | 3 | ea | Completed | Clean – feet
14684 | 2017-09-07 08:59 | 186216 | Mowing | 684 | 10.7 | ea | Completed | Erosion repair – feet
14470 | 2017-09-08 08:52 | 186379 | Mowing | 563.44 | 6.8 | ea | Completed | Mowing – acres
14470 | 2017-09-08 08:54 | 186380 | Mowing | 342 | 1.5 | ea | Completed | Slope mowing – miles
14470 | 2017-11-14 11:19 | 203778 | Debris Removal | 5019.36 |  |  | Completed | Spray Chemical – acres
23054 | 2017-11-28 | 206991 | Mowing | 228.9 | 6.8 | ea | Completed
23054 | 2017-11-28 | 206991 | Mowing | 228.9 | 6.8 | ea | Completed
14155 | 2017-11-28 | 207149 | Mowing | 936.75 | 9.3 | ea | Completed
14155 | 2017-11-28 | 206993 | Mowing | 140.86 | 3.3 | ea | Completed
23054 | 2017-11-29 | 207155 | Mowing | 282.75 | 1.6 | ea | Completed
23054 | 2017-11-29 | 207155 | Mowing | 282.75 | 1.6 | ea | Completed
14155 | 2017-11-29 | 207366 | Mowing | 64.12 | 1.2 | ea | Completed
14155 | 2017-11-29 | 206999 | Mowing | 52.82 | 1.5 | ea | Completed
14684 | 2017-12-05 | 207461 | Mowing | 140.86 | 4.5 | ea | Completed
14470 | 2017-12-08 | 209252 | Mowing | 116.94 | 1.5 | ea | Completed
14470 | 2017-12-12 | 209255 | Mowing | 1325.41 | 16.9 | ea | Completed
14684 | 2017-12-12 | 209374 | Mowing | 329.87 | 4 | ea | Completed
14470 | 2017-12-13 | 209473 | Mowing | 1126.83 | 15.5 | ea | Completed
14470 | 2017-12-13 | 209471 | Mowing | 848.25 | 6.2 | ea | Completed
14684 | 2017-12-13 | 209470 | Mowing | 754 | 6.1 | ea | Completed
14470 | 2017-12-13 10:31 | 207978 | Clean | 1984.75 | 1 | ea | Completed
14470 | 2017-12-14 | 209587 | Mowing | 467.79 | 4 | ea | Completed
14470 | 2017-12-14 | 209583 | Mowing | 377 | 0.4 | ea | Completed
14155 | 2018-01-16 07:41 | 209310 | Erosion Repair | 3503.7 |  |  | Completed
14470 | 2018-01-23 16:45 | 215203 | Spray Chemical | 374.98 | 6 | ea | Completed
23054 | 2018-01-25 15:06 | 215866 | Spray Chemical | 381.55 | 5.5 | ea | Completed
23054 | 2018-01-25 15:06 | 215866 | Spray Chemical | 381.55 | 5.5 | ea | Completed
14155 | 2018-01-26 11:01 | 215956 | Spray Chemical | 798.02 | 10.1 | ea | Completed
23054 | 2018-02-27 | 221864 | Mowing | 85.86 | 1.4 | ea | Completed
23054 | 2018-02-27 | 221864 | Mowing | 85.86 | 1.4 | ea | Completed
14684 | 2018-02-28 | 222205 | Aquatic Treatment | 3240 | 8 | ea | Completed
23054 | 2018-02-28 | 222142 | Mowing | 41.25 | 0.6 | ea | Completed
23054 | 2018-02-28 | 222142 | Mowing | 41.25 | 0.6 | ea | Completed
14155 | 2018-02-28 | 222146 | Mowing | 247.5 | 1.3 | ea | Completed
14155 | 2018-02-28 | 222138 | Mowing | 424 | 2.5 | ea | Completed
14155 | 2018-02-28 | 222120 | Mowing | 556.93 | 8.7 | ea | Completed
14470 | 2018-03-01 15:40 | 222331 | Aquatic Treatment | 6151.75 | 8 | ea | Completed
14470 | 2018-03-05 | 222690 | Mowing | 532.08 | 3.1 | ea | Completed
14684 | 2018-03-05 | 222687 | Mowing | 620.75 | 4.3 | ea | Completed
14684 | 2018-03-08 | 223811 | Mowing | 82.5 | 1.2 | ea | Completed
14155 | 2018-03-08 08:40 | 223164 | Mowing | 247.5 | 2.5 | ea | Completed
14684 | 2018-03-08 08:43 | 223167 | Mowing | 185.63 | 1.8 | ea | Completed
14470 | 2018-03-08 08:49 | 223173 | Mowing | 257.03 | 3.8 | ea | Completed
14470 | 2018-03-09 | 223870 | Mowing | 599.75 | 8.4 | ea | Completed
14470 | 2018-03-09 | 223821 | Mowing | 536.25 | 4.8 | ea | Completed
14470 | 2018-03-13 | 224205 | Mowing | 149.62 | 2.1 | ea | Completed
14470 | 2018-03-13 | 224194 | Slope Mowing | 123.75 | 2.3 | ea | Completed
14470 | 2018-03-14 | 224577 | Mowing | 256.5 | 6.7 | ea | Completed
14155 | 2018-04-10 08:42 | 217044 | Erosion Repair | 56697.54 |  |  | Completed
23054 | 2018-05-09 12:57 | 237623 | Spray Chemical | 528.07 | 3.66 | ea | Completed
23054 | 2018-05-09 12:57 | 237623 | Spray Chemical | 528.07 | 3.66 | ea | Completed
14155 | 2018-05-09 14:12 | 237764 | Spray Chemical | 587.1 | 7.38 | ea | Completed
18979 | 2018-05-11 08:32 | 236849 | Clean | 812 | 30 | ft | Completed
14155 | 2018-06-01 | 247060 | Mowing | 342.72 | 3.7 | ea | Completed
23054 | 2018-06-05 | 246530 | Mowing | 342.72 | 5.8 | ea | Completed
23054 | 2018-06-05 | 246530 | Mowing | 342.72 | 5.8 | ea | Completed
14155 | 2018-06-05 | 246534 | Mowing | 514.08 | 8 | ea | Completed
18979 | 2018-06-05 07:25 | 241992 | Clearing | 18308.64 |  |  | Completed
18979 | 2018-06-07 07:57 | 243658 | Clean | 3176.01 | 100 | ft | Completed
14684 | 2018-06-12 | 249364 | Mowing | 257.58 | 4.5 | ea | Completed
14684 | 2018-06-13 | 249466 | Mowing | 128.25 | 1.8 | ea | Completed
23054 | 2018-06-13 | 249450 | Slope Mowing | 471.25 | 2.8 | ea | Completed
23054 | 2018-06-13 | 249450 | Slope Mowing | 471.25 | 2.8 | ea | Completed
14470 | 2018-06-14 | 249879 | Mowing | 428.41 | 6.3 | ea | Completed
23054 | 2018-06-14 | 249866 | Slope Mowing | 480.67 | 2.8 | ea | Completed
23054 | 2018-06-14 | 249866 | Slope Mowing | 480.67 | 2.8 | ea | Completed
14470 | 2018-06-15 | 250449 | Mowing | 1456.57 | 18.9 | ea | Completed
14470 | 2018-06-19 | 251048 | Mowing | 642.59 | 11.4 | ea | Completed
14155 | 2018-06-19 08:28 | 250459 | Erosion Repair | 1262.37 | 8175 | ft | Completed
14155 | 2018-06-20 08:18 | 251042 | Erosion Repair | 2407.35 | 8120 | ft | Completed
14470 | 2018-06-26 | 252360 | Slope Mowing | 754 | 1.5 | mi | Completed
14684 | 2018-06-26 | 252357 | Slope Mowing | 471.25 | 2.9 | ea | Completed
14470 | 2018-06-28 | 252949 | Slope Mowing | 206.25 | 2.3 | ea | Completed
14470 | 2018-06-29 | 253515 | Slope Mowing | 144.37 | 2.3 | ea | Completed
18979 | 2018-07-03 07:34 | 249451 | Clean | 8470.16 | 2500 | ft | Completed
14155 | 2018-07-13 08:09 | 255755 | Erosion Repair | 2465.82 | 8149 | ft | Completed
18979 | 2018-07-25 10:07 | 257954 | Clean | 4051.89 | 2471 | ft | Completed
23054 | 2018-08-16 14:22 | 263300 | Spray Chemical | 472.73 | 3.85 | ea | Completed
23054 | 2018-08-16 14:22 | 263300 | Spray Chemical | 472.73 | 3.85 | ea | Completed
14155 | 2018-08-16 14:27 | 263304 | Spray Chemical | 417.17 | 2.9 | ea | Completed
23054 | 2018-08-23 10:10 | 264426 | Spray Chemical | 272.7 | 3.85 | ea | Completed
23054 | 2018-08-23 10:10 | 264426 | Spray Chemical | 272.7 | 3.85 | ea | Completed
14155 | 2018-08-24 09:24 | 264663 | Spray Chemical | 1045.98 | 8.2 | ea | Completed
23054 | 2018-09-12 | 268490 | Mowing | 214.21 | 1.9 | ea | Completed
23054 | 2018-09-12 | 268490 | Mowing | 214.21 | 1.9 | ea | Completed
14155 | 2018-09-12 | 268501 | Mowing | 856.8 | 8.4 | ea | Completed
23054 | 2018-09-12 | 268452 | Slope Mowing | 106 | 0.8 | ea | Completed
23054 | 2018-09-12 | 268452 | Slope Mowing | 106 | 0.8 | ea | Completed
14155 | 2018-09-12 | 268454 | Slope Mowing | 530 | 4.8 | ea | Completed
14155 | 2018-09-13 | 268959 | Slope Mowing | 94.25 | 0.6 | ea | Completed
14155 | 2018-09-14 | 269282 | Mowing | 385.57 | 5.9 | ea | Completed
14155 | 2018-09-14 | 269287 | Slope Mowing | 188.5 | 2.5 | ea | Completed
14684 | 2018-09-20 | 270261 | Mowing | 128.78 | 1.5 | ea | Completed
14470 | 2018-09-24 | 270698 | Mowing | 737.16 | 13.4 | ea | Completed
14684 | 2018-09-25 | 270922 | Slope Mowing | 471.25 | 5 | ea | Completed
14470 | 2018-09-27 | 271783 | Mowing | 600.3 | 12.3 | ea | Completed
14470 | 2018-09-28 | 271785 | Mowing | 257.58 | 4.9 | ea | Completed
14470 | 2018-09-28 | 271780 | Slope Mowing | 471.25 | 3.2 | ea | Completed
18979 | 2018-10-01 | 271799 | Slope Mowing | 165 | 1.3 | ea | Completed
14470 | 2018-10-01 | 271797 | Slope Mowing | 536.25 | 1.5 | mi | Completed
18979 | 2018-10-02 | 272069 | Slope Mowing | 103.13 | 1.1 | ea | Completed
14470 | 2018-10-24 | 276390 | Erosion Repair | 266.84 | 1000 | ft | Completed
14470 | 2018-10-25 | 276646 | Erosion Repair | 266 |  |  | Completed
23054 | 2018-11-21 | 281191 | Mowing | 84.19 | 1.5 |  | Completed
23054 | 2018-11-21 | 281191 | Mowing | 84.19 | 1.5 |  | Completed
14155 | 2018-11-21 | 281194 | Mowing | 505.08 | 4.7 |  | Completed
14155 | 2018-11-27 | 281690 | Mowing | 642.59 | 7.8 |  | Completed
14155 | 2018-11-28 | 281832 | Mowing | 85.69 | 0.304 |  | Completed
14155 | 2018-12-05 | 283345 | Slope Mowing | 754 | 1.6 | mi | Completed
14684 | 2018-12-06 | 283348 | Mowing | 235.66 | 3.8 |  | Completed
23054 | 2018-12-07 | 283683 | Slope Mowing | 82.5 | 1.5 |  | Completed
23054 | 2018-12-07 | 283683 | Slope Mowing | 82.5 | 1.5 |  | Completed
14155 | 2018-12-07 | 283690 | Slope Mowing | 565.5 | 4.3 |  | Completed
14470 | 2018-12-12 | 284311 | Mowing | 1113.85 | 10.1 | acre | Completed
18979 | 2018-12-13 | 284697 | Mowing | 514.08 | 9 | acre | Completed
14470 | 2018-12-14 | 285071 | Mowing | 128.51 | 3.3 | acre | Completed
14684 | 2018-12-14 | 285102 | Slope Mowing | 206.25 | 2.5 | mi | Completed
14470 | 2018-12-14 08:13 | 284696 | Mowing | 856.8 | 14.6 | acre | Completed
14470 | 2018-12-19 | 286257 | Slope Mowing | 412.5 | 3.8 | mi | Completed
18979 | 2018-12-20 | 286337 | Slope Mowing | 565.5 | 3.6 | mi | Completed
23054 | 2019-01-08 11:38 | 287727 | Spray Chemical | 963.55 | 3.5 | acre | Completed
23054 | 2019-01-08 11:38 | 287727 | Spray Chemical | 963.55 | 3.5 | acre | Completed
14155 | 2019-01-08 15:50 | 287754 | Spray Chemical | 669.02 | 4.24 | acre | Completed
14684 | 2019-02-07 13:56 | 296999 | Spray Chemical | 287.84 | 8 | acre | Completed
14470 | 2019-02-07 14:24 | 297019 | Spray Chemical | 287.84 | 10 | acre | Completed
14470 | 2019-02-12 14:43 | 297691 | Spray Chemical | 736.4 | 10 | acre | Completed
14684 | 2019-03-07 15:54 | 303592 | Spray Chemical | 136 | 9 | acre | Completed
14155 | 2019-03-08 16:42 | 303669 | Erosion Repair | 876.72 | 8092 | ft | Completed
14155 | 2019-03-08 16:42 | 297855 | Clean | 10703 | 2520 | ft | Completed
23054 | 2019-03-28 | 308038 | Spray Chemical | 765.18 | 0.5 | acre | Completed
23054 | 2019-03-28 | 308038 | Spray Chemical | 765.18 | 0.5 | acre | Completed
23054 | 2019-04-11 14:23 | 311774 | Spray Chemical | 235.03 | 4.3 | acre | Completed
23054 | 2019-04-11 14:23 | 311774 | Spray Chemical | 235.03 | 4.3 | acre | Completed
14155 | 2019-04-11 14:27 | 311781 | Spray Chemical | 201.45 | 2.9 | acre | Completed
23054 | 2019-04-26 | 316320 | Mowing | 142.28 | 1.8 | acre | Completed
23054 | 2019-04-26 | 316320 | Mowing | 142.28 | 1.8 | acre | Completed
14155 | 2019-04-26 | 316325 | Mowing | 379.44 | 4 | acre | Completed
14155 | 2019-04-30 | 316702 | Mowing | 711.44 | 7.7 | acre | Completed
23054 | 2019-05-01 15:37 | 317001 | Spray Chemical | 537.2 | 1.74 | acre | Completed
23054 | 2019-05-01 15:37 | 317001 | Spray Chemical | 537.2 | 1.74 | acre | Completed
23054 | 2019-05-03 | 318313 | Slope Mowing | 212 | 1.5 | mi | Completed
23054 | 2019-05-03 | 318313 | Slope Mowing | 212 | 1.5 | mi | Completed
14155 | 2019-05-07 | 318953 | Slope Mowing | 848 | 7.8 | mi | Completed
23054 | 2019-05-08 16:10 | 319928 | Spray Chemical | 1629.69 | 3 | acre | Completed
23054 | 2019-05-08 16:10 | 319928 | Spray Chemical | 1629.69 | 3 | acre | Completed
14155 | 2019-05-09 15:43 | 319933 | Spray Chemical | 4636.53 | 10 | acre | Completed
14684 | 2019-05-16 | 323460 | Mowing | 342 | 5.4 | acre | Completed
14684 | 2019-05-16 | 323442 | Slope Mowing | 424 | 4.5 | mi | Completed
14470 | 2019-05-17 | 323988 | Slope Mowing | 1060 | 10.4 | mi | Completed
14155 | 2019-05-21 13:48 | 324133 | Investigate | 201.45 |  |  | Completed
14470 | 2019-05-21 14:21 | 324147 | Spray Chemical | 268.9 | 11 | acre | Completed
14684 | 2019-05-21 14:25 | 324155 | Spray Chemical | 189.12 | 9 | acre | Completed
14470 | 2019-05-22 | 325549 | Mowing | 899.52 | 10.1 | acre | Completed
18979 | 2019-05-22 | 325531 | Slope Mowing | 212 | 2.1 | mi | Completed
14470 | 2019-05-22 | 325527 | Slope Mowing | 530 | 4.1 | acre | Completed
14470 | 2019-05-23 | 325567 | Mowing | 769.5 | 6.9 | acre | Completed
14470 | 2019-05-24 | 325686 | Mowing | 1418.88 | 15.1 | acre | Completed
18979 | 2019-05-24 10:31 | 325551 | Mowing | 266.03 | 2.9 | acre | Completed
14684 | 2019-06-06 13:13 | 329770 | Spray Chemical | 176.16 | 8 | acre | Completed
23054 | 2019-08-14 | 361714 | Mowing | 21.38 | 0.3 | acre | Completed
23054 | 2019-08-14 | 361714 | Mowing | 21.38 | 0.3 | acre | Completed
23054 | 2019-08-15 | 362306 | Investigate | 9.15 | 3732.664 | ft | Completed
23054 | 2019-08-15 | 362306 | Investigate | 9.15 | 3732.664 | ft | Completed
23054 | 2019-08-15 | 362281 | Mowing | 177.36 | 2 | acre | Completed
23054 | 2019-08-15 | 362281 | Mowing | 177.36 | 2 | acre | Completed
14155 | 2019-08-15 | 362286 | Mowing | 709.44 | 8.8 | acre | Completed
23054 | 2019-08-15 | 362274 | Slope Mowing | 530 | 2.1 | mi | Completed
23054 | 2019-08-15 | 362274 | Slope Mowing | 530 | 2.1 | mi | Completed
14155 | 2019-08-15 | 362275 | Slope Mowing | 583 | 2.2 | mi | Completed
14155 | 2019-08-16 | 364632 | Investigate | 6.1 |  |  | Completed
14155 | 2019-08-16 | 364022 | Mowing | 354.72 | 6.3 | acre | Completed
14155 | 2019-08-16 | 364047 | Slope Mowing | 397.5 | 2.3 | mi | Completed
14684 | 2019-08-22 | 366101 | Mowing | 183.72 | 4.5 | acre | Completed
14155 | 2019-08-22 | 366131 | Slope Mowing | 185.5 | 1.4 | mi | Completed
14470 | 2019-08-23 | 367688 | Mowing | 42.75 | 0.4 | acre | Completed
14470 | 2019-08-23 14:35 | 366215 | Spray Chemical | 979.98 | 16 | acre | Completed
14470 | 2019-08-26 | 367773 | Mowing | 1466.16 | 17.9 | acre | Completed
14684 | 2019-08-26 15:53 | 367384 | Spray Chemical | 734.84 | 8.8 | acre | Completed
14684 | 2019-08-27 | 368416 | Investigate | 6.1 | 1 | ea | Completed
18979 | 2019-08-27 | 368360 | Mowing | 443.41 | 4.7 | acre | Completed
14470 | 2019-08-27 | 368358 | Mowing | 975.47 | 10.9 | acre | Completed
14684 | 2019-08-27 | 368375 | Slope Mowing | 848 | 4.7 | mi | Completed
18979 | 2019-08-28 | 369098 | Mowing | 399.07 | 4.7 | acre | Completed
23054 | 2019-09-04 17:04 | 372479 | Spray Chemical | 733.88 | 5.5 | acre | Completed
23054 | 2019-09-04 17:04 | 372479 | Spray Chemical | 733.88 | 5.5 | acre | Completed
14470 | 2019-09-05 | 373622 | Slope Mowing | 901 | 5.2 | mi | Completed
14470 | 2019-09-06 | 375499 | Slope Mowing | 583 | 5.2 | mi | Completed
18979 | 2019-09-09 | 375504 | Slope Mowing | 583 | 3.7 | mi | Completed
23054 | 2019-10-31 08:09 | 406926 | Spray Chemical | 496.32 | 4 | acre | Completed
23054 | 2019-10-31 08:09 | 406926 | Spray Chemical | 496.32 | 4 | acre | Completed
14684 | 2019-11-07 14:21 | 412081 | Spray Chemical | 569.68 | 11 | acre | Completed
14155 | 2019-11-14 | 418176 | Slope Mowing | 835 | 5 | mi | Completed
23054 | 2019-11-15 | 420263 | Mowing | 320.62 | 2.9 | acre | Completed
23054 | 2019-11-15 | 420263 | Mowing | 320.62 | 2.9 | acre | Completed
23054 | 2019-11-15 | 420322 | Slope Mowing | 424 | 2.5 | mi | Completed
23054 | 2019-11-15 | 420322 | Slope Mowing | 424 | 2.5 | mi | Completed
14155 | 2019-11-15 | 420325 | Slope Mowing | 238.5 | 1.2 | mi | Completed
14155 | 2019-11-19 | 420826 | Mowing | 459.3 | 9.5 | acre | Completed
14155 | 2019-11-19 | 420910 | Slope Mowing | 1007 | 5.9 | mi | Completed
14684 | 2019-11-22 | 424905 | Mowing | 485.79 | 0.3 | acre | Completed
14684 | 2019-11-27 | 429416 | Mowing | 206.69 | 5.9 | acre | Completed
14470 | 2019-12-05 | 434870 | Mowing | 826.74 | 13.7 | acre | Completed
14470 | 2019-12-06 | 434941 | Slope Mowing | 318 | 2.3 | mi | Completed
14470 | 2019-12-10 | 434942 | Mowing | 684 | 8.1 | acre | Completed
14684 | 2019-12-10 | 434949 | Slope Mowing | 212 | 2 | mi | Completed
18979 | 2019-12-11 | 435605 | Mowing | 213.75 | 1.8 | acre | Completed
14470 | 2019-12-11 | 435604 | Mowing | 256.5 | 3 | acre | Completed
14684 | 2019-12-12 | 470618 | Inspect | 6.1 | 1 | ea | Completed
18979 | 2019-12-12 | 436452 | Mowing | 354.72 | 7.3 | acre | Completed
14470 | 2019-12-12 | 436445 | Mowing | 532.08 | 11.3 | acre | Completed
18979 | 2019-12-12 | 436433 | Slope Mowing | 321.66 | 2 | mi | Completed
14470 | 2019-12-12 | 436432 | Slope Mowing | 1060 | 6 | mi | Completed
14684 | 2019-12-12 | 436430 | Slope Mowing | 318 | 2.6 | mi | Completed
14155 | 2019-12-13 12:00 | 436505 | Spray Chemical | 1775.91 | 3.06 | acre | Completed
14470 | 2020-01-30 07:45 | 415271 | Erosion Repair | 79952.9 |  | ft | Completed
23054 | 2020-02-18 15:40 | 478420 | Spray Chemical | 1385.11 | 2.1 | acre | Completed
23054 | 2020-02-18 15:40 | 478420 | Spray Chemical | 1385.11 | 2.1 | acre | Completed
14155 | 2020-02-19 09:53 | 478593 | Spray Chemical | 1830.14 | 3 | acre | Completed
23054 | 2020-04-03 | 510624 | Mowing | 91.5 | 2.9 | acre | Completed
23054 | 2020-04-03 | 510624 | Mowing | 91.5 | 2.9 | acre | Completed
14155 | 2020-04-03 | 510628 | Mowing | 275.58 | 11 | acre | Completed
14684 | 2020-04-10 | 1009032587 | Mowing | 354.72 | 8.1 | acre | Completed
14684 | 2020-04-10 08:24 | 512992 | Aquatic Treatment | 1068.8 | 12 | acre | Completed
14470 | 2020-04-10 09:40 | 513034 | Aquatic Treatment | 1603.2 | 15 | acre | Completed
14470 | 2020-04-14 | 1009033477 | Mowing | 354.72 | 4 | acre | Completed
23054 | 2020-04-14 | 1009033654 | Slope Mowing | 530 | 5.9 | mi | Completed
23054 | 2020-04-14 | 1009033654 | Slope Mowing | 530 | 5.9 | mi | Completed
14470 | 2020-04-15 | 1009034520 | Mowing | 1418.88 | 15.1 | acre | Completed
14470 | 2020-04-16 | 1009035168 | Mowing | 684 | 10.9 | acre | Completed
18979 | 2020-04-17 | 515346 | Mowing | 354.72 | 8.5 | acre | Completed
14684 | 2020-04-22 | 517012 | Slope Mowing | 132.5 | 1.3 | mi | Completed
14684 | 2020-04-23 | 517912 | Slope Mowing | 424 | 2.1 | mi | Completed
14470 | 2020-04-28 | 522025 | Slope Mowing | 318 | 2.3 | mi | Completed
14470 | 2020-04-29 | 560396 | Inspect | 3.05 | 1 | ea | Completed
18979 | 2020-04-29 | 522045 | Slope Mowing | 636 | 4 | mi | Completed
14470 | 2020-04-29 | 522039 | Slope Mowing | 530 | 3.2 | mi | Completed
14470 | 2020-05-05 | 525237 | Spray Chemical | 1630.56 | 20 | acre | Completed
23054 | 2020-05-13 08:34 | 512213 | Erosion Repair | 56867.15 | 4065 | ft | Completed
23054 | 2020-05-13 08:34 | 512213 | Erosion Repair | 56867.15 | 4065 | ft | Completed
23054 | 2020-05-19 08:26 | 535170 | Other/Not Listed | 186.1 | 1 | ea | Completed
23054 | 2020-05-19 08:26 | 535170 | Other/Not Listed | 186.1 | 1 | ea | Completed
18979 | 2020-05-29 09:13 | 542057 | Install | 910.12 | 1 | ea | Completed
14470 | 2020-06-02 | 545297 | Other/Not Listed | 1013.16 | 2 | ea | Completed
18979 | 2020-06-03 09:19 | 545306 | Remove Dead Animals | 689.72 | 1 | acre | Completed
23054 | 2020-06-05 | 549091 | Spray Chemical | 144.29 | 0.5 | acre | Completed
23054 | 2020-06-05 | 549091 | Spray Chemical | 144.29 | 0.5 | acre | Completed
23054 | 2020-06-26 09:35 | 549556 | Erosion Repair | 9065.84 | 985 | ft | Completed
23054 | 2020-06-26 09:35 | 549556 | Erosion Repair | 9065.84 | 985 | ft | Completed
23054 | 2020-07-01 | 566328 | Mowing | 289.08 | 7.2 | acre | Completed
23054 | 2020-07-01 | 566328 | Mowing | 289.08 | 7.2 | acre | Completed
23054 | 2020-07-01 | 566343 | Slope Mowing | 396 | 4.6 | mi | Completed
23054 | 2020-07-01 | 566343 | Slope Mowing | 396 | 4.6 | mi | Completed
14155 | 2020-07-01 | 566344 | Slope Mowing | 396 | 7.9 | mi | Completed
14155 | 2020-07-02 08:39 | 566333 | Mowing | 192.72 | 2.4 | acre | Completed
23054 | 2020-07-02 12:57 | 566415 | Spray Chemical | 333.71 | 1 | acre | Completed
23054 | 2020-07-02 12:57 | 566415 | Spray Chemical | 333.71 | 1 | acre | Completed
14155 | 2020-07-07 | 569656 | Slope Mowing | 66 | 0.4 | mi | Completed
14684 | 2020-07-08 | 570629 | Mowing | 155.58 | 2 | acre | Completed
18979 | 2020-07-08 08:24 | 569605 | Other/Not Listed | 460.29 | 1 | ea | Completed
14684 | 2020-07-09 | 571491 | Mowing | 192.72 | 3.7 | acre | Completed
14470 | 2020-07-10 | 573793 | Mowing | 337.25 | 5.8 | acre | Completed
18979 | 2020-07-13 | 573830 | Mowing | 100.36 | 3.2 | acre | Completed
14470 | 2020-07-13 09:05 | 573821 | Mowing | 451.63 | 14.2 | acre | Completed
14155 | 2020-07-24 11:18 | 581296 | Spray Chemical | 290.76 | 1.5 | acre | Completed
14684 | 2020-07-28 | 584437 | Slope Mowing | 363 | 4 | mi | Completed
14470 | 2020-07-30 | 586542 | Slope Mowing | 891 | 7.5 | mi | Completed
18979 | 2020-07-31 | 589138 | Slope Mowing | 396 | 4 | mi | Completed
14470 | 2020-08-04 08:53 | 589134 | Slope Mowing | 264 | 3.4 | mi | Completed
23054 | 2020-08-19 08:14 | 599501 | Erosion Repair | 1142.58 | 250 | ft | Completed
23054 | 2020-08-19 08:14 | 599501 | Erosion Repair | 1142.58 | 250 | ft | Completed
23054 | 2020-08-19 10:40 | 599725 | Spray Chemical | 2684.85 | 3.5 | acre | Completed
23054 | 2020-08-19 10:40 | 599725 | Spray Chemical | 2684.85 | 3.5 | acre | Completed
14470 | 2020-08-19 13:49 | 600714 | Spray Chemical | 776.68 | 3 | acre | Completed
18979 | 2020-08-21 08:35 | 602480 | Clean | 472.9 | 75 | ft | Completed
14470 | 2020-09-01 09:08 | 610319 | Remove Dead Animals | 550.86 | 1 | ea | Completed
14684 | 2020-09-03 | 613230 | Spray Chemical | 315.36 | 4 | acre | Completed
14470 | 2020-09-03 10:34 | 612376 | Spray Chemical | 445.88 | 1 | acre | Completed
14155 | 2020-09-03 12:54 | 600574 | Spray Chemical | 5157.39 | 7.2 | acre | Completed
23054 | 2020-09-22 | 625195 | Mowing | 188.72 | 3.2 | acre | Completed
23054 | 2020-09-22 | 625195 | Mowing | 188.72 | 3.2 | acre | Completed
14155 | 2020-09-22 | 625196 | Mowing | 188.72 | 3.2 | acre | Completed
14155 | 2020-09-23 | 626222 | Mowing | 212.32 | 6.8 | acre | Completed
14470 | 2020-10-02 08:21 | 632492 | Inspect | 1.05 | 1 | ea | Completed
14470 | 2020-10-07 | 637422 | Mowing | 25.94 | 0.6 | acre | Completed
14684 | 2020-10-07 | 637421 | Mowing | 340.94 | 6.8 | acre | Completed
14470 | 2020-10-15 | 641415 | Mowing | 481.8 | 6 | acre | Completed
23054 | 2020-10-15 | 641393 | Slope Mowing | 165 | 2.5 | mi | Completed
23054 | 2020-10-15 | 641393 | Slope Mowing | 165 | 2.5 | mi | Completed
14155 | 2020-10-15 | 641395 | Slope Mowing | 594 | 7.6 | mi | Completed
14470 | 2020-10-16 | 642847 | Mowing | 867.24 | 20.5 | acre | Completed
18979 | 2020-10-20 | 643686 | Mowing | 120.46 | 1.3 | acre | Completed
14470 | 2020-10-27 | 647988 | Slope Mowing | 396 | 3.7 | mi | Completed
14684 | 2020-10-27 | 647985 | Slope Mowing | 264 | 2.8 | mi | Completed
18979 | 2020-10-29 | 666834 | Slope Mowing | 132 | 2.4 | mi | Completed
14470 | 2020-10-29 | 666833 | Slope Mowing | 198 | 3.6 | mi | Completed
23054 | 2020-11-19 09:01 | 676057 | Erosion Repair | 498 | 75 | ft | Completed
23054 | 2020-11-19 09:01 | 676057 | Erosion Repair | 498 | 75 | ft | Completed
18979 | 2020-11-19 09:23 | 676069 | Clean | 1636.68 | 150 | ft | Completed
23054 | 2020-12-03 07:53 | 683567 | Install | 250 | 1 | ea | Completed
23054 | 2020-12-03 07:53 | 683567 | Install | 250 | 1 | ea | Completed
23054 | 2021-01-13 | 708311 | Mowing | 96.36 | 1.7 | acre | Completed
23054 | 2021-01-13 | 708311 | Mowing | 96.36 | 1.7 | acre | Completed
14155 | 2021-01-13 | 708316 | Mowing | 626.35 | 10.7 | acre | Completed
23054 | 2021-02-16 | 730525 | Slope Mowing | 132 | 2 | mi | Completed
23054 | 2021-02-16 | 730525 | Slope Mowing | 132 | 2 | mi | Completed
14155 | 2021-02-16 | 730527 | Slope Mowing | 198 | 2.2 | mi | Completed
14155 | 2021-02-17 | 731775 | Slope Mowing | 429 | 5.9 | mi | Completed
14684 | 2021-02-24 | 740197 | Mowing | 181.5 | 4.5 | acre | Completed
14470 | 2021-03-02 | 744727 | Mowing | 77.78 | 2.4 | acre | Completed
14470 | 2021-03-03 | 745973 | Mowing | 89 | 0.6 | acre | Completed
14684 | 2021-03-04 | 746838 | Slope Mowing | 726 | 7.6 | mi | Completed
14470 | 2021-03-05 | 749277 | Mowing | 755.99 | 13 | acre | Completed
14470 | 2021-03-09 | 750341 | Mowing | 244.75 | 4.6 | acre | Completed
14470 | 2021-03-09 | 750339 | Slope Mowing | 561 | 6.5 | mi | Completed
14684 | 2021-03-09 | 750337 | Slope Mowing | 396 | 5 | mi | Completed
18979 | 2021-03-10 | 751684 | Mowing | 22.25 | 0.3 | acre | Completed
14470 | 2021-03-10 | 751688 | Mowing | 289.25 | 6.7 | acre | Completed
18979 | 2021-03-10 | 751674 | Slope Mowing | 132 | 1.3 | mi | Completed
14470 | 2021-03-11 | 752637 | Slope Mowing | 264 | 3.2 | mi | Completed
14684 | 2021-03-17 11:09 | 755879 | Spray Chemical | 351 | 8 | acre | Completed
14684 | 2021-03-18 14:34 | 757036 | Aquatic Treatment | 2244 | 8 | acre | Completed
23054 | 2021-05-07 14:32 | 792523 | Spray Chemical | 2198.92 | 4.4 | acre | Completed
23054 | 2021-05-07 14:32 | 792523 | Spray Chemical | 2198.92 | 4.4 | acre | Completed
14684 | 2021-05-25 14:55 | 804386 | Spray Chemical | 160.5 | 1 | acre | Completed
23054 | 2021-06-03 | 811357 | Slope Mowing | 327.9 | 4.2 | mi | Completed
23054 | 2021-06-03 | 811357 | Slope Mowing | 327.9 | 4.2 | mi | Completed
14155 | 2021-06-03 | 811358 | Slope Mowing | 396 | 3.2 | mi | Completed
14155 | 2021-06-16 | 819981 | Slope Mowing | 198 | 3.2 | mi | Completed
14155 | 2021-06-17 | 820962 | Slope Mowing | 231 | 3.4 | mi | Completed
23054 | 2021-06-22 | 824357 | Mowing | 96.36 | 2.2 | acre | Completed
23054 | 2021-06-22 | 824357 | Mowing | 96.36 | 2.2 | acre | Completed
14155 | 2021-06-23 | 825068 | Mowing | 240.91 | 4 | acre | Completed
14155 | 2021-06-24 09:11 | 824280 | Slope Mowing | 1192.88 | 4.6 | mi | Completed
14684 | 2021-06-29 | 828958 | Mowing | 144.53 | 1.6 | acre | Completed
14684 | 2021-06-30 | 829977 | Mowing | 240.91 | 4.8 | acre | Completed
14684 | 2021-06-30 | 830064 | Slope Mowing | 99 | 0.7 | mi | Completed
14470 | 2021-07-01 | 830782 | Mowing | 481.8 | 6 | acre | Completed
18979 | 2021-07-08 | 834903 | Mowing | 96.36 | 1.8 | acre | Completed
14470 | 2021-07-08 | 834818 | Mowing | 674.52 | 14.3 | acre | Completed
14470 | 2021-07-08 | 834909 | Slope Mowing | 330 | 4.8 | mi | Completed
14684 | 2021-07-08 | 834908 | Slope Mowing | 264 | 3.7 | mi | Completed
14470 | 2021-07-09 | 836811 | Mowing | 103.72 | 5.8 | acre | Completed
18979 | 2021-07-13 | 837877 | Slope Mowing | 132 | 2 | mi | Completed
14470 | 2021-07-14 | 838811 | Mowing | 73.5 | 3.2 | mi | Completed
18979 | 2021-07-20 | 846492 | Inspect | 1.05 | 1 | ea | Completed
14470 | 2021-07-20 | 842622 | Mowing | 231 | 3.5 | mi | Completed
14470 | 2021-07-22 16:17 | 843730 | Spray Chemical | 237.32 | 1 | acre | Completed
14470 | 2021-08-12 16:10 | 860288 | Spray Chemical | 1436.38 | 4.5 | acre | Completed
14684 | 2021-08-24 15:40 | 869131 | Spray Chemical | 1021.9 | 6 | acre | Completed
14470 | 2021-08-24 15:49 | 869144 | Spray Chemical | 1408.24 | 4.5 | acre | Completed
14155 | 2021-09-16 13:18 | 801851 | Spray Chemical | 2348.72 | 8 | acre | Completed
14155 | 2021-09-16 13:38 | 886391 | Spray Chemical | 423.14 | 3.5 | acre | Completed
14155 | 2021-09-16 15:13 | 885257 | Erosion Repair | 1171.15 | 125 | ft | Completed
18979 | 2021-09-24 09:51 | 892648 | Investigate | 273.6 | 1 | ea | Completed
23054 | 2021-10-07 | 903461 | Mowing | 153.53 | 4.1 | acre | Completed
23054 | 2021-10-07 | 903461 | Mowing | 153.53 | 4.1 | acre | Completed
14155 | 2021-10-07 | 903471 | Mowing | 153.53 | 1.3 | acre | Completed
23054 | 2021-10-07 | 903458 | Slope Mowing | 198 | 2.1 | mi | Completed
23054 | 2021-10-07 | 903458 | Slope Mowing | 198 | 2.1 | mi | Completed
14155 | 2021-10-07 | 903463 | Slope Mowing | 805.5 | 1.5 | mi | Completed
14155 | 2021-10-08 | 905791 | Mowing | 255.91 | 4.6 | acre | Completed
14155 | 2021-10-08 | 905799 | Slope Mowing | 132 | 1.8 | mi | Completed
18979 | 2021-10-08 08:36 | 903474 | Clean | 1543.13 | 175 | ft | Completed
23054 | 2021-10-12 | 908781 | Inspect | 1.05 | 1 | ea | Completed
23054 | 2021-10-12 | 908781 | Inspect | 1.05 | 1 | ea | Completed
14155 | 2021-10-12 | 908783 | Inspect | 1.05 | 1 | ea | Completed
14155 | 2021-10-12 | 906793 | Mowing | 364.94 | 6.2 | acre | Completed
14155 | 2021-10-12 | 906761 | Slope Mowing | 594 | 5.8 | mi | Completed
14155 | 2021-10-12 07:44 | 875965 | Clean | 5570.44 | 2375 | ft | Completed
14155 | 2021-10-13 | 907736 | Mowing | 66.75 | 1.8 | acre | Completed
14155 | 2021-10-13 | 907709 | Slope Mowing | 132 | 1.4 | mi | Completed
14684 | 2021-10-19 | 912500 | Mowing | 409.44 | 7.1 | acre | Completed
14470 |  | 286091 | Mowing | 57.75 | 2 | mi | Completed
530511.2